Application: This template is used when the Certified LPA owns the contract on a federal funded project.

Version Date: 10/3/22

GENERAL INSTRUCTIONS:

- Yellow highlighted areas include instructions that should be deleted prior to release.

- Blue highlighted areas indicate text or fields that need information provided or revised.

- “Agency” means the Certified LPA as defined in the CLPA Contract.

- Delete instructions throughout the document before executing Contract or amendment. Deletions can be automated as follows:

  - From the “Edit” menu (or “Editing” menu on the “Home” ribbon) select “Replace”;

  - With cursor in the “Find what” field, click “More” button, then “Format”, then “Font”, then in the font field select “Times New Roman” text;

  - Leave the “Replace with” field blank;

  - Click “Replace All”. This will delete all yellow highlighted text.

PROJECT-SPECFIC INSTRUCTIONS:

- The template language must be revised if needed for specifics applicable to the current project (including deletion of requirements that don’t apply to the current project).

- Not all subtasks are needed for each project.  If an entire subtask is not needed, leave the task number, add “RESERVED” after the subtask title, and delete all subtask text.

- Use Track Changes when editing template. Save electronic copy of draft in procurement file that shows Track Changes of all edits to template.

Exhibit A.1

Statement of Work and Delivery Schedule for Construction Contract Administration and Construction Engineering & Inspection (“CA/CEI”)

Contents

A.	PROJECT DESCRIPTION AND OVERVIEW OF SERVICES	2

B.	STANDARDS and GENERAL REQUIREMENTS	4

C.	REVIEW, COMMENT and SCHEDULE REQUIREMENTS	7

D.	FORMAT REQUIREMENTS	7

E.1	TASKS, DELIVERABLES and SCHEDULE	8

TASK CE-1	PROJECT MANAGEMENT OF CA/CEI SERVICES	8

Task CE-1.1	Coordination	8

Task CE-1.2	Status Reports and Invoices	8

TASK CE-2	CONSTRUCTION CONTRACT ADMINISTRATION/CONSTRUCTION ENGINEERING and INSPECTION (CA/CEI)	9

Task CE-2.1	Pre-Construction Conference	9

Task CE-2.2	Cooperative Arrangement (Partnering) (Reserved)	9

Task CE-2.3	Quality Assurance & Contract Administration Plan	9

Task CE-2.4	Construction Contract Administration	10

Task CE-2.5	Monthly Preliminary Progress Estimates	10

Task CE-2.6	Project Progress Meetings	11

Task CE-2.7	Working Drawings, Shop Drawings, and other Submittal Reviews	11

Task CE-2.8	Consultation During Construction	13

Task CE-2.9	Design Modifications (CONTINGENCY TASK)	13

Task CE-2.10	Claim(s) Support (CONTINGENCY TASK)	13

Task CE-2.11	Public Records Request Support (CONTINGENCY TASK)	14

TASK CE-3	CONSTRUCTION, ENVIRONMENTAL COMPLIANCE AND WORK ZONE MONITORING AND INSPECTION	15

Task CE-3.1	Environmental Compliance and Mitigation Monitoring	16

Task CE 3.1.1	Endangered Species Consultation for the Federal-Aid Highway Program (“FAHP”)	17

Task CE-3.1.2 Restoration As-Built Report	18

Task CE 3.1.3	Biology Restoration Monitoring Report	19

Task CE-3.1.4	Archaeological Monitoring and Report (CONTINGENCY TASK)	19

Task CE-3.2	Construction Activity Monitoring	21

Task CE-3.3	Quality Control Monitoring (Nonfield-Tested and Field-Tested Materials)	22

Task CE-3.4 	ADA Ramp and Push Button Inspection	23

Task CE-3.5 Additional Construction Activity Monitoring (CONTINGENCY TASK)	24

TASK CE-4	CONSTRUCTION SURVEYING	25

Task CE-4.1	Coordination, Calculations and Quality Assurance (QA) of Construction Contractor’s Survey Work	25

Task CE-4.2	Construction Survey and Staking	26

Task CE-4.3	Locate, Recover and Reference Monuments (CONTINGENCY TASK)	28

Task CE-4.4	Right of Way (“ROW”) Monumentation 	28

Task CE-4.5	Monumentation Survey Filing Map (SFM)	29

TASK CE-5	PROJECT CLOSE-OUT	29

Task CE-5.1	Final Inspection(s) and Submittals	30

Task CE-5.2	As-Constructed Plans	30

Task CE-5.3	Structure Load Rating	31

Task CE-5.4	Submittal of Final Project Documentation	31

E.2	PROJECT SCHEDULE	32

F.	CONTINGENCY TASKS	32

# PROJECT DESCRIPTION AND OVERVIEW OF SERVICES

This statement of work for CA/CEI Services (CA/CEI SOW) describes the Construction Engineering (CE) Tasks required for the contract.  The delivery schedule is provided in the “Deliverables and Schedule” section of each task.

The CA/CEI Services will culminate when Agency issues Final Acceptance of the Project and Consultant has completed all tasks and provided all deliverables as required.

Notes:

- Reference to “Contract” in this CA/CEI SOW is applicable if this is a Contract or Contract Amendment.

- Tasks/subtasks labeled as “Contingency Task” require written authorization from APM. See detailed requirements in Section F of this SOW.

Background [Leave this language in if adding CA/CEI as an amendment. Otherwise delete this “Background” language.]

The background for the Project is unchanged.

Phases of Services [Leave this language in if adding CA/CEI as an amendment. Otherwise delete this “Phases of Services” language.]

The Services are divided into the following phases:

[If this is an amendment, list any previous Preliminary Engineering (PE) phases of the Services for the Project completed under this Contract.]

- Preliminary Engineering/Design

- Design Acceptance

- Final Design and Bidding Assistance

- CA/CEI

Definitions and Acronyms

| DEFINED TERMS |
| --- |
| Acceptance | In this CA/CEI SOW, “Acceptance” or “Accept” means that Agency has reviewed the deliverable(s) submitted by Consultant and finds the deliverable(s) submitted in reasonable compliance with applicable requirements. Agency Acceptance does not release Consultant from liabilities due to any Errors or Omissions with respect to Consultant’s Services and deliverables. |
| Standard Specifications | General Conditions for Construction for (Agency Name) published by the Agency and the “2021 Oregon Standard Specifications for Construction”, Parts 00200 through 03000, “Technical Specifications”, current edition, published by the Oregon Department of Transportation and as amended by the Agency. |

| ACRONYMS |
| --- |
| AASHTO | American Association of State Highway and Transportation Officials |  | OCR | ODOT Office of Civil Rights |
| ODOT | Oregon Department of Transportation |  | OFW | Order for Force Work |
| APM | Agency’s Project Manager for CA/CEI Phase |  | OJT | On-the-Job Training |
| CA | Contract Administrator |  | ORS | Oregon Revised Statutes |
| CA/CEI | Contract Administration, Construction Engineering and Inspection |  | OSSC | Oregon Standard Specifications for Construction |
| CC | Construction Contractor |  | PA | Price Agreement |
| CCO | Contract Change Order |  | PE | Preliminary Engineering |
| CE | Construction Engineering |  | PM | Consultant’s Project Manager for CA/CEI Phase |
| CECI | Certified Environmental Construction Inspector |  | POR | Professional of Record |
| DBE | Disadvantaged Business Enterprises |  | PS&E | Plans, Specifications and Estimates |
| EEO | Equal Employment Opportunity |  | QA | Quality Assurance |
| EWO | Extra Work Order |  | QAC | Quality Assurance Coordinator |
| FHWA | Federal Highway Administration |  | QA/CA Plan | Quality Assurance & Contract Administration Plan (Form #734-5033) |
| FIR | Field Inspection Report |  | QC | Quality Control |
| IA | Independent Assurance |  | QCCS | Quality Control Compliance Specialist |
| IGA | Intergovernmental Agreement |  | RAS | Region Assurance Specialist |
| IQAP | Inspection Quality Assurance Program |  | RFI | Request for Information |
| LPA | Local Public Agency |  | RFP | Request for Proposal |
| LRFD | Load and Resistance Factor Design |  | ROW | Right of Way |
| NTE | Not to Exceed |  | SFM | Survey Filing Map |
| NTP | Notice to Proceed |  | SOW | Statement of Work |

# B.	STANDARDS and GENERAL REQUIREMENTS

1.	Standards applicable to CA/CEI Services

Consultant shall perform all Services in accordance with the professional standard of care set forth in the Contract.

Consultant shall complete the CA/CEI Services in accordance with the Contract, the current version in effect of the Agency’s QPP and the Local Agency Guidelines for Certified Local Public Agencies (LAG Manual), particularly Section C Chapters 8, 16, 17, ODOT Construction Manual, the Quality Control Compliance Specialist (“QCCS”) Handbook, the Manual of Field Test Procedures, the ODOT Inspector’s Manual.

The standards, manuals, directives, and other procedural guidance identified are not exhaustive and may not include all applicable standards for a given project.  Consultant shall be responsible for determining all applicable practices and standards to be used in performing Professional Services and Related Services.  Consultant shall inform and demonstrate to Agency if standards, directives, or practices required by Agency in performance of the work are insufficient, in conflict with applicable standards, or otherwise create a problem for the design or construction.  Should the requirements of any reference, standard, manual or policy referenced conflict with another, Consultant shall request Agency in writing to resolve the conflict.

ADA Compliance – Assessment, Design, Inspection.  When the Services under a Contract include assessment or design (or both) for curb ramps, sidewalks, or pedestrian-activated signals (new, modifications or upgrades), Consultant shall:

a.	 Utilize ODOT standards to assess and ensure Project compliance with the Americans with Disabilities Act of 1990 (“ADA”), including ensuring that all sidewalks, curb ramps, and pedestrian-activated signals meet current ODOT Highway Design Manual standards; and

b.	 Follow Agency’s processes for design, modification, upgrade, or construction of sidewalks, curb ramps, and pedestrian-activated signals, including using the ODOT Highway Design Manual, Agency Design Exception process, Agency and relevant ODOT Standard Drawings, Agency Construction Specifications, providing a temporary pedestrian accessible route plan and current ODOT Curb Ramp Inspection form.

When the Services under a Contract include inspection of curb ramps, sidewalks, or pedestrian-activated signals (new, modifications or upgrades), all such inspections shall include inspection for compliance with the standards and requirements in a. and b. above.  Inspections must be performed by ODOT certified inspectors (which must include certified environmental inspectors when appropriate).

[This language should be reviewed against the Certified LPA’s ODOT-approved ADA design and inspection processes. Some Certified LPAs, use ODOT’s curb ramp inspection forms while others have developed their own forms. If the work is on the local system and not on or along the state highway, these forms (or the CLPA’s approved equivalent forms) only need to be kept in the CLPA’s files. If the curb ramp is “on or along” the state highway, the forms are required to be submitted to ODOT per the instructions on the form.]

In addition, at Project completion, Consultant shall complete the applicable ramp-specific ODOT Curb Ramp Inspection Form734-5020(A-G) for each curb ramp constructed, modified, upgraded, or improved as part of the Project. Each completed form must be submitted electronically by clicking the “Submit by E-mail” button on the form (and cc APM). The forms are documentation required to show that each curb ramp meets ODOT standards and is ADA compliant. ODOT’s fillable Curb Ramp Inspection Forms and instructions are available at the following address: https://www.oregon.gov/ODOT/Engineering/Pages/Accessibility.aspx

Above references to curb ramps, sidewalks or pedestrian-activated signals also include, when applicable, shared use paths, transit stops, park-and-rides and on-street parking.

Unless otherwise specified in a Contract, the most current version of applicable standards, manuals, directives and other procedural guidance shall apply.  Unless otherwise specified, the system of measurement and language used in all deliverables will be English.

2.	General Requirements

As required in ORS 672.002 to 672.325, Consultant shall provide appropriate supervision and control with a licensed Professional Engineer in responsible charge of the CA/CEI Services.

All Inspection work must be performed by Agency-certified Inspectors as required by the Agency’s Inspection Quality Assurance Program (“IQAP”). Consultant’s Agency-certified Inspectors shall diligently monitor the work of the Construction Contractor (“CC”) in order to determine whether the Project is constructed in compliance with the construction contract documents and any applicable current standards and Agency manuals or procedures, including but not limited to those listed in the Contract. All Quality Control (“QC”) monitoring tasks must be performed by individual(s) certified by the Agency’s Technician Certification Program.

Consultant shall immediately advise Agency of any construction or planned construction which fails to conform to the construction contract requirements applicable to the Project.  Consultant shall also immediately advise Agency of any design errors or deficiencies or other problems that could have a negative impact on the Project construction schedule or construction cost. In addition, Consultant shall immediately advise Agency of any construction which Consultant knows, or with the exercise of professional care should know, fails to conform to the federal or state standards applicable to construction of the project.

3.	Communication

Communication is an important element to the successful completion of the Project and CA/CEI Services. All communication and deliverables covered under this CA/CEI SOW shall be directed to the APM (or such other individual as designated in writing to Consultant). In addition, Consultant shall submit deliverables specific to the administration of the construction contract, excluding claims to the APM for construction, as described within the ODOT Construction Manual. To the extent possible, all transmittals from Consultant to Agency must include the Project name, the Agency project number and the ODOT key number. For submittals, Consultant shall comply with naming conventions, and other instructions as specified by the APM. [Formats for the document control system shall be discussed at the initial meeting between Agency and Consultant pertaining to the CA/CEI Services.]

The CC for the Project will be determined through the competitive bidding or proposal process.  When the CC has been determined, Consultant shall establish appropriate contacts with that firm prior to the Pre-Construction Conference.

4.	Roles and Responsibilities

Agency

The APM is Agency’s primary point of contact for Consultant. The APM has the authority to review and accept, or recommend Acceptance of, all Consultant deliverables. The APM may distribute deliverables to appropriate Agency personnel for review and approval.

Agency has overall authority in scope, schedule, and budget of the Project. All construction Change Orders [Contract Change Orders (“CCO”), Extra Work Orders (“EWO”) and Orders for Force Work (OFW)] prepared by Consultant will be delivered to the Agency thorough the APM  and are subject to Agency review and approval prior to implementation by the CC.  Authority to approve all CCOs shall be by Agency.

Agency is responsible for the following:

- Execution of Intergovernmental Agreements (“IGAs”) related to the Project

- Prepare Agenda and lead/attend Pre-Construction Conference

- Contracting for material verification sampling and testing

- Concrete and Asphalt mix design review

- Providing access to construction related forms referenced in this CA/CEI SOW, Agency’s construction forms website, and hardcopy forms as needed

- Approving construction CCOs, EWOs and OFWs

- Approving requests for overrun or increase in Project authorization

- All contact with ODOT/Federal Highway Administration (“FHWA”) or other federal agencies

- All contact with ODOT for consultation with Native American Tribes (i.e. government-to-government discussions)

- Reviewing and processing monthly pay estimates for construction contract

- Final Project Acceptance

- Providing access to Agency-owned Right of Way (“ROW”) and easements

- Performing periodic quality, quantity and labor compliance documentation reviews

- Inspecting Project specific fabricated items

- Design modifications, as required [Delete if Consultant will be responsible for this task.]

Consultant:

Unless specifically stated otherwise in a particular task, Consultant shall provide all labor, equipment and materials to manage, coordinate and complete all tasks and provide all deliverables as set forth in this CA/CEI SOW (collectively, the “CA/CEI Services”) in accordance with the delivery schedules identified.

- Changes to Consultant’s Project Manager are subject to Agency approval and will require written notice to Agency prior to the change.

- If Consultant is performing the Construction Inspection, Quality Control Manager and Quality Control Compliance Specialist functions, then Consultant’s Key Persons (as identified on the approved QA/CA Plan) may not be substituted or replaced unless approved in writing by Agency.

- Consultant is not responsible for the means, methods, operating procedures or safety precautions of any CC or other entity.

Consultant is responsible for the following:

- Providing survey package to Agency and CC

- Lead/Attend Project meetings when requested by Agency

- Review and comment on progress submittals when requested

- Coordination with Agency and ODOT related to performing environmental compliance inspection

- Assist Agency with public outreach on the Project

- Design modifications, as required [Delete if Agency will be responsible for this task.]

# C.	REVIEW, COMMENT and SCHEDULE REQUIREMENTS

Consultant shall complete all CA/CEI tasks and deliverables in a timely manner to avoid unnecessary delays in the construction Project. Consultant shall provide written notice to Agency at the first sign of delays caused by Agency, Consultant, CC, or any other entity that may delay completion of the Project or otherwise have a negative impact on the construction schedule.

- Consultant shall notify APM immediately (within 2 business days) upon discovery of any changes in the Project that may impact scope, schedule, or budget of the Project or CA/CEI Services.

- Consultant shall submit to Agency all construction contract administration deliverables, excluding claims. Consultant shall submit all deliverables to APM or designee unless otherwise stated in specific tasks.

- All deliverables are considered draft until reviewed and accepted by Agency. Agency will return comments on deliverables within 5 business days of receipt.  Consultant shall make revisions to address Agency comments and submit revised deliverable(s) to APM within 3 business days of receipt of Agency review comments, unless a different timeframe is stated in specific tasks or otherwise agreed to in writing by Agency. If no revisions are necessary, the submittal will be considered final.

# D.	FORMAT REQUIREMENTS

- Deliverables shall be submitted to Agency in the format described in the ODOT Construction Manual and individual tasks. Following NTP, Consultant shall submit all construction contract deliverables, excluding claims, to the APM as described within the ODOT Construction Manual. Claims must be submitted according to Section 00199.

- The time zone is Pacific Standard Time (PST) to determine time of receipt of notices and other documents. Non-business days are Saturdays, Sundays and legal holidays as defined by ORS 187.010 and 187.020.  If received on a non-business day, or after 5:00 p.m PST on a business day, it shall be considered as received at 8:00 a.m. PST on the next business day.

- Agency and ODOT Forms – Consultant shall use Agency Forms supplied by the APM. Utilize ODOT forms where required. ODOT Construction related forms referenced in this CA/CEI SOW are available online at: https://www.oregon.gov/ODOT/Construction/Pages/Forms.aspx

- Each draft and final text-based or spreadsheet-based deliverable shall be provided in MS Office file formats (i.e., Word, Excel, MS Project, etc.) and must be fully compatible with version used by Agency.

- Additional format requirements may be listed with specific tasks or deliverables throughout the CA/CEI SOW or in the Contract.

# E.1	TASKS, DELIVERABLES and SCHEDULE

Task Numbering: For purposes of standardization, task numbers in this SOW may be non-sequential due to deletion of unneeded tasks from Agency’s CA/CEI SOW template. For convenience to the reader, the task numbering for the CA/CEI phase will use the standard task number prefaced with “CE” (CE-1, CE-2).

## TASK CE-1	PROJECT MANAGEMENT OF CA/CEI SERVICES

This activity is continuous throughout the duration of these CA/CEI Services.  Consultant shall guide and direct the CA/CEI Services and Consultant’s team in conformance with all applicable requirements of the CA/CEI Services and the Project’s goals and objectives.  Consultant shall monitor progress of the Project and CA/CEI Services.

### Task CE-1.1	Coordination

Consultant shall provide leadership, direction, and control of these CA/CEI Services to the subconsultant team.

Consultant shall:

- Direct Consultant’s team regarding overall CA/CEI activities and team meetings.

- Maintain liaison, communication and coordination between Consultant and subconsultant staff, APM, if applicable, CC and Agency staff to facilitate timely, efficient operations for all involved.

Deliverables and Schedule:

- On-going coordination and communication as needed to appropriately manage the CA/CEI Services (no tangible deliverables for this task).

### Task CE-1.2	Status Reports and Invoices

Consultant shall prepare up to 12 Monthly Status Reports throughout the duration of the CA/CEI Services which is through 3rd notice.  See Section E.2, Project Schedule.

The Monthly Status Report must:

- Describe the previous month’s Consultant activities. Describe the planned activities for the next month.

- Identify any issues or concerns that may affect the CA/CEI Services and budget or the Project schedule and Project budget.

If the construction Project schedule milestones are significantly revised, Consultant shall attach the updated Project schedule and submit with the Monthly Status Report. Consultant shall submit the Monthly Status Reports to APM with the monthly Consultant invoice.

Deliverables and Schedule:

- Monthly Status Report - Submitted to APM with the monthly invoice no later than the 5th calendar day of the month following the reporting month.

## TASK CE-2	CONSTRUCTION CONTRACT ADMINISTRATION/CONSTRUCTION ENGINEERING and INSPECTION (CA/CEI)

Consultant shall support the Project’s needs by providing CA/CEI Services required for the Agency to certify, at Second Notification and Third Notification that the Project was completed according to the Plans and Specifications for the Project.  Consultant shall engage the Professional of Record (“POR”) as required to provide engineering Services required to administer design changes that may become necessary during the construction phase of the work.

### Task CE-2.1	Pre-Construction Conference

Consultant shall prepare for and lead/attend the Pre-Construction Conference referenced in the Specifications in 00180.42, and the ODOT Construction Manual, Chapter 11 – Before On-Site Work Begins. Attendees will include the Consultant, CC, APM, ODOT staff, permitting agencies, utility representatives, local officials and others as may be appropriate to discuss the construction schedule, utility involvement, permit concerns, required documentation submittals, materials, and other items relevant to the construction of the Project.

APM will consult with the CC, and the Consultant to determine participants and schedule the Pre-Construction Conference at an agreed upon time and place.

Consultant shall:

- Lead/Attend and participate in Pre-Construction Conference.

### Task CE-2.2	Cooperative Arrangement (Partnering) (Reserved)

### Task CE-2.3	Quality Assurance & Contract Administration Plan

Consultant shall prepare a Quality Assurance & Contract Administration Plan (“QA/CA Plan”) for the CA/CEI Services for the Project, using ODOT form 734-2857 (as may be amended from time to time by ODOT) which is available electronically on the following website: https://www.oregon.gov/ODOT/Construction/Pages/Forms.aspx.

The QA/CA Plan must identify Consultant’s certified quality assurance and construction inspection personnel and the personnel responsible for each of the major construction-related tasks identified in this CA/CEI SOW.

Consultant shall submit a draft QA/CA Plan (electronically via email) to the APM for review and comment.  Agency will review the draft QA/CA Plan and return any comments to Consultant within 5 business days. Consultant shall respond to Agency comments and revise the draft QA/CA Plan as necessary.

Consultant shall prepare the final QA/CA Plan making all required revisions per the Agency draft review comments.   Agency will issue approval or return any additional comments to Consultant within 5 business days of receipt of the final QA/CA Plan. If necessary, Consultant shall revise the final QA/CA Plan to address Agency’s additional comments.

Consultant shall make any necessary updates to the QA/CA Plan as work progresses and submit the updated QA/CA Plan to the APM for review and approval.

Deliverables and Schedule:

- Draft QA/CA Plan (form 734-2857) - Submit to APM no later than 5 business days following the date of NTP for CA/CEI phase.

- Final QA/CA Plan (form 734-2857) - Submit to APM within 5 business days of receiving Agency comments on draft QA/CA Plan.

- Updated QA/CA Plan (form 734-2857) - Submit to APM within 5 business days of changes that require the update.

### Task CE-2.4	Construction Contract Administration

Agency will provide day-to-day administration of the construction contract. For items listed in this SOW Consultant shall complete contract administration tasks as outlined in the ODOT Construction Manual, the Manual of Field Test Procedures, the Nonfield-Tested Materials Acceptance Guide, the ODOT Inspector’s Manual, QCCS Handbook, Qualified Products List (“QPL”), the Contract Plans and Specifications, and this CA/CEI SOW.

Consultant shall assist Agency to prepare for up to two periodic reviews on all Project quality, quantity, labor compliance and Civil Rights documentation. The reviews will be performed by the ODOT Region Assurance Specialist (“RAS”) per the ODOT Construction Manual, Chapter 12B - Quality, Section 12B-3, and the Office of Civil Rights (“OCR”) per the ODOT Construction Manual, Chapter 18 – Workforce and Small Business Equity Programs and Section C Chapters 16- Construction Adm., 17 - Closeout, and 8 – Civil Rights in the LAG. Consultant shall resolve all documentation deficiencies noted during the periodic reviews prior to the next scheduled review.  Final documentation reviews by the RAS and OCR Field Coordinator will be performed as directed in the ODOT Construction Manual.

In addition to any other requirements identified in the reference standards identified above, Consultant shall:

- When requested prepare up to five CCO, EWO, OFW as outlined in the ODOT Construction Manual, Chapter 15 – Change Orders, Force Account, Work by Other Forces, and Chapter 12G – Extra Work Performed on a Force Account Basis. Change Orders may include, but are not limited to, modification to the plans, specifications, and contract time. Consultant may be liable for payment of the cost for any CCOs, EWOs and OFWs authorized without obtaining prior review and approval by Agency.  Only the Agency has the authority to approve and authorize changes to the construction contract including CCOs, EWOs, or OFWs.

- When requested review up to five Force Account billings from CC.

Deliverables and Schedule:

- Resolution of any documentation deficiencies as noted on the Documentation Review Report per the RAS review. Deficiencies -must be resolved prior to next review.

### Task CE-2.5	Monthly Preliminary Progress Estimates

Consultant shall prepare all source documents as “paynotes” for the monthly progress estimate and provide them to the Agency for entry into the Agency’s Engineering Contract Management System (“ECMS”) for CC’s work performed through the last working day of the pay period. (Refer to the ODOT Construction Manual Chapter 12D - Quantities).

After all paynotes are entered, Agency will generate the Preliminary Progress Payment Report and provide it to Consultant for review with the CC for concurrence on quantities being paid for the previous month’s work.

Deliverables and Schedule:

- Following each month in which CC’s work was performed, submit all source documents (“paynotes”), in electronic .pdf format, as necessary for each monthly Progress Estimate for Agency review by the Monday following the Thursday established at the pre-construction conference for the close of the pay period.

### Task CE-2.6	Project Progress Meetings

Consultant shall conduct/attend periodic Project Progress Meetings with the CC and others as needed, including but not limited to, APM, permitting agencies, and local officials if required. The Project Progress Meetings are intended to promote Project progress, proper communications, effective working relationships and timely issue resolution.

Consultant shall also conduct/attend additional activity-specific technical kick-off meetings for various activities required by the construction contract.  These activities may include, but are not limited to:

- Survey

- Asphalt Concrete Pavement

- ADA Curb Ramps

- Hazardous Materials Handling

- Traffic Signals

- Pile Driving

- Drilled Shaft Installation

- Bridge Deck Concrete Placement

Consultant shall:

- Schedule, conduct/attend and participate in Project Progress Meetings as needed, or as agreed to by APM. Project Progress Meetings are recommended to be held weekly during active construction periods but may be held less frequently during periods of low construction activity.

- Prepare Project Progress Meeting agendas and inform attendees.

- Record and distribute Project Progress Meeting minutes.

ASSUMPTIONS FOR BUDGETING PURPOSES: Project Progress Meetings are assumed to be weekly (during active construction) with no more than two Consultant staff attending and 18 (6 mo. x 3 mtgs/mo.) meetings assumed, see Section E.2 Project Schedule.

Deliverables and Schedule:

- Project Progress Meeting agendas – 1 electronic copy to each meeting attendee and APM, 2 business days prior to scheduled meeting.

- Conduct/Attend and participation at Project Progress Meetings.

- Project Progress Meeting minutes – 1 electronic copy to each meeting attendee and APM, within 5 business days after the meeting.

- Request to cancel Project Progress Meetings based on inactive construction period – Submit written request electronically to APM at least 2 business days prior to scheduled meeting.

### Task CE-2.7	Working Drawings, Shop Drawings, and other Submittal Reviews

Agency will coordinate and review construction Working Drawings, shop drawings, and other submittals submitted electronically by the CC. Consultant shall assist Agency with review of specific drawings and submittals when requested.  When electronic Working Drawings, shop drawings, and other submittals are received, according to 00150.35(c)(2), 00150.37, & 00170.08, when requested Consultant shall ensure the review is complete and the Working Drawings, shop drawings, and other submittals are returned to the Agency within the timeframes specified in the construction contract.  Consultant shall log in the submittal when it arrives, track the submittal to ensure timely response, and log out the reviewed submittal when it is returned to the Agency. Consultant shall conduct submittal review in accordance with the Specifications in 00150.35, 00150.37, 00170.08, and the ODOT Construction Manual, Chapter 16 – Working Drawings and Submittals.

Consultant shall:

- Maintain as-submitted copy in thein the Project files

- Review specific drawings and submittals when requested by the Agency. Consultant shall review and prepare mark-up/comment copies of the Working Drawings, shop drawings, and other submittals. Stamped Drawings must be signed and dated by the POR and marked as either RV = Reviewed, or RVC = Reviewed with Comment. Unstamped Drawings shall be marked as either AP = Approved, AX = Approved as Noted, RC = Returned for Correction, or R= Rejected.  All reviews will identify the individual making comment and be date marked.

- Include construction contract number on all Working Drawings, shop drawings, and other submittals.

Consultant shall review the following submittals as required using the guidelines in ODOT’s Construction Manual, Chapter 16 – Working Drawings and Submittals, and the Specifications in 00150.35, 00150.37, & 00170.08:

- Traffic control plans

- Erosion control plans

- Construction baseline schedule

- Machine control survey submittals

- Drainage structures (manholes and inlets) Working Drawings, shop drawings, and other submittals

- Retaining wall calculations and drawings

- Reinforcement

- Pile hammer

- Manufactured items (Prestress girders, steel fabrications, castings, etc.)

- Lighting pole and traffic signal pole submittals

- Blue or green sheet submittals for traffic signal or electrical equipment and materials

- Others as required by the Agency and construction contract specifications

Deliverables and Schedule:

- Return approved Working Drawings, shop drawings, and other submittals with comments (within time frame established in construction contract specifications):

  - 1 copy maintained in Project files

- Electronic Submittals:

  - Submit 1 electronic PDF mark-up/comment to the APM as required by the construction contract.

Consultant shall also ensure notification of approved Working Drawings, shop drawings and other submittals is provided to the Agency when applicable.

Files Retained by Consultant:

Consultant shall maintain files of all reviewed Working Drawings, shop drawings, and other submittals according to the retention period set forth in the terms and conditions of the Contract. Agency may request these files at any time during the retention period.  Consultant shall provide the files to Agency within 14 calendar days of the request.

### Task CE-2.8	Consultation during Construction

Consultant shall provide consultation and technical Services regarding design issues raised during construction of the Project. Consultant shall clarify construction contract documents and provide written responses to Requests for Information (“RFIs”). The design consultation will occur only as required and may be ongoing throughout the CA/CEI Services and the Project.

Upon request of Agency during construction, Consultant shall:

- Clarify construction contract documents.

- Respond to field inquiries.

- Engage the services of the POR on all matters involving design changes.

NOTE: Design requests must be initiated by either Agency or Consultant using a Change Request Form or a RFI.  A response to a RFI may also initiate a Change Request or a formal contract amendment for Consultant or CC.   No work shall be conducted on a Change Request until the APM approves the request and the appropriate Change Order document is approved. The Change Request must clearly outline Consultant’s cost, the estimated construction cost, and the cause of the change.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes up to 25 RFIs, each requiring up to 4 hours of staff time for preparation and documentation of the response.

Deliverables and Schedule:

- Written documentation of responses to CC or Agency inquiries.  Submit 1 electronic copy to APM within 2 business days of inquiry unless other delivery date is agreed to by APM.

### Task CE-2.9	Design Modifications (CONTINGENCY TASK)

If Consultant or CC determines that design modifications may be necessary, Consultant shall discuss potential changes with APM and POR prior to verbally agreeing on changes with CC or preparing the appropriate Change Order documents, depending upon the type of work (changed work, extra work, or force account work). Upon request of the APM, Consultant shall work with the POR to prepare detailed engineering design revisions necessitated by conditions encountered during construction.  These design revisions must be accompanied by the necessary Change Order documents (CCO, EWO or OFW) to make them a part of the construction contract.

Deliverables and Schedule:

- Design details for modifications (prepared or approved by the POR for appropriate changes to Project design) - Submit to APM at date agreed to when work was requested.

- Draft CCO and EWO or OFW documents with supporting documents (cost estimate and justification) - Submit to APM at date agreed to when work was requested.

### Task CE-2.10	Claim(s) Support (CONTINGENCY TASK)

If authorized by APM, Consultant shall provide support to Agency to review and respond to any and all claims submitted by the CC as specified in the Specifications in Section 00199 – Disagreements, Protests and Claims. Consultant tasks for claim(s) support may include but are not limited to:

- Prepare memoranda and supporting documentation (photo logs, inspection reports, memos, drawings, etc.) related to claims.

- Provide consultation related to claims (in person, via telephone or email).

- Attend claim resolution meetings.

- Prepare a claim decision in conformance with the requirements of the Specifications in 00199.40(a).

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than 64 hours for claim(s) support. Assume up to 1 claim submittal, each requiring 4 staff to do 1 day of preparation and attend up to 1 all-day meeting for each claim, plus Consultant Principal and PM reviews and clerical assistance.

Deliverables and Schedule:

The deliverables for claim(s) support may include but are not limited to:

- Memoranda and supporting documentation (photo logs, inspection reports, memos, drawings, etc.) related to claims

- Consultation related to claims (in person, via telephone or email)

- Attendance at claim resolution meetings

- Claim decision that satisfies the Specifications in 00199.40(a)

### Task CE-2.11	Public Records Request Support (CONTINGENCY TASK)

If authorized by APM, Consultant shall provide support to Agency to review and respond to public records requests submitted by the CC, attorneys or anyone else that may have an interest in the Project, as referenced in the ODOT Construction Manual Chapter 12 – Project Records and the ODOT Records Manual.

Requests for records may also come from other State Agencies such as the Bureau of Labor and Industries (“BOLI”).

Consultant’s primary review of records shall be of records in Consultant’s possession or control. Consultant will not be allowed access to the records or files of Agency, but Agency may provide prescreened documents to Consultant to facilitate Consultant’s Services under this task.

Consultant shall not provide any records in response to a Public Records Request or a request from another State Agency without approval from the APM.

Consultant shall provide public records request support (as needed for the Project and subject to the other requirements set forth in this task) including but not limited to the following tasks:

- Respond to requestor for clarification and questions

- Coordinate with the APM to determine whether litigation has been filed on the Project.

- Determine, in consultation with the APM, which records are being requested and whether any exemptions or privileges apply to the requested records.

- For Public Records Requests:

o Provide the requestor with an initial estimate.

o Submit written estimate via email to requestor in order to receive their notice to proceed.

o Upon receipt of requestor’s notice to proceed, copy the requested records and redact any   requested records on the exempted list.

- For records requests from other State Agencies (e.g. BOLI requests)

o Copy and provide requested records within the time frame specified by the requestor.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than 8 hours for public records request(s) and State Agency records request(s) support. Assume up to 1 records request(s), each requiring 1 staff to do 1 day of preparation, PM review and clerical assistance.

Deliverables and Schedule:

The deliverables for records request(s) support may include but are not limited to:

- Providing an initial response to the requester in writing within 10 business days after receiving the request.

- Providing an initial estimate of the cost for the requestor (for Public Records Requests

only)

- Providing redacted copies of the requested records to the requestor (for Public Records

Requests)

- Providing the requestor copies of the records, if requested by a State Agency

## TASK CE-3	CONSTRUCTION, ENVIRONMENTAL COMPLIANCE AND WORK ZONE MONITORING AND INSPECTION

Consultant shall provide on-site monitoring and inspection of construction for conformance with, and shall enforce compliance with, construction contract documents.  Consultant shall coordinate and conduct on-site monitoring and inspections so they do not cause unnecessary adverse impacts to the construction schedule.  On-site monitoring and inspections must occur at critical times during the construction process based on Consultant’s evaluation of the CC’s schedule, construction contract documents and as outlined in the ODOT Construction Manual, the Manual of Field Test Procedures and the ODOT Inspector’s Manual.

Consultant shall have certified Inspector(s) on site during all critical times during the construction process.  Consultant shall monitor the CC’s quality control process for compliance with the construction contract requirements.  All persons involved in performing inspection duties must be certified through the ODOT Inspection Quality Assurance Program (“IQAP”) in the discipline for the work they will be inspecting. Consultant’s Inspectors must be certified prior to commencement of any on-site work by the CC.

If circumstances occur that prevent the use of a Certified Inspector, Consultant may assign specific tasks to a non-certified individual.  Refer to the IQAP for a list of limited duties that may be performed by non-certified personnel.

The following are the approved ODOT Inspector Certifications currently in place in the Inspection Quality Assurance Program:

- Certified Bridge Construction Inspector (“CBCI”)

- Certified Environmental Construction Inspector (“CECI”)

- Certified Traffic Signal Inspector (“CTSI”)

- Certified General Inspector (“CGCI”)

- Certified Asphalt Concrete Pavement Inspector (“ACP”)

- Certified Drilled Shaft Inspector (“CDSI”)

- Certified ADA Curb Ramp Inspector (“ADAI”)

Consultant shall perform work zone monitoring as required by the ODOT Construction Manual, ODOT Inspector’s Manual and the construction contract documents. Accordingly, Consultant shall monitor and enforce the following for compliance to construction contract requirements:

- Permit compliance during construction

- Temporary Traffic Control measures

- Temporary Pedestrian Access Route measures

- Erosion Control installation and maintenance

- Turbidity Monitoring (if required)

Consultant shall monitor the CC to verify the following deliverables are completed and submitted (to the extent the deliverables are required by the construction contract documents). If the documents are not submitted to the Consultant, then the Consultant shall take appropriate action to require compliance by the CC:

- Traffic Control Inspection Reports (Form number 734-2474) [When the Schedule of Items does not include an item for a TCS]

- Erosion and Sediment Control Monitoring Reports

- Turbidity Monitoring Reports (if required)

### Task CE-3.1	Environmental Compliance and Mitigation Monitoring

This task involves conducting environmental inspection site visits during the construction phase of the Project, typically to document compliance with the environmental permits, including effectiveness of best management practices, avoidance and minimization measures, challenges encountered and corrective actions.

Consultant shall:

- Perform compliance and mitigation monitoring related to environmental conservation measures agreed upon with State and Federal regulatory agencies through permit conditions and as included in the construction contract.

- Conduct environmental inspections site visits to assist CC and Agency in maintaining compliance with issued regulatory permits and the special provisions.

- Provide documentation of the construction process relative to this environmental compliance.

- Coordinate and schedule monitoring visits coincident with activities that have significant environmental components.

- Evaluate on-site conditions and construction techniques during environmental inspection site visits to assess compliance with Project permits, the Pollution Control Plan, the Erosion and Sediment Control Plan, proposed site rehabilitation measures, and general environmental conservation measures.

- Identify deficiencies and potential permit compliance issues and provide guidance to Agency and CC to aid in avoiding potential regulatory agency involvement or violations.

- Provide input and clarifications during construction activities to facilitate biological functioning as outlined in Project permits.

If deficiencies are noted, Consultant’s Environmental Specialist shall immediately bring the deficiency to the attention of the CC, APM and ODOT Environmental Unit and recommend a corrective course of action to comply with environmental regulations, performance standards, and permit conditions.

Consultant shall review the CC's following submittals for compliance with the construction contract and permits.

- Erosion and Sediment Control Plan (“ESCP”),

- Pollution Control Plan (“PCP”), and

- Weed Control Work Plan (“WCWP”).

Consultant shall conduct up to 3 environmental inspection site visits and prepare brief construction environmental inspection report or monitoring memorandums summarizing site conditions and providing recommended measures to facilitate permit compliance and correct deficiencies.

Deliverables and Schedule:

- Reviewed CC-submitted Erosion and Sediment Control Monitoring Reports (Form 734-2361) for compliance no later than 14 calendar days after each inspection site visit.  Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

- Completed Consultant construction monitoring memorandums – If compliance issues are noted, document the deficiencies, recommendations and corrective action taken to correct deficiencies. Submit 1 electronic copy each to APM within 5 business days after the monitoring site visit.

- General Daily Progress Reports / Project Diary – Complete daily when performing onsite visits. Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

- Project Photography / Photo Logs – Submit with reports (when applicable) along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

### Task CE 3.1.1	Endangered Species Consultation for the Federal-Aid Highway Program (“FAHP”)

[Delete task 3.1.1 language and mark as “RESERVED” if not applicable to the Project]

This task involves conducting FAHP Programmatic environmental inspection site visits during the construction phase of the Project and post construction phase.

If the project utilized the FHWA Programmatic Endangered Species Consultation for the FAHP Environmental Inspections shall conform to the FAHP User’s Guide.

FAHP Environmental inspections site visits are required of all projects implemented under the FAHP Programmatic Biological opinion.

For the FAHP, this includes at least 1 FAHP environmental inspection site visit and environmental inspection report for the Project for each construction year, a FAHP environmental completion inspection site visit at Project completion and Project Completion Report, and As-Built Report.

FAHP environmental inspections by Consultant shall be completed by a qualified Biologist or when approved by the ODOT Region Environmental Unit, an ODOT CECI.

Professional Licenses, Registrations and Qualifications

For Services under CE Task 3.1.1, the Consultant is the Professional of Record for the work, which shall be executed by a qualified Biologist or other qualified professional meeting the following minimum qualifications: 3 full years of environmental analysis or resource project management experience and a Bachelor’s degree that included 30-quarter or 20-semester hours in biology, environmental science, physical science, natural science, or closely related field. Individuals who make determinations of effect under the Endangered Species Act (“ESA”) and prepare ESA documentation must also have ODOT Biologist certification (as per Technical Services Bulletin GE12-01(B) or updated). Additional qualifications may be required for certain tasks.

The number of FAHP environmental inspection site visits shall correspond with construction stages that include high risk environmental items and best management practices. The Consultant, through the Biologist or approved CECI, shall review high risk items related to the following:

[List all activities anticipated to require environmental inspection, as applicable, based on FAHP guidance listed above, this will require the APM to discuss the list of activities with the ODOT Region Environmental Unit and the Project Biologist. Add or delete items in the following list as individual project requires.]

- Erosion and Sediment Control

- Pollution Control/ Containment

- Sensitive Areas (No work zones)

- Site Restoration

- Fish and Wildlife Protection

- Native materials designated for avoidance

- Cleared Vegetation

- Native materials (soil, streambed substrate, logs, trees) designated for use in restoration

- Herbicide treatment buffers

- Fish screens and in-water work area isolation

- High stream flow events

- In-water work [e.g., bank stabilization, pile driving]

- Containment practices and structures

- Treated wood

- Hydro-acoustic impact minimization measures implementation

- Bank stabilization/ site restoration implementation

- Migratory Bird Nesting

Consultant shall conduct up to 3 FAHP environmental inspection site visits and prepare environmental inspection reports summarizing site conditions and providing recommendations of measures to facilitate permit compliance and correct deficiencies.

Consultant shall conduct 1 FAHP environmental completion inspection site visit and prepare the final Project Completion Report summarizing site conditions and providing recommended measures to facilitate permit compliance and documentation of any corrected deficiencies.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than 4 environmental site inspection(s) for Endangered Species Consultation for the FAHP.  Assume up to 8 hours for each FAHP environmental site inspection(s) and environmental inspection report by either an ODOT-certified Biologist or approved CECI.

Deliverables and Schedule:

- A draft and final Environmental Inspection Report for each inspection site visit using ODOT’s template report 734-2902 (for the FAHP, it is available on the FAHP website) – and submitted to the Agency and the ODOT Region Environmental Unit.  The draft Environmental Inspection Report due no later than 14 calendar days after each inspection.  Final Environmental Inspection Report due no later than 14 calendar days after receiving final comments from Agency.

- Final Project Completion Report - Summarizing site conditions, recommended measures to facilitate permit compliance and documentation of any corrected deficiencies. Submitted to the REU within 60 calendar days of Second Notification.

- As-Built Report – Submit 1 electronic (PDF copy) each to APM within 30 calendar days of conducting the final site visit. The As-Built drawings can be handwritten markups of the plan sheets.

### Task CE-3.1.2 Restoration As-Built Report

[Delete task 3.1.2 language and mark as “RESERVED” if not applicable to the Project. If applicable, the following must be included without any additions, deletions or revisions.]

Consultant shall prepare a Restoration As-Built Report to document restoration completion.  Consultant’s Restoration As-Built Report must document construction and effectiveness of onsite restoration for the Project.  Prior to preparation of the report, Consultant shall conduct 1 site visit within 30 days of restoration construction completion to determine if restoration measures were constructed according to Project permits.  The Restoration As-Built Report must include a narrative summary describing Project construction and restoration as well as maps, and representative photographs with descriptions.

Consultant shall visit the site to collect data regarding restoration conditions, planting survival, and to evaluate if corrective measures are necessary.  As part of this work, Consultant shall conduct the quarterly plant establishment site visits (in accordance with Section 01040 of the Standard Specifications) during the spring, summer and fall the first year after Acceptance of initial planting and seeding (unless otherwise specified in the construction contract).  During the site visits, Consultant shall record general site conditions, hydrology, plant cover, plant communities, erosion, and related aspects of the restoration.  Consultant shall conduct inspections that document plant stress and planting survival.  Consultant shall provide recommendations for replacement plantings and invasive species controls (if necessary).  Consultant shall establish photo point locations and shall take photographs to document annual site conditions.

Deliverables and Schedule:

- Restoration As-Built Report – Submit 1 electronic (PDF copy) to APM within 30 calendar days of conducting the site visit.

### Task CE 3.1.3	Biology Restoration Monitoring Report

[Delete task 3.1.3 language and mark as “RESERVED” if not applicable to the Project. If applicable, the following must be included without any additions, deletions or revisions.]

After the first year of site visits, Consultant shall prepare the first annual Biology Restoration Monitoring Report to document compliance with the permits issued for the Project, following ODOT standards. (Additional annual monitoring reports will be prepared by Agency or ODOT if required.)

Consultant shall utilize Agency’s template reports and shall document the condition of mitigation or enhancement, features, and the restoration of the site including planting survival estimates, any deficiencies noted during the monitoring period, and recommendations to facilitate permit compliance.

Deliverables and Schedule:

- First Annual Restoration Monitoring Report – Submit1 electronic (PDF copy) each to APM within 30 calendar days of conducting the site visit.

### Task CE-3.1.4	Archaeological Monitoring and Report (CONTINGENCY TASK)

[If Section 00290.51 of the Specifications identifies sensitive cultural sites on this Project then this task must be included. Delete task 3.1.4 language and mark as “RESERVED” if not applicable to the Project. Label this subtask as “Contingency” if it is not known at time of Contract execution, on whether or not it is needed. If applicable, the following must be included without any additions, deletions or revisions except blue highlighted fields.]

General Requirements and Applicable Standards

Consultant shall ensure compliance with protection of cultural resources, protection of sensitive cultural sites, and archaeological monitoring practices in accordance with the Specifications Sections 00290.50 and 00290.51, and the ODOT Construction Manual, Chapter 32 – Protection of Cultural Resources.

The Services required by this task must be completed by professional staff archaeologists who meet the Secretary of the Interior's professional standards for Archaeology (36 CFR 61, Appendix A). All work must be reviewed (QA/QC) and approved by professional staff archaeologists who have been qualified through the Agency Cultural Resources Consultant Qualification Training Program.  If Agency returns deliverable(s) with extensive edits or comments, Consultant’s research, writing and editing to address Agency’s edits and comments must be at the expense of Consultant.

Agency’s Archaeologist will be responsible for:

- All tribal consultation (i.e. government-to -government discussions),

- Drafting Finding of Effect (“FOE”) documents and submitting to SHPO,

- Obtaining necessary clearance documents from SHPO, and

- Submitting Determination of Eligibility (“DOE”) and Memorandum of Agreement (“MOA”) documents to State Historic Preservation Office (“SHPO”) and Tribes.

Consultant shall:

- Prior to on-site construction, Consultant shall discuss location of archaeological sites and high probability areas with CC, Inspector(s), Agency Regional Environmental Coordinator and Agency Archaeologist. Consultant shall ensure the CC has fenced all No Work Zones with orange plastic mesh fencing or lath and flagging, as required by the Plans and Special Provisions.

Consultant shall conduct research and tribal coordination as needed for the Project including, but not limited to, checking tribal databases, coordinating with tribes to conduct necessary literature reviews, and satisfying obligations outlined in state archaeology permits.

Consultant’s cultural monitor must be a professional staff archaeologist.  Consultant’s cultural monitor shall:

- Review cultural reports prepared for Project.

- Complete and sign ODOT’s Archaeology QC Checklist and submit with deliverables.

- As applicable, obtain SHPO, Tribal Historic Preservation Officer (“THPO”), or Archaeological Resources Protection Act of 1979 (“ARPA”) archaeological permit.

- Attend pre-construction meeting at request of Agency Archaeologist.

- Provide on-site Project monitoring and maintain daily log of findings.

- Prepare draft and final Monitoring Reports documenting activities and discoveries. Submit Monitoring Report in Word and *.pdf formats with the following (if no cultural materials are found):

  - Project Description

  - Map of Area of Potential Effect (“APE”)

  - Dates of monitoring and personnel that conducted monitoring

  - General observations with statement of probability of future inadvertent discoveries within APE

- If cultural materials or human remains are discovered during monitoring, Consultant’s cultural monitor shall:

- Notify Engineer immediately and comply with Section 00290.51 (a) and (b) of Specifications.

- Contact Agency Archaeologist to determine additional archaeological investigation requirements.

- Conduct required literature review, which must include a review of all applicable archaeological survey/testing reports for comparable information and checking the SHPO database and any other facilities or necessary documentation.

- Obtain archaeological permits if necessary and share draft with Agency Archaeologist prior to submittal to SHPO.

- Prepare a DOE (which may be included in the Monitoring Report).

- Include the following additional information in the Monitoring Report required above:

  - Ethno-historic information,

  - Previous archaeological studies,

  - Section on field methodology with maps showing placement of shovel probes and test units,

  - Section on findings,

  - Artifact descriptions,

  - Recommendations and summary including a discussion on the site tested and if it meets National Register of Historic Places (“NRHP”) criteria and maintains integrity,

  - All applicable maps showing Project location and site boundaries and areas monitored,

  - Photos including pictures of overall construction work in and near area monitored, and any features, sites, and/or isolates encountered,

  - Artifact catalogue, site and isolate forms and any update forms for previously recorded sites.

Deliverables and Schedule

- If applicable, draft archaeological permit(s) within __business days of NTP.

- Draft Monitoring Report and DOE (in Word format) within 20 business days of completion of fieldwork. Include completed ODOT Archaeology QC Checklist.

- Final Monitoring Report and DOE (in *.pdf format with SHPO coversheet) with GIS shape file of monitored area within 10 business days of receiving comments from Agency

### Task CE-3.2	Construction Activity Monitoring

Consultant shall monitor construction activities during construction of the Project utilizing ODOT-certified Inspectors and require compliance with the construction contract documents. Consultant shall provide inspection concurrently with the CC’s operation. Consultant shall coordinate closely with CC to ensure on-site inspections are coordinated with the construction schedule. Consultant shall perform inspections as detailed in the ODOT Construction Manual and the ODOT Inspector’s Manual. Consultant shall prepare General Daily Progress Reports of construction for days Consultant is on site. Consultant shall take photos of the various construction activities and keep a current digital photo-log of critical construction activities. The photo-log must be kept up to date throughout construction and available for review by Agency.

Consultant shall determine and document all pay quantities for work and materials incorporated into the Project.  As required by the ODOT Construction Manual, Chapter 12D – Quantities, Consultant shall prepare source documents (“paynotes”) for all pay items and include supporting documentation to support each payment. Consultant shall always keep quantity documentation current and available for Agency review upon request.

Deliverables and Schedule:

- General Daily Progress Reports – Complete each day Consultant is on-site. Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

- Current Digital Photo-log of construction activities - Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

- Source Documents “paynotes” - Field notes, calculations, receipts, invoices, reports used to determine Project pay quantities, installation sheets, and other supporting documentation – Complete and submit to APM as work is performed. In addition, follow protocol provided in Task CE-2.5 – Monthly Preliminary Progress Estimates and Task CE-5.4. – Submittal of Final Project Documentation.

- CC’s EEO/DBE and OJT/Apprenticeship reports, if required – Submit as required by construction contract.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than six months of full-time inspection.

### Task CE-3.3	Quality Control Monitoring (Nonfield-Tested and Field-Tested Materials)

Consultant shall document the work and Nonfield-Tested materials incorporated into the Project by completing Field Inspection Reports (FIRs) as required by the ODOT Construction Manual, Chapter 12C – Quality and the Nonfield-Tested Materials Acceptance Guide. Consultant shall log the FIRs and other supporting quality documentation into the applicable Test Summary and keep up to date and available for review by Agency. Consultant shall maintain the Nonfield-Tested Materials Test Summary (Test Summary “A” 734-1902A) as detailed in the ODOT Construction Manual.

Consultant shall monitor the CC’s Quality Control (“QC”) program for conformance with requirements of the ODOT Manual of Field Test Procedures and the construction contract documents.  Consultant shall coordinate with the ODOT Region Quality Assurance Coordinator (“QAC”) to confirm that adequate verification and independent assurance (“IA”) testing is performed.

Agency staff /Agency’s independent testing laboratory will perform the verification and IA testing; it is not a Consultant task under this CA/CEI SOW.

Consultant shall monitor the CC’s QC Program. Oversight of the QC Program is conducted by the 
QCCS who is experienced and certified in all areas of field material testing and documentation.  According to the Agency’s Technician Certification Program, the QCCS is required to maintain certification in at least the following disciplines:  CAgt, CEBT, CAT 1, CDT and QCT.  The QCCS is required to maintain certification in these material testing disciplines throughout the duration of all the CA/CEI Services.  The QCCS shall follow the requirements of the Quality Assurance Program located in Section 2 of the ODOT Manual of Field Test Procedures and the roles and responsibilities outlined in the QCCS Handbook.

The following are the approved Technician Certifications currently in place in the Technician Certification Program:

- Certified Aggregate Technician (“CAgT”)

- Certified Embankment and Base Technician (“CEBT”)

- Certified Density Technician (“CDT”)

- Certified Asphalt Technician I (“CAT-I”)

- Certified Asphalt Technician II (“CAT-II”)

- Certified Mix Design Technician (“CMDT”)

- Quality Control Technician (“QCT”)

- Concrete Control Technician (“CCT”)

- Concrete Strength Testing Technician (“CSTT”)

Consultant shall:

- Review and monitor the CC's documentation for the quality of all materials incorporated into the Project.

- Verify that all materials furnished and placed on the Project comply with the approved specifications.

- Certify that the documentation confirms that all materials comply with construction contract requirements.

- Maintain the Test Summary for Nonfield-Tested Materials and Field-Tested Materials (Test Summary “A”, “B” and “C” Form numbers 734-1902A, 734-1902B and 734-1902C) as detailed in the ODOT Construction Manual, Chapter 12B - Quality.

- Identify and monitor CC’s quality control technicians and require proper and current certification(s) and require that proper testing frequencies and procedures are being followed.  Monitoring must be done by Consultant staff experienced in all areas of field testing and documentation and certified by ODOT’s Technician Certification Program for the specific tests being monitored.

- Take appropriate action if CC’s quality contract technicians do not have proper or current certifications or if proper testing frequencies and procedures are not being followed.

- Obtain, review and compile all required Project quality documentation in accordance with the ODOT Construction Manual and the construction contract documents.

- Communicate with Agency’s QAC to facilitate timeliness and efficiency in the verification and IA testing work and compliance with all requirements of the ODOT Manual of Field Test Procedures and contract documents.

- Compare CC’s QC test results to ODOT’s verification test results to verify they are within IA parameters.

- Take appropriate action and work with APM to resolve any discrepancies between CC’s QC test results and the ODOT verification test results.

- Prepare quality price adjustments as necessary for materials.

Deliverables and Schedule:

- Field Inspection Reports (“FIRs”) and Nonfield-Tested Summary – Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

- Field-Test Summaries and other Project field-tested materials quality documentation – Submit to APM as Project work progresses along with following protocol provided in Task CE-5.4 – Submittal of Final Project Documentation.

### Task CE-3.4 	ADA Ramp and Push Button Inspection

[Delete task 3.4 language and mark as “RESERVED” if not applicable to the Project. This task is required if there are any ADA ramps being constructed on the Project.]

Consultant shall perform inspection of CC installed ADA ramps, review and respond to CC Working Drawings and Sidewalk Ramp Plan, and attend all preplacement meetings as required in the Specifications in Section 00759.

Consultant shall:

- Conduct a submittal review according to the Specifications in 00150.35 of CC’s Working Drawings and Sidewalk Ramp Plan submitted electronically.

- Maintain 1 of the as-submitted copies in the Project files.

- Review, respond and return any corrections or comments to the CC’s Working Drawings and Sidewalk Ramp Plan according Task CE-2.7 Working Drawings, Shop Drawings, and other Submittal Reviews.

- Attend all Preplacement Conference(s) as noted in the Specifications in 00759.03.

- Determine and obtain information from the POR if there is an approved design exception on any ADA Ramps.

- Perform ADA ramp inspection(s) according to the most current version of the ADA Curb Ramp Inspection form(s) (734-5020 A-G), as applicable, and the latest ODOT guidance on smart level tools.  ODOT’s fillable ADA Curb Ramp Inspection Forms and instructions are available at the following address:  https://www.oregon.gov/ODOT/Engineering/Pages/Accessibility.aspx

- Complete ADA Curb Ramp Inspection form(s) (734-5020 A-G), as applicable, and include this documentation with Agency source documents “paynotes” as noted in Task CE-2.5 Monthly Preliminary Progress Estimates and Task CE-3.2 Construction Activity Monitoring.

If a design change has occurred impacting an ADA ramp and Task CE-2.9 Design Modifications is authorized, Consultant shall coordinate with the POR to provide additional or modified plan(s) to CC as part of Task CE-2.9.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than 28 ADA curb ramp inspection(s). This task assumes up to 2 Preplacement Conference(s).  Each Preplacement Conference is expected to last no more than 1 hours, with no more than 1 Consultant staff in attendance.

Deliverables and Schedule:

The deliverables for ADA curb ramp review and inspection include, but are not limited to:

- Return Working Drawings and Sidewalk Ramp Plan submittals to CC within the time frames in the Specifications in 00150.35.

- Documentation of all ADA Curb Ramp Inspection forms to support “paynotes” in the Project documents as noted in Task CE-2.5 Monthly Preliminary Progress Estimates and Task CE-3.2 Construction Activity Monitoring.

- Submittal of fully complying ADA Curb Ramp Inspection form(s) (734-5020 A-G), as applicable, to the APM monthly upon completion of inspection and “paynote” documentation.

- Submittal of approved design exception, if applicable, accompanying the ADA Curb Ramp Inspection form(s) to the APM monthly upon completion of inspection and “paynote” documentation.

### Task CE-3.5 Additional Construction Activity Monitoring (CONTINGENCY TASK)

If authorized by APM, Consultant shall provide additional construction activity monitoring during

construction in coordination with Task CE-3.2.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than 130 additional hours.

Deliverables and Schedule:

Deliverables and schedule are defined in Task CE-3.2.

## TASK CE-4	CONSTRUCTION SURVEYING

CC licensed Land Surveyor shall provide land surveying Services and deliverables that conform to all state statutes pertaining to survey and land boundary laws. These include, but are not limited to, the following Oregon Revised Statutes (ORS):

- ORS Chapter 92 - Subdivisions and Partitions

- ORS Chapter 93 - Conveyancing and Recording

- ORS Chapter 209 - Agency Surveyors

- ORS Chapter 672 - Professional Engineers; Land Surveyors; Photogrammetrists; Geologists

CC survey personnel shall perform all construction surveying tasks in accordance with the most recent version of the ODOT Construction Surveying Manual for Contractors, as required to ensure conformance of the Project construction with the approved plans and specifications. Consultant shall provide qualified personnel to verify the Project is constructed to the lines and grades as shown, specified, or established.

### Task CE-4.1	Coordination, Calculations and Quality Assurance (QA) of Construction Contractor’s Survey Work

[If CC is performing construction survey and staking, the following must be included without any additions, deletions or revisions except blue highlighted fields. Delete this task and mark as “RESERVED” if CA/CEI Consultant is performing construction survey and staking required under task 4.2.]

Consultant shall:

• Coordinate with APM and CC as needed to require compliance with and verify that the

construction survey work completed by the CC for the Project is in conformance with the

approved plans, specifications and applicable laws.

• Attend and participate in a pre-survey meeting with the CC, APM, and

others as appropriate.

• Coordinate with CC, APM and (LAPM if applicable) to determine participants and to schedule the

pre-survey meetings at an agreed-upon time no later than 14 calendar days prior to beginning

construction.

• Prepare and distribute the meeting agenda to APM and other participants at least 4 business

days prior to meeting.

• Prepare and distribute the meeting minutes to APM and other participants within 1 week of

meeting.

• Perform QA review of CC’s survey data such as, but not limited to, office calculations and stakeout information.

• Provide memo indicating dates and times grade calculation checks were performed and the

results of the calculation checks along with copy of notification to CC on items not in compliance

from calculation checks and when/what corrections were made.

• Perform QA review of CC’s field survey work. Provide memo indicating dates and times the

survey field checks of CC’s survey work were performed and the results of the field checks along

with copy of notification to CC on items not in compliance with approved construction plans and

when/what corrections were made.

• Provide a map, digital ASCII file of the coordinates, and field notes as applicable, of horizontal

and vertical control points (from the construction contract plans) for use by the CC's surveyor.

• Prepare horizontal and vertical alignment print outs, construction grade data, including annotated cross sections (from the construction contract plans) for use by the CC's surveyor.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than five (5) 1-day site visit(s) by a 2-person survey crew for construction surveying.

Deliverables and Schedule:

• Pre-survey meeting agenda – Submit 1 copy to each meeting attendee and the APM 4

business days prior to the scheduled meeting.

• Pre-survey meeting minutes – 1 copy to each meeting attendee and the APM within 1 week after the meeting.

• Memo regarding grade calculation checks – Submit via email to CC with copy to APM

within 5 business days of receipt of survey data from CC.

• Memo regarding survey field checks – Submit via email to CC with copy to APM within 5

business days of request.

• Map, digital ASCII file of the coordinates and field notes as applicable, of horizontal and

vertical control points – Submit original to CC at the pre-construction or pre-survey

meeting.

• Horizontal and vertical alignment print outs, construction grade data, including annotated

cross sections – Submit original to CC at the pre-construction or pre-survey meeting.

### Task CE-4.2	Construction Survey and Staking

[If CC is NOT performing construction survey and staking, the following must be included without any additions, deletions or revisions except blue highlighted fields or as noted below. Delete this task and mark as “RESERVED” if CA/CEI Consultant is performing task 4.1.]

Consultant shall provide all construction surveying for control of the Project as required to establish the position, orientation and elevation of the work from control stations, including furnishing and setting construction stakes and marks, reference marks, and additional control stations.

Consultant shall:

- Attend and participate in a pre-survey meeting with the CC, APM, and (LAPM if applicable) and others as may be appropriate.

- Coordinate with CC, APM and (LAPM if applicable) to determine participants and to schedule the pre-survey meetings at an agreed-upon time no later than 14 calendar days prior to beginning construction.

- Prepare and distribute the meeting agenda to APM and other participants at least 4 business days prior to meeting. Prepare and distribute the meeting minutes to APM and other participants within 1 week of meeting.

- Coordinate with APM and CC to discuss and agree upon the extent of construction survey needs for the Project to be successfully constructed in the correct location and in accordance with the approved plans and specifications for the work.

- Verify all initial horizontal and vertical control stations in the proximity of the Project.

- Establish additional control stations as necessary to control the Project.

- Make supporting calculations as required to establish the position of all elements of the Project.  Make calculations in accordance with established Agency policies and procedures.  Calculations must be sufficient to establish the correct position, orientation, and elevation of the work within required tolerances from control stations.

- Prepare horizontal and vertical alignment construction grade data from the construction contract plans. Provide calculations, field notes, and survey drawings for the layout and control of the work as are required to construct the Project.

- Perform staking of the Project clearing limits.

- Set stakes to define the temporary signs for each stage of construction.

- Perform staking for approximate ROW and easements.

- Perform staking to delineate existing wetlands and other regulated work areas. [Delete if not applicable to the Project.]

- Perform staking for retaining walls including foundations and copings. [Delete if not applicable to the Project.]

- Provide staking necessary for construction of all roadways and sidewalks as follows:

      - Slope stakes for construction of earthwork, including intersections and match lines

      - Grade hubs for subgrade

      - Grade hubs for top of rock

      - Staking for finish grades

      - Permanent drainage, including manholes, inlets and pipes

      - Temporary and permanent striping

      - ADA Ramps

- Provide staking for curbs and curb returns, driveways, utility vaults, water quality facilities as applicable.

- Provide staking for permanent signs. [Delete if not applicable to the Project.]

- Provide staking for traffic signals and illumination. [Delete if not applicable to the Project.]

- Provide staking for permanent stormwater treatment facilities. [Delete if not applicable to the Project.]

- Provide staking for guardrail and barriers. [Delete if not applicable to the Project.]

- Provide staking for seeding and plantings. [Delete if not applicable to the Project.]

- Provide other staking as required by construction contract specifications.

- Provide staking necessary for construction of the bridge(s), as follows: [Delete this bullet and the following sub-bullets if not applicable to the Project.]

      - Substructure Elements:

        - Piling

        - Drilled shafts

        - End bents and wingwalls

        - Columns and cross beams

        - Beam seats and bearing pads

      - Superstructure Elements:

        - Horizontal alignment and deck edges

        - Bridge deck soffit and finish grade elevations

        - Bridge end panels

        - Asphalt concrete pavement buildup for finish grade on precast deck elements.

ASSUMPTIONS FOR BUDGETING PURPOSES: This task assumes no more than __ 1-day site visit(s) by a 2 person survey crew for construction surveying.

Deliverables and Schedule: [Double-click checkbox(s) below to select applicable distribution option(s).]

Submit the deliverables below to CC, ODOT and APM (required for projects on or connected to an ODOT facility).

Submit the deliverables below to CC and APM. Provide via email a copy of transmittal letter to APM.

- Calculations, survey drawings and grade reports for layout and control of the work - Submit electronically at least 2 business days prior to staking a specific element. Keep copies in the Project file.  If required by APM, hard copies shall be provided.

- Staking reports (field notes, cut sheets, and survey drawings) for the specific items that have been staked out - Submit electronically within 1 day after staking of the specific element is complete. If required by APM, hard copies shall be provided.

### Task CE-4.3	Locate, Recover and Reference Monuments (CONTINGENCY TASK)

[If monuments are disturbed or destroyed during the construction activities of this Project then this task must be included.  If the utility relocation or clearing activities disturb or destroy monuments prior to or during construction due to the Project needs, then this task must be accomplished.

Consultant shall recover and reference monuments (as indicated below) in the location of the ROW identified in the control, recovery and retracement survey.  Consultant shall document in field notes the monuments either found, or not found during the search phase. Consultant shall ensure compliance with the requirements of ORS 209.155.

For all monuments not destroyed during construction activities, Consultant shall note in the field notes that:

- All monuments were recovered (include date),

- All monuments exist per the control, recovery, and retracement survey, or

- All monuments are within the new ROW and do not need to be reset.

The monuments may or may not be retied to confirm their original surveyed positions.  This decision will be made based on Consultant surveyor’s professional judgment.

Consultant shall:

- Recover monuments shown on the control, recovery, and retracement survey to confirm they either still exist or were destroyed during construction. Consultant shall note destroyed monuments that are within the Project limits.

- Locate and recover any new monumentation within the Project work zone which were placed after the original field search and survey ties, which may include research of Agency records as appropriate.  Agency may provide monuments tied prior to construction not filed with the control, recovery, and retracement survey.

- Use Agency point number range for control points and monuments.

Deliverables and Schedule:

Submit the deliverables below to APM (required for projects on or connected to an ODOT facility).

- ASCII File of located monuments with monument point numbers and coordinates and any other electronic files (such as .fwd, .alg, ASCII, etc.) created or produced for the Project documenting Monumentation surveying -  Submit within 14 calendar days after recording of the survey filing map (SFM) with the Agency Surveyor’s office.

- Original field notes and 1 electronic .pdf copy - Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

### Task CE-4.4	Right of Way (“ROW”) Monumentation

[If new ROW is purchased for a Project then this task must be accomplished. Label this subtask as “CONTINGENCY TASK” if it is not known at time of Contract execution whether or not it is needed.]

Consultant shall document the location of the ROW lines at the completion of the Project construction.  Consultant shall preserve the location of the monuments found prior to construction and shall document the ROW lines for all property acquired for the Project.

Unless otherwise approved by the Agency, Consultant shall monument the new ROW using the Boundary Method in conformance with the ODOT Monumentation Policy and the Survey Filing Map Standards (available on the Internet at http://cms.oregon.gov/ODOT/HWY/GEOMETRONICS/Pages/documents.aspx ). Consultant may be assigned the method of monumentation, which could be the Network Method, Boundary Method, or a combination of both methods which are defined in the ODOT Monumentation Policy.

Consultant shall set control and ROW monuments, as applicable, within 60 calendar days after issuance of Second Notification.

Deliverables and Schedule:

Submit the deliverables below to APM (required for projects on or connected to an ODOT facility).

- AutoCAD Civil3D.DWG file displaying the control and monuments as applicable – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

- AutoCAD Civil3D.DWG file with centerline(s), control and monument data, and report of alignment(s) showing coordinates, bearing, stations, etc., per Bentley Inroads standard reports – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

- Final report of monument station and offset relationship to the alignment(s) – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

- Agency ROW files and copies of all deeds, court judgments, etc., from the Agency – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

- Original field notes and 1 copy in .pdf format – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

- Final ASCII file of all control and monument points set – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

### Task CE-4.5	Monumentation Survey Filing Map (SFM)

[If tasks 4.3 or 4.4 are included in the CA/CEI SOW then this SFM task must be accomplished. Label this subtask as “CONTINGENCY TASK” if it is not known at time of Contract execution whether or not it is needed.]

Consultant shall create SFM in accordance with Agency and ORS 209 requirements.  Consultant shall ensure preservation of existing survey markers in conformance with Chapter 6.2 of the ODOT Construction Survey Manual for Contractors.

Consultant shall monument any newly acquired ROW in accordance with Survey Filing Map Standards for Right of Way Monumentation.

Consultant shall submit the survey to the Agency Surveyor’s Office for filing on archival Mylar or acceptable media per Agency requirements.

Deliverables and Schedule:

- SFM File at the Agency Surveyor's office within 45 calendar days after setting monuments.

Submit the deliverables below to APM (required for projects on or connected to an ODOT facility).

- Final recorded SFM and narrative regarding methodologies used – Submit within 14 calendar days after recording of the SFM with the Agency Surveyor's office.

## TASK CE-5	PROJECT CLOSE-OUT

Consultant shall assist Agency to complete interim and final on-site inspections and submit all Project records required for final payment and Project Acceptance.

### Task CE-5.1	Final Inspection(s) and Submittals

Agency shall issue Second Notification when all on-site work including CCO and EWO work is completed per the Specifications, in 00150.90(a) and 00180.50(g) (Refer to the ODOT Construction Manual, Chapter 13 – Contract Time).

Consultant shall:

- Schedule a review of the Project at a time close to completion of on-site work.

- Schedule and lead/Attend a Project Final Inspection with CC and Agency within 15 days after receiving notice from the CC that all punch list items, final trimming and cleanup according to the Specifications in 00140.90 have been completed.

- Prepare/Assist with preparing a punch-list of items to be corrected by the CC.

- Once the punch-list items have been corrected, meet at Project site with Agency and ODOT for a follow-up to the Final Inspection.

- Prepare and send the Recommendation of Project Acceptance (ODOT form 734-1384) to APM, once CC has satisfactorily completed all construction contract work and fulfilled its obligations concerning Project documentation. (Refer to the ODOT Construction Manual, Chapter 36 – Acceptance of Project.)

- Issue Third Notification to CC after all construction contract work and inspections are complete, and all required documentation is submitted per OSSC, according to the Specifications in 00150.90. (Refer to the ODOT Construction Manual, Chapter 40 – Third Notification.)

- Complete the Prime Contractor Performance Evaluation (form 734-2884) annually within 60 calendar days of NTP anniversary and within 60 calendar days of Second Notification and submit to Agency after receipt back from CC. (Refer to the ODOT Construction Manual, Chapter 34 – Contractor Performance Evaluation).

Deliverables and Schedule:

- Provide a punch-list of items.

- Second Notification - due within 2 business days of completion of on-site work. Submit 1 electronic copy to APM. Also submit via email, 1 copy to ODOT.

- Recommendation of Project Acceptance (ODOT form 734-1384) - Submit electronic copy to APM upon completion of final inspection per Construction Manual Chapter 36 – Acceptance of Project.

- Third Notification – due within 2 business days of completion of all construction contract work. Submit 1 electronic copy to APM. Also submit via email, 1 copy to ODOT.

- Prime Contractor Performance Evaluation (form 734-2884). Submit to CC annually, and within 60 calendar days of issuance of Second Notification. Submit electronic form to Agency upon receipt from CC. If CC does not sign and return, submit unsigned forms to Agency within 15 calendar days of sending to CC.

- Contractor Construction Process Feedback (form 734-2469). Send to CC when sending final evaluation for the Project. Submit electronic form to Agency upon receipt from CC.

### Task CE-5.2	As-Constructed Plans

Throughout Project construction, Consultant shall maintain a paper copy of the plans with any field changes noted in red. Based upon those red-lined plans, Consultant shall prepare, stamp and sign as-constructed drawings prepared in AutoCAD .dwg format. As-constructed plans must be reviewed and approved by the POR prior to submittal to Agency.

Deliverables and Schedule:

- Submit the red-lined plan set and final as-constructed plans (AutoCAD and PDF format) to the APM within 90 calendar days of issuance of Second Notification.

### Task CE-5.3	Structure Load Rating

[Delete task 5.3 language and mark “RESERVED” if the Project does not include a structure.]

ODOT Bridge Section has implemented the Load and Resistance Factor Rating (“LRFR”) method, based on the AASHTO Manual for Bridge Evaluation (“MBE”) with interim revisions.  All bridges in Oregon (regardless of the owner) will be rated following the ODOT LRFR Load Rating Procedures. ODOT owned bridges will use the Oregon Specific Live Load Factors and all other bridges will use the re-calibrated National Live Load Factors.

Consultant shall perform load ratings in conformance with the LRFR procedures and software specified in the ODOT LRFR Manual (current edition at time load rating work is performed), including all reference standards incorporated into the manual in section 1.3.1.

The ODOT LRFR Manual and all resources and templates that must be used for LRFR load rating procedures, as described in the ODOT LRFR Manual, are available online at the following link: ftp://ftp.odot.state.or.us/Bridge/LoadRating/LRFR.

For structure types that are not covered in the ODOT LRFR Manual - as stated in Section 23.2 of the ODOT LRFR Manual; it is expected that the methodology and workflow be as consistent as possible with the other structure types already covered in the manual. All load ratings in LRFR follow the same Load and Resistance Factor methodology.

Consultant shall base load rating on the final construction contract plans and modified to reflect as-constructed conditions. Consultant shall develop load rating reports for the bridge completed for the Project based on the ODOT load rating format.

Deliverables and Schedule:

- Load Rating Report conforming to the requirements detailed in Section 22: “Deliverables” of the ODOT LRFR Manual, due to AMP within 90 calendar days after Second Notification.

### Task CE-5.4	Submittal of Final Project Documentation

Consultant shall:

- Assist Agency with organizing and submitting the final Project quality, quantity documentation according to the Semi-Final Documentation Submittal (form 734-2706) associated with the Project and as detailed in the ODOT Construction Manual, Chapter 37 – Submittal of Final Project Documentation.

- Organize and submit the final Project quality, quantity and labor compliance documentation to the Agency.

- Review documentation with Agency’s QAC and the ODOT RAS.

- Upon issuance of Second Notification, perform a final review with the Agency of all Project quality and quantity documentation and mutually agree that all contractual requirements have been met and recommend Acceptance.

- Perform a final review and submit the final labor compliance documentation to the Agency for acceptance.

- Complete any quality, quantity and labor compliance documentation associated with plant establishment work completed after the final Project documentation has been submitted for Agency review and documentation Acceptance (within 14 calendar days after the plant establishment work has been completed).

- Prepare and submit electronically, all certified payroll reports, including the signed Statement of Certification/Compliance page, Employee Interview Reports (ODOT form 734-3478), and Project Manager’s Labor Compliance Certification (ODOT form 734-1734) for the plant establishment work for APM review and Acceptance (within 14 calendar days after the plant establishment work has been completed).

Deliverables and Schedule:

- All final Project quality, quantity and labor compliance documentation, excluding documentation related to plant establishment work. The documents must be submitted electronically to the Agency within 60 calendar days after Second Notification.

- All Project quality, quantity and labor compliance documentation related to plant establishment work. The documents must be submitted electronically to Agency within 14 calendar days after plant establishment work.

# E.2	PROJECT SCHEDULE

Schedule Assumptions

The Project is scheduled for a (date) bid opening for the CC.  It is anticipated that the CC will receive NTP no later than (date). Agency shall issue the CC Notice of Award and NTP in accordance with the Specifications in Section 00130.

- All construction work, except for the Establishment Period as per section 01030 work is assumed to be completed by (date).

- The plant establishment period is assumed to be a 1–year period.

- All work for this CA/CEI SOW is to be completed within 30 calendar days of Consultant issuing Third Notification to the CC.

- Construction Contract Completion Date as specified in the Specifications in 00180.50 of the construction contract is (date).

- Third notification to the CC is assumed to be issued on or before (date).

# F.	CONTINGENCY TASKS

The table below is a summary of contingency tasks that Agency, at its discretion, may authorize Consultant to produce. Details of the contingency tasks and associated deliverables are stated in the task section of this CA/CEI SOW. Consultant shall complete only the specific contingency task(s) identified and authorized via written (email acceptable) NTP issued by Agency's APM. If requested by Agency, Consultant shall submit a detailed cost estimate (within the NTE amount(s) in the Contingency Task Summary Table) for the agreed-to contingency Services within the scope of the contingency task.

If Agency chooses to authorize some or all of these tasks, Consultant shall complete the authorized tasks and deliverables per the schedule identified for each task. The NTP will include the contingency task name and number, due date for completion, and agreed-to NTE for the authorized contingency task.

Each contingency task is only billable (up to the NTE amount identified for the task) if specifically authorized per NTP. In the table below, the contingency NTE amount for a contingency task includes all labor, overhead, profit, and expenses for the task. The funds budgeted for contingency tasks may not be applied to non-contingency tasks without a fully executed amendment. The total amount for all contingency tasks authorized shall not exceed the maximum identified in the table below. Each authorized contingency task must be billed as a separate line item on Consultant’s invoice.

Contingency Task Summary Table

| Contingency Task Description | (UNIT) NTE | Max Quan. | Method of Comp. | Contingency NTE Amount |
| --- | --- | --- | --- | --- |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
|  |  |  |  | $ |
| Total NTE For All Contingency Tasks: | $__________ |