## Upcoming RW Projects
Region | Key Number | Work Types | Section | Applicant | Counties | Description | RW Cost | RW YR | Monitor Code | Status | Admin By
1 | 18837 | BIKPED, MODERN | NE Columbia Blvd: Cully Blvd & Alderwood Rd | CITY OF PORTLAND | MULTNOMAH | Install or replace a signal and construct a taper on Columbia Blvd's east leg at Alderwood for future side-by-side left-turn lanes between Cully and Alderwood. Construct sidewalks at the Columbia/Alderwood intersection and on N side to Cully. The project will keep Columbia Blvd a viable freight route while enhancing neighborhood connections and improving safety. | 1595017 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL/COBO
1 | 19357 | BIKPED | Beaverton Creek Trail:Westside Trail-SW Hocken Ave | TUALATIN HILLS PARK & REC DIST | WASHINGTON | Construct a 1.5-mile long; 12-foot wide regional trail consisting of paving; bridges/boardwalks; lighting; road right-of-way improvements; environmental mitigation and bicycle/pedestrian amenities and site furnishings. This section of trail will provide an off-street; safer and more pleasant transportation option to connect with light-rail; bus lines; employment and commercial areas as well as providing recreation opportunities for walkers; joggers and cyclists. | 1301569 | 2024 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 19358 | MODERN | Basalt Creek Ext: Grahams Ferry Rd-Boones Ferry Rd | WASHINGTON COUNTY | WASHINGTON | Construct a new arterial roadway providing industrial freight access in the Basalt Creek planning area. The extension of the parkway is an east-west alignment crossing the Seely Ditch with a 600ft long bridge. | 4001000 | 2026 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 20238 | BIKPED | OR200: Elmira - Veneta multi-use path | CITY OF VENETA | LANE | Complete NEPA studies and design a separated path between Veneta and Elmira for pedestrians and cyclists. | 10900 | 2025 | ROWACQ | Land Purchase 2025 | LOCAL/COBO
1 | 20332 | BIKPED | I-205 Overcrossing at NE Halsey | CITY OF PORTLAND | MULTNOMAH | Provide safe access across I-205 for pedestrians and bicyclists by improving local street corridors on the west and east sides of 1-205 and modifying the NE Halsey Street Viaduct over I-205. | 107900 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
4 | 20378 | BRIDGE | Archie Briggs Rd (Deschutes River) Bridges | CITY OF BEND | DESCHUTES | Replace bridges 17C05 & 17C040 with ones that meet current standards. | 10000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | ODOT/LOCAL
1 | 20488 | BRIDGE | North Dakota Street: Fanno Creek Bridge | CITY OF TIGARD | WASHINGTON | Construct a new single span bridge on the same alignment because the existing bridge is failing. Raise the vertical grade line to improve site distance approaching the railroad crossing. | 430000 | 2024 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 21017 | CMAQ | West Pine St reconstruction | CITY OF CENTRAL POINT | JACKSON | Add sidewalk; curb & gutter; bike lanes; 2 travel lanes and one continuous left turn lane. | 525000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 21185 | SAFETY | Queen Avenue Rail Crossing (Albany) | RAIL DIVISION | LINN | Upgrade existing railroad warning devices to improve pedestrian safety. | 285000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | RAIL
2 | 21449 | BIKPED | Hunsaker Lane: Daffodil Ct to Taito St (Eugene) | CITY OF EUGENE | LANE | Complete Hunsaker lane designs with curb; gutter; sidewalk; and east-bound and west-bound buffered bike lanes; and improve drainage ditch from 300’ west of Daffodil Ct to Taito Street to expand low-stress active transportation connectivity and access. | 557227 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 21607 | BIKPED, OP-SSI | OR213 at NE Glisan St and NE Davis St | ODOT | MULTNOMAH | Upgrade the signal at the Glisan St intersection and modify the Davis St intersection to increase safety. | 495275 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 21629 | SAFETY | SE Division St: 148th Ave - 174th Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Convert existing two-way left turn lane to a raised median to improve safety on this section. | 45000 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 21630 | SAFETY | SE Stark St: 111th - 151st Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Convert existing two-way left turn lanes to a raised median with pedestrian crossing improvements at various intersections of SE Stark to improve safety. | 75000 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 21633 | SAFETY | SW Shattuck Rd at OR10 (Portland) | CITY OF PORTLAND | MULTNOMAH | Rebuild traffic signal to increase visibility and accommodate left turn signal heads and phases on Shattuck Road to improve safety at this intersection. | 36612 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL/CERT
4 | 21663 | SAFETY | All Roads Transportation Safety (Wasco County) | ODOT | WASCO | Curve signs; pavement markers; and striping to increase safety and reduce collisions in the area. | 10000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | ODOT/LOCAL
4 | 21663 | SAFETY | All Roads Transportation Safety (Wasco County) | WASCO COUNTY | WASCO | Curve signs; pavement markers; and striping to increase safety and reduce collisions in the area. | 10000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | ODOT/LOCAL
3 | 21728 | SAFETY | Crater Lake Ave Signal Improvements (Medford) | CITY OF MEDFORD | JACKSON | Install retroreflective backplates at 8 signalized intersections. Install flashing lights at the intersections of Minnesota Ave; Grand Ave; and Bradbury St with a ped refuge island at Bradbury. Replace the signal at Brookhurst St to include east/west left turn pockets; replace all permissive left turn phasing and relocate a refuge island; modify the signal at Roberts Rd N to replace five section "doghouse" signal heads. Upgrade ADA. | 100000 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
2 | 21879 | BIKPED | Pedestrian Safety Improved Crossings (Salem) | CITY OF SALEM | MARION | Installation of enhanced pedestrian crossings at the following locations: River Rd N at Riviera Dr NE; Lancaster Dr NE at Weathers St NE; and State St at 21st St SE. | 165000 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 21880 | BRIDGE | Cornelius Pass Road: Rock Creek Bridge | WASHINGTON COUNTY | WASHINGTON | Replace the bridge due to structural deterioration. The new bridge is planned to have wider travel lanes and shoulders to increase safety. | 75000 | 2024 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 21883 | CMAQ | Orchard Heights Rd NW: Snowbird to Westhaven (Salem) | CITY OF SALEM | POLK | Construct curb; stormwater; and sidewalk along the south side of Orchard Heights Rd between Snowbird Dr and Schoolhouse Ct and between Chapman Hill Dr and Westhaven Ave. Install enhanced pedestrian crossing at Parkway Dr. | 135000 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
2 | 21890 | BIKPED | Commercial St SE: Vista St to Ratcliff Dr (Salem) | CITY OF SALEM | MARION | Construct sidewalks along the east side of Commercial Street SE and add a new signal at Ratcliff to increase safety. | 320000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 21895 | MODERN | State St: 4106 State St to 46th Ave | MARION COUNTY | MARION | Construct a center turn lane; bike lanes and sidewalks to improve pedestrian safety. | 300000 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 21897 | OP-SLD | Kitson Springs Slide Repair at MP 2.6 | LANE COUNTY | LANE | Address a continuing slide on Kitson Springs Road southeast of Oakridge. Final scoping will evaluate the most cost effective solution to dewater; stabilize and repair the slide area. | 65000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL/CERT
2 | 21998 | BRIDGE | Scotts Mills Road: Butte Creek Bridge (Scotts Mills) | MARION COUNTY | MARION | Replace the bridge with a new structure that conforms to current standards. | 97800 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
5 | 22017 | BRIDGE | Holbrook Creek Road: Pine Creek bridge (Baker County) | BAKER COUNTY | BAKER | Replace a bridge that was previously washed out. Modify the river bed to prevent future flood events from washing the bridge out again. | 25000 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
3 | 22030 | BRIDGE | Douglas Avenue: Deer Creek Bridge (Roseburg) | CITY OF ROSEBURG | DOUGLAS | Replace the bridge due to deterioration. | 95900 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
4 | 22042 | BRIDGE | 6th St. Viaduct: Bridge over Spring St. and Union Pacific RR | CITY OF KLAMATH FALLS | KLAMATH | Rehabilitate bridge components to improve the structural condition of the structure. | 31600 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 22128 | BIKPED | Aloha Access Improvements: SW 174th Ave - SW 187th Ave | WASHINGTON COUNTY | WASHINGTON | Design and implement various access and crossing enhancements in the Aloha Town Center area to improve pedestrian safety. | 360000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 22131 | CMAQ | Courtney Ave Complete Street: River Rd - OR99E | CLACKAMAS COUNTY | CLACKAMAS | On Courtney Ave from River Rd to OR99E; construct separated sidewalks; bike lanes; storm water management rain gardens; curb ramps; and crosswalk enhancements to improve safety and accessibility. | 1096695 | 2024 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22134 | BIKPED | NE 122nd Ave Safety & Access: Beech St - Wasco St | CITY OF PORTLAND | MULTNOMAH | Construct new enhanced & marked crossings on NE 122nd Avenue near NE Beech Street/NE Failing Street; NE Sacramento Street/NE Brazee Street; NE Broadway/NE Hancock Street; and NE Wasco Street/ NE Multnomah Street to improve safety and accessibility. | 160000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22135 | BIKPED | NE MLK Blvd Safety & Access to Transit: Cook - Highland | CITY OF PORTLAND | MULTNOMAH | Construct pedestrian crossing and intersection channelization improvements on NE MLK Blvd at various locations between Cook St and Highland St. Complete signal upgrades at NE Fremont and NE Killingsworth. Add protected left turn lane at both intersections. These improvements will increase safety and accessibility. | 87000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22138 | BIKPED | Stark & Washington Safety: SE 92nd Ave - SE 109th Ave | CITY OF PORTLAND | MULTNOMAH | Construct protected bike lanes; protected signal phasing for pedestrians and bicyclists; pedestrian crossing; transit islands to improve transit operations and comfort; pedestrian islands to shorten crossing distance; paving; and signal controller upgrades to better manage speeds and traffic flow. | 800000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22141 | BIKPED | Washington/Monroe Street: SE 37th - SE Linwood Ave | CITY OF MILWAUKIE | CLACKAMAS | Construct bicycle and pedestrian improvements (segments D & E) on Washington & Monroe starting on Washington Street/37th Ave east to Ada Lane to Home Ave; Home Ave to Monroe; and Monroe east to Linwood providing pedestrian/cyclists safety improvements. | 671000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 22278 | BIKPED, CMAQ | Clay Street: Faith Ave to Siskiyou Blvd | JACKSON COUNTY | JACKSON | Install bike and pedestrian facilities with curb; gutter; sidewalk and drainage to facilitate the addition of the bike and pedestrian facilities. | 1205000 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22346 | CMAQ | West Bank Path extension (Eugene) | CITY OF EUGENE | LANE | Extend West Bank shared-use Path north from Hunsaker St to Admirals St; adding sidewalk to Admiral St and enhanced crosswalks at River Loop 1 and Wilkes Drive crossings to reduce congestion and improve air quality. | 50000 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
2 | 22351 | OP-Carbon, SAFETY | Walking and biking network improvements (Springfield) | CITY OF SPRINGFIELD | LANE | Addressing highest need locations for filling gaps in the walking and biking networks and near schools and the downtown corridor in Springfield to complete connections; reduce congestion and address safety. Project includes two portable temporary rapid flashing beacons; crossing on Mohawk Blvd south of I St; crossing on 5th St north of Q St; flashing beacons at Pioneer Parkway East and West at E St; at Thurston Rd at 69th St; and EWEB path crossing enhancements with refuge islands at 5th and 19th Streets; sidewalk rehabilitation at various locations | 112439.54 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL
2 | 22356 | TRANST | South Salem Multi-Modal Transit Facility | SALEM-KEIZER TRANSIT DISTRICT | MARION | Design and property acquisition for future construction of a new multi-modal transit facility to serve the south Salem area to improve the transit service in the area and provide options for multi-modal transfers. | 3200000 | 2025 | ROWACQ | Land Purchase 2025 | LOCAL
2 | 22460 | BIKPED | Berkeley Park Path (Eugene) | CITY OF EUGENE | LANE | Construction of an approximately 0.13 mile path through Berkeley Park; connecting Wilson St to a higher density housing development parking lot and then connecting to Fern Ridge Trail through the park. The path will improve access and safety for people walking and biking through the area. | 20000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
4 | 22471 | BIKPED | Mill Creek Greenway (The Dalles) | WASCO COUNTY & PARKS & REC | WASCO | Construct a portion of the Mill Creek Greenway to connect residential areas of The Dalles to the downtown district; parks; a public pool; a senior center; and the existing Riverfront Trail. | 171500 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | ODOT/LOCAL
1 | 22592 | BRIDGE | Earthquake ready Burnside Br: NE/SE Grand Ave-NW/SW 3 Ave | MULTNOMAH COUNTY | MULTNOMAH | Design plans to replace and construct a new Burnside Bridge to seismic standards covering the limits of NE/SE Grand Ave to NW/SW 3rd Ave and from the I-84/I-5 split south to SE Ash St with street & intersection upgrades within the project limits for increased public safety. | 34600000 | 2024 | ROWACQ | Land Purchase 2024 | LOCAL/CERT
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | CITY OF EUGENE | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | CITY OF SPRINGFIELD | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 22596 | MODERN | Franklin Blvd A Partnership to Rebuild and Revive a Corridor | LANE TRANSIT DISTRICT | LANE | The Franklin Boulevard Transformation project will provide a multi-modal complete street across both cities of Eugene and Springfield to better serve the facility's users. From 11th Ave in Eugene to Mississippi Ave in Springfield. Work includes repaving the street; reduce travel lanes; construct bikeways on both sides of the street; construct a dedicated bus lane; add roundabouts to key intersections; and reconstruct sidewalks and sidewalk access ramps. The project will also include traffic signal work at select intersections; lighting; stormwater facilities; and landscaping. | 2500000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
5 | 22625 | BRIDGE | OR52: Snake River Bridge | IDAHO DOT | MALHEUR | Replace bridge to meet current design standards. | 47950 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | IDAHODOT
3 | 22638 | BRIDGE | Arizona Ranch Rd: Myrtle Creek Bridge | CURRY COUNTY | CURRY | Replace the bridge with a wider and modern bridge to increase safety and improve access. | 6300 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 22639 | BRIDGE | Days Creek Rd: Days Creek Bridge | DOUGLAS COUNTY | DOUGLAS | Replace the bridge to restore load rating and access for all vehicles. | 6300 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 22640 | BRIDGE | South Deer Creek (Hatfield Truss) | DOUGLAS COUNTY | DOUGLAS | Replace the existing structure with a new bridge that meets current standards. | 10100 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 22655 | BRIDGE | Newton Creek Bridge | CITY OF ROSEBURG | DOUGLAS | Replace bridge to restore load rating and access for all vehicles. | 12700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22656 | BRIDGE | Luckiamute River; Helmick Road bridge (Polk Co) | POLK COUNTY | POLK | Rehabilitation of bridge including seismic retrofit; erosion control repair and other general maintenance needs to preserve the historic integrity of the bridge. | 50700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22657 | BRIDGE | Dougherty Slough; Blum Lane; Prince bridge (Tillamook Co) | TILLAMOOK COUNTY | TILLAMOOK | Replace the bridge in order to meet current bridge standards. | 107700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22658 | BRIDGE | Ash Swale; Patty Lane bridge (Yamhill Co) | YAMHILL COUNTY | YAMHILL | Replace the bridge in order to meet current road standards. | 107700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22659 | BRIDGE | North Beaver Creek bridge (Lincoln Co) | LINCOLN COUNTY | LINCOLN | Replace the bridge in order to meet current road standards. | 44300 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22660 | BRIDGE | Small (Mt. View) Creek/Elliot Circle bridge (Benton Co) | BENTON COUNTY | BENTON | Replace the bridge in order to meet current road standards. | 25300 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
5 | 22661 | BRIDGE | Lostine River-Caudle Ln bridge | WALLOWA COUNTY | WALLOWA | Replace the bridge in order to meet current bridge standards. | 63300 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22663 | BRIDGE | Trail Creek; County Rd 776 | JACKSON COUNTY | JACKSON | Replace bridge to serve two lanes of traffic. | 19000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22696 | SAFETY | Virginia/Daisy Ave.: 32nd St. to Bob Straub Parkway (Springfield) | CITY OF SPRINGFIELD | LANE | Design and install various pedestrian and bicycle treatments consistent with a bicycle boulevard on Virginia Avenue/Daisy Avenue. These treatments include improvements to pedestrian crossings; speed bumps and adding bike lane pavement markings. | 67977 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22701 | SAFETY | Division Avenue Roundabouts Corridor (Eugene) | CITY OF EUGENE | LANE | Design and construct two roundabouts on Division Avenue (from River Road to 400 feet southeast of Lone Oak Way) to include additional speed reduction features; travel lane reductions; crossing improvements; and protected bike lanes. This roundabout project includes enhancements that support people walking and biking at this location that will increase safety. | 750000 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22725 | SAFETY | Ehlen Rd NE at Butteville Rd NE (Marion County) | MARION COUNTY | MARION | Install a rural; single lane roundabout at the intersection of Ehlen Rd NE/Butteville Rd NE to improve traffic flow and safety. | 162533 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22753 | PRESRV | Clear Lake Rd: Lakeview Dr to Hwy 99 pavement preserv. (Eug) | LANE COUNTY | LANE | Pavement preservation along Clear Lake Rd from Highway 99 to the urban boundary (approximately at Lakeview Dr). This project will prevent more costly repairs in the future and promote safety. Project includes speed treatments; safety countermeasure; and operational upgrades at Green Hill Rd intersection to include rehabilitation of conduits and junction boxes and a signal upgrade. | 25000 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
4 | 22767 | SAFETY | Driver Feedback Signs (Deschutes County) | ODOT | DESCHUTES | Install two speed feedback signs on each of the following roads; Alfalfa Market Rd; Burgess Rd; Cline Falls Hwy; Day Rd; Old Bend-Redmond Hwy; Powell Butte Hwy; South Canal Blvd and South Century Dr. | 69567 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 22780 | SAFETY | Bailey Hill Rd and Bertelsen Rd roundabout (Eugene) | CITY OF EUGENE | LANE | Project will construct a roundabout with accompanying bicycle and pedestrian facilities at the intersection of Bailey Hill Rd and Bertelsen Rd to reduce vehicle speeds at the intersection and continuing on to more dense areas of Eugene. | 222890.89 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 22781 | BRIDGE | Goodpasture Island Rd Bridge seismic retrofit (Eugene) | CITY OF EUGENE | LANE | Project will strengthen the existing bridge on Goodpasture Island Rd over the Delta Highway (bridge number 09359) to reduce the structure's vulnerability during a seismic event. | 10000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22825 | SAFETY | SE Cesar Chavez Blvd: Lafayette Ct - Schiller St (Portland) | CITY OF PORTLAND | MULTNOMAH | Reduce this section from 4 to 3 lanes (one in each direction and a center turn lane). Add north-south left-turn lanes on SE Chavez at SE Raymond St. Rebuild the signal at SE Holgate to protect left turns. Relocate the bus stop at SE Holgate St closer to the crosswalk. | 20000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22826 | SAFETY | NE Cornell Rd at 17th Ave and 21st Ave | WASHINGTON COUNTY | WASHINGTON | Restrict the 17th Ave intersection to right in right out only and install a signal at the 21st Ave intersection. Install streetlights at both locations. | 150000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 22827 | SAFETY | 92nd Ave; E Burnside St and N Basin Ave (Portland) | CITY OF PORTLAND | MULTNOMAH | Signal and lighting upgrades with curb extensions to improve visibility and safety at the intersections of SE 92nd Ave at SE Division St; E Burnside at 122nd and 148th Ave; N Basin St at Emerson St. | 29000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22828 | SAFETY | SE Sunnyside Rd: 132nd Ave - 172nd Ave (Clackamas) | CLACKAMAS COUNTY | MULTNOMAH | Install adaptive signal system to coordinate signals on this section of the corridor to improve traffic flow and reduce crashes at various intersections on this section. | 5000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22829 | SAFETY | Lake Oswego Signals Visibility Upgrades | CITY OF LAKE OSWEGO | CLACKAMAS, MULTNOMAH | Signal upgrades to improve visibility and safety at various locations. Install leading pedestrian intervals and changes from permissive-only green left turn signals to flashing yellow arrows. | 5000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL
1 | 22830 | SAFETY | N Basin Ave: N Leverman St - N Emerson St (Portland) | CITY OF PORTLAND | MULTNOMAH | Install a raised median; improved street lighting; signage and markings to reduce the potential for vehicle crashes. | 18000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 22831 | SAFETY | SE Foster Rd: 101st Ave - 136th Ave | CITY OF PORTLAND | MULTNOMAH | Install speed feedback signs; additional lighting and raised pavement markers to improve safety. | 12000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 22832 | SAFETY | Gresham Pedestrian Improvements | GRESHAM | MULTNOMAH | Install crosswalks with flashing lights; stop bars and signs to improve safety. Install curb ramps to meet current standards. | 20000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
3 | 22846 | SAFETY | N Columbus Ave at W Jackson St Roundabout (Medford) | CITY OF MEDFORD | JACKSON | Construct a roundabout at the intersection of North Columbus Avenue and Jackson Street in the city of Medford to reduce the number and severity of intersection crashes. | 173702 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 22860 | SAFETY | Pine Street Signal Improvements (Central Point) | CITY OF CENTRAL POINT | JACKSON | Intersection updates that may include signal upgrades; install a right-turn signal and pedestrian crossing on the northbound right turn lane at Pine;10th and Freeman Street to provide a safer route for the traveling public. | 46912 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 22914 | SAFETY | Garden Valley Rd at Melrose Rd Roundabout | DOUGLAS COUNTY | DOUGLAS | Construct a partial multi-lane roundabout at the Garden Valley Road and Melrose Road Intersection to reduce the number and severity of intersection crashes. | 165672 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
2 | 22946 | SAFETY | Beta Drive SW Rail Crossing (Albany) | RAIL DIVISION | LINN | Complete design to install light and gates and improve humped crossing to standard to improve safety and reduce incidents at crossings. | 192603 | 2026 | ROWACQ | Land Purchase 2026 | RAIL
2 | 22949 | SAFETY | Ehlen Rd NE Rail Crossing (Aurora) | RAIL DIVISION | MARION | Complete design to install a traffic control signal in eastbound direction to prevent stopping on tracks to improve safety and reduce incidents at crossings. | 56649 | 2026 | ROWACQ | Land Purchase 2026 | RAIL
1 | 23083 | BRIDGE | S Holly Lane: Abernethy Creek Bridge | CLACKAMAS COUNTY | CLACKAMAS | Replace the existing bridge with a new single-span bridge to ensure continued connectivity. | 126700 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23125 | BRIDGE | Willamette River and Independence bridge | MARION COUNTY | POLK | Strengthen the bridge to increase the load rating and perform other general repairs and maintenance to preserve the bridge. | 88700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 23134 | BRIDGE | Murder Creek (Nygren Road) bridge (Linn Co) | LINN COUNTY | LINN | Rehab existing bridge to include installing erosion protection; add new pavement; replace bridge rail and other general maintenance needs to maintain bridge integrity. | 25300 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
2 | 23138 | BRIDGE | South Santiam River-McDowell Creek Drive bridge (Linn Co) | LINN COUNTY | LINN | Fix the existing erosion to maintain the integrity of the bridge. | 10100 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 23140 | BRIDGE | Truax Creek (Clover Ridge Road) bridge (Linn Co) | LINN COUNTY | LINN | Replace the bridge to meet current standards. | 95000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 23141 | BRIDGE | Sand Creek; Sand Lake Road "Atkinson" bridge (Tillamook Co) | TILLAMOOK COUNTY | TILLAMOOK | Replace the bridge with a new one to meet current bridge standards. | 107700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 23142 | BRIDGE | Old Railroad Grade (N Yamhill River) bridge | YAMHILL COUNTY | YAMHILL | Replace the bridge to meet current standards. | 50700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 23143 | BRIDGE | Cox Creek (Waverly) Dr bridge (city of Millersburg) | CITY OF MILLERSBURG | LINN | Replace the bridge with one that meets current standards. | 88700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/COBO
2 | 23145 | BRIDGE | Crowley Creek (Three Rocks Rd) bridge (Lincoln Co) | LINCOLN COUNTY | LINCOLN | Replace the bridge to meet current standards. | 95000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 23146 | BRIDGE | Muddy Creek (Bowers Drive) bridge (Linn Co) | LINN COUNTY | LINN | Replace the bridge with one that meets current standards. | 50700 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
3 | 23161 | BRIDGE | Althouse Creek (Takilma Road) bridge | JOSEPHINE COUNTY | JOSEPHINE | Replace the existing bridge to meet current standards. | 111800 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
3 | 23163 | BRIDGE | Galls Creek (Lampman Rd) bridge | JACKSON COUNTY | JACKSON | Replace the existing bridge to meet current standards. | 63300 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 23242 | BIKPED | Willamette Falls Dr: 16th St - Ostman Rd Ped/Bike Upgrades | CITY OF WEST LINN | CLACKAMAS | Install grade separated bike facilities; pedestrian crossings; bus stops and access to transit facility; and intersection treatments prioritizing pedestrian visibility and protection. | 400000 | 2027 | ROWACQ | Land Purchase 2027 | LOCAL
1 | 23245 | BIKPED | 162nd Ave ped/bike upgrades: NE Glisan to NE Halsey | GRESHAM | MULTNOMAH | Complete street safety elements including arterial rehabilitation; ADA ramps; and crossings; pedestrian sidewalk and buffered bike lane construction to 162nd Ave from NE Glisan St north to NE Halsey St for increased pedestrian and bicyclist safety. | 239112 | 2026 | ROWACQ | Land Purchase 2026 | LOCAL/CERT
1 | 23246 | BIKPED | NE Sandy Blvd: NE 201st Ave to Quail Hollow mobile home park | MULTNOMAH COUNTY | MULTNOMAH | Construct and install bicycle facilities; sidewalks & pedestrian crossings; plus transit access amenities to increase comfort; safety; and access for all modes. | 434999 | 2027 | ROWACQ | Land Purchase 2027 | LOCAL
1 | 23254 | CMAQ | Council Creek Regional Trail: Enhanced Pedestrian Crossings | WASHINGTON COUNTY | WASHINGTON | Complete 20 street and driveway crossings along the Council Creek Regional Trail corridor to facilitate safe; convenient; and comfortable connections for people walking; biking or rolling between the centers of Forest Grove; Cornelius and Hillsboro. Trail portion being delivered under project key 23549. | 100000 | 2027 | ROWACQ | Land Purchase 2027 | LOCAL
3 | 23301 | CMAQ | 10th St Bike and Pedestrian Improvements | CITY OF CENTRAL POINT | JACKSON | Construct multi-use path for bicycle and pedestrian travel and install water quality structures for stormwater containment. | 528000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 23302 | CMAQ | Delta Waters: Waterford Ct to Colonial Ave | CITY OF MEDFORD | JACKSON | Improvements to include widening and restriping of the roadway; add new sidewalks and bike/ped facilities to improve pedestrian safety. | 175000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
3 | 23303 | CMAQ | Table Rock Rd: Merriman to I-5 | CITY OF MEDFORD | JACKSON | Add sidewalks; bike lanes; center turn lane and lighting to provide a safer travel experience for pedestrians and bicycles on the roadway. | 1000000 | 2026 | ROWACQ | Land Purchase 2026 | ODOT/LOCAL
3 | 23304 | BIKPED, CMAQ | Lincoln Rd Multi-Modal and Transit Enhancement | CITY OF GRANTS PASS | JOSEPHINE | Modernize Lincoln Rd from Bridge to G St to include bike lanes and sidewalks. Work to include turn lane and resurfacing of existing lanes. | 2265016 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | ODOT/LOCAL
1 | 23399 | TR-CAP | TriMet Beaverton Transit Center Renovation (2022 5339b) | TRIMET | WASHINGTON | Reconfigure; update; and renovate depreciated and undersized bus layover facilities at TriMet’s Beaverton Transit Center to provide a safer pedestrian environment; improved layover pull-in/ pull-out procedures; and added space for service operation. | 2509084 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL
1 | 23459 | BRIDGE | SE Bull Run Rd: Bull Run River Bridge | CLACKAMAS COUNTY | CLACKAMAS | Design and right of way acquisition to replace the existing bridge to ensure continued connectivity. | 250000 | 2025 | ROWACQ | Land Purchase 2025 | LOCAL/CERT
1 | 23463 | TRANST | TriMet Transit center EV chargers | TRIMET | MULTNOMAH, WASHINGTON | Purchase and install electric chargers at Powell bus garage and Beaverton Transit Center for electric vehicles (EV). | 15000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL
1 | 23475 | TR-CAP | TriMet Oregon City Transit Center | TRIMET | CLACKAMAS | This project includes acquisition of property; design and planning; sitework; construction and renovation of facilities at the Oregon City transit center for improved transit operations. | 2499437 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL
2 | 23484 | OPERAT | North Fork Road Improvements Project (Marion County) | MARION COUNTY | MARION | Design and construct corridor management improvements on North Fork Road and Gates Hill Road. | 50000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 23491 | OPERAT | Oregon City Quiet Zone | CITY OF OREGON CITY | CLACKAMAS | Establish a railroad quiet zone in historic downtown Oregon City to foster prosperous economic transformation; support housing and business development; grow the Oregon City Regional Center; and advance the Willamette Falls legacy project. | 100000 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
4 | 23494 | BIKPED | Hawthorne Ave Pedestrian & Bicyclist Overcrossing (Bend) | CITY OF BEND | DESCHUTES | Provide safe access for pedestrians and bicyclists by designing and constructing a bridge over US97 and BNSF railroad connecting east Hawthorne Avenue to downtown Bend. | 1068783.07 | 2024 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
2 | 23503 | BIKPED | Mill Creek Greenway Trail System (Woodburn) | CITY OF WOODBURN | MARION | Add 1.3 miles of five new trails to connect existing Mill Creek trail system 1) Evergreen (s. of W. Hays St.) to approximately Ben Brown Lane; 2) Wyffels Park; 3) Woodburn High School; 4) Settlemier Park; 5) Hermanson Pond Trail Extension. The paths will improve access and safety for people walking and biking. | 167168.17 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
2 | 23504 | BIKPED | Pringle Creek Path Connection (Salem) | CITY OF SALEM | MARION | Construct missing segment of Pringle Creek Path along the north bank of Pringle Creek connecting existing Pringle Creek paths and Salem Civic Center to Riverfront Park and to paths that extend from there to Minto Island and west Salem. The path will improve access and safety for people walking and biking. | 111445.45 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
1 | 23505 | BIKPED | Gresham Park Paths: Columbia View Park and N. Gresham Park | CITY OF GRESHAM | MULTNOMAH | Construct an approximately 800 foot multi-use path across Columbia View Park; and an approximately 1;400 foot multi-use path across North Gresham Park. Both paths will provide pedestrian and local bicycle connectivity and school access. | 6000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 23511 | BIKPED | Indian Creek Trail Critical Link Repair | HOOD RIVER PARKS & REC DISTRCT | HOOD RIVER | Construction for a 1;800 foot long; 12-foot wide; fully accessible; bike and pedestrian path connecting a gap in the Indian Creek Trail improving access and safety for people walking and biking. | 1687500 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 23524 | OPERAT | Ice Age Drive: Oregon St-SW Dahlke Ln (Tonquin) | CITY OF SHERWOOD | WASHINGTON | Planned one-mile east/west industrial collector road between SW Oregon Street and SW Dahlke Ln in Sherwood to ease traffic flow on SW Tualatin-Sherwood Road; improve access to I-5; and make it easier for companies to locate in Sherwood’s Tonquin employment area. | 873500 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
4 | 23533 | OP-Carbon | Gilliam County EV Chargers | GILLIAM COUNTY | GILLIAM | Installation of level 2 charging ports and level 3 DC fast chargers in Gilliam County. | 101002.11 | 2025 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL
1 | 23549 | BIKPED | Council Creek Regional Trail: Douglas St-Dennis Ave | WASHINGTON COUNTY | WASHINGTON | The project will construct an approximately 5.5-mile multi-use trail along an unused railroad right-of-way. The trail will extend from Hillsboro through Cornelius; to Forest Grove. Crossing portion of project being delivered under project K23254. | 150000 | 2024 | PSEDOC | Const. scheduled to begin in 2024 | LOCAL
4 | 23553 | OP-Carbon | Klamath County EV Charging Stations | KLAMATH COUNTY | KLAMATH | Install level 2 chargers and level 3 chargers at multiple locations in Klamath County to support local agency electric vehicle purchases. | 10030.09 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 23554 | BRIDGE | Burgard Bridge Resiliency and Multimodal Enhancement Project | CITY OF PORTLAND | MULTNOMAH | Replace/reconstruct existing Burgard bridge over UPRR; plus culvert; and include bicycle/pedestrian upgrades for safer freight and pedestrian movements. | 69656.25 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | LOCAL/CERT
1 | 23555 | OPERAT | 181st Ave Safety Upgrades: SE Stark St to E Burnside St | CITY OF GRESHAM | MULTNOMAH | Complete safety upgrades and enhancements between Stark St and Burnside St including: new traffic signals; adding and rehabbing sidewalks; a buffered bike lane; street lighting improvements and street utility upgrades for greater pedestrian safety. | 600000 | 2025 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL/CERT
1 | 23556 | BIKPED | 122nd Ave Safety Upgrades: Sandy Blvd to Foster Rd | CITY OF PORTLAND | MULTNOMAH | Safety improvements on 5.5 miles of 122nd Avenue from Sandy Blvd south to Foster Rd including: street lighting upgrades; 4 miles of protected bike lanes; pedestrian/bicycle signal upgrades; reducing vehicle lanes; adding pedestrian crossings; adding raised medians; landscaping; bus stop curb extensions; speed reader boards with automated enforcement and a roundabout. | 125000 | 2026 | PSEDOC | Const. scheduled to begin in 2027 | LOCAL
2 | 23573 | OPERAT | Siuslaw Road: Shaw Creek Crossing (Lane County) | LANE COUNTY | LANE | Install new fish passage near mile point 36.8 on Siuslaw Road which is under threat of failure due to the nature of an existing culvert stream crossing at Shaw Creek; a tributary to the main stem of the Siuslaw River to open up nearly five miles of salmon spawning habitat. | 15000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | ODOT/LOCAL
1 | 23574 | CULVRT | Beaver Creek Fish Passage Restoration at Troutdale Rd | MULTNOMAH COUNTY | MULTNOMAH | Design; right-of-way acquisition; and permitting for the replacement of the existing Troutdale Rd culvert and fish ladder on Beaver Creek with a new at-grade bridge. | 125000 | 2025 | ROWACQ | Land Purchase 2025 | LOCAL/CERT
1 | 23578 | CULVRT | Conway Creek at Aschoff Rd culvert replacement | CLACKAMAS COUNTY | CLACKAMAS | Design and construction to replace existing culverts carrying Conway Creek under Aschoff Road in Rhododendron; Oregon in Clackamas County. | 103000 | 2025 | PSEDOC | Const. scheduled to begin in 2026 | LOCAL/CERT
2 | 23625 | BIKPED | Main Avenue/OR 104 Pedestrian Route (Warrenton) | CITY OF WARRENTON | CLATSOP | Design and construct pedestrian improvements on the west side of Main Avenue/US 104 from the south side of 10th Place to 13th Place. | 100000 | 2024 | PSEDOC | Const. scheduled to begin in 2025 | ODOT/LOCAL