## Timeline
Target date:
Sequence | Required vs. leading practice | Category | Task | Frequency | by 9/30 | 1st month | 2nd month | 3rd month | 6th month | 1st year | 2nd year | 5th year
1 | Required | Infrastructure | Become familiar with professional auditing standards: Red Book (IPPF/IIA) and Yellow Book (GAGAS/GAO) and select one to follow. | once, long-term update
2 | Required (RB) | Action | Develop a documentation method to make independence/ethics disclosures | annually
3 | Required | Infrastructure | Create foundational IA program infrastructure (draft IA & AC charters, position description, initial QAIP, key audit procedures, and key work paper templates) | once, long-term update
4 | Required | Action | Conduct triage risk assessment; prepare short-term audit plan; begin first audit or consulting engagement | once, evolves to full risk assessment
5 | Leading practice | Action | Develop intra-agency stakeholder relationships (i.e. create Intro to IA presentation & use at various team meetings, meet with key members of leadership); participate in agency orientation (find opportunities to learn about agency operations); familiarize with state environment | ongoing
6 | Required | Infrastructure | Form audit committee (AC), convene regular meetings; consider having mentee attend first meeting | ongoing
7 | Leading practice | Action | Develop external relationships (e.g. Audits Division, CAEC, local IIA chapter, similar agencies from other state's) | ongoing
8 | Leading practice | Action | Provide or arrange for Audit Committee training | once, long-term update
9 | Leading practice | Infrastructure | Define expectations (vis-a-vis liaison with external audit, attendance at mgmt meetings, internal audit classification and reporting structure, CPE, etc.) | once, long-term update
10 | Required | Action | File annual report of IA activities with DAS | annually
11 | Required (RB) | Action | Provide annual report on IA activities to agency management | annually
12 | Required | Action | Facilitate full, formal risk assessment (or updates) | annually
13 | Required | Action | Create audit plan from risk assessment and present to AC | annually
14 | Required | Action | QAIP self-assessment (incorporate capability maturity model; address any deficiencies noted) | annually
15 | Leading practice | Infrastructure | Develop strategic plan, mission, goals, performance metrics, and benchmarks for IA | once, long-term update
16 | Required | Infrastructure | Achieve and maintain professional audit certifications & continuing education | once, annually for CPE
17 | Required | Infrastructure | Build the IA Function's QAIP | once, long-term update
18 | Required | Infrastructure | Ensure IA's policies/procedures manual is fully developed & template work papers are established | once, long-term update
19 | Required | Action | Complete an audit of a governance topic | Within 5 years
20 | Required | Action | Have an external Quality Assurance Review (QAR or Peer Review) performed | Within 3 - 5 years
21 | Required | Action | Prepare an action plan for any deficiencies or opportunities for improvement noted in QAR report and report on progress to AC periodically. | 5 years, ongoing as needed