## January 2021 - Less Aggressive (hidden)
GOAL: Implementation January 1, 2021
| January 2020 | February 2020 | March 2020 | April 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021
Project milestones
* WHAT ABOUT BUDGETING ISSUES? Not meeting the March 2020 deadline?
Communications
Regenerate class specs (1 week)
Place allocations in new salary ranges (2 months)
Implementation
Update/vet new salary ranges (2 months)
Refresh market (2 months)
Project email
update to Agency and HR Directors
Retrain HR analysts on new classes/ allocation (1 month) -----
- prepare training (1 week)
- multiple 2 hour classes
Audit new allocations (2 months)
Send agencies allocations for review and update. (2 months)
- Notify employees / Review appeals
- Input new classifications and salaries into Workday
ELT update
Training notifications to HR community
Initial allocations and instructions to agencies/HR
Conversations with agencies about allocations.
Final stakeholder approval of salary ranges (ELT?)
Notify employees of new allocations and appeal process
Notify agencies of all agency allocations

## Sheet
Classes Study Timeline
Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Month 18 | Month 19 | Month 20 | Month 21 | Month 22 | Month 23 | Month 24
Management Classifciation Review Implementation ¦ Timeline w/ NO additional staffing
October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021
Conduct market analysis, internal equity review, evaluate job content, develop job family and class specs
Evaluate and address issues and requests agency feedback
SME CET presentation preparation
TOMP Update Training
(JC, DM, NK)
Update/vet new salary ranges
Market refresh
Class Development (AP, CL, DM, LS, HY)
1st PLE, Plus Lines
2nd Most Populous
3rd Generalized for Occ Group
4th One Offs/Custom
*Goal is 90-95% of class specs developed
Pay equity for new allocations
Develop appeal process
and forms
Employee classification & PE notification, appeals
CHRO review of classification and pay
equity appeals
Workday Implentation
Agency Review Finalization
Finalize Spec
(AP, CL, DM)
Notify Agencies of Allocations
Cluster Analysis, Agency Meetings, and Planning
(DM, CL, TH)
Hold SME meetings to review occupation, agency needs, class spec drafts, discuss work details, and fonalize specs
CET Session
LRU Bargains study results and creates LOA (3-6 months but often longer).
Agencies conduct preallocations for bargaining preparation
Draft report and submit study results to DAS LRU for bargaining
Pay Setting (CET + internal equity review + market study)
Send final class specs to agency management and unions for review and comment
Agencies finalize allocations. Agencies send allocation letters to employees and completes allocation process
Send allocation letters to employees (within 2 weeks of audit completion) and complete agency level appeals
Send allocation letters to employees (within 2 weeks of audit completion) and complete agency level appeals
LRU submits eBoard letter (quarterly submission)
Workday + CnC creates job profile
Agencies key position changes and report position changes to CFO/SABRS

## July 2021 (hidden)
Management Classifciation Review Implementation
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021
Management Classification Review Implementation
Management Classifciation Review Implementation ¦ Timeline w/ NO additional staffing
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021
Management Classification Review Implementation
Increasing Training and Accountability Implementation
Increasing Training and Accountabilitiy Implementation
Increasing Training and Accountability Communications
TOMP Update Training
Update/vet new salary ranges
Market refresh
Pay equity for new allocations
Develop appeal process
and forms
Employee classification & PE notification, appeals
CHRO review of classification and pay
equity appeals
Workday Implentation
Classificaton Specification Development
TOMP Update Training
(JC, DM, NK)
Update/vet new salary ranges
Market refresh
Class Development (AP, CL, DM, LS, HY)
1st PLE, Plus Lines
2nd Most Populous
3rd Generalized for Occ Group
4th One Offs/Custom
*Goal is 90-95% of class specs developed
Pay equity for new allocations
Develop appeal process
and forms
Employee classification & PE notification, appeals
CHRO review of classification and pay
equity appeals
Workday Implentation
Agency Review Finalization
Finalize Spec
(AP, CL, DM)
Notify Agencies of Allocations
Cluster Analysis, Agency Meetings, and Planning
(DM, CL, TH)
ONLINE
Training pilot
ONLINE
Review and approve modules
ONLINE and IN-CLASS
All managers of managers complete mandatory training by April 15, 2020
AFTER managers-of-manager completes required training,
All supervisory managers recieve first performance feedback/check-in by June 30, 2020.
IN-CLASS
Training pilot
IN-CLASS
Logistics coordination, including procuring facilities, opening registrations, etc.
Request participation from pilot agencies/ groups
Project update to all agency directors and HR community
Information and training on process to pilot agencies/ groups
Feedback from pilot agencies and groups
Official "start" communications of training and performance requirements
ONLINE
Update training from pilot feedback
IN-CLASS
Update training from pilot feedback
Ongoing communications:
-Reports sent to Agency Directors monthly
- Individual completion reminders to managers
Agency Allocations
Agency allocation validation and update

## October 2021 (hidden)
Management Classifciation Review Implementation
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021 | July 2021 | August 2021 | September 2021
Management Classification Review Implementation
Management Classifciation Review Implementation ¦ Timeline w/ NO additional staffing
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021
Management Classification Review Implementation
Increasing Training and Accountability Implementation
Increasing Training and Accountabilitiy Implementation
Increasing Training and Accountability Communications
TOMP Update Training
Update/vet new salary ranges
Market refresh
Develop appeal process
and forms
Employee classification appeals
CHRO review of classification appeals
Workday Implentation
Classificaton Specification Development
TOMP Update Training
(JC, DM, NK)
Update/vet new salary ranges
Market refresh
Class Development (AP, CL, DM, LS, HY)
1st PLE, Plus Lines
2nd Most Populous
3rd Generalized for Occ Group
4th One Offs/Custom
*Goal is 90-95% of class specs developed
Pay equity for new allocations
Develop appeal process
and forms
Employee classification & PE notification, appeals
CHRO review of classification and pay
equity appeals
Workday Implentation
Agency Review Finalization
Finalize Spec
(AP, CL, DM)
Notify Agencies of Allocations
Cluster Analysis, Agency Meetings, and Planning
(DM, CL, TH)
ONLINE
Training pilot
ONLINE
Review and approve modules
ONLINE and IN-CLASS
All managers of managers complete mandatory training by April 15, 2020
AFTER managers-of-manager completes required training,
All supervisory managers recieve first performance feedback/check-in by June 30, 2020.
IN-CLASS
Training pilot
IN-CLASS
Logistics coordination, including procuring facilities, opening registrations, etc.
Request participation from pilot agencies/ groups
Project update to all agency directors and HR community
Information and training on process to pilot agencies/ groups
Feedback from pilot agencies and groups
Official "start" communications of training and performance requirements
ONLINE
Update training from pilot feedback
IN-CLASS
Update training from pilot feedback
Ongoing communications:
-Reports sent to Agency Directors monthly
- Individual completion reminders to managers
Agency Allocations
Agency allocation validation and update

## December 2021 (hidden)
Management Classifciation Review Implementation
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021 | July 2021 | August 2021 | September 2021 | October 2021 | November 2021
Management Classification Review Implementation
Management Classifciation Review Implementation ¦ Timeline w/ NO additional staffing
| October 2019 | November 2019 | December 2019 | January 2020 | February 2020 | March 2020 | April 2020 | May 2020 | June 2020 | July 2020 | August 2020 | September 2020 | October 2020 | November 2020 | December 2020 | January 2021 | February 2021 | March 2021 | April 2021 | May 2021 | June 2021
Management Classification Review Implementation
Increasing Training and Accountability Implementation
Increasing Training and Accountabilitiy Implementation
Increasing Training and Accountability Communications
TOMP Update Training
Update/vet new salary ranges
Market refresh
Develop appeal process
and forms
Employee classification appeals
CHRO review of classification appeals
Workday Implentation
Classificaton Specification Development
TOMP Update Training
(JC, DM, NK)
Update/vet new salary ranges
Market refresh
Class Development (AP, CL, DM, LS, HY)
1st PLE, Plus Lines
2nd Most Populous
3rd Generalized for Occ Group
4th One Offs/Custom
*Goal is 90-95% of class specs developed
Pay equity for new allocations
Develop appeal process
and forms
Employee classification & PE notification, appeals
CHRO review of classification and pay
equity appeals
Workday Implentation
Agency Review Finalization
Finalize Spec
(AP, CL, DM)
Notify Agencies of Allocations
Cluster Analysis, Agency Meetings, and Planning
(DM, CL, TH)
ONLINE
Training pilot
ONLINE
Review and approve modules
ONLINE and IN-CLASS
All managers of managers complete mandatory training by April 15, 2020
AFTER managers-of-manager completes required training,
All supervisory managers recieve first performance feedback/check-in by June 30, 2020.
IN-CLASS
Training pilot
IN-CLASS
Logistics coordination, including procuring facilities, opening registrations, etc.
Request participation from pilot agencies/ groups
Project update to all agency directors and HR community
Information and training on process to pilot agencies/ groups
Feedback from pilot agencies and groups
Official "start" communications of training and performance requirements
ONLINE
Update training from pilot feedback
IN-CLASS
Update training from pilot feedback
Ongoing communications:
-Reports sent to Agency Directors monthly
- Individual completion reminders to managers
Agency Allocations
Agency allocation validation and update