## Home
Design / Build Construction | Tips, Risk Reduction Strategies and Loss Examples
Less Common Project-Delivery Method The contractor designs and constructs the project. This gives a single point of responsibility for delivering the entire project. Design/build is an alternative to the traditional design/bid/build project method. | These tips, risk reduction strategies and loss examples help offer insight when conducting an insurance risk assessment.
Risk Management
Construction risk assessment tool
Design/build construction

## Loss Example
Tips, Risk Reduction Strategies and Loss Examples
Design Build Procurement
These tips, risk reduction strategies and loss examples should be used to assist with the risk assessment.
Home Page
Tips
Risk Reduction Strategies
Loss Examples
Tips
Occurrence vs. Claims-made Coverage
Occurrence Coverage:
Covers all claims arising out of incidents occurring during the policy period, regardless of whether or not the policy is still in effect at the time that the claim is made. Occurrence-based coverage should be generally available, except on professional liability and pollution liability coverage.
Claims-made Coverage:
A claim for injury or damage must be reported or filed during a policy period when coverage is in force in order to be covered. To ensure coverage is in force when a claim is made, the claims made policy needs to be continuously renewed (and premium paid). Generally, professional liability, high hazard products liability and pollution liability policies are written on a claims made basis. “Tail” coverage may be purchased to extend the time to report a claim after the claims made policy has ended.
Documentation
Conduct an insurance risk assessment to identify suggested insurance types and amounts, document the summary page with the contract documentation, and update the contract insurance requirements template.
Verify the contractor has the required insurance coverage, endorsements and proper insurance language as outlined within the insurance requirements template.
Contact DAS Risk Management
Contact DAS Risk Management with questions or concerns at:
|  | Email: | Risk.Management@oregon.gov
|  | Phone: | 503-373-7475
The examples below are to help prompt the thinking/assessment process, but is not an exhaustive list of examples. Additional questions/examples may need to be addressed. Be sure to involve subject matter experts.
Risk Reduction Strategies
Verify the scope of work is within the contractor's area of expertise and experience.
Put into place a security plan for the project, which could include but is not limited to fencing off the construction zone, providing security lighting / cameras within construction zone, contracting with a security service to patrol the area, etc.
For construction within a partially occupied building consider if the work can be performed after hours, if the employees can be moved from the construction zone and if the construction zone can be partitioned off.
If the construction requires demolishing or remodeling existing structures, establish the value of the structures before any removal/remodeling work begins. Also consider photographic or video log of all existing conditions before work begins. This is necessary to properly document the amount of work performed and can be a valuable record of existing conditions.
Design-Build Loss Examples
Automobile and Pollution Liability: Excess of $500,000
Contractor’s refueling vehicle was in an accident while in route to a construction site to refuel equipment. The resulting fuel spill flowed into a storm sewer which discharged into a wetlands area. Claim costs were in excess of $500,000, plus expenses associated with the restoration of the wetlands. 1
Pollution Liability: Excess of $100,000
While performing building renovations, a general contractor used gas powered generators and equipment. The contractor failed to properly vent or contain the emissions from the equipment during operations. Employees working in a nearby area of the building complained of headaches, nausea and respiratory problems. The results of an air quality study concluded that the increased carbon dioxide levels in the building resulted from the construction equipment. The contractor was liable for causing building-related illnesses that resulted in 30 bodily injury claims totaling over $100,000. 2
Pollution Liability: $1 million
Two years after the completion of a new school, it was discovered that water was infiltrating through the window system into the building. The water intrusion created the right environment for the growth of mold. It was determined that faulty installation and window defects were the cause. The contractor and the windows manufacturer shared remediation costs. The contractor did not have pollution coverage for mold and paid close to $1,000,000 out-of-pocket. 3
Pollution Liability: $10 million
A $10 million claim was filed against a general contractor performing renovation of a city building. The claim alleged negligence in creating unsafe air quality conditions in the ventilation and air filtration systems, causing employees on the premises to suffer serious injuries from inhalation of, and exposure to, toxic fumes and airborne contaminants. 4
Pollution Liability: $10 million
A general contractor was responsible for overseeing the renovation of a hospital wing. When two patients died in the intensive care unit adjacent to the construction zone, the contractor was sued for inadequate monitoring and containment of the construction zone. The patients’ cause of death was determined to be an organic fungus found in the ventilation system, and traced back to dusts generated during demolition activities in the construction zone. The contractor apparently misinterpreted construction drawings with regard to the connection of the duct system for the renovation zone and the intensive care unit. The general contractor was responsible for $10 million in damages. 5
Professional Liability: Excess of $300,000
A commercial developer retained a design/build delivery system for the construction of a multi-story office building. The general contractor’s project manager failed to check the adequacy of the safety netting system installed in connection with the project’s roof installation. A worker fell and sustained injuries, and his attorney alleged inadequate safety controls and monitoring on the part of the general contractor. The contractor’s general liability policy contained a professional services exclusion. The general contractor was responsible for damages exceeding $300,000. 6
Professional Liability: $350,000
A general contractor sub-contracted masonry work for a warehouse project. The masonry sub-contractor did not construct the loading dock according to the design plans. The general contractor was accused of poor supervision and was held responsible for damages of $350,000 including costs to rebuild the loading dock. 7
Professional Liability: Excess of $500,000
A general contractor and architect retained a design/build contract for design and construction services to rehabilitate the roof of a retail shopping center. Half of the roof was replaced before shutdown for the winter. In January, several stores occupying areas of the shopping center where the roof had already been rehabilitated reported extensive leaking. One of the shopping center tenants retained an engineer who alleged that the leakage was due to ice damming resulting from inappropriate design. Damages for the tenant’s business loss and damaged inventory exceeded $500,000. To be removed from this claim, the general contractor exhausted defense costs in excess of $200,000. 8
Professional Liability: $3 million
A Contractor was hired to construct a class “A” office building with both residential and commercial retail space with the HVAC system to be provided under a design/build delivery method by the contractor. The project was completed but within weeks of opening there were many complaints regarding the temperature and comfort within the building. Several weeks following that, mold was discovered in a few sections of the commercial building, and then ultimately throughout most sections of the building, including the residential sections. The claim was litigated, involving the contractor, as well as numerous subcontractors engaged in the project. It was determined that a portion of the loss which resulted from deficiencies in the design-builder’s oversight, including system installation and commissioning, resulting in almost $3 million in damages. 9
Footnote:
The above loss examples have been provided by:
1 XL Catlin; 2 Partner One Environmental; 3 XL Catlin; 4, 5, 6 Partner One Environmental; 7 Philadelphia Insurance Companies; 8 Partner One Environmental; 9 XL Catlin

## Design-Build (DB)
Design / Build
New Building Construction | Existing Building Construction
Includes general contractor work for new public and institutional buildings and related structures, such as parking structures. | Includes general contractor or specialty trade contractor work for additions, alterations, maintenance, and repairs of existing public and institutional buildings and related structures, such as parking structures. Specialty trade contractors are included if they are engaged in activities primarily related to the additions, alterations, maintenance, and repairs.
Home

## Scope of Work (DB-EB)
Home | Design / Build | Scope of Work |  |  | Insurance Assessment | Summary / Print
Review Scope of Work and Select Contractor Types |  |  | Site Preparation Contractors |  |  |  | Notes
|  |  | FALSE | Site Preparation Contractors
|  |  | FALSE | Remediation Services
Foundation, Structure and Building Exterior Contractors
|  |  | FALSE | Poured Concrete Foundation / Structure Contractors
|  |  | FALSE | Structural Steel and Precast Concrete Contractors
|  |  | FALSE | Framing Contractors
|  |  | FALSE | Masonry Contractors
|  |  | FALSE | Glass and Glazing Contractors
|  |  | FALSE | Roofing Contractors
|  |  | FALSE | Siding Contractors
|  |  | FALSE | Other Foundation, Structure and Exterior Contractors
Building Finishing Contractors
|  |  | FALSE | Electrical and Other Wiring Installation Contractors
|  |  | FALSE | Plumbing, Heating and Air-Conditioning Contractors
|  |  | FALSE | Other Building Equipment Contractors
|  |  | FALSE | Drywall and Insulation Contractors
|  |  | FALSE | Painting and Wall Covering Contractors
|  |  | FALSE | Flooring Contractors |  |  | Click here to continue to Insurance Assessment
|  |  | FALSE | Tile and Terrazzo Contractors
|  |  | FALSE | Finish Carpentry Contractors
|  |  | FALSE | Other Building Finishing Contractors
Other Specialty Trade Contractors
|  |  | FALSE | All Other Specialty Trade Contractors
Note on L21: This industry comprises establishments primarily engaged in site preparation activities, such as excavating and grading, demolition of buildings and other structures, and septic system installation. Earthmoving and land clearing for all types of sites (e.g., building, nonbuilding, mining) is included in this industry. Establishments primarily engaged in construction equipment rental with operator (except cranes) are also included. Illustrative Examples: Blasting, building demolition Foundation digging (i.e., excavation) Concrete breaking and cutting for demolition Foundation drilling contractors Cutting new rights of way Grading construction sites Demolition, building and structure Line slashing or cutting (except maintenance) Dewatering contractors Septic system contractors Dirt moving for construction Trenching (except underwater) Equipment rental (except crane), construction, with operator Underground tank (except hazardous) removal Excavating, earthmoving, or land clearing contractors Wrecking, building or other structure
Note on L22: This industry comprises establishments primarily engaged in one or more of the following: (1) remediation and cleanup of contaminated buildings, mine sites, soil, or ground water; (2) integrated mine reclamation activities, including demolition, soil remediation, waste water treatment, hazardous material removal, contouring land, and revegetation; and (3) asbestos, lead paint, and other toxic material abatement.
Note on L24: This industry comprises establishments primarily engaged in pouring and finishing concrete foundations and structural elements. This industry also includes establishments performing grout and shotcrete work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete pouring and finishing Gunite contractors Concrete pumping (i.e., placement) Mud-jacking contractors Concrete work (except paving) Shotcrete contractors Footing and foundation concrete contractors
Note on L25: This industry comprises establishments primarily engaged in (1) erecting and assembling structural parts made from steel or precast concrete (e.g., steel beams, structural steel components, and similar products of precast concrete) and/or (2) assembling and installing other steel construction products (e.g., steel rods, bars, rebar, mesh, and cages) to reinforce poured-in-place concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete product (e.g., structural precast, structural prestressed) installation Rebar contractors Erecting structural steel Reinforcing steel contractors Placing and tying reinforcing rod at a construction site Structural steel contractors Precast concrete panel, slab, or form installation
Note on L26: This industry comprises establishments primarily engaged in structural framing and sheathing using materials other than structural steel or concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Building framing (except structural steel) Post framing contractors Foundation, building, wood, contractors Steel framing contractors Framing contractors Wood frame component (e.g., truss) fabrication on site
Note on L27: This industry comprises establishments primarily engaged in masonry work, stone setting, bricklaying, and other stone work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Block laying Marble, granite, and slate, exterior, contractors Bricklaying Masonry pointing, cleaning, or caulking Concrete block laying Stucco contractors Foundation (e.g., brick, block, stone), building, contractors
Note on L28: This industry comprises establishments primarily engaged in installing glass panes in prepared openings (i.e., glazing work) and other glass work for buildings. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Decorative glass and mirror installation Glazing contractors Glass cladding installation Stained glass installation Glass coating and tinting (except automotive) contractors Window pane or sheet installation Glass installation (except automotive) contractors
Note on L29: This industry comprises establishments primarily engaged in roofing. This industry also includes establishments treating roofs (i.e., spraying, painting, or coating) and installing skylights. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Painting, spraying, or coating, roof Sheet metal roofing installation Shake and shingle, roof, installation Skylight installation
Note on L30: This industry comprises establishments primarily engaged in installing siding of wood, aluminum, vinyl, or other exterior finish material (except brick, stone, stucco, or curtain wall). This industry also includes establishments installing gutters and downspouts. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Downspout, gutter, and gutter guard installation Fascia and soffit installation Siding (e.g., vinyl, wood, aluminum) installation
Note on L31: This industry comprises establishments primarily engaged in building foundation and structure trades work (except poured concrete, structural steel, precast concrete, framing, masonry, glass and glazing, roofing, and siding). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Curtain wall, metal, installation Forms for poured concrete, erecting and dismantling Welding, on-site, contractors Ornamental metal work installation Fire escape installation Decorative steel and wrought iron work installation
Note on L33: This industry comprises establishments primarily engaged in installing and servicing electrical wiring and equipment. Contractors included in this industry may include both the parts and labor when performing work. These contractors may perform new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Airport runway lighting contractors Fiber optic cable (except transmission line) contractors Alarm system (e.g., fire, burglar), electric, installation only Highway, street, and bridge lighting and electrical signal installation Audio equipment (except automotive) installation contractors Home automation system installation Lighting system installation Cable television hookup contractors Telecommunications equipment and wiring (except transmission line) installation contractors Computer and network cable installation Traffic signal installation Environmental control system installation Cable splicing, electrical or fiber optic
Note on L34: This industry comprises establishments primarily engaged in installing and servicing plumbing, heating, and air-conditioning equipment. Contractors in this industry may provide both parts and labor when performing work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Cooling tower installation Heating, ventilation, and air-conditioning (HVAC) contractors Duct work (e.g., cooling, dust collection, exhaust, heating, ventilation) installation Lawn sprinkler system installation Fire sprinkler system installation Mechanical contractors Fireplace, natural gas, installation Refrigeration system (e.g., commercial, industrial, scientific) installation Furnace installation Sewer hookup and connection, building
Note on L35: This industry comprises establishments primarily engaged in installing or servicing building equipment (except electrical, plumbing, heating, cooling, or ventilation equipment). The repair and maintenance of miscellaneous building equipment is included in this industry. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Automated and revolving door installation Lightning protection equipment (e.g., lightning rod) installation Boiler and pipe insulation installation Machine rigging Commercial-type door installation Millwrights Conveyor system installation Overhead door, commercial- or industrial-type, installation Dismantling large-scale machinery and equipment Revolving door installation Elevator installation Satellite dish, household-type, installation Escalator installation Vacuum cleaning system, built-in, installation Gasoline pump, service station, installation
Note on L36: This industry comprises establishments primarily engaged in drywall, plaster work, and building insulation work. Plaster work includes applying plain or ornamental plaster, and installation of lath to receive plaster. The work performed may include new work, additions, alterations, maintenance, and repairs. Establishments primarily engaged in providing firestop services are included in this industry. Illustrative Examples: Acoustical ceiling tile and panel installation Lathing contractors Drop ceiling installation Plastering (i.e., ornamental, plain) contractors Drywall contractors Soundproofing contractors Firestop contractors Fresco (i.e., decorative plaster finishing) contractors Taping and finishing drywall Gypsum board installation Wall cavity and attic space insulation installation
Note on L37: This industry comprises establishments primarily engaged in interior or exterior painting or interior wall covering. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bridge painting Paperhanging or removal contractors House painting Ship painting contractors Paint and wallpaper stripping Wallpaper hanging and removal contractors
Note on L38: This industry comprises establishments primarily engaged in the installation of resilient floor tile, carpeting, linoleum, and hardwood flooring. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Carpet, installation only Resilient floor tile or sheet (e.g., linoleum, rubber, vinyl), installation only Vinyl flooring contractors Resurfacing hardwood flooring Hardwood flooring, installation only Floor laying, scraping, finishing, and refinishing
Note on L39: This industry comprises establishments primarily engaged in setting and installing ceramic tile, stone (interior only), and mosaic and/or mixing marble particles and cement to make terrazzo at the job site. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Ceramic tile installation Mosaic work Mantel, marble or stone, installation Tile (except resilient) laying and setting Stone flooring installation Marble, granite, and slate, interior installation contractors
Note on L40: This industry comprises establishments primarily engaged in finish carpentry work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Built-in wood cabinets constructed on site Molding or trim, wood or plastic, installation Countertop, residential-type, installation Paneling installation Door and window frame construction Prefabricated kitchen and bath cabinet, residential-type, installation Garage door, residential-type, installation Ship joinery contractors Millwork installation Window and door, residential-type, of any material, prefabricated, installation
Note on L41: This industry comprises establishments primarily engaged in building finishing trade work (except drywall, plaster, and insulation work; painting and wall covering work; flooring work; tile and terrazzo work; and finish carpentry work). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bathtub refinishing, on-site Fabricating metal cabinets or countertops on site Closet organizer system installation Modular furniture system attachment and installation Concrete coating, glazing, or sealing Trade show exhibit installation and dismantling Countertop and cabinet, metal (except residential-type), installation Waterproofing contractors Drapery fixture (e.g., hardware, rods, tracks) installation Window shade and blind installation
Note on L43: This industry comprises establishments primarily engaged in specialized trades (except foundation, structure, and building exterior contractors; building equipment contractors; building finishing contractors; and site preparation contractors). The specialty trade work performed includes new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Billboard erection Outdoor swimming pool construction Cleaning building interiors during and immediately after construction Paver, brick (e.g., driveway, patio, sidewalk), installation Crane rental with operator Paving, residential and commercial driveway and parking lot Sandblasting building exteriors Fence installation Scaffold erecting and dismantling Interlocking brick and block installation Steeplejack work Manufactured (mobile) home set up and tie-down work Driveway paving or sealing
Existing building construction

## Insurance Requirements (DB-EB)
Home | Design / Build |  | Scope of Work |  | Insurance Assessment |  | Summary / Print
General Liability and Umbrella Coverage |  | Automobile Liability |  | Contractor's Pollution Liability |  | Installation Floater and Builder's Risk |  | Contractor's Professional Liability | Additional Coverages
Commercial General Liability (CGL) is required in all contracts. It is perhaps the most important of all insurance policies in a contractual relationship. It ensures the Contractor has broad liability coverage for contractual activities and for completed operations. Note: CGL does not provide coverage for Professional Liability. |  | Automobile Liability insurance is typically required in most contracts. Automobile Liability is need whenever contracted work requires use of a licensed vehicle on public roads or on your property (this includes driving between job sites, to and from meetings, and/or occasional trips). |  | Contractor's Pollution Liability insurance is required when the contractor will be using, removing, hauling, storing, or disposing of hazardous materials. |  | Installation Floater coverage is required for maintenance, repair or interior renovation. This policy is designed to protect a specific contractor from the loss of property installed by that contractor. |  | Contractor's Professional Liability insurance is required when the Contractor's work is in a professional field requiring specialized knowledge and intellectual skills. | Additional coverages are non-typical coverages that may be required based on the exposures from specialized contracted services. These types of coverages include, but are not limited to Aircraft Liability, Drone Liability, Marine Liability and more. Review to confirm if additional coverages are needed.
Builder's Risk insurance is required during the course of construction to add additional square footage of. This policy is designed to cover property at the construction site, off-site storage locations and in transit.
Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. | Click HERE for more information.
Existing building construction
Note on L23: Hazardous Material includes lead and asbestos, such as when a contractor is involved in lead and/or asbestos removal/abatement. A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).
Note on Q23: Use whenever a building is being constructed, repaired, or remodeled and there will be more than $10,000 in building materials and supplies at a storage location, in transit, or during the installation and testing process that are intended to become a permanent part of the building. Builders´ Risk Installation Floaters cover property installed at a work site by a particular contractor or sub-contractor. The coverage normally applies while the property is in transit or in temporary storage, and during the installation and testing process. Installation floaters are generally associated with such property as plumbing, heating, cooling, and electrical systems but can be used to insure any property being installed. Carpeting, tile, windows, elevators, and machinery are examples of property that can be covered. Theft and vandalism are covered. Coverage is usually an add-on to a Builders´ Risk Policy, but may be purchased separately by sub-contractors on the project. A separate policy may be written for specific job sites, or a blanket policy may be written for a contractor who has many jobs in progress at the same time. Coverage usually ends at the earliest of the following: When the financial interest of the contractor (insured) stops. When the state (purchaser) accepts the property as complete. When the policy expires or is canceled. Coverage should extend until installed equipment, materials or fixtures are accepted by the state upon satisfactory completion by the Contractor.
Note on Q33: Use when a new building is being constructed, when substantial alternations will be made to an existing structure, i.e., bearing walls, lifting foundations, extensive construction, or when equipment is installed in an existing building. The Policy will pay for damages up to the coverage limit. The limit must accurately reflect the total completed value of the structure (all materials and labor costs, excluding land value). Coverage for direct physical loss by a covered peril to an entire building or other structure at the "jobsite" during the course of construction, including limited coverage (See also Builders´ Risk Installation Floater) for the building supplies and materials that will become part of the covered structure. Also covers: Foundations, excavations, grading, filling, attachments, permanent fencing, and other permanent fixtures. Scaffolding, construction forms or temporary fencing at the described "jobsite" and temporary structures at the described "jobsite". Project size or type triggers Builder's Risk insurance recommendation.

## CGL Umbrella (DB-EB)
Home |  |  | Design / Build | Scope of Work |  | Insurance Assessment | Summary / Print
Commercial General Liability (CGL) and Excess/Umbrella Coverage Selection |  |  |  |  | Notes |  |  | Risk Reduction Strategies
The contract is for a: |  |  |  |  | Commercial General Liability coverage is a risk transfer strategy to help cover the cost of liability claims for personal injury, property damage and advertising injury. |  |  | 1. | Move employees from construction zone.
FALSE | Specialty Trade Contractor | [6 empty] | 2. | If building is occupied by employees, perform the construction work after hours.
FALSE | General contractor (GC) contract size less than $10M
[5 empty] | Note: Require an additional insured endorsement with respect to liability arising out of ongoing operations and completed operations. This practice helps protect the contractor and the state from losses that occur during the course of construction, as well as claims arising out of the completed project (damages found after the project is completed). Review Insurance Template for more detail. |  |  | 3. | Partition off construction zone for safety and security reasons.
FALSE | General contractor (GC) contract size greater than $10M but less than $20M
[8 empty] | 4. | Before work begins, document existing conditions and values of existing structures.
| Note: | Projects equal to or more than
$20M contact DAS Risk Management.
[8 empty] | 5. | Before work begins, memorialize the condition of adjacent properties and document distance from project.
Commercial General Liability Coverage:
Suggested per occurrence amount:
Suggested aggregate amount: |  |  |  |  | Note: Excess/umbrella insurance coverage shall be provided and will apply over all liability policies, without exception, including but not limited to Commercial General Liability, Automobile Liability, and Employers’ Liability coverage.
Click here to continue working on Insurance Assessment
Excess/Umbrella Coverage:
Suggested coverage amount:
Existing building construction

## Automobile (DB-EB)
Home |  | Design / Build | Scope of Work |  |  | Insurance Assessment | Summary / Print
Automobile Liability |  |  |  | Automobile Liability Endorsement |  |  |  | Tips, Risk Reduction Strategies and Loss Examples
Will the Contractor: |  |  |  | Will the Contractor: |  |  |  | Click HERE to review tips, risk reduction strategies and loss examples which will help offer insight when conducting an insurance risk assessment.
FALSE | 1. Use a vehicle to accomplish the work? |  |  | FALSE | Transport hazardous materials?
FALSE | 2. Travel to or from state locations? |  |  | Automobile Liability Endorsement:
Transportation of Hazardous Materials CA 99 48 and MCS-90 Endorsements:
FALSE | 3. Transport state property, clients, or employees?
Automobile Liability Coverage:
Suggested minimum combined single limit:
Note: Automobile Liability Coverage is set for a minimum of $1M as it takes into account the Excess/Umbrella Coverage which should also apply over the Automobile Liability Coverage (Excess/Umbrella Coverage recommendation is set within the General Liability and Umbrella Coverage section).
Click here to continue working on Insurance Assessment
Existing building construction
Note on L27: Hazardous Material includes lead and asbestos, such as when a contractor is involved in lead and/or asbestos removal/abatement. A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).

## Pollution (DB-EB)
Contractor's Pollution Liability (CPL) for Existing Building Construction |  |  | Step 3: Contractor's Pollution Liability Endorsements: |  | Risk Reduction Strategies
Will the Contractor:
Step 1: Phase I Environmental Site Assessment (ESA) |  |  | FALSE | 1. Abate, remove, dispose and/or work with asbestos? |  | Asbestos Risk - Buildings built in or before 1985 have a higher chance of containing asbestos. It is important to identify any asbestos-containing materials before work begins. Any abatement of asbestos must be performed by an Oregon DEQ Licensed Asbestos Abatement Contractor.
| 1. Has a Phase I ESA been done? |  | FALSE | 2. Abate, remove, dispose and/or work with lead?
| FALSE | Yes, and hazardous materials are not present
TRUE | FALSE | Yes, and hazardous materials are present | Contractor's Pollution Liability Endorsements:
| FALSE | No, hazardous materials at the site are unknown | Asbestos Liability Endorsement:
Lead Liability Endorsement:
Step 2: Will the Contractor: | [5 empty] | Lead Risk - Buildings built in or before 1978 have a higher chance of containing lead based paint. It is important to identify any lead based materials before work begins.
FALSE | 1. Store hazardous materials on the job site? |  | Contractor's Pollution Liability Coverage:
Suggested minimum per occurrence:
FALSE | 2. Apply, use or handle hazardous materials on job site? |  | Suggested minimum aggregate:
FALSE | 3. Are other hazardous materials present?
4. Abate, remove and/or dispose of hazardous materials?
| FALSE | Small scale / low risk abatement |  |  | Click here to continue working on Insurance Assessment
| FALSE | Medium-large scale / medium-high risk abatement
FALSE | 5. Work in, around or over water, wells, wetlands, or protected species area?
Existing building construction
Note on C26: A Phase I Environmental Site Assessment (ESA) is conducted by a qualified environmental professional to identify potential or existing environmental contamination within underlying land as well as physical improvements to the property. Standards for a Phase I ESA are outlined by the United States Environmental Protection agency.
Note on C34: Hazardous materials can include operating fluids such as fuel, lubricants, hydraulics, etc. and can also include hazardous building materials, treatments and finishes.
Note on C36: Hazardous materials can include operating fluids such as fuel, lubricants, hydraulics, etc. and can also include hazardous building materials, treatments and finishes.
Note on C38: i.e. lead paint, underground fuel tanks, soil contamination, etc.
Note on C40: A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).
Note on D41: Small Scale/Low Risk – Abatement work in a section of a building and abatement does not require containment. Example hazardous materials include but are not limited to nonfriable asbestos, lead paint, mold, regulated hazardous materials, chemicals, contaminated soil, fuels, etc...
Note on D42: Medium-large scale/medium-high risk – Abatement work building wide and or abatement requires containment of building and materials (air monitoring inside/outside building containment area, negative air pressure maintained throughout abatement) and or building is partially occupied (employees and or clients). Example hazardous materials include but are not limited to friable asbestos, mold, regulated hazardous materials, chemicals, contaminated soil, fuels, etc...

## Builder's Risk (DB-EB)
Home |  | Design / Build |  | Scope of Work |  |  | Insurance Assessment |  | Summary / Print
Installation Floater for Existing Building Construction |  |  |  |  | Builder's Risk for Existing Building Construction |  |  |  |  | Policy Review
Project Costs
Not Adding Square Footage and Not Making Significant Structural Changes |  |  |  |  | Adding Square Footage / Significant Structural Changes
If the cost of the architect, engineer and building permits are included within the project cost, confirm these costs are covered in the policy.
Step 1: Partial Occupancy During Construction:
Installation Floater: | [5 empty] | If the building will be partially occupied at any time during construction, Partial Occupancy Coverage is required of the contractor.
| An Installation Floater is required if the project is for installation, maintenance, repair or interior renovation of an existing building (if adding additional sqft and/or making significant structural changes consider Builder's Risk coverage). | [8 empty] | Offsite Storage
If the contractor's or state-owned property is temporarily stored off the project site (more than 1,000 feet away), confirm the policy has proper storage value limit.
[5 empty] | FALSE | Will Partial Occupancy Coverage be required?
Step 2: Builder's Risk for Projects Less than $20M:
FALSE | Will an Installation Floater be required of the Contractor? | [8 empty] | Hot or Cold Testing
Require a Builder's Risk Policy from the Contractor
| What is the total value of materials? |  | 0 |  | FALSE | Will a Builder's Risk Policy be required of the Contractor? |  |  |  | If there is hot or cold testing exposure, confirm proper coverage.
Installation Floater Insurance Coverage: | [5 empty] | What is the value of the contract? |  | 0
Suggested minimum coverage: | [9 empty] | Click here to continue working on Insurance Assessment
Partial Occupancy Insurance Coverage:
Partial Occupancy Coverage:
Builder's Risk Insurance Coverage:
Suggested minimum coverage:
Note on B24: Please contact DAS Risk Management concerning significant structural changes.
Note on K24: Please contact DAS Risk Management concerning significant structural changes.
Note on L28: Builder's Risk Policy Most Builder's Risk Policies contain some kind of partial occupancy exclusion. If the building is going to be occupied at any time during construction, the partial occupancy exclusion needs to be removed within the policy. In addition, a Partial Occupancy Endorsement to the Builder's Risk Policy should be purchased. Partial Occupancy Coverage does not have to be covered through the Builder's Risk Policy, but could be covered by another policy.
Note on C29: The Installation Floater provides coverage only for the policyholder. It does not provide coverage for any other party on a project site other than the contractor who purchased the installation floater. Most Installation Floaters are blanket for all work performed and not specific to any one project. It is specific to the limits of the policy. TIP: To avoid co-insurance penalties for projects that exceed the limits of the Installation Floater, the policy should either waive co-insurance penalties or have a 0% co-insurance penalty factor.
Note on C38: Installation Floater Policies reflect the total value of materials used for the completion of the work performed (including in transit, on site and at a temporary off site storage location). The construction budget is the best source for determining the appropriate limit of insurance. Note: There are Installation Floater Policies that include labor costs as part of the policy. If the addition of labor cost is deemed necessary to include within the Installation Floater Policy: 1. Use the value of the contract to determine the necessary amount of coverage; and 2. Update the Insurance Template to include labor costs coverage within the Insulation Floater language.
Note on T38: Hot or cold testing can be covered under a builder's risk policy. A system, like a back-up generator, should be tested before project completion.
Note on L40: Builder's Risk Policies reflect the total completed value of the structure (all materials and labor costs, excluding land value). The construction budget is the best source for determining the appropriate limit of insurance.
Existing building construction

## Professional (DB-EB)
Home |  |  | Design / Build | Scope of Work |  | Insurance Assessment | Summary / Print
Contractor's Professional Liability for Existing Building Construction |  |  |  |  | Notes |  |  | Tips, Risk Reduction Strategies and Loss Examples
The addition, remodel, or tenant improvement design is for: |  |  |  |  | Professional Liability coverage is a risk transfer strategy to help cover the cost of liability claims as a result of errors and omissions in performing professional services. It is important to note that professional liability policy limits cover the insurer’s payment of defense costs, which reduces available policy limits (unlike Commercial General Liability policies where defense costs are paid in addition to policy limits). Because of this, it is important to consider higher limits in regards to professional liability coverage. |  |  | Click HERE to review tips, risk reduction strategies and loss examples which will help offer insight when conducting an insurance risk assessment.
FALSE | Small project (small interior remodel)
FALSE | Medium to large project less than $20M (additions, medium to large remodel, etc.)
| Note: | Projects equal to or more than
$20M contact DAS Risk Management.
Contractor's Professional Liability Coverage:
Suggested per claim amount:
Suggested aggregate amount:
Click here to continue working on Insurance Assessment
Existing building construction

## Additional Coverages (DB-EB)
Home |  | Design / Build |  | Scope of Work |  |  | Insurance Assessment | Summary / Print
Additional Coverages |  |  |  |  | Aircraft Liability |  |  |  | Bailee's Coverage
Additional coverages are non-typical coverages that may be required based on the exposures from specialized contracted services. |  |  |  |  | Will the Contractor: |  |  |  | Will the Contractor:
[5 empty] | FALSE | 1. Operate a single engine piston aircraft? |  |  | FALSE | Have care, custody and control of state owned property for storage or servicing?
[5 empty] | FALSE | 2. Operate a multi engine piston aircraft?
Review to confirm if additional coverages are needed. | [9 empty] | If so, what is the property value? |  | 0
[5 empty] | FALSE | 3. Operate a single engine turbine aircraft?
● | Aircraft Liability | [7 empty] | Bailee's Coverage:
● | Bailee's Coverage |  |  |  | FALSE | 4. Operate a multi engine turbine aircraft? |  |  | Suggested minimum combined single limit:
● | Crime Protection
● | Drone Liability |  |  |  | Aircraft Liability Coverage:
● | Marine Coverage |  |  |  | Suggested minimum combined single limit:
Click HERE for more information on Additional Coverages. |  |  |  |  | Click HERE for more information on Aircraft Liability. |  |  |  | Click HERE for more information on Bailee's Coverage.
Continue working on Additional Coverages below
Crime Protection Coverage |  |  |  |  | Drone Liability |  |  |  | Marine Coverage
If vessels will be used on navigable waters, contact DAS Risk Management for assistance in determining appropriate coverage(s), limits, and for obtaining additional Insurance Requirement Template language.
Will the Contractor: |  |  |  |  | Will the Contractor:
FALSE | Have access to substantially valuable state owned tangible movable property? |  |  |  | 1. | Operate a drone(s) over rural, and/or other low risk areas?
FALSE
| If so, what is the property value? |  | 0 |  | 2. | Operate a drone(s) over urban, high vehicle traffic, high fire risk and/or other high risk areas?
[5 empty] | FALSE |  |  |  |  | Marine Liability | 0
Employee Dishonesty or Fidelity Bond:
Suggested minimum combined single limit: | [9 empty] | Hull and Machinery | 0
Note: Drones are also known as Unmanned Aircraft Systems (UAS) and Unmanned Aerial Vehicle (UAV).
[10 empty] | Protection and Indemnity | 0
[10 empty] | Vessel Pollution Liability | 0
Drone Liability Coverage:
[5 empty] | Suggested minimum combined single limit: |  |  |  | Marine Coverage:
Review Summary/Print document for suggested coverage.
Click HERE for more information on Crime Protection. | [8 empty] | Click HERE for more information on Marine Coverage.
Additional Coverages
[5 empty] | FALSE | Have the above additional coverages been reviewed?
Click here to continue working on Insurance Assessment
Existing building construction
Note on U27: An example of when Bailee’s Coverage would be used is when the contractor is storing state owned property not related to the building materials of the project (computers, documents, and other state owned assets/contents).
Note on Z30: To ensure adequate coverage, ask of the contractor the total value of all property of others entrusted to the contractor at any one point in time. Request an insurance requirement in an amount equal to this value.
Note on T50: The term "vessel" has been broadly defined to include any kind of watercraft or equipment capable of being used on navigable waters. In addition to the usual craft found upon rivers, lakes, and oceans, the following have been found to be vessels even though they lack motive power: houseboats, rafts, dredging barges, floating cranes, floating derricks, drilling barges, jack-up drilling rigs, and submersible or semi-submersible rigs. The controlling factors in determining whether a craft is a "vessel" are the purpose for which it was constructed and the business in which it is engaged.
Note on C53: Coverage is particularly important when the contractor has unsupervised access to state property, including access during non-business hours.

## Summary (DB-EB)
Risk Assessment Insurance Summary
Design / Build Construction Procurement (Existing Building)
Summary Document to Assist with Insurance Requirement Template - Link
This risk assessment insurance summary is based off of a risk assessment and is meant to be used as a guide. If a different conclusion is made, document the reasoning.
Save this Summary document by clicking File, Save As, select location to save, update file name, select PDF within Save as type, and then click Save.
WORKERS' COMPENSATION & EMPLOYERS' LIABILITY:
Workers' Compensation does not need to be risk assessed. Requirements are already included in the Insurance Requirements template.
COMMERCIAL GENERAL LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per occurrence.
Annual aggregate limit shall not be less than |  |  |  | .
EXCESS/UMBRELLA COVERAGE:
| Required | X | Not Required
Coverage shall be written and provided in an amount of not less than |  |  |  |  | .
Note: Excess/umbrella insurance coverage shall be provided and will apply over all liability policies, without exception, including but not limited to Commercial General Liability, Automobile Liability, and Employers’ Liability coverage.
AUTOMOBILE LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
A. AUTOMOBILE LIABILITY BROADENED POLLUTION LIABILITY ENDORSEMENT (CA 99 48 or equivalent Endorsement and MSC-90 Endorsement (if regulated motor carrier) for transporting hazardous materials):
| Required | X | Not Required
CONTRACTOR'S POLLUTION LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per occurrence.
Annual aggregate limit shall not be less than |  |  |  | .
A. CONTRACTOR'S POLLUTION LIABILITY ENDORSEMENT (Asbestos Liability Endorsement):
| Required | X | Not Required
B. CONTRACTOR'S POLLUTION LIABILITY ENDORSEMENT (Lead Liability Endorsement):
| Required | X | Not Required
BUILDER'S RISK:
| Required | X | Not Required
Coverage shall be written and provided in an amount of not less than |  |  |  |  | .
PARTIAL OCCUPANCY COVERAGE (Builder’s Risk Partial Occupancy Endorsement):
| Required | X | Not Required
INSTALLATION FLOATER:
| Required | X | Not Required
Coverage shall be written and provided in an amount of not less than |  |  |  |  | .
Builders Risk or Installation Floater coverage is recommended on this type of contract.
CONTRACTOR'S PROFESSIONAL LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per claim.
Annual aggregate limit shall not be less than |  |  |  | .
ADDITIONAL COVERAGES (listed below) may be needed. Refer to the Additional Coverages section within the Insurance Assessment or click HERE
AIRCRAFT LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
BAILEE'S COVERAGE:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
CRIME PROTECTION COVERAGE (EMPLOYEE DISHONESTY or FIDELITY BOND):
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
DRONE / UNMANNED AIRCRAFT SYSTEMS (UAS) / UNMANNED AERIAL VEHICLE (UAV) LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE HULL AND MACHINERY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE PROTECTION AND INDEMNITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
VESSEL POLLUTION LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
SCOPE OF WORK (CONTRACTOR TYPE SELECTION):
Site Preparation Contractors
Site Preparation Contractors
Remediation Services
Foundation, Structure and Building Exterior Contractors
Poured Concrete Foundation and Structure Contractors
Structural Steel and Precast Concrete Contractors
Framing Contractors
Masonry Contractors
Glass and Glazing Contractors
Roofing Contractors
Siding Contractors
Other Foundation, Structure and Building Exterior Contractors
Building Finishing Contractors
Electrical Contractors and Other Wiring Installation Contractors
Plumbing, Heating and Air-Conditioning Contractors
Other Building Equipment Contractors
Drywall and Insulation Contractors
Painting and Wall Covering Contractors
Flooring Contractors
Tile and Terrazzo Contractors
Finish Carpentry Contractors
Other Building Finishing Contractors
Other Specialty Trade Contractors
All Other Specialty Trade Contractors
Click here to continue working on Insurance Assessment
Note on C102: This industry comprises establishments primarily engaged in site preparation activities, such as excavating and grading, demolition of buildings and other structures, and septic system installation. Earthmoving and land clearing for all types of sites (e.g., building, nonbuilding, mining) is included in this industry. Establishments primarily engaged in construction equipment rental with operator (except cranes) are also included. Illustrative Examples: Blasting, building demolition Foundation digging (i.e., excavation) Concrete breaking and cutting for demolition Foundation drilling contractors Cutting new rights of way Grading construction sites Demolition, building and structure Line slashing or cutting (except maintenance) Dewatering contractors Septic system contractors Dirt moving for construction Trenching (except underwater) Equipment rental (except crane), construction, with operator Underground tank (except hazardous) removal Excavating, earthmoving, or land clearing contractors Wrecking, building or other structure
Note on C103: This industry comprises establishments primarily engaged in one or more of the following: (1) remediation and cleanup of contaminated buildings, mine sites, soil, or ground water; (2) integrated mine reclamation activities, including demolition, soil remediation, waste water treatment, hazardous material removal, contouring land, and revegetation; and (3) asbestos, lead paint, and other toxic material abatement.
Note on C105: This industry comprises establishments primarily engaged in pouring and finishing concrete foundations and structural elements. This industry also includes establishments performing grout and shotcrete work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete pouring and finishing Gunite contractors Concrete pumping (i.e., placement) Mud-jacking contractors Concrete work (except paving) Shotcrete contractors Footing and foundation concrete contractors
Note on C106: This industry comprises establishments primarily engaged in (1) erecting and assembling structural parts made from steel or precast concrete (e.g., steel beams, structural steel components, and similar products of precast concrete) and/or (2) assembling and installing other steel construction products (e.g., steel rods, bars, rebar, mesh, and cages) to reinforce poured-in-place concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete product (e.g., structural precast, structural prestressed) installation Rebar contractors Erecting structural steel Reinforcing steel contractors Placing and tying reinforcing rod at a construction site Structural steel contractors Precast concrete panel, slab, or form installation
Note on C107: This industry comprises establishments primarily engaged in structural framing and sheathing using materials other than structural steel or concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Building framing (except structural steel) Post framing contractors Foundation, building, wood, contractors Steel framing contractors Framing contractors Wood frame component (e.g., truss) fabrication on site
Note on C108: This industry comprises establishments primarily engaged in masonry work, stone setting, bricklaying, and other stone work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Block laying Marble, granite, and slate, exterior, contractors Bricklaying Masonry pointing, cleaning, or caulking Concrete block laying Stucco contractors Foundation (e.g., brick, block, stone), building, contractors
Note on C109: This industry comprises establishments primarily engaged in installing glass panes in prepared openings (i.e., glazing work) and other glass work for buildings. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Decorative glass and mirror installation Glazing contractors Glass cladding installation Stained glass installation Glass coating and tinting (except automotive) contractors Window pane or sheet installation Glass installation (except automotive) contractors
Note on C110: This industry comprises establishments primarily engaged in roofing. This industry also includes establishments treating roofs (i.e., spraying, painting, or coating) and installing skylights. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Painting, spraying, or coating, roof Sheet metal roofing installation Shake and shingle, roof, installation Skylight installation
Note on C111: This industry comprises establishments primarily engaged in installing siding of wood, aluminum, vinyl, or other exterior finish material (except brick, stone, stucco, or curtain wall). This industry also includes establishments installing gutters and downspouts. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Downspout, gutter, and gutter guard installation Fascia and soffit installation Siding (e.g., vinyl, wood, aluminum) installation
Note on C112: This industry comprises establishments primarily engaged in building foundation and structure trades work (except poured concrete, structural steel, precast concrete, framing, masonry, glass and glazing, roofing, and siding). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Curtain wall, metal, installation Forms for poured concrete, erecting and dismantling Welding, on-site, contractors Ornamental metal work installation Fire escape installation Decorative steel and wrought iron work installation
Note on C114: This industry comprises establishments primarily engaged in installing and servicing electrical wiring and equipment. Contractors included in this industry may include both the parts and labor when performing work. These contractors may perform new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Airport runway lighting contractors Fiber optic cable (except transmission line) contractors Alarm system (e.g., fire, burglar), electric, installation only Highway, street, and bridge lighting and electrical signal installation Audio equipment (except automotive) installation contractors Home automation system installation Lighting system installation Cable television hookup contractors Telecommunications equipment and wiring (except transmission line) installation contractors Computer and network cable installation Traffic signal installation Environmental control system installation Cable splicing, electrical or fiber optic
Note on C115: This industry comprises establishments primarily engaged in installing and servicing plumbing, heating, and air-conditioning equipment. Contractors in this industry may provide both parts and labor when performing work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Cooling tower installation Heating, ventilation, and air-conditioning (HVAC) contractors Duct work (e.g., cooling, dust collection, exhaust, heating, ventilation) installation Lawn sprinkler system installation Fire sprinkler system installation Mechanical contractors Fireplace, natural gas, installation Refrigeration system (e.g., commercial, industrial, scientific) installation Furnace installation Sewer hookup and connection, building
Note on C116: This industry comprises establishments primarily engaged in installing or servicing building equipment (except electrical, plumbing, heating, cooling, or ventilation equipment). The repair and maintenance of miscellaneous building equipment is included in this industry. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Automated and revolving door installation Lightning protection equipment (e.g., lightning rod) installation Boiler and pipe insulation installation Machine rigging Commercial-type door installation Millwrights Conveyor system installation Overhead door, commercial- or industrial-type, installation Dismantling large-scale machinery and equipment Revolving door installation Elevator installation Satellite dish, household-type, installation Escalator installation Vacuum cleaning system, built-in, installation Gasoline pump, service station, installation
Note on C117: This industry comprises establishments primarily engaged in drywall, plaster work, and building insulation work. Plaster work includes applying plain or ornamental plaster, and installation of lath to receive plaster. The work performed may include new work, additions, alterations, maintenance, and repairs. Establishments primarily engaged in providing firestop services are included in this industry. Illustrative Examples: Acoustical ceiling tile and panel installation Lathing contractors Drop ceiling installation Plastering (i.e., ornamental, plain) contractors Drywall contractors Soundproofing contractors Firestop contractors Fresco (i.e., decorative plaster finishing) contractors Taping and finishing drywall Gypsum board installation Wall cavity and attic space insulation installation
Note on C118: This industry comprises establishments primarily engaged in interior or exterior painting or interior wall covering. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bridge painting Paperhanging or removal contractors House painting Ship painting contractors Paint and wallpaper stripping Wallpaper hanging and removal contractors
Note on C119: This industry comprises establishments primarily engaged in the installation of resilient floor tile, carpeting, linoleum, and hardwood flooring. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Carpet, installation only Resilient floor tile or sheet (e.g., linoleum, rubber, vinyl), installation only Vinyl flooring contractors Resurfacing hardwood flooring Hardwood flooring, installation only Floor laying, scraping, finishing, and refinishing
Note on C120: This industry comprises establishments primarily engaged in setting and installing ceramic tile, stone (interior only), and mosaic and/or mixing marble particles and cement to make terrazzo at the job site. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Ceramic tile installation Mosaic work Mantel, marble or stone, installation Tile (except resilient) laying and setting Stone flooring installation Marble, granite, and slate, interior installation contractors
Note on C121: This industry comprises establishments primarily engaged in finish carpentry work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Built-in wood cabinets constructed on site Molding or trim, wood or plastic, installation Countertop, residential-type, installation Paneling installation Door and window frame construction Prefabricated kitchen and bath cabinet, residential-type, installation Garage door, residential-type, installation Ship joinery contractors Millwork installation Window and door, residential-type, of any material, prefabricated, installation
Note on C122: This industry comprises establishments primarily engaged in building finishing trade work (except drywall, plaster, and insulation work; painting and wall covering work; flooring work; tile and terrazzo work; and finish carpentry work). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bathtub refinishing, on-site Fabricating metal cabinets or countertops on site Closet organizer system installation Modular furniture system attachment and installation Concrete coating, glazing, or sealing Trade show exhibit installation and dismantling Countertop and cabinet, metal (except residential-type), installation Waterproofing contractors Drapery fixture (e.g., hardware, rods, tracks) installation Window shade and blind installation
Note on C124: This industry comprises establishments primarily engaged in specialized trades (except foundation, structure, and building exterior contractors; building equipment contractors; building finishing contractors; and site preparation contractors). The specialty trade work performed includes new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Billboard erection Outdoor swimming pool construction Cleaning building interiors during and immediately after construction Paver, brick (e.g., driveway, patio, sidewalk), installation Crane rental with operator Paving, residential and commercial driveway and parking lot Sandblasting building exteriors Fence installation Scaffold erecting and dismantling Interlocking brick and block installation Steeplejack work Manufactured (mobile) home set up and tie-down work Driveway paving or sealing

## Scope of Work (DB-NB)
Home | Design / Build | Scope of Work |  |  | Insurance Assessment | Summary / Print
Review Scope of Work and Select Contractor Types |  |  | Site Preparation Contractors |  |  |  | Notes
|  |  | FALSE | Site Preparation Contractors
|  |  | FALSE | Remediation Services
Foundation, Structure and Building Exterior Contractors
|  |  | FALSE | Poured Concrete Foundation / Structure Contractors
|  |  | FALSE | Structural Steel and Precast Concrete Contractors
|  |  | FALSE | Framing Contractors
|  |  | FALSE | Masonry Contractors
|  |  | FALSE | Glass and Glazing Contractors
|  |  | FALSE | Roofing Contractors
|  |  | FALSE | Siding Contractors
|  |  | FALSE | Other Foundation, Structure and Exterior Contractors
Building Finishing Contractors
|  |  | FALSE | Electrical and Other Wiring Installation Contractors
|  |  | FALSE | Plumbing, Heating and Air-Conditioning Contractors
|  |  | FALSE | Other Building Equipment Contractors
|  |  | FALSE | Drywall and Insulation Contractors
|  |  | FALSE | Painting and Wall Covering Contractors
|  |  | FALSE | Flooring Contractors |  |  | Click here to continue to Insurance Assessment
|  |  | FALSE | Tile and Terrazzo Contractors
|  |  | FALSE | Finish Carpentry Contractors
|  |  | FALSE | Other Building Finishing Contractors
Other Specialty Trade Contractors
|  |  | FALSE | All Other Specialty Trade Contractors
Note on L21: This industry comprises establishments primarily engaged in site preparation activities, such as excavating and grading, demolition of buildings and other structures, and septic system installation. Earthmoving and land clearing for all types of sites (e.g., building, nonbuilding, mining) is included in this industry. Establishments primarily engaged in construction equipment rental with operator (except cranes) are also included. Illustrative Examples: Blasting, building demolition Foundation digging (i.e., excavation) Concrete breaking and cutting for demolition Foundation drilling contractors Cutting new rights of way Grading construction sites Demolition, building and structure Line slashing or cutting (except maintenance) Dewatering contractors Septic system contractors Dirt moving for construction Trenching (except underwater) Equipment rental (except crane), construction, with operator Underground tank (except hazardous) removal Excavating, earthmoving, or land clearing contractors Wrecking, building or other structure
Note on L22: This industry comprises establishments primarily engaged in one or more of the following: (1) remediation and cleanup of contaminated buildings, mine sites, soil, or ground water; (2) integrated mine reclamation activities, including demolition, soil remediation, waste water treatment, hazardous material removal, contouring land, and revegetation; and (3) asbestos, lead paint, and other toxic material abatement.
Note on L24: This industry comprises establishments primarily engaged in pouring and finishing concrete foundations and structural elements. This industry also includes establishments performing grout and shotcrete work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete pouring and finishing Gunite contractors Concrete pumping (i.e., placement) Mud-jacking contractors Concrete work (except paving) Shotcrete contractors Footing and foundation concrete contractors
Note on L25: This industry comprises establishments primarily engaged in (1) erecting and assembling structural parts made from steel or precast concrete (e.g., steel beams, structural steel components, and similar products of precast concrete) and/or (2) assembling and installing other steel construction products (e.g., steel rods, bars, rebar, mesh, and cages) to reinforce poured-in-place concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete product (e.g., structural precast, structural prestressed) installation Rebar contractors Erecting structural steel Reinforcing steel contractors Placing and tying reinforcing rod at a construction site Structural steel contractors Precast concrete panel, slab, or form installation
Note on L26: This industry comprises establishments primarily engaged in structural framing and sheathing using materials other than structural steel or concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Building framing (except structural steel) Post framing contractors Foundation, building, wood, contractors Steel framing contractors Framing contractors Wood frame component (e.g., truss) fabrication on site
Note on L27: This industry comprises establishments primarily engaged in masonry work, stone setting, bricklaying, and other stone work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Block laying Marble, granite, and slate, exterior, contractors Bricklaying Masonry pointing, cleaning, or caulking Concrete block laying Stucco contractors Foundation (e.g., brick, block, stone), building, contractors
Note on L28: This industry comprises establishments primarily engaged in installing glass panes in prepared openings (i.e., glazing work) and other glass work for buildings. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Decorative glass and mirror installation Glazing contractors Glass cladding installation Stained glass installation Glass coating and tinting (except automotive) contractors Window pane or sheet installation Glass installation (except automotive) contractors
Note on L29: This industry comprises establishments primarily engaged in roofing. This industry also includes establishments treating roofs (i.e., spraying, painting, or coating) and installing skylights. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Painting, spraying, or coating, roof Sheet metal roofing installation Shake and shingle, roof, installation Skylight installation
Note on L30: This industry comprises establishments primarily engaged in installing siding of wood, aluminum, vinyl, or other exterior finish material (except brick, stone, stucco, or curtain wall). This industry also includes establishments installing gutters and downspouts. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Downspout, gutter, and gutter guard installation Fascia and soffit installation Siding (e.g., vinyl, wood, aluminum) installation
Note on L31: This industry comprises establishments primarily engaged in building foundation and structure trades work (except poured concrete, structural steel, precast concrete, framing, masonry, glass and glazing, roofing, and siding). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Curtain wall, metal, installation Forms for poured concrete, erecting and dismantling Welding, on-site, contractors Ornamental metal work installation Fire escape installation Decorative steel and wrought iron work installation
Note on L33: This industry comprises establishments primarily engaged in installing and servicing electrical wiring and equipment. Contractors included in this industry may include both the parts and labor when performing work. These contractors may perform new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Airport runway lighting contractors Fiber optic cable (except transmission line) contractors Alarm system (e.g., fire, burglar), electric, installation only Highway, street, and bridge lighting and electrical signal installation Audio equipment (except automotive) installation contractors Home automation system installation Lighting system installation Cable television hookup contractors Telecommunications equipment and wiring (except transmission line) installation contractors Computer and network cable installation Traffic signal installation Environmental control system installation Cable splicing, electrical or fiber optic
Note on L34: This industry comprises establishments primarily engaged in installing and servicing plumbing, heating, and air-conditioning equipment. Contractors in this industry may provide both parts and labor when performing work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Cooling tower installation Heating, ventilation, and air-conditioning (HVAC) contractors Duct work (e.g., cooling, dust collection, exhaust, heating, ventilation) installation Lawn sprinkler system installation Fire sprinkler system installation Mechanical contractors Fireplace, natural gas, installation Refrigeration system (e.g., commercial, industrial, scientific) installation Furnace installation Sewer hookup and connection, building
Note on L35: This industry comprises establishments primarily engaged in installing or servicing building equipment (except electrical, plumbing, heating, cooling, or ventilation equipment). The repair and maintenance of miscellaneous building equipment is included in this industry. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Automated and revolving door installation Lightning protection equipment (e.g., lightning rod) installation Boiler and pipe insulation installation Machine rigging Commercial-type door installation Millwrights Conveyor system installation Overhead door, commercial- or industrial-type, installation Dismantling large-scale machinery and equipment Revolving door installation Elevator installation Satellite dish, household-type, installation Escalator installation Vacuum cleaning system, built-in, installation Gasoline pump, service station, installation
Note on L36: This industry comprises establishments primarily engaged in drywall, plaster work, and building insulation work. Plaster work includes applying plain or ornamental plaster, and installation of lath to receive plaster. The work performed may include new work, additions, alterations, maintenance, and repairs. Establishments primarily engaged in providing firestop services are included in this industry. Illustrative Examples: Acoustical ceiling tile and panel installation Lathing contractors Drop ceiling installation Plastering (i.e., ornamental, plain) contractors Drywall contractors Soundproofing contractors Firestop contractors Fresco (i.e., decorative plaster finishing) contractors Taping and finishing drywall Gypsum board installation Wall cavity and attic space insulation installation
Note on L37: This industry comprises establishments primarily engaged in interior or exterior painting or interior wall covering. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bridge painting Paperhanging or removal contractors House painting Ship painting contractors Paint and wallpaper stripping Wallpaper hanging and removal contractors
Note on L38: This industry comprises establishments primarily engaged in the installation of resilient floor tile, carpeting, linoleum, and hardwood flooring. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Carpet, installation only Resilient floor tile or sheet (e.g., linoleum, rubber, vinyl), installation only Vinyl flooring contractors Resurfacing hardwood flooring Hardwood flooring, installation only Floor laying, scraping, finishing, and refinishing
Note on L39: This industry comprises establishments primarily engaged in setting and installing ceramic tile, stone (interior only), and mosaic and/or mixing marble particles and cement to make terrazzo at the job site. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Ceramic tile installation Mosaic work Mantel, marble or stone, installation Tile (except resilient) laying and setting Stone flooring installation Marble, granite, and slate, interior installation contractors
Note on L40: This industry comprises establishments primarily engaged in finish carpentry work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Built-in wood cabinets constructed on site Molding or trim, wood or plastic, installation Countertop, residential-type, installation Paneling installation Door and window frame construction Prefabricated kitchen and bath cabinet, residential-type, installation Garage door, residential-type, installation Ship joinery contractors Millwork installation Window and door, residential-type, of any material, prefabricated, installation
Note on L41: This industry comprises establishments primarily engaged in building finishing trade work (except drywall, plaster, and insulation work; painting and wall covering work; flooring work; tile and terrazzo work; and finish carpentry work). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bathtub refinishing, on-site Fabricating metal cabinets or countertops on site Closet organizer system installation Modular furniture system attachment and installation Concrete coating, glazing, or sealing Trade show exhibit installation and dismantling Countertop and cabinet, metal (except residential-type), installation Waterproofing contractors Drapery fixture (e.g., hardware, rods, tracks) installation Window shade and blind installation
Note on L43: This industry comprises establishments primarily engaged in specialized trades (except foundation, structure, and building exterior contractors; building equipment contractors; building finishing contractors; and site preparation contractors). The specialty trade work performed includes new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Billboard erection Outdoor swimming pool construction Cleaning building interiors during and immediately after construction Paver, brick (e.g., driveway, patio, sidewalk), installation Crane rental with operator Paving, residential and commercial driveway and parking lot Sandblasting building exteriors Fence installation Scaffold erecting and dismantling Interlocking brick and block installation Steeplejack work Manufactured (mobile) home set up and tie-down work Driveway paving or sealing
New bulding construction

## Insurance Requirements (DB-NB)
Home | Design / Build |  | Scope of Work |  | Insurance Assessment |  | Summary / Print
General Liability and Umbrella Coverage |  | Automobile Liability |  | Contractor's Pollution Liability |  | Builder's Risk |  | Contractor's Professional Liability | Additional Coverages
Commercial General Liability (CGL) is required in all contracts. It is perhaps the most important of all insurance policies in a contractual relationship. It ensures the Contractor has broad liability coverage for contractual activities and for completed operations. Note: CGL does not provide coverage for Professional Liability. |  | Automobile Liability insurance is typically required in most contracts. Automobile Liability is need whenever contracted work requires use of a licensed vehicle on public roads or on your property (this includes driving between job sites, to and from meetings, and/or occasional trips). |  | Contractor's Pollution Liability insurance is required when the contractor will be using, removing, hauling, storing, or disposing of hazardous materials. |  | Builder's Risk insurance is required during the course of construction. This policy is designed to cover property at the construction site, off-site storage locations and in transit. The Policy will pay for damages up to the coverage limit. The limit must accurately reflect the total completed value of the structure (all materials and labor costs, excluding land value). |  | Contractor's Professional liability insurance is required when the Contractor's work is in a professional field requiring specialized knowledge and intellectual skills. | Additional coverages are non-typical coverages that may be required based on the exposures from specialized contracted services. These types of coverages include, but are not limited to Aircraft Liability, Drone Liability, Marine Liability and more. Review to confirm if additional coverages are needed.
DA
Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. |  | Click HERE for more information. | Click HERE for more information.
New building construction
Note on L24: Hazardous Material includes lead and asbestos, such as when a contractor is involved in lead and/or asbestos removal/abatement. A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).
Note on Q24: Use when a new building is being constructed, when substantial alternations will be made to an existing structure, i.e., bearing walls, lifting foundations, extensive construction, or when equipment is installed in an existing building. The Policy will pay for damages up to the coverage limit. The limit must accurately reflect the total completed value of the structure (all materials and labor costs, excluding land value). Coverage for direct physical loss by a covered peril to an entire building or other structure at the "jobsite" during the course of construction, including limited coverage (See also Builders´ Risk Installation Floater) for the building supplies and materials that will become part of the covered structure. Also covers: Foundations, excavations, grading, filling, attachments, permanent fencing, and other permanent fixtures. Scaffolding, construction forms or temporary fencing at the described "jobsite" and temporary structures at the described "jobsite". Project size or type triggers Builder's Risk insurance recommendation.

## CGL Umbrella (DB-NB)
Home |  |  | Design / Build | Scope of Work |  | Insurance Assessment | Summary / Print
Commercial General Liability (CGL) and Excess/Umbrella Coverage Selection |  |  |  |  | Notes |  |  | Risk Reduction Strategies
The contract is for a: |  |  |  |  | Commercial General Liability coverage is a risk transfer strategy to help cover the cost of liability claims for personal injury, property damage and advertising injury. |  |  | 1. | Move employees from construction zone.
FALSE | Specialty Trade Contractor | [6 empty] | 2. | Partition off construction zone for safety and security reasons.
FALSE | General contractor (GC) contract size less than $10M
[5 empty] | Note: Require an additional insured endorsement with respect to liability arising out of ongoing operations and completed operations. This practice helps protect the contractor and the state from losses that occur during the course of construction, as well as claims arising out of the completed project (damages found after the project is completed). Review Insurance Template for more detail. |  |  | 3. | Before work begins, document existing conditions and values of existing structures.
FALSE | General contractor (GC) contract size greater than $10M but less than $20M
[8 empty] | 4. | Before work begins, memorialize the condition of adjacent properties and document distance from project.
| Note: | Projects equal to or more than
$20M contact DAS Risk Management.
Commercial General Liability Coverage:
Suggested per occurrence amount:
Suggested aggregate amount: |  |  |  |  | Note: Excess/umbrella insurance coverage shall be provided and will apply over all liability policies, without exception, including but not limited to Commercial General Liability, Automobile Liability, and Employers’ Liability coverage. |  |  | Click here to continue working on Insurance Assessment
Excess/Umbrella Coverage:
Suggested coverage amount:
New buidling construction

## Automobile (DB-NB)
Home |  | Design / Build | Scope of Work |  |  | Insurance Assessment | Summary / Print
Automobile Liability |  |  |  | Automobile Liability Endorsement |  |  |  | Tips, Risk Reduction Strategies and Loss Examples
Will the Contractor: |  |  |  | Will the Contractor: |  |  |  | Click HERE to review tips, risk reduction strategies and loss examples which will help offer insight when conducting an insurance risk assessment.
FALSE | 1. Use a vehicle to accomplish the work? |  |  | FALSE | Transport hazardous materials?
FALSE | 2. Travel to or from state locations? |  |  | Automobile Liability Endorsement:
Transportation of Hazardous Materials CA 99 48 and MCS-90 Endorsements:
FALSE | 3. Transport state property, clients, or employees?
Automobile Liability Coverage:
Suggested minimum combined single limit:
Note: Automobile Liability Coverage is set for a minimum of $1M as it takes into account the Excess/Umbrella Coverage which should also apply over the Automobile Liability Coverage (Excess/Umbrella Coverage recommendation is set within the General Liability and Umbrella Coverage section).
Click here to continue working on Insurance Assessment
New building construction
Note on L27: Hazardous Material includes lead and asbestos, such as when a contractor is involved in lead and/or asbestos removal/abatement. A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).

## Pollution (DB-NB)
Contractor's Pollution Liability (CPL) for Existing Building Construction |  |  | Step 3: Contractor's Pollution Liability Endorsements: |  | Risk Reduction Strategies
Will the Contractor:
Step 1: Phase I Environmental Site Assessment (ESA) |  |  | FALSE | 1. Abate, remove, dispose and/or work with asbestos? |  | Asbestos Risk - Buildings built in or before 1985 have a higher chance of containing asbestos. It is important to identify any asbestos-containing materials before work begins. Any abatement of asbestos must be performed by an Oregon DEQ Licensed Asbestos Abatement Contractor.
| 1. Has a Phase I ESA been done? |  | FALSE | 2. Abate, remove, dispose and/or work with lead?
| FALSE | Yes, and hazardous materials are not present
TRUE | FALSE | Yes, and hazardous materials are present | Contractor's Pollution Liability Endorsements:
| FALSE | No, hazardous materials at the site are unknown | Asbestos Liability Endorsement:
Lead Liability Endorsement:
Step 2: Will the Contractor: | [5 empty] | Lead Risk - Buildings built in or before 1978 have a higher chance of containing lead based paint. It is important to identify any lead based materials before work begins.
FALSE | 1. Store hazardous materials on the job site? |  | Contractor's Pollution Liability Coverage:
Suggested minimum per occurrence:
FALSE | 2. Apply, use or handle hazardous materials on job site? |  | Suggested minimum aggregate:
FALSE | 3. Are other hazardous materials present?
4. Abate, remove and/or dispose of hazardous materials?
| FALSE | Small scale / low risk abatement |  |  | Click here to continue working on Insurance Assessment
| FALSE | Medium-large scale / medium-high risk abatement
FALSE | 5. Work in, around or over water, wells, wetlands, or protected species area?
New building construction
Note on C26: A Phase I Environmental Site Assessment (ESA) is conducted by a qualified environmental professional to identify potential or existing environmental contamination within underlying land as well as physical improvements to the property. Standards for a Phase I ESA are outlined by the United States Environmental Protection agency.
Note on C34: Hazardous materials can include operating fluids such as fuel, lubricants, hydraulics, etc. and can also include hazardous building materials, treatments and finishes.
Note on C36: Hazardous materials can include operating fluids such as fuel, lubricants, hydraulics, etc. and can also include hazardous building materials, treatments and finishes.
Note on C38: i.e. lead paint, underground fuel tanks, soil contamination, etc.
Note on C40: A hazardous material is any item or agent (biological, chemical, radiological, and/or physical), which has the potential to cause harm to humans, animals, or the environment, either by itself or through interaction with other factors. (Definition provided by: Institute of Hazardous Material Management.) OSHA's definition includes any substance or chemical which is a "health hazard" or "physical hazard," including: chemicals which are carcinogens, toxic agents, irritants, corrosives, sensitizers; agents which act on the hematopoietic system; agents which damage the lungs, skin, eyes, or mucous membranes; chemicals which are combustible, explosive, flammable, oxidizers, pyrophorics, unstable-reactive or water-reactive; and chemicals which in the course of normal handling, use, or storage may produce or release dusts, gases, fumes, vapors, mists or smoke which may have any of the previously mentioned characteristics. (Full definitions can be found at 29 Code of Federal Regulations (CFR) 1910.1200.) EPA incorporates the OSHA definition, and adds any item or chemical which can cause harm to people, plants, or animals when released by spilling, leaking, pumping, pouring, emitting, emptying, discharging, injecting, escaping, leaching, dumping or disposing into the environment. (40 CFR 355 contains a list of over 350 hazardous and extremely hazardous substances.) DOT defines a hazardous material as any item or chemical which, when being transported or moved in commerce, is a risk to public safety or the environment, and is regulated as such under its Pipeline and Hazardous Materials Safety Administration regulations (49 CFR 100-199), which includes the Hazardous Materials Regulations (49 CFR 171-180).
Note on D41: Small Scale/Low Risk – Abatement work in a section of a building and abatement does not require containment. Example hazardous materials include but are not limited to nonfriable asbestos, lead paint, mold, regulated hazardous materials, chemicals, contaminated soil, fuels, etc...
Note on D42: Medium-large scale/medium-high risk – Abatement work building wide and or abatement requires containment of building and materials (air monitoring inside/outside building containment area, negative air pressure maintained throughout abatement) and or building is partially occupied (employees and or clients). Example hazardous materials include but are not limited to friable asbestos, mold, regulated hazardous materials, chemicals, contaminated soil, fuels, etc...

## Builder's Risk (DB-NB)
Home |  | Design / Build |  | Scope of Work |  |  | Insurance Assessment | Summary / Print
Builder's Risk Insurance for New Building Construction |  |  |  |  | Construction Considerations |  |  |  | Policy Review
Project Costs
Builder's Risk for Projects Less than $20M: |  |  |  |  | Occupancy:
If the cost of the architect, engineer and building permits are included within the project cost, confirm these costs are covered in the policy.
A Builder's Risk Policy should be required from the Contractor. | [5 empty] | Occupancy prior to final completion:
[5 empty] | ● | Report to DAS Risk Management for coverage; or
[5 empty] | ● | Negotiate coverage with Builder's Risk Policy for occupancy.
FALSE | Will a Builder's Risk Policy be required of the Contractor? | [7 empty] | Offsite Storage
[6 empty] | Occupancy after final completion: |  |  | If the contractor's or state-owned property is temporarily stored off the project site (more than 1,000 feet away), confirm the policy has proper storage value limit.
| What is the value of the contract? |  | 0 |  | ● | Report to DAS Risk Management for coverage.
Builder's Risk Insurance Coverage: |  |  |  |  | Liquidated Damages:
Suggested minimum coverage:
[5 empty] | ● | Address liquidated damages within the contract regarding financial or operational impact if the project is not completed on time. |  |  | Hot or Cold Testing
Partial Occupancy During Construction:
If the building will be partially occupied at any time during construction, Partial Occupancy Coverage is required of the contractor. | [8 empty] | If there is hot or cold testing exposure, confirm proper coverage.
[5 empty] | ● | Consider long lead time between ordering and final delivery on special items, equipment, raw materials, etc.
Click here to continue working on Insurance Assessment
FALSE | Will Partial Occupancy Coverage be required? |  |  |  | ● | Consider offsite storage and transit coverage on high value items being shipped to the building site or off site storage.
Partial Occupancy Insurance Coverage:
Partial Occupancy Coverage:
Note on C32: Builder's Risk Policies reflect the total completed value of the structure (all materials and labor costs, excluding land value). The construction budget is the best source for determining the appropriate limit of insurance.
Note on B38: Builder's Risk Policy Most Builder's Risk Policies contain some kind of partial occupancy exclusion. If the building is going to be occupied at any time during construction, the partial occupancy exclusion needs to be removed within the policy. In addition, a Partial Occupancy Endorsement to the Builder's Risk Policy should be purchased. Partial Occupancy Coverage does not have to be covered through the Builder's Risk Policy, but could be covered by another policy.
Note on T38: Hot or cold testing can be covered under a builder's risk policy. A system, like a back-up generator, should be tested before project completion.
New building construction

## Professional (DB-NB)
Home |  |  | Design / Build | Scope of Work |  | Insurance Assessment | Summary / Print
Contractor's Professional Liability for New Building Construction |  |  |  |  | Notes |  |  | Tips, Risk Reduction Strategies and Loss Examples
The new structure or building design is for a: |  |  |  |  | Professional Liability coverage is a risk transfer strategy to help cover the cost of liability claims as a result of errors and omissions in performing professional services. It is important to note that professional liability policy limits cover the insurer’s payment of defense costs, which reduces available policy limits (unlike Commercial General Liability policies where defense costs are paid in addition to policy limits). Because of this, it is important to consider higher limits in regards to professional liability coverage. |  |  | Click HERE to review tips, risk reduction strategies and loss examples which will help offer insight when conducting an insurance risk assessment.
FALSE | Small to medium project (less than $20M)
| Note: | Projects equal to or more than
$20M contact DAS Risk Management.
Contractor's Professional Liability Coverage:
Suggested per claim amount:
Suggested aggregate amount:
Click here to continue working on Insurance Assessment
New building construction

## Additional Coverages (DB-NB)
Home |  | Design / Build |  | Scope of Work |  |  | Insurance Assessment | Summary / Print
Additional Coverages |  |  |  |  | Aircraft Liability |  |  |  | Bailee's Coverage
Additional coverages are non-typical coverages that may be required based on the exposures from specialized contracted services. |  |  |  |  | Will the Contractor: |  |  |  | Will the Contractor:
[5 empty] | FALSE | 1. Operate a single engine piston aircraft? |  |  | FALSE | Have care, custody and control of state owned property for storage or servicing?
[5 empty] | FALSE | 2. Operate a multi engine piston aircraft?
Review to confirm if additional coverages are needed. | [9 empty] | If so, what is the property value? |  | 0
[5 empty] | FALSE | 3. Operate a single engine turbine aircraft?
● | Aircraft Liability | [7 empty] | Bailee's Coverage:
● | Bailee's Coverage |  |  |  | FALSE | 4. Operate a multi engine turbine aircraft? |  |  | Suggested minimum combined single limit:
● | Crime Protection
● | Drone Liability |  |  |  | Aircraft Liability Coverage:
● | Marine Coverage |  |  |  | Suggested minimum combined single limit:
Click HERE for more information on Additional Coverages. |  |  |  |  | Click HERE for more information on Aircraft Liability. |  |  |  | Click HERE for more information on Bailee's Coverage.
Continue working on Additional Coverages below
Crime Protection Coverage |  |  |  |  | Drone Liability |  |  |  | Marine Coverage
If vessels will be used on navigable waters, contact DAS Risk Management for assistance in determining appropriate coverage(s), limits, and for obtaining additional Insurance Requirement Template language.
Will the Contractor: |  |  |  |  | Will the Contractor:
FALSE | Have access to substantially valuable state owned tangible movable property? |  |  |  | 1. | Operate a drone(s) over rural, and/or other low risk areas?
FALSE
| If so, what is the property value? |  | 0 |  | 2. | Operate a drone(s) over urban, high vehicle traffic, high fire risk and/or other high risk areas?
[5 empty] | FALSE |  |  |  |  | Marine Liability | 0
Employee Dishonesty or Fidelity Bond:
Suggested minimum combined single limit: | [9 empty] | Hull and Machinery | 0
Note: Drones are also known as Unmanned Aircraft Systems (UAS) and Unmanned Aerial Vehicle (UAV).
[10 empty] | Protection and Indemnity | 0
[10 empty] | Vessel Pollution Liability | 0
Drone Liability Coverage:
[5 empty] | Suggested minimum combined single limit: |  |  |  | Marine Coverage:
Review Summary/Print document for suggested coverage.
Click HERE for more information on Crime Protection. | [8 empty] | Click HERE for more information on Marine Coverage.
Additional Coverages
[5 empty] | FALSE | Have the above additional coverages been reviewed?
Click here to continue working on Insurance Assessment
New building construction
Note on U27: An example of when Bailee’s Coverage would be used is when the contractor is storing state owned property not related to the building materials of the project (computers, documents, and other state owned assets/contents).
Note on Z30: To ensure adequate coverage, ask of the contractor the total value of all property of others entrusted to the contractor at any one point in time. Request an insurance requirement in an amount equal to this value.
Note on T50: The term "vessel" has been broadly defined to include any kind of watercraft or equipment capable of being used on navigable waters. In addition to the usual craft found upon rivers, lakes, and oceans, the following have been found to be vessels even though they lack motive power: houseboats, rafts, dredging barges, floating cranes, floating derricks, drilling barges, jack-up drilling rigs, and submersible or semi-submersible rigs. The controlling factors in determining whether a craft is a "vessel" are the purpose for which it was constructed and the business in which it is engaged.
Note on C53: Coverage is particularly important when the contractor has unsupervised access to state property, including access during non-business hours.

## Summary (DB-NB)
Risk Assessment Insurance Summary
Design / Build Construction Procurement (New Building)
Summary Document to Assist with Insurance Requirement Template - Link
This risk assessment insurance summary is based off of a risk assessment and is meant to be used as a guide. If a different conclusion is made, document the reasoning.
Save this Summary document by clicking File, Save As, select location to save, update file name, select PDF within Save as type, and then click Save.
WORKERS' COMPENSATION & EMPLOYERS' LIABILITY:
Workers' Compensation does not need to be risk assessed. Requirements are already included in the Insurance Requirements template.
COMMERCIAL GENERAL LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per occurrence.
Annual aggregate limit shall not be less than |  |  |  | .
EXCESS/UMBRELLA COVERAGE:
| Required | X | Not Required
Coverage shall be written and provided in an amount of not less than |  |  |  |  | .
Note: Excess/umbrella insurance coverage shall be provided and will apply over all liability policies, without exception, including but not limited to Commercial General Liability, Automobile Liability, and Employers’ Liability coverage.
AUTOMOBILE LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
A. AUTOMOBILE LIABILITY BROADENED POLLUTION LIABILITY ENDORSEMENT (CA 99 48 or equivalent Endorsement and MSC-90 Endorsement (if regulated motor carrier) for transporting hazardous materials):
| Required | X | Not Required
CONTRACTOR'S POLLUTION LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per occurrence.
Annual aggregate limit shall not be less than |  |  |  | .
A. CONTRACTOR'S POLLUTION LIABILITY ENDORSEMENT (Asbestos Liability Endorsement):
| Required | X | Not Required
B. CONTRACTOR'S POLLUTION LIABILITY ENDORSEMENT (Lead Liability Endorsement):
| Required | X | Not Required
BUILDER'S RISK:
| Required | X | Not Required
Coverage shall be written and provided in an amount of not less than |  |  |  |  | .
PARTIAL OCCUPANCY COVERAGE (Builder’s Risk Partial Occupancy Endorsement):
| Required | X | Not Required
Builders Risk coverage is recommended on this type of contract.
CONTRACTOR'S PROFESSIONAL LIABILITY:
| Required | X | Not Required
Coverage shall be written on an occurrence basis in an amount of not less than | [5 empty] | per claim.
Annual aggregate limit shall not be less than |  |  |  | .
ADDITIONAL COVERAGES (listed below) may be needed. Refer to the Additional Coverages section within the Insurance Assessment or click HERE
AIRCRAFT LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
BAILEE'S COVERAGE:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
CRIME PROTECTION COVERAGE (EMPLOYEE DISHONESTY or FIDELITY BOND):
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
DRONE / UNMANNED AIRCRAFT SYSTEMS (UAS) / UNMANNED AERIAL VEHICLE (UAV) LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE HULL AND MACHINERY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
MARINE PROTECTION AND INDEMNITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
VESSEL POLLUTION LIABILITY:
| Required | X | Not Required
Coverage shall be written on a combined single limit of not less than |  |  |  |  | .
SCOPE OF WORK (CONTRACTOR TYPE SELECTION):
Site Preparation Contractors
Site Preparation Contractors
Remediation Services
Foundation, Structure and Building Exterior Contractors
Poured Concrete Foundation and Structure Contractors
Structural Steel and Precast Concrete Contractors
Framing Contractors
Masonry Contractors
Glass and Glazing Contractors
Roofing Contractors
Siding Contractors
Other Foundation, Structure and Building Exterior Contractors
Building Finishing Contractors
Electrical Contractors and Other Wiring Installation Contractors
Plumbing, Heating and Air-Conditioning Contractors
Other Building Equipment Contractors
Drywall and Insulation Contractors
Painting and Wall Covering Contractors
Flooring Contractors
Tile and Terrazzo Contractors
Finish Carpentry Contractors
Other Building Finishing Contractors
Other Specialty Trade Contractors
All Other Specialty Trade Contractors
Click here to continue working on Insurance Assessment
Note on C98: This industry comprises establishments primarily engaged in site preparation activities, such as excavating and grading, demolition of buildings and other structures, and septic system installation. Earthmoving and land clearing for all types of sites (e.g., building, nonbuilding, mining) is included in this industry. Establishments primarily engaged in construction equipment rental with operator (except cranes) are also included. Illustrative Examples: Blasting, building demolition Foundation digging (i.e., excavation) Concrete breaking and cutting for demolition Foundation drilling contractors Cutting new rights of way Grading construction sites Demolition, building and structure Line slashing or cutting (except maintenance) Dewatering contractors Septic system contractors Dirt moving for construction Trenching (except underwater) Equipment rental (except crane), construction, with operator Underground tank (except hazardous) removal Excavating, earthmoving, or land clearing contractors Wrecking, building or other structure
Note on C99: This industry comprises establishments primarily engaged in one or more of the following: (1) remediation and cleanup of contaminated buildings, mine sites, soil, or ground water; (2) integrated mine reclamation activities, including demolition, soil remediation, waste water treatment, hazardous material removal, contouring land, and revegetation; and (3) asbestos, lead paint, and other toxic material abatement.
Note on C101: This industry comprises establishments primarily engaged in pouring and finishing concrete foundations and structural elements. This industry also includes establishments performing grout and shotcrete work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete pouring and finishing Gunite contractors Concrete pumping (i.e., placement) Mud-jacking contractors Concrete work (except paving) Shotcrete contractors Footing and foundation concrete contractors
Note on C102: This industry comprises establishments primarily engaged in (1) erecting and assembling structural parts made from steel or precast concrete (e.g., steel beams, structural steel components, and similar products of precast concrete) and/or (2) assembling and installing other steel construction products (e.g., steel rods, bars, rebar, mesh, and cages) to reinforce poured-in-place concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Concrete product (e.g., structural precast, structural prestressed) installation Rebar contractors Erecting structural steel Reinforcing steel contractors Placing and tying reinforcing rod at a construction site Structural steel contractors Precast concrete panel, slab, or form installation
Note on C103: This industry comprises establishments primarily engaged in structural framing and sheathing using materials other than structural steel or concrete. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Building framing (except structural steel) Post framing contractors Foundation, building, wood, contractors Steel framing contractors Framing contractors Wood frame component (e.g., truss) fabrication on site
Note on C104: This industry comprises establishments primarily engaged in masonry work, stone setting, bricklaying, and other stone work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Block laying Marble, granite, and slate, exterior, contractors Bricklaying Masonry pointing, cleaning, or caulking Concrete block laying Stucco contractors Foundation (e.g., brick, block, stone), building, contractors
Note on C105: This industry comprises establishments primarily engaged in installing glass panes in prepared openings (i.e., glazing work) and other glass work for buildings. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Decorative glass and mirror installation Glazing contractors Glass cladding installation Stained glass installation Glass coating and tinting (except automotive) contractors Window pane or sheet installation Glass installation (except automotive) contractors
Note on C106: This industry comprises establishments primarily engaged in roofing. This industry also includes establishments treating roofs (i.e., spraying, painting, or coating) and installing skylights. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Painting, spraying, or coating, roof Sheet metal roofing installation Shake and shingle, roof, installation Skylight installation
Note on C107: This industry comprises establishments primarily engaged in installing siding of wood, aluminum, vinyl, or other exterior finish material (except brick, stone, stucco, or curtain wall). This industry also includes establishments installing gutters and downspouts. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Downspout, gutter, and gutter guard installation Fascia and soffit installation Siding (e.g., vinyl, wood, aluminum) installation
Note on C108: This industry comprises establishments primarily engaged in building foundation and structure trades work (except poured concrete, structural steel, precast concrete, framing, masonry, glass and glazing, roofing, and siding). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Curtain wall, metal, installation Forms for poured concrete, erecting and dismantling Welding, on-site, contractors Ornamental metal work installation Fire escape installation Decorative steel and wrought iron work installation
Note on C110: This industry comprises establishments primarily engaged in installing and servicing electrical wiring and equipment. Contractors included in this industry may include both the parts and labor when performing work. These contractors may perform new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Airport runway lighting contractors Fiber optic cable (except transmission line) contractors Alarm system (e.g., fire, burglar), electric, installation only Highway, street, and bridge lighting and electrical signal installation Audio equipment (except automotive) installation contractors Home automation system installation Lighting system installation Cable television hookup contractors Telecommunications equipment and wiring (except transmission line) installation contractors Computer and network cable installation Traffic signal installation Environmental control system installation Cable splicing, electrical or fiber optic
Note on C111: This industry comprises establishments primarily engaged in installing and servicing plumbing, heating, and air-conditioning equipment. Contractors in this industry may provide both parts and labor when performing work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Cooling tower installation Heating, ventilation, and air-conditioning (HVAC) contractors Duct work (e.g., cooling, dust collection, exhaust, heating, ventilation) installation Lawn sprinkler system installation Fire sprinkler system installation Mechanical contractors Fireplace, natural gas, installation Refrigeration system (e.g., commercial, industrial, scientific) installation Furnace installation Sewer hookup and connection, building
Note on C112: This industry comprises establishments primarily engaged in installing or servicing building equipment (except electrical, plumbing, heating, cooling, or ventilation equipment). The repair and maintenance of miscellaneous building equipment is included in this industry. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Automated and revolving door installation Lightning protection equipment (e.g., lightning rod) installation Boiler and pipe insulation installation Machine rigging Commercial-type door installation Millwrights Conveyor system installation Overhead door, commercial- or industrial-type, installation Dismantling large-scale machinery and equipment Revolving door installation Elevator installation Satellite dish, household-type, installation Escalator installation Vacuum cleaning system, built-in, installation Gasoline pump, service station, installation
Note on C113: This industry comprises establishments primarily engaged in drywall, plaster work, and building insulation work. Plaster work includes applying plain or ornamental plaster, and installation of lath to receive plaster. The work performed may include new work, additions, alterations, maintenance, and repairs. Establishments primarily engaged in providing firestop services are included in this industry. Illustrative Examples: Acoustical ceiling tile and panel installation Lathing contractors Drop ceiling installation Plastering (i.e., ornamental, plain) contractors Drywall contractors Soundproofing contractors Firestop contractors Fresco (i.e., decorative plaster finishing) contractors Taping and finishing drywall Gypsum board installation Wall cavity and attic space insulation installation
Note on C114: This industry comprises establishments primarily engaged in interior or exterior painting or interior wall covering. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bridge painting Paperhanging or removal contractors House painting Ship painting contractors Paint and wallpaper stripping Wallpaper hanging and removal contractors
Note on C115: This industry comprises establishments primarily engaged in the installation of resilient floor tile, carpeting, linoleum, and hardwood flooring. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Carpet, installation only Resilient floor tile or sheet (e.g., linoleum, rubber, vinyl), installation only Vinyl flooring contractors Resurfacing hardwood flooring Hardwood flooring, installation only Floor laying, scraping, finishing, and refinishing
Note on C116: This industry comprises establishments primarily engaged in setting and installing ceramic tile, stone (interior only), and mosaic and/or mixing marble particles and cement to make terrazzo at the job site. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Ceramic tile installation Mosaic work Mantel, marble or stone, installation Tile (except resilient) laying and setting Stone flooring installation Marble, granite, and slate, interior installation contractors
Note on C117: This industry comprises establishments primarily engaged in finish carpentry work. The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Built-in wood cabinets constructed on site Molding or trim, wood or plastic, installation Countertop, residential-type, installation Paneling installation Door and window frame construction Prefabricated kitchen and bath cabinet, residential-type, installation Garage door, residential-type, installation Ship joinery contractors Millwork installation Window and door, residential-type, of any material, prefabricated, installation
Note on C118: This industry comprises establishments primarily engaged in building finishing trade work (except drywall, plaster, and insulation work; painting and wall covering work; flooring work; tile and terrazzo work; and finish carpentry work). The work performed may include new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Bathtub refinishing, on-site Fabricating metal cabinets or countertops on site Closet organizer system installation Modular furniture system attachment and installation Concrete coating, glazing, or sealing Trade show exhibit installation and dismantling Countertop and cabinet, metal (except residential-type), installation Waterproofing contractors Drapery fixture (e.g., hardware, rods, tracks) installation Window shade and blind installation
Note on C120: This industry comprises establishments primarily engaged in specialized trades (except foundation, structure, and building exterior contractors; building equipment contractors; building finishing contractors; and site preparation contractors). The specialty trade work performed includes new work, additions, alterations, maintenance, and repairs. Illustrative Examples: Billboard erection Outdoor swimming pool construction Cleaning building interiors during and immediately after construction Paver, brick (e.g., driveway, patio, sidewalk), installation Crane rental with operator Paving, residential and commercial driveway and parking lot Sandblasting building exteriors Fence installation Scaffold erecting and dismantling Interlocking brick and block installation Steeplejack work Manufactured (mobile) home set up and tie-down work Driveway paving or sealing