## Sheet2
Importance by Pathway
# | Title | Timeline | No OSW | Econ Only | Pilot | Turbines | Lead | Partners | Funding
OBJECTIVE: Meaningful and Effective Engagement
1 | Identify and fulfill the funding and capacity needs of state agencies in charge of convening engagement | 3–5 yrs | Low | High | High | High | Legis. | Relevant state agencies; Tribes; Local govt | TBD
2 | Coordinate with federal agencies and developers on outreach and engagement efforts to retain state involvement and reflect state interests in community engagement | 3–5 yrs | Medium | High | High | High | DLCD | Relevant state agencies; Tribes; BOEM | Existing
3 | Build community engagement partnerships with other agencies, local government staff, and nongovernmental organizations to combine resources and facilitate consistency in information to communities related to offshore wind energy | 3–5 yrs | Low | High | High | High | DLCD | Relevant state agencies; Tribes; NGOs; BOEM | Existing
4 | Clarify community participation expectations in Joint Agency Review Teams and other regulatory processes at the state and local level, and document these opportunities in policy or guidance | 0–3 yrs | Medium | High | High | High | DLCD | DSL | Existing
5 | For state-led engagement activities, establish and consult an ongoing body/steering committee to guide engagement | (3-5 yrs) | High | High | High | High | DLCD | Relevant state agencies; Tribes; BOEM | Existing
6 | Publicize public engagement opportunities for major process milestones in coastal newspapers and agency websites and listservs | Ongoing | High | High | High | High | DLCD; DSL | ODOT; Ports; Local govt; Labor; WA/CA partners; BOEM | Existing
7 | Incorporate equitable, contextual data transparency standards — including data provenance/lineage and data sovereignty | 5+ yrs | Medium | High | High | High | DLCD | Tribes; SHPO; DOJ; DSL; OPRD; Governor’s Office | Existing
8 | Provide clear public comment response logs to build trust in formal permitting and other decision-making processes | Ongoing | High | High | High | High | DLCD; DSL | Relevant state agencies | Existing
9 | Operate consistently with state law and policy related to consultation with Oregon tribes. | Ongoing | High | High | High | High | DLCD | Relevant state agencies; Tribes; BOEM | Existing
OBJECTIVE: Achieve State Energy and Climate Policy Objectives and Clarify the Pathways to Offshore Wind Energy Development
Strategy: Increase Regional Planning, Coordination, and Energy Market Integration
10 | Pursue regional power market opportunities, and transmission planning related to offshore wind energy | 3–5 yrs | Low | Low | High | High | ODOE | Legislature; PUC; BPA; Utilities; Western state agencies; | TBD
11 | Address transboundary energy issues and opportunities with California, Washington, and other western states related to offshore wind energy costs and benefits | 5+ yrs | Low | Medium | High | High | Gov Office | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
Strategy: Explore Policies and Investments to Create a Future Energy System that Can Meet Oregon’s Energy and Climate Goals Prepare for Offshore Wind Energy Potential
12 | Support investments and planning for grid infrastructure to increase resilience and facilitate new energy options. | 0–3 yrs + Ongoing | High | High | High | High | Legis.; ODOE | PUC; BPA; Utilities; CA/WA agencies; DLCD; BOEM | $10M+
13 | Explore potential economic incentives, energy planning policies, procurement frameworks and authorities, or other amendments to Oregon energy policy that might attract and facilitate long lead-time resources such as offshore wind energy. | 0–2 yrs | Medium | Medium | High | High | Legis.; ODOE | PUC; BPA; Utilities; CA/WA agencies; DLCD; BOEM | TBD
14 | Consider policy that would require offshore wind energy off the coast of Oregon to connect to the Oregon Coast grid. | 0–3 yrs | Low | Low | Medium | High | Legis.; DLCD | ODOE; PUC; BPA; Utilities; CA/WA agencies | Existing
Strategy: Improve Understanding of Offshore Wind Potential Benefits and Costs for Oregon to Clarify Investment Decisions
15 | Continue to refine the Oregon Energy Strategy to account for changing conditions related to offshore wind energy technology and the regional energy market. | Ongoing | Medium | Medium | High | High | ODOE |  | TBD
16 | Complete coastal and state-wide socioeconomic studies to quantify and refine the economic costs and benefits and job opportunities from offshore wind energy for Oregon. | 5+ yrs | Medium | Medium | High | High | BIZOR | Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | $1-3M
17 | Evaluate energy infrastructure needs more holistically to determine what role offshore wind energy and other renewables can play in improving energy resilience and reliability. | 5+ yrs | Medium | Medium | High | High | ODOE | BIZOR; PUC; Utilities | TBD
Objective: Protect the Environment and Species
Strategy: Strengthen State and Local Government Policies, Processes, and Capacity to Address Environmental Effects from Offshore Wind Energy
18 | Amend Oregon’s Territorial Sea Plan (and other policies as applicable) to address gaps. | 0–3 yrs | Medium | High | High | High | DLCD; OPAC | DSL; ODFW; OPRD; DOGAMI; Tribes; DOJ; BOEM | $300K - $500K
19 | Support agency capacity for building expertise in offshore wind energy effects and participating in regulatory processes. | 3–5 yrs | Medium | Medium | High | High | Legis. | Relevant state agencies | TBD
20 | Monitor changes to federal environmental protection standards and adopt new state policies as needed to maintain existing levels of protectiveness. | Ongoing | High | High | High | High | DLCD | Relevant state agencies; Legislature | TBD
Strategy: Responsibly Manage Uncertainty and Risk
21 | Conduct marine/coastal zone spatial planning to identify suitable sea space for development led by State interests and policies. | 3–5 yrs | Low | Low | High | High | DLCD; OPAC | Oregon Ocean Science Trust; Universities; Relevant state agencies; NGOs; Local govt; Tribes; BOEM; NOAA | $500k–$3M
22 | Develop and pursue an offshore wind energy research agenda for Oregon. | 3–5 yrs + Ongoing | Low | Low | High | High | DLCD; OPAC | Oregon Ocean Science Trust; Universities; Relevant state agencies; NGOs; Local govt; Tribes; BOEM; NOAA | $500k–$3M
23 | Clarify the timing of a cumulative impact assessment and other information needs before leasing and permitting. | 0–3 yrs | Medium | Medium | High | High | DLCD; OPAC | Relevant state agencies; Tribes; BOEM | Existing
24 | Establish a research collaborative to build Oregon-specific scientific consensus around offshore wind energy effects and coordinate with other west coast states. | 3–5 yrs + Ongoing | Low | Low | High | High | DLCD | OPAC; Oregon Ocean Science Trust; NGOs; Universities; Relevant state agencies; Tribes; Local govt; BOEM; NOAA | $500k–$3M
25 | Funding support for an Oregon Offshore Wind Energy Research Agenda and Oregon Offshore Wind Energy Science Collaborative. | 3–5 yrs | Medium | Medium | High | High | DLCD | OPAC; Oregon Ocean Science Trust; NGOs; Universities; Relevant state agencies; Tribes | $3M+
26 | Define a framework for monitoring and adaptive management specific to offshore wind energy development. | 3–5 yrs | Medium | Medium | High | High | DLCD | OPAC; Oregon Ocean Science Trust; Universities; Relevant state agencies Tribes; BOEM; NOAA | Existing
27 | Clarify and strengthen accountability measures for offshore wind energy projects throughout their entire lifecycle. | 0–3 yrs | Medium | Medium | High | High | DLCD | Relevant state agencies; Tribes; BOEM/BSEE | Existing
28 | Establish clear decommissioning expectations and require adequate financial assurance for decommissioning and incident response at the permitting phase. | 0–3 yrs | Low | Low | High | High | DLCD | Relevant state agencies; Tribes; BOEM/BSEE | Existing
29 | Involve State agencies early in site characterization activities, looking ahead to uncertainty management needs. | Ongoing | Low | Low | High | High | DLCD | OPAC/STAC; Oregon Ocean Science Trust; Universities; ODFW; DOGAMI; Tribes; BOEM; NOAA | Existing
Strategy: Recognize the Effects of Shoreside Development as an Essential Component of an Offshore Wind Energy Presence in Oregon
30 | State reviews of offshore wind energy authorizations should consider the cumulative effects of dependent or interrelated shoreside and in-estuary development. | 0–3 yrs | Medium | High | High | High | DLCD | OPAC/STAC; DSL | Existing
Objective: Protect Tribal Cultural and Archaeological Resources, Culturally Significant Viewsheds, Subsistence Activities, and other Interests of Tribes
Strategy: Protection of Culturally Significant Viewsheds
31 | Amend Part Five of the Territorial Sea Plan to include visual effects of cultural significance to Tribes. | 3–5 yrs | Medium | Medium | High | High | DLCD | OPAC; DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | TBD
Strategy: Protection of Natural Resources as Cultural Resources
32 | Protect Natural Resources as Cultural Resources by Implementing the Actions Identified in Section 6.3 (Protect the Environment and Species). | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; SHPO; DOJ; DSL; OPRD | $3M+ for all
Strategy: Protection of Archaeological Resources, including Underwater Villages
33 | Place conditions on any future offshore wind energy leasing or permitting consistent with the coordination and oversight conditions used in the 2024 BOEM leasing decision. | Ongoing | Medium | High | High | High | DLCD | Tribes; SHPO; BOEM | Existing
34 | Require Qualified Marine Archaeologists for certain offshore exploration activities. | Ongoing | Medium | High | High | High | DLCD | Tribes; SHPO; BOEM | Existing
35 | Include the opportunity for Tribal observers during potentially ecologically disturbing activities offshore. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; SHPO; BOEM | Existing
36 | Tribal oversight of ground disturbing activities. | Ongoing | Medium | High | High | High | DLCD | Tribes; SHPO; BOEM | Existing
37 | Reduce Federal barriers to Tribal archaeological participation through credentialing requirements. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; SHPO; BOEM | Existing
Strategy: Protection of Areas Used for Cultural Practices
38 | Encourage local policies to protect cultural sites. | 3–5 yrs | High | High | High | High | DLCD | Tribes; SHPO; Local govt | TBD
39 | Seek legislative action to amend state statutes and rules to exclude cultural resource areas from public disclosure when necessary. | 0–3 yrs | High | High | High | High | Legis. | DLCD; Tribes; SHPO; DOJ | Existing
40 | Require cultural site inventories as part of the offshore wind energy process. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; SHPO | Existing
Strategy: Protection of Tribal Fishing
41 | Explicitly include Tribal fishing uses in Territorial Sea Plan fishery protection policies. | 3–5 yrs | High | High | High | High | DLCD | OPAC; DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | Existing
42 | Develop model memoranda of agreement between offshore wind energy developers and Tribal governments related to Tribal fishery impacts. | 3–5 yrs | Medium | High | High | High | DLCD | Oregon Sea Grant; Tribes; Developers; BOEM | Existing
43 | Amend the Territorial Sea Plan Part Five area-specific fishery use protection standards to make them broadly applicable to types of environments rather than specific geographical areas. This includes the standard of presumptive exclusion unless the project proponent can demonstrate no significant adverse effect on areas important to fisheries and that there be no practicable alternative site. | 3–5 yrs | High | High | High | High | DLCD | OPAC; Relevant state agencies; Tribes | Existing
44 | Amend the Territorial Sea Plan Part Five policy around memorialized agreements to make them a firm requirement rather than an encouraged action. Regardless of an explicit policy change, the state should in practice seek evidence of consistency with the fisheries protection policies through memorialized agreements as it has done in past projects. | 3–5 yrs | Medium | High | High | High | DLCD | OPAC; DSL; ODFW; Tribes | Existing
Strategy: Use Indigenous and Traditional Knowledge in State Decision-Making
45 | Incorporate Traditional Ecological Knowledge in the Territorial Sea Plan information requirements for marine energy projects. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; Relevant state agencies | Existing
46 | Include Tribes in a Research Collaborative to build Oregon-specific scientific consensus and coordinate with other west coast states. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes | Tribal Cap TBD
47 | Conduct state-led marine/coastal zone spatial planning to identify suitable sea space for offshore wind energy development, with Tribal involvement. | 3–5 yrs | Low | High | High | High | DLCD | Tribes | Tribal Cap TBD
Strategy: Tribal Engagement Expectations in Future Offshore Wind Energy Processes and Inclusion in Offshore Wind Energy Decision-Making
48 | Tribal government policy consideration during State Federal Consistency reviews | Ongoing | Medium | High | High | High | DLCD | Tribes; Relevant state agencies | Existing
Strategy: Opportunities for Co-stewardship and Business Partnership
49 | Explore creation of a natural resource endowment fund | 3–5 yrs | Low | Medium | Medium | Medium | DLCD; Legis. | Relevant state agencies; Tribes | TBD
Strategy: Data Collection, Monitoring, and Access
50 | Include data accessibility conditions in Federal Consistency reviews. | Ongoing | Medium | High | High | High | DLCD |  | Existing
51 | Memorandum of Agreement/ Memorandum of Understanding between the state and Tribes for data sovereignty agreements, subject to applicable information protection requirements. | 3–5 yrs | Medium | High | High | High | DLCD | Tribes; DOJ | Existing
Strategy: State Role in Sovereign Communications between Tribes and Federal Government
52 | Seek a Memorandum of Understanding with federal agencies (notably BOEM) to clearly outline expectations for simultaneous engagement with state and Tribal representatives, with clearly defined goals and expectations for those interactions. | 3–5 yrs | Low | High | High | High | DLCD | Tribes; BOEM | Existing
Strategy: Tri-Party Communication with Tribes, State, and Developers
53 | Require ongoing communication between the State, Tribes, and developers | 3–5 yrs | Low | High | High | High | DLCD | Relevant state agencies; Tribes; BOEM | Existing
54 | Expand Tribal participation in Joint Agency Review Teams | Ongoing | Medium | High | High | High | DLCD | OPAC; DSL; Tribes | Existing
55 | At the request of Tribes, the State should seek information from project developers about funding sources. | 3–5 yrs | Low | High | High | High | DLCD | Tribes | Existing
Strategy: Tribal Capacity Needs to Support Offshore Wind Energy Engagement
56 | Support Tribal capacity needs to participate in offshore wind energy processes and activities | 3–5 yrs | Medium | High | High | High | Legis, | Tribes; DLCD | TBD
Strategy: Protection of Tribal People During Implementation of Offshore Wind Energy Projects
57 | Safety and Missing and Murdered Indigenous People Protection Plans. | 3–5 yrs | Medium | High | High | High | DLCD; Local Govt; Ports | BOLI; Community Colleges; Labor | TBD
OBJECTIVE: Support Coastal and Regional Communities
Strategy: Protect and Sustain Coastal Communities and Existing Uses
58 | Update Oregon’s visual resource inventory and further study community and Tribal values surrounding visual resource effects. | Ongoing | Medium | High | High | High | DLCD | Tribes; Local govt; SHPO; DOJ; DSL; OPRD; BOEM; NOAA/NMFS | $100k-$500k
59 | Socioeconomic studies to support offshore wind energy decision-making. | 5+ yrs | Medium | High | High | High | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
60 | Assess community needs to support offshore wind energy development. | 3–5 yrs | Medium | High | High | High | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
61 | Support local governments in amending comprehensive plans and codes to address Identified Gaps. | 0–3 yrs | Medium | High | High | High | DLCD | BIZOR; ODOT; Ports; Local govt; Labor; WA/CA partners; BOEM | TBD
Strategy: Protect and Maintain Optimum Management and Uses of Oregon’s Fisheries
62 | Include fishing communities in effective and precautionary offshore wind energy area siting. | 3–5 yrs | Low | Low | High | High | DLCD | OPAC; ODFW; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | Existing
63 | Assess the use of existing state fisheries protection policies in TSP Part Five for Tribal community impacts and amend as necessary to explicitly consider Tribal ceremonial and subsistence fishing uses in addition to commercial and recreational fishing. | 3–5 yrs | Medium | Medium | High | High | DLCD; OPAC | DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | Existing
64 | Amend the Territorial Sea Plan Part Five area-specific fishery use protection standards to make them broadly applicable to types of environments rather than specific geographical areas. This includes the standard of presumptive exclusion unless the project proponent can demonstrate no significant adverse effect on areas important to fisheries and that there be no practicable alternative site. | 3–5 yrs | Medium | Medium | High | High | DLCD; OPAC | DOJ; DSL; ODFW; DOGAMI; Tribes; Fishing groups; BOEM | Existing
65 | Amend the Territorial Sea Plan Part Five policy around memorialized agreements to make them a firm requirement rather than an encouraged action. | 3–5 yrs | Medium | Medium | High | High | DLCD; OPAC | DOJ; DSL; Tribes | Existing
66 | For any future leasing actions for offshore wind energy exploration, DLCD should establish an Offshore Wind Energy Fisheries Working Group to facilitate the development memorialized agreements between offshore wind energy developers and fishing communities. | 3–5 yrs | Medium | Medium | High | High | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD
67 | Include fishing community perspectives in an Oregon Offshore Wind Energy Research Agenda, Oregon-Based Science Collaborative, and the California-led West Coast Science Collaborative. | 3–5 yrs | Medium | Medium | High | High | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD
68 | Support and require fisheries compensation agreements | 0–3 yrs | Medium | Medium | High | High | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | Existing
69 | Sustain ongoing Engagement with fishing communities through support of fishing community groups focused on marine energy. | 5+ yrs | Medium | Medium | High | High | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD
Strategy: Enforceable Community Agreements to Support Coastal Communities
70 | Explore creation of new Enforceable Policies to require large-scale coastal development have a net benefit to coastal communities. | 0–3 yrs | Medium | High | High | High | DLCD | Relevant state agencies; Local govt; Tribes; BOEM | Existing
71 | Promote and pursue enforceability and accountability for Community Agreements. | Ongoing | Medium | High | High | High | DLCD | Local govt; CBOs; Tribes; BIZOR; ODOE; ODFW | Existing
72 | State support and guidance for convening Community Agreement negotiations. | 3–5 yrs | Low | High | High | High | Legis. | DLCD; Ports; Local govt; Labor; Tribes; NGOs | TBD
73 | Explore Community Agreement requirements in power procurement policies. | 0–3 yrs | Low | High | High | High | PUC | ODOE; BPA; Utilities; CA/WA partners; DLCD; BOEM; Legis. | Existing
74 | Fulfill the resource needs for Community Agreement capacity. | 3–5 yrs | Low | High | High | High | DLCD | Local govt; CBOs; Tribes; BIZOR | TBD
75 | Conduct Community Needs Assessments to support future community Agreement negotiations. | 5+ yrs | Medium | High | High | High | BIZOR | Local govt; CBOs; Colleges; Universities | TBD
OBJECTIVE: Support the Creation of New Economic Opportunities from Offshore Wind Energy Under Alternative Futures
Strategy: Identify and Secure Economic Opportunities
76 | Senior state official to coordinate with California and Washington regarding supply chain and other economic opportunities for the West Coast. | 0–5 yrs | Low | High | High | High | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
77 | State-led supply chain market opportunity assessment, inclusive of California and international markets. | 0–5 yrs | Low | High | High | High | BIZOR | Ports; Oregon businesses; Universities | TBD
78 | Promote relationships between Oregon businesses and interstate or international markets. | Ongoing | Low | High | High | High | BIZOR | Oregon businesses; Universities | Existing
Strategy: Identify Investment and Planning Needs
79 | Clarify port infrastructure development needs and integrate with existing estuary management plans and other applicable Enforceable Policies. | 0–5 yrs | Low | High | High | High | BIZOR | DLCD; Ports; Local govt; WA/CA partners; BOEM | Existing
80 | Understand and prepare for future port development needs to support offshore wind energy. | 3–5 yrs | Low | High | High | High | BIZOR | Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
81 | Assess complementary community investment needs under different scenarios. | 3–5 yrs | Medium | High | High | High | DLCD; BIZOR | Local govt; Tribes; CBOs; other affected communities | TBD
82 | Conduct Supply Chain and Workforce Assessment and Planning | 3–5 yrs | Low | High | High | High | DLCD | OPAC; Oregon Ocean Science Trust; Colleges; Universities; ODFW; DOGAMI; Tribes; BOEM; NOAA | TBD
OBJECTIVE: Position Oregon to have an Offshore Wind Energy Workforce that is Housed, Trained, and Equitable
83 | Strengthen and enforce labor and safety standards. | Ongoing | Medium | High | High | High | DLCD | BOLI; DOJ; Labor | TBD
84 | Develop a workforce development and training plan. | 3–5 yrs | Medium | High | High | High | Labor | BOLI; Community Colleges; BIZOR; Local govt; DLCD; Labor | TBD
85 | Assess community policy and investment needs to support a future offshore wind energy workforce, including housing, infrastructure, and social support services. | 5+ yrs | Medium | High | High | High | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
86 | Assess the compatibility of Port and Supply Chain readiness needs with local policies and estuary plans and seek solutions. | 3–5 yrs | Medium | High | High | High | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD
Note: this has ODFW concerns.
ODFW concern.
ODFW concern

## Sheet3
# | Objective |  | Objective | Title | Start Time | No OSW | Econ Only | Pilot | Turbines | Lead | Partners | Funding | "How it happens" | Legislative Action? | Tie to existing state action? | New discrete funding? | Agency capacity funding needed? | "Package"
Ref. # |  | OBJ # |  | OBJECTIVE: Meaningful and Effective Engagement
1 | A | A1 | MEE | Identify and fulfill the funding and capacity needs of state agencies in charge of convening engagement | 3–5 yrs | L | H | H | H | Legis. | Relevant state agencies; Tribes; Local govt | TBD | Legislative action | Yes
2 | A | A2 | MEE | Coordinate with federal agencies and developers on outreach and engagement efforts to retain state involvement and reflect state interests in community engagement | 3–5 yrs | M | H | H | H | DLCD | Relevant state agencies; Tribes; BOEM | Existing | Agency Discretion
3 | A | A3 | MEE | Build community engagement partnerships with other agencies, local government staff, and nongovernmental organizations to combine resources and facilitate consistency in information to communities related to offshore wind energy | 3–5 yrs | L | H | H | H | DLCD | Relevant state agencies; Tribes; NGOs; BOEM | Existing | Agency Discretion
4 | A | A4 | MEE | Clarify community participation expectations in Joint Agency Review Teams and other regulatory processes at the state and local level, and document these opportunities in policy or guidance | 0–3 yrs | M | H | H | H | DLCD | DSL | Existing | Agency Discretion
5 | A | A5 | MEE | For state-led engagement activities, establish and consult an ongoing body/steering committee to guide engagement | (3-5 yrs) | H | H | H | H | DLCD | Relevant state agencies; Tribes; BOEM | Existing | Agency Discretion
6 | A | A6 | MEE | Publicize public engagement opportunities for major process milestones in coastal newspapers and agency websites and listservs | Ongoing | H | H | H | H | DLCD; DSL | ODOT; Ports; Local govt; Labor; WA/CA partners; BOEM | Existing | Agency Discretion
7 | A | A7 | MEE | Incorporate equitable, contextual data transparency standards — including data provenance/lineage and data sovereignty | 5+ yrs | M | H | H | H | DLCD | Tribes; SHPO; DOJ; DSL; OPRD; Governor’s Office | Existing | Agency Discretion |  | Yes
8 | A | A8 | MEE | Provide clear public comment response logs to build trust in formal permitting and other decision-making processes | Ongoing | H | H | H | H | DLCD; DSL | Relevant state agencies | Existing | Agency Discretion
9 | A | A9 | MEE | Operate consistently with state law and policy related to consultation with Oregon tribes. | Ongoing | H | H | H | H | DLCD | Relevant state agencies; Tribes; BOEM | Existing | Agency Discretion
OBJECTIVE: Achieve State Energy and Climate Policy Objectives and Clarify the Pathways to Offshore Wind Energy Development
Strategy: Increase Regional Planning, Coordination, and Energy Market Integration
10 | B | B1 | E&C | Pursue regional power market opportunities, and transmission planning related to offshore wind energy | 3–5 yrs | L | L | H | H | ODOE | Legislature; PUC; BPA; Utilities; Western state agencies; | TBD | Legislative action | Yes
11 | B | B2 | E&C | Address transboundary energy issues and opportunities with California, Washington, and other western states related to offshore wind energy costs and benefits | 5+ yrs | L | M | H | H | Gov Office | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | State Leadership Coordination; Legislative Action | Yes
Strategy: Explore Policies and Investments to Create a Future Energy System that Can Meet Oregon’s Energy and Climate Goals Prepare for Offshore Wind Energy Potential
12 | B | B3 | E&C | Support investments and planning for grid infrastructure to increase resilience and facilitate new energy options. | 0–3 yrs + Ongoing | H | H | H | H | Legis.; ODOE | PUC; BPA; Utilities; CA/WA agencies; DLCD; BOEM | H | Legislative action; Agency Discretion | Maybe
13 | B | B4 | E&C | Explore potential economic incentives, energy planning policies, procurement frameworks and authorities, or other amendments to Oregon energy policy that might attract and facilitate long lead-time resources such as offshore wind energy. | 0–2 yrs | M | M | H | H | Legis.; ODOE | PUC; BPA; Utilities; CA/WA agencies; DLCD; BOEM | TBD | Legislative action | Yes
14 | B | B5 | E&C | Consider policy that would require offshore wind energy off the coast of Oregon to connect to the Oregon Coast grid. | 0–3 yrs | L | L | M | H | Legis.; DLCD | ODOE; PUC; BPA; Utilities; CA/WA agencies | Existing | Rulemaking or Legislative Action | Maybe
Strategy: Improve Understanding of Offshore Wind Potential Benefits and Costs for Oregon to Clarify Investment Decisions
15 | B | B6 | E&C | Continue to refine the Oregon Energy Strategy to account for changing conditions related to offshore wind energy technology and the regional energy market. | Ongoing | M | M | H | H | ODOE |  | TBD | Legislative action; Agency Discretion | Yes
16 | B | B7 | E&C | Complete coastal and state-wide socioeconomic studies to quantify and refine the economic costs and benefits and job opportunities from offshore wind energy for Oregon. | 5+ yrs | M | M | H | H | BIZOR | Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | Med | Legislative Action; Alternative Funding | Maybe
17 | B | B8 | E&C | Evaluate energy infrastructure needs more holistically to determine what role offshore wind energy and other renewables can play in improving energy resilience and reliability. | 5+ yrs | M | M | H | H | ODOE | BIZOR; PUC; Utilities | TBD | Agency Discretion
Objective: Protect the Environment and Species
Strategy: Strengthen State and Local Government Policies, Processes, and Capacity to Address Environmental Effects from Offshore Wind Energy
18 | C | C1 | ENV | Amend Oregon’s Territorial Sea Plan (and other policies as applicable) to address gaps. | 0–3 yrs | M | H | H | H | DLCD; OPAC | DSL; ODFW; OPRD; DOGAMI; Tribes; DOJ; BOEM | L | Agency Rulemaking
19 | C | C2 | ENV | Support agency capacity for building expertise in offshore wind energy effects and participating in regulatory processes. | 3–5 yrs | M | M | H | H | Legis. | Relevant state agencies | TBD | Legislative action | Yes
20 | C | C3 | ENV | Monitor changes to federal environmental protection standards and adopt new state policies as needed to maintain existing levels of protectiveness. | Ongoing | H | H | H | H | DLCD | Relevant state agencies; Legislature | TBD | Agency Discretion; Agency Rulemaking; Legislative action | Maybe
Strategy: Responsibly Manage Uncertainty and Risk
21 | C | C4 | ENV | Conduct marine/coastal zone spatial planning to identify suitable sea space for development led by State interests and policies. | 3–5 yrs | L | L | H | H | DLCD; OPAC | Oregon Ocean Science Trust; Universities; Relevant state agencies; NGOs; Local govt; Tribes; BOEM; NOAA | L-Mid | Agency Discretion; Legislative action (funding) | Funding
22 | C | C5 | ENV | Develop and pursue an offshore wind energy research agenda for Oregon. | 3–5 yrs + Ongoing | L | L | H | H | DLCD; OPAC | Oregon Ocean Science Trust; Universities; Relevant state agencies; NGOs; Local govt; Tribes; BOEM; NOAA | L-Mid | Agency Discretion; Legislative action (funding) | Funding
23 | C | C6 | ENV | Clarify the timing of a cumulative impact assessment and other information needs before leasing and permitting. | 0–3 yrs | M | M | H | H | DLCD; OPAC | Relevant state agencies; Tribes; BOEM | Existing | Agency Rulemaking
24 | C | C7 | ENV | Establish a research collaborative to build Oregon-specific scientific consensus around offshore wind energy effects and coordinate with other west coast states. | 3–5 yrs + Ongoing | L | L | H | H | DLCD | OPAC; Oregon Ocean Science Trust; NGOs; Universities; Relevant state agencies; Tribes; Local govt; BOEM; NOAA | L-Mid | Agency Discretion; Legislative action (funding) | Funding
25 | C | C8 | ENV | Funding support for an Oregon Offshore Wind Energy Research Agenda and Oregon Offshore Wind Energy Science Collaborative. | 3–5 yrs | M | M | H | H | DLCD | OPAC; Oregon Ocean Science Trust; NGOs; Universities; Relevant state agencies; Tribes | Mid-H | Legislative Action | Funding
26 | C | C9 | ENV | Define a framework for monitoring and adaptive management specific to offshore wind energy development. | 3–5 yrs | M | M | H | H | DLCD | OPAC; Oregon Ocean Science Trust; Universities; Relevant state agencies Tribes; BOEM; NOAA | Existing | Agency Rulemaking
27 | C | C10 | ENV | Clarify and strengthen accountability measures for offshore wind energy projects throughout their entire lifecycle. | 0–3 yrs | M | M | H | H | DLCD | Relevant state agencies; Tribes; BOEM/BSEE | Existing | Agency Rulemaking
28 | C | C11 | ENV | Establish clear decommissioning expectations and require adequate financial assurance for decommissioning and incident response at the permitting phase. | 0–3 yrs | L | L | H | H | DLCD | Relevant state agencies; Tribes; BOEM/BSEE | Existing | Agency Rulemaking
29 | C | C12 | ENV | Involve State agencies early in site characterization activities, looking ahead to uncertainty management needs. | Ongoing | L | L | H | H | DLCD | OPAC/STAC; Oregon Ocean Science Trust; Universities; ODFW; DOGAMI; Tribes; BOEM; NOAA | Existing | Agency Discretion
Strategy: Recognize the Effects of Shoreside Development as an Essential Component of an Offshore Wind Energy Presence in Oregon
30 | C | C13 | ENV | State reviews of offshore wind energy authorizations should consider the cumulative effects of dependent or interrelated shoreside and in-estuary development. | 0–3 yrs | M | H | H | H | DLCD | OPAC/STAC; DSL | Existing | Agency Rulemaking
Objective: Protect Tribal Cultural and Archaeological Resources, Culturally Significant Viewsheds, Subsistence Activities, and other Interests of Tribes
Strategy: Protection of Culturally Significant Viewsheds
31 | D | D1 | TCR | Amend Part Five of the Territorial Sea Plan to include visual effects of cultural significance to Tribes. | 3–5 yrs | M | M | H | H | DLCD | OPAC; DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | TBD | Agency Rulemaking
Strategy: Protection of Natural Resources as Cultural Resources
32 | D | D2 | TCR | Protect Natural Resources as Cultural Resources by Implementing the Actions Identified in Section 6.3 (Protect the Environment and Species). | 3–5 yrs | M | H | H | H | DLCD | Tribes; SHPO; DOJ; DSL; OPRD | Mid-H | Agency Discretion; Agency Rulemaking; Legislative action | Maybe
Strategy: Protection of Archaeological Resources, including Underwater Villages
33 | D | D3 | TCR | Place conditions on any future offshore wind energy leasing or permitting consistent with the coordination and oversight conditions used in the 2024 BOEM leasing decision. | Ongoing | M | H | H | H | DLCD | Tribes; SHPO; BOEM | Existing | Agency Discretion
34 | D | D4 | TCR | Require Qualified Marine Archaeologists for certain offshore exploration activities. | Ongoing | M | H | H | H | DLCD | Tribes; SHPO; BOEM | Existing | Agency Discretion; Agency Rulemaking
35 | D | D5 | TCR | Include the opportunity for Tribal observers during potentially ecologically disturbing activities offshore. | 3–5 yrs | M | H | H | H | DLCD | Tribes; SHPO; BOEM | Existing | Agency Discretion
36 | D | D6 | TCR | Tribal oversight of ground disturbing activities. | Ongoing | M | H | H | H | DLCD | Tribes; SHPO; BOEM | Existing | Agency Discretion
37 | D | D7 | TCR | Reduce Federal barriers to Tribal archaeological participation through credentialing requirements. | 3–5 yrs | M | H | H | H | DLCD | Tribes; SHPO; BOEM | Existing | Agency Discretion; Agency Rulemaking
Strategy: Protection of Areas Used for Cultural Practices
38 | D | D8 | TCR | Encourage local policies to protect cultural sites. | 3–5 yrs | H | H | H | H | DLCD | Tribes; SHPO; Local govt | TBD | Agency Discretion; Local Government Rulemaking
39 | D | D9 | TCR | Seek legislative action to amend state statutes and rules to exclude cultural resource areas from public disclosure when necessary. | 0–3 yrs | H | H | H | H | Legis. | DLCD; Tribes; SHPO; DOJ | Existing | Legislative Action
40 | D | D10 | TCR | Require cultural site inventories as part of the offshore wind energy process. | 3–5 yrs | M | H | H | H | DLCD | Tribes; SHPO | Existing | Agency Rulemaking; Local Government Rulemaking; Legislative Action (potential) | Maybe
Strategy: Protection of Tribal Fishing
41 | D | D11 | TCR | Explicitly include Tribal fishing uses in Territorial Sea Plan fishery protection policies. | 3–5 yrs | H | H | H | H | DLCD | OPAC; DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | Existing | Agency Rulemaking
42 | D | D12 | TCR | Develop model memoranda of agreement between offshore wind energy developers and Tribal governments related to Tribal fishery impacts. | 3–5 yrs | M | H | H | H | DLCD | Oregon Sea Grant; Tribes; Developers; BOEM | Existing | Agency Discretion
43 | D | D13 | TCR | Amend the Territorial Sea Plan Part Five area-specific fishery use protection standards to make them broadly applicable to types of environments rather than specific geographical areas. This includes the standard of presumptive exclusion unless the project proponent can demonstrate no significant adverse effect on areas important to fisheries and that there be no practicable alternative site. | 3–5 yrs | H | H | H | H | DLCD | OPAC; Relevant state agencies; Tribes | Existing | Agency Rulemaking
44 | D | D14 | TCR | Amend the Territorial Sea Plan Part Five policy around memorialized agreements to make them a firm requirement rather than an encouraged action. Regardless of an explicit policy change, the state should in practice seek evidence of consistency with the fisheries protection policies through memorialized agreements as it has done in past projects. | 3–5 yrs | M | H | H | H | DLCD | OPAC; DSL; ODFW; Tribes | Existing | Agency Rulemaking
Strategy: Use Indigenous and Traditional Knowledge in State Decision-Making
45 | D | D15 | TCR | Incorporate Traditional Ecological Knowledge in the Territorial Sea Plan information requirements for marine energy projects. | 3–5 yrs | M | H | H | H | DLCD | Tribes; Relevant state agencies | Existing | Agency Rulemaking
46 | D | D16 | TCR | Include Tribes in a Research Collaborative to build Oregon-specific scientific consensus and coordinate with other west coast states. | 3–5 yrs | M | H | H | H | DLCD | Tribes | Tribal Cap TBD | Agency Discretion
47 | D | D17 | TCR | Conduct state-led marine/coastal zone spatial planning to identify suitable sea space for offshore wind energy development, with Tribal involvement. | 3–5 yrs | L | H | H | H | DLCD | Tribes | Tribal Cap TBD | Agency Discretion
Strategy: Tribal Engagement Expectations in Future Offshore Wind Energy Processes and Inclusion in Offshore Wind Energy Decision-Making
48 | D | D18 | TCR | Tribal government policy consideration during State Federal Consistency reviews | Ongoing | M | H | H | H | DLCD | Tribes; Relevant state agencies | Existing | Agency Discretion; Agency Rulemaking
Strategy: Opportunities for Co-stewardship and Business Partnership
49 | D | D19 | TCR | Explore creation of a natural resource endowment fund | 3–5 yrs | L | M | M | M | DLCD; Legis. | Relevant state agencies; Tribes | TBD | Legislative Action | Yes
Strategy: Data Collection, Monitoring, and Access
50 | D | D20 | TCR | Include data accessibility conditions in Federal Consistency reviews. | Ongoing | M | H | H | H | DLCD |  | Existing | Agency Discretion; Agency Rulemaking
51 | D | D21 | TCR | Memorandum of Agreement/ Memorandum of Understanding between the state and Tribes for data sovereignty agreements, subject to applicable information protection requirements. | 3–5 yrs | M | H | H | H | DLCD | Tribes; DOJ | Existing | Agency Discretion
Strategy: State Role in Sovereign Communications between Tribes and Federal Government
52 | D | D22 | TCR | Seek a Memorandum of Understanding with federal agencies (notably BOEM) to clearly outline expectations for simultaneous engagement with state and Tribal representatives, with clearly defined goals and expectations for those interactions. | 3–5 yrs | L | H | H | H | DLCD | Tribes; BOEM | Existing | Agency Discretion
Strategy: Tri-Party Communication with Tribes, State, and Developers
53 | D | D23 | TCR | Require ongoing communication between the State, Tribes, and developers | 3–5 yrs | L | H | H | H | DLCD | Relevant state agencies; Tribes; BOEM | Existing | Agency Discretion
54 | D | D24 | TCR | Expand Tribal participation in Joint Agency Review Teams | Ongoing | M | H | H | H | DLCD | OPAC; DSL; Tribes | Existing | Agency Rulemaking
55 | D | D25 | TCR | At the request of Tribes, the State should seek information from project developers about funding sources. | 3–5 yrs | L | H | H | H | DLCD | Tribes | Existing | Agency Discretion
Strategy: Tribal Capacity Needs to Support Offshore Wind Energy Engagement
56 | D | D26 | TCR | Support Tribal capacity needs to participate in offshore wind energy processes and activities | 3–5 yrs | M | H | H | H | Legis, | Tribes; DLCD | TBD | Legislative Action; Federal Coordination | Yes
Strategy: Protection of Tribal People During Implementation of Offshore Wind Energy Projects
57 | D | D27 | TCR | Safety and Missing and Murdered Indigenous People Protection Plans. | 3–5 yrs | M | H | H | H | DLCD; Local Govt; Ports | BOLI; Community Colleges; Labor | TBD | Agency Rulemaking
OBJECTIVE: Support Coastal and Regional Communities
Strategy: Protect and Sustain Coastal Communities and Existing Uses
58 | E | E1 | CC | Update Oregon’s visual resource inventory and further study community and Tribal values surrounding visual resource effects. | Ongoing | M | H | H | H | DLCD | Tribes; Local govt; SHPO; DOJ; DSL; OPRD; BOEM; NOAA/NMFS | L | Agency Rulemaking; Legislative Action (funding) | Funding
59 | E | E2 | CC | Socioeconomic studies to support offshore wind energy decision-making. | 5+ yrs | M | H | H | H | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | Agency Discretion; Agency Rulemaking; Legislative action (funding); | Funding
60 | E | E3 | CC | Assess community needs to support offshore wind energy development. | 3–5 yrs | M | H | H | H | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | Agency Discretion; Legislative action (funding) | Funding
61 | E | E4 | CC | Support local governments in amending comprehensive plans and codes to address Identified Gaps. | 0–3 yrs | M | H | H | H | DLCD | BIZOR; ODOT; Ports; Local govt; Labor; WA/CA partners; BOEM | TBD | Agency Discretion; Legislative action (funding) | Funding
Strategy: Protect and Maintain Optimum Management and Uses of Oregon’s Fisheries
62 | E | E5 | CC | Include fishing communities in effective and precautionary offshore wind energy area siting. | 3–5 yrs | L | L | H | H | DLCD | OPAC; ODFW; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | Existing | Agency Discretion
63 | E | E6 | CC | Assess the use of existing state fisheries protection policies in TSP Part Five for Tribal community impacts and amend as necessary to explicitly consider Tribal ceremonial and subsistence fishing uses in addition to commercial and recreational fishing. | 3–5 yrs | M | M | H | H | DLCD; OPAC | DOJ; DSL; ODFW; DOGAMI; Tribes; BOEM | Existing | Agency Rulemaking
64 | E | E7 | CC | Amend the Territorial Sea Plan Part Five area-specific fishery use protection standards to make them broadly applicable to types of environments rather than specific geographical areas. This includes the standard of presumptive exclusion unless the project proponent can demonstrate no significant adverse effect on areas important to fisheries and that there be no practicable alternative site. | 3–5 yrs | M | M | H | H | DLCD; OPAC | DOJ; DSL; ODFW; DOGAMI; Tribes; Fishing groups; BOEM | Existing | Agency Rulemaking
65 | E | E8 | CC | Amend the Territorial Sea Plan Part Five policy around memorialized agreements to make them a firm requirement rather than an encouraged action. | 3–5 yrs | M | M | H | H | DLCD; OPAC | DOJ; DSL; Tribes | Existing | Agency Rulemaking
66 | E | E9 | CC | For any future leasing actions for offshore wind energy exploration, DLCD should establish an Offshore Wind Energy Fisheries Working Group to facilitate the development memorialized agreements between offshore wind energy developers and fishing communities. | 3–5 yrs | M | M | H | H | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD | Agency Discretion; Legislative action (funding) | Maybe
67 | E | E10 | CC | Include fishing community perspectives in an Oregon Offshore Wind Energy Research Agenda, Oregon-Based Science Collaborative, and the California-led West Coast Science Collaborative. | 3–5 yrs | M | M | H | H | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD | Agency Discretion
68 | E | E11 | CC | Support and require fisheries compensation agreements | 0–3 yrs | M | M | H | H | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | Existing | Agency Discretion; Agency Rulemaking
69 | E | E12 | CC | Sustain ongoing Engagement with fishing communities through support of fishing community groups focused on marine energy. | 5+ yrs | M | M | H | H | DLCD | ODFW; OPAC; Oregon Sea Grant; NOAA/NMFS; Tribes; Fishing groups; BOEM | TBD | Agency Discretion; Legislative action (funding); Alternative Funding | Funding
Strategy: Enforceable Community Agreements to Support Coastal Communities
70 | E | E13 | CC | Explore creation of new Enforceable Policies to require large-scale coastal development have a net benefit to coastal communities. | 0–3 yrs | M | H | H | H | DLCD | Relevant state agencies; Local govt; Tribes; BOEM | Existing | Agency Rulemaking; Legislative Action (uncertain) | Maybe
71 | E | E14 | CC | Promote and pursue enforceability and accountability for Community Agreements. | Ongoing | M | H | H | H | DLCD | Local govt; CBOs; Tribes; BIZOR; ODOE; ODFW | Existing | Agency Rulemaking; Legislative Action (uncertain) | Maybe
72 | E | E15 | CC | State support and guidance for convening Community Agreement negotiations. | 3–5 yrs | L | H | H | H | Legis. | DLCD; Ports; Local govt; Labor; Tribes; NGOs | TBD | Agency Discretion
73 | E | E16 | CC | Explore Community Agreement requirements in power procurement policies. | 0–3 yrs | L | H | H | H | PUC | ODOE; PUC; BPA; Utilities; CA/WA partners; DLCD; BOEM; Legis. | Existing | Agency Rulemaking; Legislative Action (uncertain) | Maybe
74 | E | E17 | CC | Fulfill the resource needs for Community Agreement capacity. | 3–5 yrs | L | H | H | H | DLCD | Local govt; CBOs; Tribes; BIZOR | TBD | Legislative Action; Alternative Funding | Funding
75 | E | E18 | CC | Conduct Community Needs Assessments to support future community Agreement negotiations. | 5+ yrs | M | H | H | H | BIZOR | Local govt; CBOs; Colleges; Universities | TBD | Agency Discretion; Legislative action (funding) | Funding
OBJECTIVE: Support the Creation of New Economic Opportunities from Offshore Wind Energy Under Alternative Futures
Strategy: Identify and Secure Economic Opportunities
76 | F | F1 | NEO | Senior state official to coordinate with California and Washington regarding supply chain and other economic opportunities for the West Coast. | 0–5 yrs | L | H | H | H | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | State Leadership Coordination
77 | F | F2 | NEO | State-led supply chain market opportunity assessment, inclusive of California and international markets. | 0–5 yrs | L | H | H | H | BIZOR | Ports; Oregon businesses; Universities | TBD | Legislative Action; Agency Action | Yes
78 | F | F3 | NEO | Promote relationships between Oregon businesses and interstate or international markets. | Ongoing | L | H | H | H | BIZOR | Oregon businesses; Universities | Existing | Agency Discretion; State Leadership Coordination
Strategy: Identify Investment and Planning Needs
79 | F | F4 | NEO | Clarify port infrastructure development needs and integrate with existing estuary management plans and other applicable Enforceable Policies. | 0–5 yrs | L | H | H | H | BIZOR | DLCD; Ports; Local govt; WA/CA partners; BOEM | Existing | Agency Discretion
80 | F | F5 | NEO | Understand and prepare for future port development needs to support offshore wind energy. | 3–5 yrs | L | H | H | H | BIZOR | Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | Agency Discretion
81 | F | F6 | NEO | Assess complementary community investment needs under different scenarios. | 3–5 yrs | M | H | H | H | DLCD; BIZOR | Local govt; Tribes; CBOs; other affected communities | TBD | Agency Discretion; Legislative Action (funding) | Funding
82 | F | F7 | NEO | Conduct Supply Chain and Workforce Assessment and Planning | 3–5 yrs | L | H | H | H | DLCD | OPAC; Oregon Ocean Science Trust; Colleges; Universities; ODFW; DOGAMI; Tribes; BOEM; NOAA | TBD | Agency Discretion; Legislative Action (funding) | Funding
OBJECTIVE: Position Oregon to have an Offshore Wind Energy Workforce that is Housed, Trained, and Equitable
83 | G | G1 | OSWW | Strengthen and enforce labor and safety standards. | Ongoing | M | H | H | H | DLCD | BOLI; DOJ; Labor | TBD | Agency Rulemaking; Legislative Action (uncertain) | Maybe
84 | G | G2 | OSWW | Develop a workforce development and training plan. | 3–5 yrs | M | H | H | H | Labor | BOLI; Community Colleges; BIZOR; Local govt; DLCD; Labor | TBD | Agency Discretion; Legislative Action (funding) | Funding
85 | G | G3 | OSWW | Assess community policy and investment needs to support a future offshore wind energy workforce, including housing, infrastructure, and social support services. | 5+ yrs | M | H | H | H | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | Agency Discretion; Legislative Action (funding) | Funding
86 | G | G4 | OSWW | Assess the compatibility of Port and Supply Chain readiness needs with local policies and estuary plans and seek solutions. | 3–5 yrs | M | H | H | H | BIZOR | ODOT; Ports; Local govt; Labor; DLCD; WA/CA partners; BOEM | TBD | Agency Discretion; Legislative Action (funding) | Funding
Note: this has ODFW concerns.
ODFW concern.
ODFW concern