State Performance Plan / Annual Performance Report: Part C

for STATE FORMULA GRANT PROGRAMS under the 
Individuals with Disabilities Education Act

For reporting on 
FFY 2024

Oregon

PART C DUE 
February 2, 2026

U.S. DEPARTMENT OF EDUCATION

WASHINGTON, DC 20202

# Introduction

Instructions

Provide sufficient detail to ensure that the Secretary and the public are informed of and understand the State’s systems designed to drive improved results for infants and toddlers with disabilities and their families and to ensure that the Lead Agency (LA) and early intervention service (EIS) providers and EIS programs meets the requirements of Part C of the IDEA. This introduction must include descriptions of the State’s General Supervision System, Technical Assistance System, Professional Development System, Stakeholder Involvement, and Reporting to the Public.

## Intro - Indicator Data

Executive Summary

The Oregon Department of Education (ODE), Office of Enhancing Student Opportunities, is the Lead Agency for IDEA Part C and oversees 35 Early Intervention/Early Childhood Special Education (EI/ECSE) programs serving eligible infants and toddlers across the state. ODE administers a comprehensive system of general supervision, technical assistance, professional development, stakeholder engagement, and public reporting to ensure that IDEA Part C requirements are met and that programs are supported in delivering timely, effective services to children and families.

The State works collaboratively with EI/ECSE programs to support improved functional outcomes for children and to ensure consistent implementation of federal and state requirements. These efforts are implemented through an integrated system that includes data-based monitoring, fiscal oversight, dispute resolution, and continuous improvement planning.

ODE maintains a Technical Assistance System that uses both technology and staff expertise to provide timely access to data, guidance, and support. Education specialists serve as primary points of contact for programs, and a web-based system provides access to data tools, monitoring resources, and on-demand guidance.

The State’s Professional Development System ensures that personnel have access to coordinated training and support focused on effective practices, compliance requirements, and service delivery quality. Activities include statewide training on data collections and compliance requirements, family-focused trainings on procedural safeguards and IFSP processes, and targeted technical assistance to programs upon request.

Stakeholder input is incorporated into APR development, target setting, and improvement planning through engagement with the State Interagency Coordinating Council (SICC), the Parent Training and Information Center, and other advisory groups. The State publishes program performance information through publicly available Special Education Profiles and posts the SPP/APR on its website.

Together, these systems are designed to promote consistent expectations, timely services, and effective implementation of IDEA Part C across Oregon. Public reporting site: https://www.oregon.gov/ode/reports-and-data/spedreports/pages/default.aspx

Additional information related to data collection and reporting

N/A

General Supervision System

The systems that are in place to ensure that the IDEA Part C requirements are met (e.g., integrated monitoring activities; data on processes and results; the SPP/APR; fiscal management; policies, procedures, and practices resulting in effective implementation; and improvement, correction, incentives, and sanctions). Include a description of all the mechanisms the State uses to identify and verify correction of noncompliance and improve results. This should include, but not be limited to, State monitoring, State database/data system, dispute resolution, fiscal management systems as well as other mechanisms through which the State is able to determine compliance and/or issue written findings of noncompliance. The State should include the following elements:

Describe the process the State uses to select EIS providers and/or EIS programs for monitoring, the schedule, and number of EIS providers/programs monitored per year.

Oregon’s general supervision system is a coordinated, data-based framework designed to ensure compliance with IDEA Part C and to support continuous improvement in program performance. The system integrates monitoring, fiscal oversight, dispute resolution, data management, and enforcement to identify noncompliance, verify correction, and strengthen program implementation. The system is administered by the Office of Enhancing Student Opportunities and includes the following components:

--Fiscal management and grant oversight

--System Performance Review & Improvement (SPR&I)

--Statewide data systems (ecWeb)

--Dispute resolution and complaint management

--Policy and procedure guidance

--Graduated enforcement and corrective action

All 35 EI/ECSE programs are monitored annually through the System Performance Review and Improvement (SPR&I) process. This is a universal monitoring system rather than a cyclical or risk-based sample. Each year, every program conducts required file reviews, submits procedural compliance data, and receives program-specific SPP/APR indicator data for review and improvement planning. In addition to annual SPR&I monitoring, ODE conducts focused reviews and audits of a subset of programs each year using the same tools and procedures, based on risk, performance trends, data quality concerns, or other identified issues.

Describe how child records are chosen, including the number of child records that are selected, as part of the State’s process for determining an EIS provider’s and EIS program’s compliance with IDEA requirements and verifying the EIS provider/program’s correction of any identified noncompliance.

Programs use Oregon’s statewide data system, ecWeb, to select records for review. ecWeb generates a pool of eligible records based on the required monitoring periods and file types, including Early Intervention, Early Childhood Special Education, and transition records. The system selects records using demographic and program-level criteria, including age, disability category, race and ethnicity, gender, and service area, to ensure the sample reasonably reflects the population served by the program. ecWeb identifies the required number of records and assigns them to the program’s SPR&I review list. These records are then reviewed by the program using the State’s standardized monitoring protocols.

Describe the data system(s) the State uses to collect monitoring and SPP/APR data, and the period from which records are reviewed.

Oregon uses two primary systems: the System Performance Review and Improvement (SPR&I) system and the statewide EI/ECSE database, ecWeb. SPR&I is the State’s annual monitoring and accountability system. Programs submit procedural compliance data based on child record reviews and receive program-specific indicator data within the system. For the current cycle, programs submitted SPR&I data on February 1, 2025. The State reviewed submissions and issued findings on April 15, 2025. Programs must correct any identified noncompliance as soon as possible, but no later than one year from the date of identification. ecWeb is the official system of record for EI/ECSE. It houses individual child records and supports data collection for child outcomes, timelines, monitoring, audits, and verification of correction. ODE staff also use ecWeb when conducting focused reviews and audits of programs. Records reviewed are from the applicable federal fiscal year monitoring window, consistent with the State’s monitoring protocols and OSEP guidance.

Describe how the State issues findings: by EIS provider and/or EIS program; and if findings are issued by the number of instances or by EIS provider and/or EIS program.

The State issues findings by EI/ECSE program. Findings are issued based on the number of instances of noncompliance identified through SPR&I submissions, audits, complaints, due process decisions, or other substantiated sources. For the current cycle, findings were issued on April 15, 2025.

If applicable, describe the adopted procedures that permit its EIS providers/ programs to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction).

N/A

Describe the State’s system of graduated and progressive sanctions to ensure the correction of identified noncompliance and to address areas in need of improvement, used as necessary and consistent with IDEA Part C’s enforcement provisions, the OMB Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards (Uniform Guidance), and State policies.

ODE uses a tiered system aligned with IDEA enforcement categories: Meets Requirements, Needs Assistance, Needs Intervention, and Needs Substantial Intervention. Programs that meet requirements may receive continued support and optional technical assistance to sustain performance. Programs identified as needing assistance receive targeted technical assistance, may be designated as high-risk grantees, and may be required to direct program resources toward specific improvement activities. Programs identified as needing intervention are subject to increased oversight, required corrective action plans, restrictions on fiscal flexibility, and may have IDEA funds partially withheld or recovered. Programs identified as needing substantial intervention may be subject to the most significant enforcement actions, including withholding of funds and referral for additional legal or fiscal enforcement as appropriate. This framework ensures that enforcement is proportional, timely, and focused on achieving correction and strengthening system performance.

Describe how the State makes annual determinations of EIS program performance, including the criteria the State uses and the schedule for notifying EIS programs of their determinations. If the determinations are made public, include a web link for the most recent determinations.

ODE makes annual determinations for each EI/ECSE program each June, based on FFY data from two years prior. Determinations are based on compliance indicators, timely and accurate data submission, correction of noncompliance, dispute resolution data, and other required measures. Programs are assigned to one of four categories: Meets Requirements, Needs Assistance, Needs Intervention, or Needs Substantial Intervention, using the State’s Determination and Enforcement Matrix. Programs are notified of their determinations in writing. Determinations are publicly posted at: https://www.oregon.gov/ode/students-and-family/specialeducation/generalsupervision/pages/2024-2025eiecsespriresources.aspx

Provide the web link to information about the State’s general supervision policies, procedures, and process that is made available to the public.

https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/EI-ECSE-Contractor%27s-Information.aspx

Technical Assistance System:

The mechanisms that the State has in place to ensure the timely delivery of high quality, evidence-based technical assistance and support to EIS programs.

The State provides technical assistance through a combination of assigned education specialists, statewide training, communities of practice, and data-based supports. This includes annual data manager trainings, fall and spring statewide technical assistance sessions, and ongoing targeted support based on monitoring results, data trends, and program needs. The State facilitates a bimonthly intake and referral community of practice that brings together staff from across regions to address referral processes, eligibility pathways, form updates, and statewide trends. The State also coordinates with partner agencies to support consistent and timely service coordination. These mechanisms ensure timely, consistent, and practical support to EI/ECSE programs.

Professional Development System:

The mechanisms the State has in place to ensure that service providers have the skills to effectively provide services that improve results for infants and toddlers with disabilities and their families.

Oregon’s professional development system is guided by its Comprehensive Professional Development Plan and the ECTA System Framework. Focus areas include personnel standards, preservice and inservice training, and workforce stability.

In October 2023, Oregon updated its EI/ECSE personnel standards by adopting national professional standards for specialists, assistants, and supervisors. These standards guide individual professional development plans, statewide training priorities, technical assistance activities, and alignment with higher education programs. The standards are reviewed and updated on a five-year cycle to ensure continued alignment with current practice.

Stakeholder Engagement:

The mechanisms for broad stakeholder engagement, including activities carried out to obtain input from, and build the capacity of, a diverse group of parents to support the implementation activities designed to improve outcomes, including target setting and any subsequent revisions to targets, analyzing data, developing improvement strategies, and evaluating progress.

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

Apply stakeholder input from introduction to all Part C results indicators. (y/n)

YES

Number of Parent Members:

25

Parent Members Engagement:

Describe how the parent members of the Interagency Coordinating Council, parent center staff, parents from local and statewide advocacy and advisory committees, and individual parents were engaged in setting targets, analyzing data, developing improvement strategies, and evaluating progress.

The SPP/APR is presented annually to the SICC, which includes parent members and representatives from the parent training center. Parent members participate in reviewing data, discussing system performance, and providing input on targets and improvement priorities. FACT Oregon and SICC members also participate in the Parent Involvement Survey collaboration, which sets joint goals and timelines related to family experience indicators.

Activities to Improve Outcomes for Children with Disabilities:

Describe the activities conducted to increase the capacity of diverse groups of parents to support the development of implementation activities designed to improve outcomes for infants and toddlers with disabilities and their families.

Oregon conducts targeted activities to increase the capacity of diverse groups of parents to support the development and implementation of improvement activities designed to improve outcomes for infants and toddlers with disabilities and their families. These efforts focus on building parent knowledge of the Part C system, strengthening understanding of family rights and early intervention services, and supporting meaningful participation in system improvement processes.

The State provides translated materials, interpretation services, and accessible communication supports to ensure families who are English learners or who have additional communication needs can participate in improvement activities. Oregon partners with parent organizations and community-based agencies, including the State’s Parent Training and Information Center, to deliver culturally responsive outreach and family education, with an emphasis on reaching families from historically underserved communities.

Oregon also supports parent leadership development by recruiting diverse parents to serve on advisory and stakeholder groups, including the State Interagency Coordinating Council (SICC). Parent members receive orientation, access to relevant data and background materials, and ongoing support to enable informed participation in discussions related to system performance, improvement priorities, and implementation strategies. Flexible and virtual engagement options are used to reduce participation barriers.

In addition, Oregon gathers family input through the Early Intervention Parent Involvement Survey and reviews the results with parent partners and advisory groups to identify strengths, disparities, and improvement priorities. This process builds parent capacity to contribute to continuous improvement by demonstrating how family input informs implementation and system change.

Soliciting Public Input:

The mechanisms and timelines for soliciting public input for setting targets, analyzing data, developing improvement strategies, and evaluating progress.

The State solicited broad public input during FFY 2020 when setting the current targets and continues to engage the SICC and stakeholders in reviewing data and progress. The State provides regular updates to the SICC, including information about system performance, policy changes, and implementation priorities. Public input is also solicited during major policy or system changes.

Making Results Available to the Public:

The mechanisms and timelines for making the results of the setting targets, data analysis, development of the improvement strategies, and evaluation available to the public.

The State posts the SPP/APR annually on its website at: https://www.oregon.gov/ode/reports-and-data/spedreports/pages/default.aspx

The State also issues a public news release summarizing results and providing access to the full report.

Reporting to the Public:

How and where the State reported to the public on the FFY 2023 performance of each EIS Program located in the State on the targets in the SPP/APR as soon as practicable, but no later than 120 days following the State’s submission of its FFY 2023 APR, as required by 34 CFR §303.702(b)(1)(i)(A); and a description of where, on its website, a complete copy of the State’s SPP/APR, including any revisions if the State has revised the targets that it submitted with its FFY 2023 APR in 2025, is available.

The State reports publicly on the performance of each EI/ECSE program within 120 days of submitting the APR, as required by 34 CFR §303.702(b)(1)(i)(A), through its public reporting website and Special Education Profiles. A complete copy of the State’s SPP/APR, including any revisions, is available at: https://www.oregon.gov/ode/reports-and-data/spedreports/pages/default.aspx

## Intro - Prior FFY Required Actions

None

## Intro - OSEP Response

The State Interagency Coordinating Council (SICC) submitted to the Secretary its annual report that is required under IDEA Section 641(e)(1)(D) and 34 C.F.R. § 303.604(c). The SICC noted it has elected to support the State lead agency's submission of its SPP/APR as its annual report in lieu of submitting a separate report. OSEP accepts the SICC form, which will not be posted publicly with the State's SPP/APR documents.

On June 5, 2025, OSEP issued findings in its monitoring report, which are not fully resolved. Longstanding noncompliance (from any unresolved finding identified by OSEP) may be a factor in the Department’s 2027 determinations. OSEP will work with Oregon to clarify what actions remain.

## Intro - Required Actions

# Indicator 1: Timely Provision of Services

Instructions and Measurement

Monitoring Priority: Early Intervention Services In Natural Environments

Compliance indicator: Percent of infants and toddlers with Individual Family Service Plans (IFSPs) who receive the early intervention services on their IFSPs in a timely manner. (20 U.S.C. 1416(a)(3)(A) and 1442)

Data Source

Data to be taken from monitoring or State data system and must be based on actual, not an average, number of days. Include the State’s criteria for “timely” receipt of early intervention services (i.e., the time period from parent consent to when IFSP services are actually initiated).

Measurement

Percent = [(# of infants and toddlers with IFSPs who receive the early intervention services on their IFSPs in a timely manner) divided by the (total # of infants and toddlers with IFSPs)] times 100.

Account for untimely receipt of services, including the reasons for delays.

Instructions

If data are from State monitoring, describe the method used to select early intervention service (EIS) programs for monitoring. If data are from a State database, describe the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period) and how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

Targets must be 100%.

Describe the results of the calculations and compare the results to the target. Describe the method used to collect these data and if data are from the State’s monitoring, describe the procedures used to collect these data. States report in both the numerator and denominator under Indicator 1 on the number of children for whom the State ensured the timely initiation of new services identified on the IFSP. Include the timely initiation of new early intervention services from both initial IFSPs and subsequent IFSPs. Provide actual numbers used in the calculation.

The State’s timeliness measure for this indicator must be either: (1) a time period that runs from when the parent consents to IFSP services; or (2) the IFSP initiation date (established by the IFSP Team, including the parent).

States are not required to report in their calculation the number of children for whom the State has identified the cause for the delay as exceptional family circumstances, as defined in 34 CFR §303.310(b), documented in the child’s record. If a State chooses to report in its calculation children for whom the State has identified the cause for the delay as exceptional family circumstances documented in the child’s record, the numbers of these children are to be included in the numerator and denominator. Include in the discussion of the data the numbers the State used to determine its calculation under this indicator and report separately the number of documented delays attributable to exceptional family circumstances.

Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in the Office of Special Education Programs’ (OSEP’s) response for the previous SPP/APR. If the State did not ensure timely correction of the previous noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance, methods to ensure correction, and any enforcement actions that were taken.

If the State reported less than 100% compliance for the previous reporting period (e.g., for the FFY 2024 SPP/APR, the data for FFY 2023), and the State did not identify any findings of noncompliance, provide an explanation of why the State did not identify any findings of noncompliance.

If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), the explanation within each applicable indicator must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

## 1 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 99.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data | 97.47% | 96.84% | 97.97% | 98.72% | 96.13% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

FFY 2024 SPP/APR Data

| Number of infants and toddlers with IFSPs who receive the early intervention services on their IFSPs in a timely manner | Total number of infants and toddlers with IFSPs | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 146 | 151 | 96.13% | 100% | 97.35% | Did not meet target | No Slippage |

Number of documented delays attributable to exceptional family circumstances

This number will be added to the "Number of infants and toddlers with IFSPs who receive their early intervention services on their IFSPs in a timely manner" field above to calculate the numerator for this indicator.

1

Provide reasons for delay, if applicable.

In addition to one delay attributed to exceptional family circumstances due to the child being absent, four delays were associated with agency-related factors. Two delays resulted from staff illness or absence, which required rescheduling services beyond Oregon’s definition of timely receipt of services. The remaining two delays occurred when staff scheduled services after the start date documented on the IFSP.

Include your State’s criteria for “timely” receipt of early intervention services (i.e., the time period from parent consent to when IFSP services are actually initiated).

Oregon defines “timely manner” (based on guidance from OSEP) as the initiation date on the IFSP or ten days from when the parent provides consent for the IFSP service.

What is the source of the data provided for this indicator?

State monitoring

Describe the method used to select EIS programs for monitoring.

The Oregon Department of Education (ODE) uses the System Performance Review and Improvement (SPR&I) process to select files from all Early Intervention (EI) programs for annual monitoring. All programs receiving IDEA Part C funds participate in this statewide accountability system, which focuses on procedural compliance and performance on key federal and state indicators. The SPR&I system provides the State with the mechanism for review of corrective actions and of program policies, procedures, and systems to ensure the requirements set forth in 34 CFR §§303.700–303.708 are met.

Each year, EI programs conduct reviews of individual child records based on a number of files determined by the State. Files are divided evenly between Early Intervention and Transition from Early Intervention and are selected to reflect the program’s population by race/ethnicity, disability, and gender using the most recent December 1 child count. Programs submit individual child procedural compliance data electronically through the SPR&I database, including timelines from parent consent to service implementation and documentation of any delays.

ODE reviews these data to evaluate compliance, verify correction of noncompliance, and identify areas for improvement. Through the SPR&I process, ODE collaborates with local programs on data collection and analysis, improvement planning, implementation, and reporting of progress. This continuous improvement process enables the State to monitor program performance, ensure timely service delivery, and strengthen outcomes for infants and toddlers and their families.

Provide additional information about this indicator (optional)

Correction of Findings of Noncompliance Identified in FFY 2023

| Findings of Noncompliance Identified | Findings of Noncompliance Verified as Corrected Within One Year | Findings of Noncompliance Subsequently Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |
| 6 | 6 | 0 | 0 |

FFY 2023 Findings of Noncompliance Verified as Corrected

Describe how the State verified that the source of noncompliance is correctly implementing the regulatory requirements.

To ensure that the sources of noncompliance were correctly implementing the regulatory requirements, the State conducted additional verification activities. Through our monitoring process, a total of six instances of child-specific noncompliance were identified. Each EI program with identified noncompliance completed and submitted subsequent file reviews in SPR&I for child records developed after the original noncompliance was corrected.

The State reviewed these subsequent files in SPR&I and cross-checked the information in ecWeb, Oregon’s statewide EI/ECSE data system, to confirm current compliance and correct implementation of required procedures. Through this review, the State verified that all programs with previous noncompliance demonstrated sustained correction and full adherence to the regulatory requirements.

Describe how the State verified that each individual case of noncompliance was corrected.

For FFY 2023, the State completed a comprehensive verification process to ensure correction of all six identified instances of individual noncompliance. In accordance with OSEP QA 23-01, the State verified correction through individual file review and review and approval of correction data submitted by Early Intervention programs in SPR&I, Oregon’s online monitoring system. The State confirmed that 100% (6 of 6) of identified incidents of noncompliance were corrected within one year of identification.

To verify correction of the identified noncompliance, the State completed the following actions:

The Early Intervention (EI) program submitted documentation of the correction of noncompliance for each of the six individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

The State reviewed the six individual child records in ecWeb, Oregon’s statewide EI/ECSE data system, to see if services were provided, although late, or the child was no longer in the program’s jurisdiction.

The State verified correction in accordance with OSEP QA 23-01 through review of all six individual child data submitted in SPR&I and review of the six child-specific files in ecWeb. Through review of the individual child files, the State verified that in each of the six instances of noncompliance, the children ultimately received the early intervention services listed on their IFSPs—although delayed—unless the child was no longer within the jurisdiction of the EIS program, consistent with OSEP QA 23-01.

If procedures have been adopted that permit EIS program or providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), describe how, for instances of noncompliance discovered in FFY 2023, the State verified: (1) that the source of noncompliance is correctly implementing the regulatory requirements; and, (2) each individual case of noncompliance was corrected.

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 1 - Prior FFY Required Actions

Because the State reported less than 100% compliance for FFY 2023, the State must report on the status of correction of noncompliance identified in FFY 2023 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2024 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2023 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2024 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2023, although its FFY 2023 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2023. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

Response to actions required in FFY 2023 SPP/APR

To ensure that the sources of noncompliance were correctly implementing the regulatory requirements, the State conducted additional verification activities. Through our monitoring process, a total of six instances of child-specific noncompliance were identified. Each EI program with identified noncompliance completed and submitted subsequent file reviews in SPR&I for child records developed after the original noncompliance was corrected.

The State reviewed these subsequent files in SPR&I and cross-checked the information in ecWeb, Oregon’s statewide EI/ECSE data system, to confirm current compliance and correct implementation of required procedures. Through this review, the State verified that all programs with previous noncompliance demonstrated sustained correction and full adherence to the regulatory requirements.

For FFY 2023, the State completed a comprehensive verification process to ensure correction of all six identified instances of individual noncompliance. In accordance with OSEP QA 23-01, the State verified correction through individual file review and review and approval of correction data submitted by Early Intervention programs in SPR&I, Oregon’s online monitoring system. The State confirmed that 100% (6 of 6) of identified incidents of noncompliance were corrected within one year of identification.

To verify correction of the identified noncompliance, the State completed the following actions:

The Early Intervention (EI) program submitted documentation of the correction of noncompliance for each of the six individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

The State reviewed the six individual child records in ecWeb, Oregon’s statewide EI/ECSE data system, to see if services were provided, although late, or the child was no longer in the program’s jurisdiction.

The State verified correction in accordance with OSEP QA 23-01 through review of all six individual child data submitted in SPR&I and review of the six child-specific files in ecWeb. Through review of the individual child files, the State verified that in each of the six instances of noncompliance, the children ultimately received the early intervention services listed on their IFSPs—although delayed—unless the child was no longer within the jurisdiction of the EIS program, consistent with OSEP QA 23-01.

## 1 - OSEP Response

## 1 - Required Actions

Because the State reported less than 100% compliance for FFY 2024, the State must report on the status of correction of noncompliance identified in FFY 2024 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2025 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2024 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2025 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2024, although its FFY 2024 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2024. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

# Indicator 2: Services in Natural Environments

Instructions and Measurement

Monitoring Priority: Early Intervention Services In Natural Environments

Results indicator: Percent of infants and toddlers with IFSPs who primarily receive early intervention services in the home or community-based settings. (20 U.S.C. 1416(a)(3)(A) and 1442)

Data Source

Same data as used for reporting to the Department under section 618 of the IDEA, using the definitions in EDFacts file specification FS902.

Measurement

Percent = [(# of infants and toddlers with IFSPs who primarily receive early intervention services in the home or community-based settings) divided by the (total # of infants and toddlers with IFSPs)] times 100.

Instructions

Sampling from the State’s 618 data is not allowed.

Describe the results of the calculations and compare the results to the target.

The data reported in this indicator should be consistent with the State’s 618 data reported in Table 2. If not, explain.

## 2 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 81.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target>= | 96.50% | 96.50% | 96.50% | 96.50% | 96.50% |
| Data | 98.66% | 99.31% | 97.42% | 97.54% | 98.02% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target>= | 96.50% | 96.50% |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

Prepopulated Data

| Source | Date | Description | Data |
| --- | --- | --- | --- |
| SY 2024-25 IDEA Part C Child Count - Infants and Toddlers with Disabilities (EDFacts file spec FS902; Data group 5023) | 07/30/2025 | Number of infants and toddlers with IFSPs who primarily receive early intervention services in the home or community-based settings | 3,852 |
| SY 2024-25 IDEA Part C Child Count - Infants and Toddlers with Disabilities (EDFacts file spec FS902; Data group 5023) | 07/30/2025 | Total number of infants and toddlers with IFSPs | 3,915 |

FFY 2024 SPP/APR Data

| Number of infants and toddlers with IFSPs who primarily receive early intervention services in the home or community-based settings | Total number of Infants and toddlers with IFSPs | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 3,852 | 3,915 | 98.02% | 96.50% | 98.39% | Met target | No Slippage |

Provide additional information about this indicator (optional).

## 2 - Prior FFY Required Actions

None

## 2 - OSEP Response

## 2 - Required Actions

# Indicator 3: Early Childhood Outcomes

Instructions and Measurement

Monitoring Priority: Early Intervention Services In Natural Environments

Results indicator: Percent of infants and toddlers with IFSPs who demonstrate improved:

A. Positive social-emotional skills (including social relationships);

B. Acquisition and use of knowledge and skills (including early language/ communication); and

C. Use of appropriate behaviors to meet their needs.

(20 U.S.C. 1416(a)(3)(A) and 1442)

Data Source

State selected data source.

Measurement

Outcomes:

A. Positive social-emotional skills (including social relationships);

B. Acquisition and use of knowledge and skills (including early language/communication); and

C. Use of appropriate behaviors to meet their needs.

Progress categories for A, B and C:

a. Percent of infants and toddlers who did not improve functioning = [(# of infants and toddlers who did not improve functioning) divided by (# of infants and toddlers with IFSPs assessed)] times 100.

b. Percent of infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers = [(# of infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers) divided by (# of infants and toddlers with IFSPs assessed)] times 100.

c. Percent of infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it = [(# of infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it) divided by (# of infants and toddlers with IFSPs assessed)] times 100.

d. Percent of infants and toddlers who improved functioning to reach a level comparable to same-aged peers = [(# of infants and toddlers who improved functioning to reach a level comparable to same-aged peers) divided by (# of infants and toddlers with IFSPs assessed)] times 100.

e. Percent of infants and toddlers who maintained functioning at a level comparable to same-aged peers = [(# of infants and toddlers who maintained functioning at a level comparable to same-aged peers) divided by (# of infants and toddlers with IFSPs assessed)] times 100.

Summary Statements for Each of the Three Outcomes:

Summary Statement 1: Of those infants and toddlers who entered early intervention below age expectations in each Outcome, the percent who substantially increased their rate of growth by the time they turned 3 years of age or exited the program.

Measurement for Summary Statement 1:

Percent = [(# of infants and toddlers reported in progress category (c) plus # of infants and toddlers reported in category (d)) divided by (# of infants and toddlers reported in progress category (a) plus # of infants and toddlers reported in progress category (b) plus # of infants and toddlers reported in progress category (c) plus # of infants and toddlers reported in progress category (d))] times 100.

Summary Statement 2: The percent of infants and toddlers who were functioning within age expectations in each Outcome by the time they turned 3 years of age or exited the program.

Measurement for Summary Statement 2:

Percent = [(# of infants and toddlers reported in progress category (d) plus # of infants and toddlers reported in progress category (e)) divided by the (total # of infants and toddlers reported in progress categories (a) + (b) + (c) + (d) + (e))] times 100.

Instructions

Sampling of infants and toddlers with IFSPs is allowed. When sampling is used, submit a description of the sampling methodology outlining how the design will yield valid and reliable estimates. (See General Instructions page 2 for additional instructions on sampling.)

In the measurement, include in the numerator and denominator only infants and toddlers with IFSPs who received early intervention services for at least six months before exiting the Part C program.

Report: (1) the number of infants and toddlers who exited the Part C program during the reporting period, as reported in the State’s Part C exiting data under Section 618 of the IDEA; and (2) the number of those infants and toddlers who did not receive early intervention services for at least six months before exiting the Part C program.

Describe the results of the calculations and compare the results to the targets. States will use the progress categories for each of the three Outcomes to calculate and report the two Summary Statements.

Report progress data and calculate Summary Statements to compare against the six targets. Provide the actual numbers and percentages for the five reporting categories for each of the three Outcomes.

In presenting results, provide the criteria for defining “comparable to same-aged peers.” If a State is using the Early Childhood Outcomes Center (ECO) Child Outcomes Summary Process (COS), then the criteria for defining “comparable to same-aged peers” has been defined as a child who has been assigned a score of 6 or 7 on the COS.

In addition, list the instruments and procedures used to gather data for this indicator, including if the State is using the ECO COS.

If the State’s Part C eligibility criteria include infants and toddlers who are at risk of having substantial developmental delays (or “at-risk infants and toddlers”) under IDEA section 632(5)(B)(i), the State must report data in two ways. First, it must report on all eligible children but exclude its at-risk infants and toddlers (i.e., include just those infants and toddlers experiencing developmental delay (or “developmentally delayed children”) or having a diagnosed physical or mental condition that has a high probability of resulting in developmental delay (or “children with diagnosed conditions”)). Second, the State must separately report outcome data on either: (1) just its at-risk infants and toddlers; or (2) aggregated performance data on all of the infants and toddlers it serves under Part C (including developmentally delayed children, children with diagnosed conditions, and at-risk infants and toddlers).

## 3 - Indicator Data

Does your State's Part C eligibility criteria include infants and toddlers who are at risk of having substantial developmental delays (or “at-risk infants and toddlers”) under IDEA section 632(5)(B)(i)? (yes/no)

NO

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices is included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input has been gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

Historical Data

| Outcome | Baseline | FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A1 | 2015 | Target>= | 85.40% | 85.40% | 85.60% | 85.80% | 86.00% |
| A1 | 84.89% | Data | 85.92% | 87.84% | 85.90% | 85.89% | 86.14% |
| A2 | 2015 | Target>= | 42.30% | 42.30% | 42.50% | 42.70% | 42.90% |
| A2 | 41.00% | Data | 38.54% | 43.74% | 43.07% | 39.84% | 40.01% |
| B1 | 2015 | Target>= | 66.70% | 66.70% | 67.90% | 68.10% | 68.30% |
| B1 | 66.42% | Data | 61.98% | 61.58% | 60.34% | 63.29% | 63.29% |
| B2 | 2015 | Target>= | 36.00% | 36.00% | 36.20% | 36.40% | 36.60% |
| B2 | 35.69% | Data | 31.72% | 34.24% | 33.65% | 31.69% | 31.68% |
| C1 | 2015 | Target>= | 77.80% | 77.80% | 78.00% | 78.20% | 78.40% |
| C1 | 77.28% | Data | 74.85% | 74.22% | 71.66% | 70.79% | 71.74% |
| C2 | 2015 | Target>= | 40.60% | 40.60% | 40.80% | 40.80% | 41.20% |
| C2 | 40.33% | Data | 33.87% | 36.36% | 35.45% | 33.32% | 33.32% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target A1>= | 86.20% | 86.40% |
| Target A2>= | 43.10% | 43.30% |
| Target B1>= | 68.50% | 68.70% |
| Target B2>= | 36.80% | 37.00% |
| Target C1>= | 78.60% | 78.80% |
| Target C2>= | 41.40% | 41.60% |

Outcome A: Positive social-emotional skills (including social relationships)

| Outcome A Progress Category | Number of children | Percentage of Total |
| --- | --- | --- |
| a. Infants and toddlers who did not improve functioning | 51 | 1.77% |
| b. Infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers | 282 | 9.79% |
| c. Infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it | 1,367 | 47.47% |
| d. Infants and toddlers who improved functioning to reach a level comparable to same-aged peers | 856 | 29.72% |
| e. Infants and toddlers who maintained functioning at a level comparable to same-aged peers | 324 | 11.25% |

| Outcome A | Numerator | Denominator | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A1. Of those children who entered or exited the program below age expectations in Outcome A, the percent who substantially increased their rate of growth by the time they turned 3 years of age or exited the program | 2,223 | 2,556 | 86.14% | 86.20% | 86.97% | Met target | No Slippage |
| A2. The percent of infants and toddlers who were functioning within age expectations in Outcome A by the time they turned 3 years of age or exited the program | 1,180 | 2,880 | 40.01% | 43.10% | 40.97% | Did not meet target | No Slippage |

Outcome B: Acquisition and use of knowledge and skills (including early language/communication)

| Outcome B Progress Category | Number of Children | Percentage of Total |
| --- | --- | --- |
| a. Infants and toddlers who did not improve functioning | 43 | 1.49% |
| b. Infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers | 895 | 31.08% |
| c. Infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it | 930 | 32.29% |
| d. Infants and toddlers who improved functioning to reach a level comparable to same-aged peers | 539 | 18.72% |
| e. Infants and toddlers who maintained functioning at a level comparable to same-aged peers | 473 | 16.42% |

| Outcome B | Numerator | Denominator | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B1. Of those children who entered or exited the program below age expectations in Outcome B, the percent who substantially increased their rate of growth by the time they turned 3 years of age or exited the program | 1,469 | 2,407 | 63.29% | 68.50% | 61.03% | Did not meet target | Slippage |
| B2. The percent of infants and toddlers who were functioning within age expectations in Outcome B by the time they turned 3 years of age or exited the program | 1,012 | 2,880 | 31.68% | 36.80% | 35.14% | Did not meet target | No Slippage |

Provide reasons for B1 slippage, if applicable

Slippage occurred may be attributed to lack of tiered supports to special education staff and administrators connecting the assessment tool to child outcomes data and improvement activities; Additional factors include varied implementation of quality home visiting models, limited coaching capacity to improve family or caregiver coaching, minimal improvement activities system-wide targeting cognitive, communication, and early literacy domains with this age group during routines and daily activities, and an increase in staff turnover and personnel shortages system-wide.

Outcome C: Use of appropriate behaviors to meet their needs

| Outcome C Progress Category | Number of Children | Percentage of Total |
| --- | --- | --- |
| a. Infants and toddlers who did not improve functioning | 32 | 1.11% |
| b. Infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers | 696 | 24.17% |
| c. Infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it | 1,156 | 40.14% |
| d. Infants and toddlers who improved functioning to reach a level comparable to same-aged peers | 712 | 24.72% |
| e. Infants and toddlers who maintained functioning at a level comparable to same-aged peers | 284 | 9.86% |

| Outcome C | Numerator | Denominator | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| C1. Of those children who entered or exited the program below age expectations in Outcome C, the percent who substantially increased their rate of growth by the time they turned 3 years of age or exited the program | 1,868 | 2,596 | 71.74% | 78.60% | 71.96% | Did not meet target | No Slippage |
| C2. The percent of infants and toddlers who were functioning within age expectations in Outcome C by the time they turned 3 years of age or exited the program | 996 | 2,880 | 33.32% | 41.40% | 34.58% | Did not meet target | No Slippage |

FFY 2024 SPP/APR Data

The number of infants and toddlers who did not receive early intervention services for at least six months before exiting the Part C program.

| Question | Number |
| --- | --- |
| The number of infants and toddlers who exited the Part C program during the reporting period, as reported in the State’s Part C exiting 618 data. | 3,771 |
| The number of those infants and toddlers who did not receive early intervention services for at least six months before exiting the Part C program. | 1,134 |
| Number of infants and toddlers with IFSPs assessed. | 2,880 |

| Sampling Question | Yes / No |
| --- | --- |
| Was sampling used? | NO |

Did you use the Early Childhood Outcomes Center (ECO) Child Outcomes Summary (COS) process? (yes/no)

NO

Provide the criteria for defining “comparable to same-aged peers.”

Beginning in 2008 for all children qualifying for early childhood special education services, all State EI/ECSE programs are required to enter the child Assessment, Evaluation, and Programming System (AEPS) data into the Early Childhood Web (ecWeb) system, starting with all children qualifying for early childhood special education services in May of 2008.

Criteria for defining “comparable to same-aged peers":

In 2015, using a national AEPS data set from typically developing children, a review team considered 90%, 85%, and 80% percentile cut offs against the national data results to decide the cut off level that best reflected the State’s children in ECSE programs. The review team, State staff, EI/ECSE Contractors and EI/ECSE stakeholder groups were all asked to analyze the percentile cut offs and determine the cut off level that the State should use for reporting to the ECSE child outcomes. The consensus was to use the 80% cut off level. This most closely represents the children who are eligible for Early Childhood Special Education programs and receive services in Oregon.

Child progress is measured using the following rubric:

If a child enters service with a score below the normal range and stays the same or regresses at the next test administration, the child is categorized as: (a) does not improve functioning. If the child makes progress and the ratio of how far below the normal level of development increases between test administrations, the child is categorized as: (b) improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers. If the child makes progress but the ratio of how far below the normal level of development decreases between test administrations, the child is categorized as: (c) improved functioning to a level nearer to the functioning of same-aged peers but did not reach it. If a child enters services with a score below the normal range and increases to reach or exceed the normal range at the next test administration, the child is categorized as: (d) improved functioning sufficient to reach a level comparable to same-aged peers. If a child enters with a score at or above the normal range and maintains their score at or above the normal range at the next test administration, the child is categorized as: (e) maintains functioning at or above same age peers.

List the instruments and procedures used to gather data for this indicator.

As of 2008, all EI/ECSE programs in the State are required to enter individual child assessment results from the Assessment, Evaluation, and Programming System (AEPS) into the Early Childhood Web (ecWeb). The aggregate results are utilized for reporting on this indicator.

Provide additional information about this indicator (optional).

## 3 - Prior FFY Required Actions

None

## 3 - OSEP Response

## 3 - Required Actions

# Indicator 4: Family Involvement

Instructions and Measurement

Monitoring Priority: Early Intervention Services In Natural Environments

Results indicator: Percent of families participating in Part C who report that early intervention services have helped the family:

A. Know their rights;

B. Effectively communicate their children's needs; and

C. Help their children develop and learn.

(20 U.S.C. 1416(a)(3)(A) and 1442)

Data Source

State selected data source. State must describe the data source in the SPP/APR.

Measurement

A. Percent = [(# of respondent families participating in Part C who report that early intervention services have helped the family know their rights) divided by the (# of respondent families participating in Part C)] times 100.

B. Percent = [(# of respondent families participating in Part C who report that early intervention services have helped the family effectively communicate their children’s needs) divided by the (# of respondent families participating in Part C)] times 100.

C. Percent = [(# of respondent families participating in Part C who report that early intervention services have helped the family help their children develop and learn) divided by the (# of respondent families participating in Part C)] times 100.

Instructions

Sampling of families participating in Part C is allowed. When sampling is used, submit a description of the sampling methodology outlining how the design will yield valid and reliable estimates. (See General Instructions page 2 for additional instructions on sampling.)

Provide the actual numbers used in the calculation.

Describe the results of the calculations and compare the results to the target.

While a survey is not required for this indicator, a State using a survey must submit a copy of any new or revised survey with its SPP/APR.

Report the number of families to whom the surveys were distributed and the number of respondent families participating in Part C. The survey response rate is auto calculated using the submitted data.

States will be required to compare the current year’s response rate to the previous year(s) response rate(s) and describe strategies that will be implemented which are expected to increase the response rate year over year, particularly for those groups that are underrepresented.

The State must also analyze the response rate to identify potential nonresponse bias and take steps to reduce any identified bias and promote response from a broad cross section of families that received Part C services.

Include the State’s analysis of the extent to which the demographics of the infants or toddlers for whom families responded are representative of the demographics of infants and toddlers receiving services in the Part C program. States should consider categories such as race/ethnicity, age of infant or toddler, and geographic location in the State.

States must describe the metric used to determine representativeness (e.g., +/- 3% discrepancy in the proportion of responders compared to target group).

If the analysis shows that the demographics of the infants or toddlers for whom families responded are not representative of the demographics of infants and toddlers receiving services in the Part C program, describe the strategies that the State will use to ensure that in the future the response data are representative of those demographics. In identifying such strategies, the State should consider factors such as how the State distributed the survey to families (e.g., by mail, by e-mail, on-line, by telephone, in-person), if a survey was used, and how responses were collected.

When reporting the extent to which the demographics of the infants or toddlers for whom families responded are representative of the demographics of infants and toddlers enrolled in the Part C program, States must include race/ethnicity in its analysis. In addition, the State’s analysis must also include at least one of the following demographics: socioeconomic status, parents, or guardians whose primary language is other than English and who have limited English proficiency, maternal education, geographic location, and/or another demographic category approved through the stakeholder input process.

States are encouraged to work in collaboration with their OSEP-funded parent centers in collecting data.

## 4 - Indicator Data

Historical Data

| Measure | Baseline | FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 2014 | Target>= | 91.00% | 89.52% | 89.92% | 90.31% | 90.71% |
| A | 89.63% | Data | 89.44% | 90.63% | 86.41% | 91.26% | 91.19% |
| B | 2014 | Target>= | 91.00% | 91.29% | 91.63% | 91.97% | 92.32% |
| B | 89.50% | Data | 91.30% | 93.75% | 92.23% | 92.31% | 90.67% |
| C | 2014 | Target>= | 93.09% | 91.27% | 91.72% | 92.16% | 92.61% |
| C | 92.09% | Data | 91.25% | 90.63% | 90.29% | 90.56% | 91.71% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target A>= | 91.10% | 91.50% |
| Target B>= | 92.66% | 93.00% |
| Target C>= | 93.05% | 93.50% |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices are included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input has been gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

FFY 2024 SPP/APR Data

| The number of families to whom surveys were distributed | 1,456 |
| --- | --- |
| Number of respondent families participating in Part C | 247 |
| Survey Response Rate | 16.96% |
| A1. Number of respondent families participating in Part C who report that early intervention services have helped the family know their rights | 221 |
| A2. Number of responses to the question of whether early intervention services have helped the family know their rights | 247 |
| B1. Number of respondent families participating in Part C who report that early intervention services have helped the family effectively communicate their children's needs | 227 |
| B2. Number of responses to the question of whether early intervention services have helped the family effectively communicate their children's needs | 247 |
| C1. Number of respondent families participating in Part C who report that early intervention services have helped the family help their children develop and learn | 222 |
| C2. Number of responses to the question of whether early intervention services have helped the family help their children develop and learn | 247 |

| Measure | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- |
| A. Percent of families participating in Part C who report that early intervention services have helped the family know their rights (A1 divided by A2) | 91.19% | 91.10% | 89.47% | Did not meet target | Slippage |
| B. Percent of families participating in Part C who report that early intervention services have helped the family effectively communicate their children's needs (B1 divided by B2) | 90.67% | 92.66% | 91.90% | Did not meet target | No Slippage |
| C. Percent of families participating in Part C who report that early intervention services have helped the family help their children develop and learn (C1 divided by C2) | 91.71% | 93.05% | 89.88% | Did not meet target | Slippage |

Provide reasons for part A slippage, if applicable

Slippage may be due to the configuration of the counties selected this year as part of the sampling plan. The State does not survey each program every year. The State determined that the difference in the rates this year compared to last year could be due to different counties surveyed in the sampling plan.

Given the decreases in scores, the State examined whether the decrease was specific to particular counties when they were last surveyed two years ago. The State created a spreadsheet to show which counties had the largest/smallest difference in their Indicator 4 rates, to determine whether any follow-up was warranted. In addition, each county receives a report of its results over time, so it can be observed whether its Indicator 4 rates have decreased/increased/stayed the same.

Provide reasons for part C slippage, if applicable

Slippage may be due to the configuration of the counties selected this year as part of the sampling plan. The State does not survey each program every year. The State determined that the difference in the rates this year compared to last year could be due to different counties surveyed in the sampling plan.

Given the decreases in scores, the State examined whether the decrease was specific to particular counties when they were last surveyed two years ago. The State created a spreadsheet to show which counties had the largest/smallest difference in their Indicator 4 rates, to determine whether any follow-up was warranted. In addition, each county receives a report of its results over time, so it can be observed whether its Indicator 4 rates have decreased/increased/stayed the same.

| Sampling Question | Yes / No |
| --- | --- |
| Was sampling used? | YES |
| If yes, has your previously approved sampling plan changed? | NO |

Describe the sampling methodology outlining how the design will yield valid and reliable estimates.

The sampling methodology is designed to choose a representative set of counties each year that is reflective of the State’s population as a whole, with counties following an every-other-year rotation. For counties that have more than 100 children with disabilities receiving services, a sample of children is selected for their families  to receive the survey. This sample is stratified by county, program, age, race/ethnicity, gender, primary disability, and language to ensure representativeness within each county.

| Question | Yes / No |
| --- | --- |
| Was a collection tool used? | YES |
| If yes, is it a new or revised collection tool? | NO |

Response Rate

| FFY | 2023 | 2024 |
| --- | --- | --- |
| Survey Response Rate | 15.23% | 16.96% |

Describe the metric used to determine representativeness (e.g., +/- 3% discrepancy in the proportion of responders compared to target group).

+/- 3% discrepancy in the proportion of responders compared to the population of a given target group

Include the State’s analysis of the extent to which the demographics of the infants or toddlers for whom families responded are representative of the demographics of infants and toddlers enrolled in the Part C program. States should consider categories such as race/ethnicity, age of infant or toddler, and geographic location in the State. States must include race/ethnicity in their analysis. In addition, the State’s analysis must include at least one of the following demographics: socioeconomic status, parents, or guardians whose primary language is other than English and who have limited English proficiency, maternal education, geographic location, and/or another category approved through the stakeholder input process.

The State compared the representation by race/ethnicity and primary disability in the population to the representation among respondents, using a +/- 3% criterion to identify over- or under-representation.

Using this methodology, no differences were found by disability. All disability groups were within +/- 3% of the population. One difference was found by race/ethnicity. The population consists of 57% White students, whereas the respondents comprised 60% White students. All of the racial/ethnic categories were within +/- 3% of the population. Families from a wide range of counties across the State responded to the survey and results are weighted by county to ensure that the family survey results reflect the geographic distribution of families. Due to the differences in race/ethnicity, the State concludes that the results are not representative.

The demographics of the infants or toddlers for whom families responded are representative of the demographics of infants and toddlers enrolled in the Part C program. (yes/no)

NO

If no, describe the strategies that the State will use to ensure that in the future the response data are representative of those demographics.

The State will be revising it's outreach materials to be family-friendly and easy for programs to personalize. The outreach materials will continue to be translated into multiple languages. The State will also hold parent survey informational sessions in Spanish in collaboration with the Parent Training and Information Center (PTIC). The State will collaborate with local programs to send out reminders to families.

Describe strategies that will be implemented which are expected to increase the response rate year over year, particularly for those groups that are underrepresented.

The State held a series of feedback sessions with families, community partners, program directors, and providers to gather feedback on the survey materials and process. The goal was to determine ways to increase the response rate and ensure the results are representative. Based on feedback from those sessions, the State is making several changes, with an emphasis on updating outreach materials to be more family-friendly, culturally responsive, and easier for programs to personalize. Additional changes include modifying some survey questions, rewording the cover letter, providing clear information for families about the text message they will receive, and coordinating outreach efforts with the Parent Training and Information Center (PTIC).

Survey results show white children are overrepresented compared to population data. To address this and better reflect all children, the state will introduce more culturally responsive outreach materials. The materials, including flyers and social media graphics, will feature images of diverse children, use simplified language, and be translated into 13 languages. The State will partner with the PTIC to offer Spanish informational sessions and encourage programs to share survey information with families via trusted messengers.

Describe the analysis of the response rate including any nonresponse bias that was identified, and the steps taken to reduce any identified bias and promote response from a broad cross section of families that received Part C services.

Nonresponse bias measures the differences in opinions between respondents and non-respondents in meaningful ways, such as the positivity of responses. A few factors can be examined to determine nonresponse bias. One is the overall response rate. The higher the response rate, the less likely nonresponse bias is to occur. The response rate is 16.96%, which is higher than last year’s response rate of 15.23%. However, it is possible that families who did not respond differ in some measurable way in their level of positivity from those who did. Therefore, the State examined nonresponse bias by comparing representativeness and survey response rates for earlier versus later responses.

When the representativeness of the responses was examined, no differences were found by disability; however, one difference was found by race/ethnicity. The three measure scores showed no differences by race/ethnicity. Despite results being weighted by county to ensure that the family survey results reflect the population of families in terms of geographic distribution, the lack of representativeness by race/ethnicity indicates possible nonresponse bias in the response rate.

The survey response rates for earlier versus later respondents were also examined. It is possible that respondents who do not immediately respond to the survey differ in some measurable way from those who do. Therefore, the responses of families who responded early in the process were compared with those who responded later. The results showed no statistically significant differences between families who responded earlier and families who responded later. However, due to the differences in response rates by race/ethnicity, the State concludes that nonresponse bias might be present.

Analysis of the survey results shows that white children are overrepresented compared to population data. The state is taking several steps to reduce potential bias arising from the lack of racial and ethnic representation. This includes updating outreach efforts to be more culturally responsive. Outreach materials, including flyers and social media graphics, have been updated to feature images of diverse children, use simplified language, and have been translated into 13 languages.  The State is encouraging programs to share survey information with families via trusted messengers. Additionally, the State is partnering with the Parent Training and Information Center to advertise the survey and do targeted outreach (e.g., Spanish informational sessions).

Provide additional information about this indicator (optional).

## 4 - Prior FFY Required Actions

None

## 4 - OSEP Response

## 4 - Required Actions

In the FFY 2025 SPP/APR, the State must report whether its FFY 2025 response data are representative of the demographics of infants, toddlers, and families enrolled in the Part C program, and, if not, the actions the State is taking to address this issue. The State must also include its analysis of the extent to which the demographics of the families responding are representative of the population.

# Indicator 5: Child Find (Birth to One)

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Child Find

Results indicator: Percent of infants and toddlers birth to 1 with IFSPs.

(20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Same data as used for reporting to the Department under section 618 of the IDEA, using the definitions in EDFacts file specification FS902 and Census (for the denominator).

Measurement

Percent = [(# of infants and toddlers birth to 1 with IFSPs) divided by the (population of infants and toddlers birth to 1)] times 100.

Instructions

Sampling from the State’s 618 data is not allowed.

Describe the results of the calculations. The data reported in this indicator should be consistent with the State’s reported 618 data reported in Table 1. If not, explain why.

The State should conduct a root cause analysis of child find identification rates, including reviewing data (if available) on the number of children referred, evaluated, and identified. This analysis may include examining not only demographic data but also other child-find related data available to the State (e.g., geographic location, family income, primary language, etc.). The State should report the results of this analysis. If the State is required to report on the reasons for slippage, the State must include the results of its analyses.

## 5 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 0.75% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target >= | 0.80% | 0.80% | 0.81% | 0.81% | 0.82% |
| Data | 1.04% | 0.78% | 0.94% | 1.02% | 0.96% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target >= | 0.82% | 0.83% |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The state collaborates with the Oregon Pediatric Improvement Partnership (OPIP) to enhance coordination and outreach with medical providers, supporting Child Find efforts. Collaboration includes ongoing updates and promotion of the Universal Referral Form (URF) to streamline medical referrals to EI/ECSE. Additionally, the state sought input from OPIP and other medical and mental health experts, including the Oregon Infant Mental Health Association (ORIMHA), Early Hearing Detection and Intervention (EHDI), and partners within the Oregon Health Authority (OHA), to update the Diagnosed Physical and Mental Conditions in Early Intervention document for Oregon.

The state coordinates a bi-monthly Community of Practice (COP) for Referral and Intake Coordinators to support Child Find efforts. During COP meetings, participants review current data on state and regional referral rates and provide feedback on Child Find processes. The COP also includes facilitated discussions with state partners in Child Find (e.g., child welfare, OPIP) to address barriers and solutions to the referral and intake process. Additionally, the state engages in quarterly reviews of Child Find referral data with EI/ECSE Directors. COP and EI/ECSE Director input is utilized to make updates to referral and intake practices.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

Prepopulated Data

| Source | Date | Description | Data |
| --- | --- | --- | --- |
| SY 2024-25 IDEA Part C Child Count - Infants and Toddlers with Disabilities (EDFacts file spec FS902; Data group 5023) | 07/30/2025 | Number of infants and toddlers birth to 1 with IFSPs | 401 |
| Annual State Resident Population Estimates for 6 Race Groups (5 Race Alone Groups and Two or More Races) by Age, Sex, and Hispanic Origin: April 1, 2020 to July 1, 2024 | 06/03/2025 | Population of infants and toddlers birth to 1 | 38,672 |

FFY 2024 SPP/APR Data

| Number of infants and toddlers birth to 1 with IFSPs | Population of infants and toddlers birth to 1 | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 401 | 38,672 | 0.96% | 0.82% | 1.04% | Met target | No Slippage |

Provide results of the root cause analysis of child find identification rates

N/A

Provide additional information about this indicator (optional)

## 5 - Prior FFY Required Actions

None

## 5 - OSEP Response

## 5 - Required Actions

# Indicator 6: Child Find (Birth to Three)

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Child Find

Results indicator: Percent of infants and toddlers birth to 3 with IFSPs.

(20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Same data as used for reporting to the Department under section 618 of the IDEA, using the definitions in EDFacts file specification FS902 and Census (for the denominator).

Measurement

Percent = [(# of infants and toddlers birth to 3 with IFSPs) divided by the (population of infants and toddlers birth to 3)] times 100.

Instructions

Sampling from the State’s 618 data is not allowed.

Describe the results of the calculations. The data reported in this indicator should be consistent with the State’s reported 618 data reported in Table 1. If not, explain why.

The State should conduct a root cause analysis of child find identification rates, including reviewing data (if available) on the number of children referred, evaluated, and identified. This analysis may include examining not only demographic data but also other child-find related data available to the State (e.g. geographic location, family income, primary language, etc.). The State should report the results of this analysis. If the State is required to report on the reasons for slippage, the State must include the results of its analysis.

## 6 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 1.78% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target >= | 2.40% | 2.40% | 2.50% | 2.50% | 2.60% |
| Data | 3.27% | 2.58% | 3.00% | 3.38% | 3.53% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target >= | 2.60% | 2.70% |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices is included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input has been gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

Prepopulated Data

| Source | Date | Description | Data |
| --- | --- | --- | --- |
| SY 2024-25 IDEA Part C Child Count - Infants and Toddlers with Disabilities (EDFacts file spec FS902; Data group 5023) | 07/30/2025 | Number of infants and toddlers birth to 3 with IFSPs | 3,915 |
| Annual State Resident Population Estimates for 6 Race Groups (5 Race Alone Groups and Two or More Races) by Age, Sex, and Hispanic Origin: April 1, 2020 to July 1, 2024 | 06/03/2025 | Population of infants and toddlers birth to 3 | 119,133 |

FFY 2024 SPP/APR Data

| Number of infants and toddlers birth to 3 with IFSPs | Population of infants and toddlers birth to 3 | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 3,915 | 119,133 | 3.53% | 2.60% | 3.29% | Met target | No Slippage |

Provide results of the root cause analysis of child find identification rates

In reviewing child find efforts, it was determined that the following processes are in place and being utilized accordingly.

The EI/ECSE contractor has joint responsibility with school districts to locate, identify, and evaluate all children birth up to age of eligibility for public school residing within its jurisdiction, suspected of being eligible for early intervention (EI) or early childhood special education (ECSE). This ongoing system applies to all children with disabilities, regardless of the severity of their disabilities, including children who are:

1.	Highly mobile children with disabilities (such as migrant children and children who are experiencing homelessness

2.	Children who are wards of the state

3.	Preschool children who reside on reservations

4.	Children below the age of compulsory school attendance who are not enrolled in a public or private program

5.	Attending private (religious or secular) preschool located within the boundaries of each EI/ECSE contractor area.

6.	Children under the age of three who

a. Are involved in a substantiated case of abuse or neglect; or

b. Are identified as affected by illegal substance abuse or withdrawal symptoms resulting from prenatal drug exposure.

The joint EI/ECSE and school district responsibilities are:

1. Conducting public awareness activities including announcements on television, radio, or newspaper; presentations at community meetings; and outreach to those who may not understand English, who may move frequently, or who may live in rural or isolated areas

2. Disseminating materials to parents on the availability of EI/ECSE services including how to make a referral and how to obtain an eligibility evaluation for EI/ECSE services. This includes materials for reaching non-English speaking families

3. Developing communication links with various agencies that provide services to children who may be eligible for EI/ECSE within the community, including the dissemination of child find materials including but not limited to hospitals, clinics, public health agencies, pediatricians, pediatric nurses, Head Start, Early Head Start, Preschool Promise, Baby Promise, community preschools, child care providers and social service professionals involved in family or child services; and

4. Publishing notices, before any major child find activity, informing parents that confidentiality requirements apply to these activities. Circulation for this notice must be adequate to inform parents within the EI/ECSE program’s and district’s jurisdiction.

Local school districts are responsible, financially and legally, for EI/ECSE eligibility evaluations. School districts may contract with the local EI/ECSE program or other entity for fulfilling these requirements. Evaluating children for EI/ECSE eligibility includes:

1. Administering assessments, scoring tests, interpreting evaluation scores, conducting child observations, gathering developmental histories, conducting parent interviews and writing evaluation reports.

2. Evaluating children referred for an EI eligibility evaluation within 45 calendar days (45 days from confirming valid referral to IFSP).

3. Evaluating children referred for an ECSE eligibility evaluation within 60 school days from parent consent for an evaluation.

4. Conducting ECSE eligibility evaluations for children enrolled in EI and approaching their third birthday (OAR 581-015-2805).

Local EI/ECSE programs are responsible for providing a referral and evaluation process in each county, including:

1. Providing a year-round primary contact who receives referrals for children suspected of being eligible for EI/ECSE services.

2. Assuring that all children referred as suspected of having a disability are referred to the child’s local school district (or agency contracted by the district) for EI/ECSE eligibility evaluations.

3. Assisting in local school districts’ responsibility for eligibility evaluations for EI services within 45 calendar days from referral and for ECSE within 60 school days of parent consent for evaluation, by helping form evaluation consortia through district contracts with ESD’s or other sources.

4. Convening eligibility teams to determine eligibility for EI or ECSE services.

5. Assuring eligibility determinations are conducted in compliance with applicable federal and State of Oregon statutes, regulations and guidelines.

6. Referring children who are eligible for EI/ECSE services to the county’s EI/ECSE program for the development of the Individual Family Service Plan (IFSP) and placement in appropriate services.

7. Assuring child find materials are disseminated to reach non-English speaking families and are available in locations frequented by families of young children.

8. Staff Awareness. A system in each school in the EI/ECSE area and school districts to ensure that:

-District and EI/ECSE staff are knowledgeable of the characteristics of disabilities and appropriate referral of children suspected of having disabilities; and

-Early intervention and early childhood special education referrals from parents, teachers, and others are directed to appropriate EI/ECSE staff.

-Staff Awareness of Community Partners: The EI/ECSE contractor and school district provide information about and EI and ECSE services and the referral process to facilities in the EI/ECSE contractor area including child care centers, preschools, homeless shelters, group homes, hospitals, Head Start, Oregon Pre-Kindergarten, Preschool Promise, Migrant/Seasonal Head Start, Migrant education programs, Early Head Start, Even Start, Tribal Head Start and other facilities that serve children birth to five years old.

9. Interagency Agreements with the Department of Human Services: The Oregon Department of Education and each EI/ECSE Contractor establish and maintain interagency agreements addressing the requirements “Child Abuse Prevention and Treatment Act” (CAPTA).

Provide additional information about this indicator (optional).

## 6 - Prior FFY Required Actions

None

## 6 - OSEP Response

## 6 - Required Actions

# Indicator 7: 45-Day Timeline

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Child Find

Compliance indicator: Percent of eligible infants and toddlers with IFSPs for whom an initial evaluation and initial assessment and an initial IFSP meeting were conducted within Part C’s 45-day timeline. (20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Data to be taken from monitoring or State data system and must address the timeline from point of referral to initial IFSP meeting based on actual, not an average, number of days.

Measurement

Percent = [(# of eligible infants and toddlers with IFSPs for whom an initial evaluation and initial assessment and an initial IFSP meeting were conducted within Part C’s 45-day timeline) divided by the (# of eligible infants and toddlers evaluated and assessed for whom an initial IFSP meeting was required to be conducted)] times 100.

Account for untimely evaluations, assessments, and initial IFSP meetings, including the reasons for delays.

Instructions

If data are from State monitoring, describe the method used to select EIS programs for monitoring. If data are from a State database, describe the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period) and how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

Targets must be 100%.

Describe the results of the calculations and compare the results to the target. Describe the method used to collect these data and if data are from the State’s monitoring, describe the procedures used to collect these data. Provide actual numbers used in the calculation.

States are not required to report in their calculation the number of children for whom the State has identified the cause for the delay as exceptional family circumstances, as defined in 34 CFR §303.310(b), documented in the child’s record. If a State chooses to report in its calculation children for whom the State has identified the cause for the delay as exceptional family circumstances documented in the child’s record, the numbers of these children are to be included in the numerator and denominator. Include in the discussion of the data the numbers the State used to determine its calculation under this indicator and report separately the number of documented delays attributable to exceptional family circumstances.

Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in OSEP’s response for the previous SPP/APR. If the State did not ensure timely correction of the previous noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance, methods to ensure correction, and any enforcement actions that were taken.

If the State reported less than 100% compliance for the previous reporting period (e.g., for the FFY 2024 SPP/APR, the data for FFY 2023), and the State did not identify any findings of noncompliance, provide an explanation of why the State did not identify any findings of noncompliance.

If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), the explanation within each applicable indicator must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

## 7 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 99.40% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data | 99.23% | 96.67% | 96.25% | 95.03% | 94.66% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

FFY 2024 SPP/APR Data

| Number of eligible infants and toddlers with IFSPs for whom an initial evaluation and assessment and an initial IFSP meeting was conducted within Part C’s 45-day timeline | Number of eligible infants and toddlers evaluated and assessed for whom an initial IFSP meeting was required to be conducted | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 2,861 | 3,658 | 94.66% | 100% | 97.81% | Did not meet target | No Slippage |

Number of documented delays attributable to exceptional family circumstances

This number will be added to the "Number of eligible infants and toddlers with IFSPs for whom an initial evaluation and assessment and an initial IFSP meeting was conducted within Part C's 45-day timeline" field above to calculate the numerator for this indicator.

717

Provide reasons for delay, if applicable.

For FFY 2024, a total of 797 incidents of delay of services occurred. The reasons for delay for 717 incidents were attributable to exceptional family circumstances and have been reported accordingly online. The reasons for the remaining 80 delays are listed below:

• 2 incidents due to staff communication problems

• 1 incident due to staff illness

• 5 incidents due to full evaluation schedule due to staff shortage

• 4 incidents due to data entry/clerical errors

• 14 incidents due to staff unavailability

• 6 incidents due to program delay in contacting family due to staff shortage

• 24 Provider delay in scheduling eligibility, evaluation, or IFSP

• 24 incidents due to delay from out of state or district providers

What is the source of the data provided for this indicator?

State database

Provide the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period).

July 2024-June 2025

Describe how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

The data accurately reflects data for infants and toddlers with IFSPs for the full reporting period. The State calculated the percentage using aggregated data collected monthly from all EI/ECSE programs in the state. Each monthly data report represents all children in the EI referral process from the second day of the previous month to the first day of the current month. Programs submit data completion status of EI evaluations, eligibility, and initial IFSP meeting each month. Of those children, programs must document: (1) how many completed the process within 45 days of referral; (2) how many completed the process but not within 45 days of referral (these programs must submit a corrective action plan); (3) how many have not completed the process; and (4) how many discontinued the process and why.

Provide additional information about this indicator (optional).

Correction of Findings of Noncompliance Identified in FFY 2023

| Findings of Noncompliance Identified | Findings of Noncompliance Verified as Corrected Within One Year | Findings of Noncompliance Subsequently Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |
| 202 | 202 | 0 | 0 |

FFY 2023 Findings of Noncompliance Verified as Corrected

Describe how the State verified that the source of noncompliance is correctly implementing the regulatory requirements.

For FFY 2023, the State verified that EI/ECSE programs were correctly implementing the regulatory requirements by having the programs continue to submit monthly corrective action plans (CAPs) to the State for any child for whom the 45-day timeline was not met. Included in the CAP that programs submitted: 1) the number of days needed to complete the referral, eligibility and initial IFSP meeting; 2) the child’s initials and birth date; 3) the specific reasons for not meeting the 45-day timeline (parent delay or program delay); 4) the corrective actions based on an analysis of the problem(s); 5) the activities planned to address each problem identified and 6) request for ODE technical assistance if desired.

The programs with noncompliance developed and implemented CAPs detailing solutions for 100% (202/202) correction of noncompliance for each individual case and submitted these to the State for review and approval. The CAPs included working with school districts to hire additional evaluators, staff training, hiring new intake coordinators, and implementing an automatic notification system to alert staff of pending timelines for scheduling. The State reviewed and approved all 202 individual CAPs submitted. An email was sent to each program stating ODE review and verification of each case of noncompliance.

The State verified as per OSEP QA 23-01 that all programs with past noncompliance were correctly implementing the regulatory requirements of 34 CFR §§303.310(a) and 303.342(a) based on updated monthly 45-day timeline data from each program. The state summarized continued new monthly CAP data for each program detailing no new cases over the 45-day timeline or only CAPs with parent delays. Subsequent individual evaluations were also reviewed by the State in ecWeb, the State IFSP database, and confirmed subsequent timely evaluations.

Describe how the State verified that each individual case of noncompliance was corrected.

The State verified that 100% (202/202) of the individual incidents of noncompliance in FFY 2023 were corrected within one year. All programs with noncompliance conducted the initial evaluation, assessment, and IFSP meeting, although late, for each individual child for whom the 45-day timeline was not met based on a monthly State review and approved submitted individual Corrective Action Plans (CAPs) documenting each of the 202 cases of noncompliance were corrected to 100% (consistent with OSEP QA 23-01).

The programs with noncompliance developed and implemented individual CAPs detailing solutions for 100% (202/202) correction of noncompliance and submitted these to the State for review and approval. The CAPs included working with school districts to hire additional evaluators, staff training, hiring new intake coordinators, and implementing an automatic notification system to alert staff of pending timelines for scheduling. The State reviewed and approved all 202 CAPs submitted. An email was sent to each program stating ODE review and verification of each individual case of noncompliance.

The State verified as per OSEP QA 23-01 that all programs with past noncompliance were correctly implementing the regulatory requirements of 34 CFR §§303.310(a) and 303.342(a) based on updated monthly 45-day timeline data from each program. The State summarized continued new monthly CAP data for each program detailing no new cases over the 45-day timeline or only CAPs with parent delays. Subsequent evaluations were also reviewed by the State in ecWeb, the State IFSP database, and confirmed subsequent timely evaluations.

If procedures have been adopted that permit EIS program or providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), describe how, for instances of noncompliance discovered in FFY 2023, the State verified: (1) that the source of noncompliance is correctly implementing the regulatory requirements; and, (2) each individual case of noncompliance was corrected.

N/A

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 7 - Prior FFY Required Actions

Because the State reported less than 100% compliance for FFY 2023, the State must report on the status of correction of noncompliance identified in FFY 2023 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2024 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2023 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2024 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2023, although its FFY 2023 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2023. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

Response to actions required in FFY 2023 SPP/APR

## 7 - OSEP Response

## 7 - Required Actions

Because the State reported less than 100% compliance for FFY 2024, the State must report on the status of correction of noncompliance identified in FFY 2024 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2025 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2024 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2025 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2024, although its FFY 2024 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2024. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

# Indicator 8A: Early Childhood Transition

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Effective Transition

Compliance indicator: The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

A. Developed an IFSP with transition steps and services at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday;

B. Notified (consistent with any opt-out policy adopted by the State) the State educational agency (SEA) and the local educational agency (LEA) where the toddler resides at least 90 days prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services; and

C. Conducted the transition conference held with the approval of the family at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services.

(20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Data to be taken from monitoring or State data system.

Measurement

A. Percent = [(# of toddlers with disabilities exiting Part C at age 3 who have an IFSP with transition steps and services at least 90 days, and at the discretion of all parties not more than nine months, prior to their third birthday) divided by the (# of toddlers with disabilities exiting Part C at age 3)] times 100.

B. Percent = [(# of toddlers with disabilities exiting Part C where notification (consistent with any opt-out policy adopted by the State) to the SEA and LEA occurred at least 90 days prior to their third birthday for toddlers potentially eligible for Part B preschool services) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

C. Percent = [(# of toddlers with disabilities exiting Part C where the transition conference occurred at least 90 days, and at the discretion of all parties not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

Account for untimely transition planning under 8A, 8B, and 8C, including the reasons for delays.

Instructions

Indicators 8A, 8B, and 8C: Targets must be 100%.

Describe the results of the calculations and compare the results to the target. Describe the method used to collect these data. Provide the actual numbers used in the calculation.

Indicators 8A and 8C: If data are from the State’s monitoring, describe the procedures used to collect these data. If data are from State monitoring, also describe the method used to select EIS programs for monitoring. If data are from a State database, describe the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period) and how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

Indicators 8A and 8C: States are not required to report in their calculation the number of children for whom the State has identified the cause for the delay as exceptional family circumstances, as defined in 34 CFR §303.310(b), documented in the child’s record. If a State chooses to report in its calculation children for whom the State has identified the cause for the delay as exceptional family circumstances documented in the child’s record, the numbers of these children are to be included in the numerator and denominator. Include in the discussion of the data the numbers the State used to determine its calculation under this indicator and report separately the number of documented delays attributable to exceptional family circumstances.

Indicator 8A: The measurement is intended to capture those children exiting at age 3 for whom an IFSP must be developed with transition steps and services within the required timeline consistent with 34 CFR §303.209(d) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8B: Under 34 CFR §303.401(e), the State may adopt a written policy that requires the lead agency to provide notice to the parent of an eligible child with an IFSP of the impending notification to the SEA and LEA under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §303.209(b)(1) and (2) and permits the parent within a specified time period to “opt-out” of the referral. Under the State’s opt-out policy, the State is not required to include in the calculation under 8B (in either the numerator or denominator) the number of children for whom the parents have opted out. However, the State must include in the discussion of data the number of parents who opted out. In addition, any written opt-out policy must be on file with the Department of Education as part of the State’s Part C application under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §§303.209(b) and 303.401(d).

Indicator 8C: The measurement is intended to capture those children for whom a transition conference must be held within the required timeline consistent with 34 CFR §303.209(e) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8C: Do not include in the calculation but provide a separate number for those toddlers for whom the parent did not provide approval for the transition conference.

Indicators 8A, 8B, and 8C: Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in OSEP’s response for the previous SPP/APR. If the State did not ensure timely correction of the previous noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance, methods to ensure correction, and any enforcement actions that were taken.

If the State reported less than 100% compliance for the previous reporting period (e.g., for the FFY 2024 SPP/APR, the data for FFY 2023), and the State did not identify any findings of noncompliance, provide an explanation of why the State did not identify any findings of noncompliance.

If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), the explanation within each applicable indicator must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

## 8A - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 94.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data | 88.24% | 92.31% | 87.50% | 93.29% | 93.29% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

FFY 2024 SPP/APR Data

Data include only those toddlers with disabilities exiting Part C at age 3 for whom the Lead Agency was required to develop an IFSP with transition steps and services at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday. (yes/no)

YES

| Number of children exiting Part C who have an IFSP with transition steps and services | Number of toddlers with disabilities exiting Part C | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 138 | 152 | 93.29% | 100% | 92.11% | Did not meet target | Slippage |

Provide reasons for slippage, if applicable

The programs reported this was due to insufficient training and staffing issues as described below.

Number of documented delays attributable to exceptional family circumstances 
This number will be added to the “Number of children exiting Part C who have an IFSP with transition steps and services” field to calculate the numerator for this indicator.

2

Provide reasons for delay, if applicable.

The reasons were as follows:

Six incidents in which transition services were added more than nine months prior to the child’s third birthday. Program staff reported that this was due to insufficient staff training.

Two incidents in which transition services were added fewer than 90 days before the child’s third birthday. Program staff reported that this was due to staffing issues.

Four incidents in which no documentation was available to verify that transition conferences occurred. Program staff reported that these omissions resulted from insufficient training on documentation requirements.

What is the source of the data provided for this indicator?

State monitoring

Describe the method used to select EIS programs for monitoring.

The Oregon Department of Education (ODE) uses the System Performance Review and Improvement (SPR&I) process to select Early Intervention (EI) programs for annual monitoring. All programs receiving IDEA Part C funds participate in this statewide accountability system, which focuses on procedural compliance and performance on key federal and state indicators.

Each year, programs conduct a review of individual child records based on a number set by the State. Files are divided evenly between Early Intervention and Transition from Early Intervention and are selected to reflect the program’s population by race/ethnicity, disability, and gender using data from the most recent December 1 child count.

Programs enter compliance data into the SPR&I database, including timely transition planning and reasons for not meeting the required timeline. ODE reviews these data to evaluate compliance, verify correction of noncompliance, and identify areas for improvement. Through the SPR&I process, ODE and local programs work together to use data for continuous improvement and ensure timely, high-quality transition services for children and families.

Provide additional information about this indicator (optional).

Correction of Findings of Noncompliance Identified in FFY 2023

| Findings of Noncompliance Identified | Findings of Noncompliance Verified as Corrected Within One Year | Findings of Noncompliance Subsequently Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |
| 10 | 10 | 0 | 0 |

FFY 2023 Findings of Noncompliance Verified as Corrected

Describe how the State verified that the source of noncompliance is correctly implementing the regulatory requirements.

In FFY 2023, 93.29% (139 of 149) of Early Intervention (EI) child records reviewed for transition demonstrated that transition steps and services were developed at least 90 calendar days—and, at the discretion of the parties, up to nine months—before the child’s third birthday to support a smooth transition to preschool or other appropriate community services.

Of the 35 EI programs statewide, seven programs were issued findings of noncompliance, representing a total of ten child-specific instances of noncompliance.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition steps and services were provided in accordance with federal and state requirements.

Through this review of subsequent data, the State verified that each of the seven EI programs achieved 100% compliance within one year of identification and is now correctly implementing the regulatory requirements for timely transition planning and service provision.

Describe how the State verified that each individual case of noncompliance was corrected.

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

The EI program submitted documentation of the correction of noncompliance for each of the ten individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

The state reviewed the ten individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition plans were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (10 of 10) incidents of noncompliance, identified across seven regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition plans with steps and services for each child, unless the child was no longer within the jurisdiction of the EI program.

If procedures have been adopted that permit EIS program or providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), describe how, for instances of noncompliance discovered in FFY 2023, the State verified: (1) that the source of noncompliance is correctly implementing the regulatory requirements; and, (2) each individual case of noncompliance was corrected.

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 8A - Prior FFY Required Actions

Because the State reported less than 100% compliance for FFY 2023, the State must report on the status of correction of noncompliance identified in FFY 2023 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2024 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2023 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2024 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2023, although its FFY 2023 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2023. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

Response to actions required in FFY 2023 SPP/APR

In FFY 2023, 93.29% (139 of 149) of Early Intervention (EI) child records reviewed for transition demonstrated that transition steps and services were developed at least 90 calendar days—and, at the discretion of the parties, up to nine months—before the child’s third birthday to support a smooth transition to preschool or other appropriate community services.

Of the 35 EI programs statewide, seven programs were issued findings of noncompliance, representing a total of ten child-specific instances of noncompliance.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition steps and services were provided in accordance with federal and state requirements.

Through this review of subsequent data, the State verified that each of the seven EI programs achieved 100% compliance within one year of identification and is now correctly implementing the regulatory requirements for timely transition planning and service provision.

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

The EI program submitted documentation of the correction of noncompliance for each of the ten individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

The state reviewed the ten individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition plans were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (10 of 10) incidents of noncompliance, identified across seven regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition plans with steps and services for each child, unless the child was no longer within the jurisdiction of the EI program.

## 8A - OSEP Response

## 8A - Required Actions

Because the State reported less than 100% compliance for FFY 2024, the State must report on the status of correction of noncompliance identified in FFY 2024 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2025 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2024 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2025 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2024, although its FFY 2024 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2024. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

# Indicator 8B: Early Childhood Transition

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Effective Transition

Compliance indicator: The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

A. Developed an IFSP with transition steps and services at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday;

B. Notified (consistent with any opt-out policy adopted by the State) the State educational agency (SEA) and the local educational agency (LEA) where the toddler resides at least 90 days prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services; and

C. Conducted the transition conference held with the approval of the family at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services.

(20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Data to be taken from monitoring or State data system.

Measurement

A. Percent = [(# of toddlers with disabilities exiting Part C at age 3 who have an IFSP with transition steps and services at least 90 days, and at the discretion of all parties not more than nine months, prior to their third birthday) divided by the (# of toddlers with disabilities exiting Part C at age 3)] times 100.

B. Percent = [(# of toddlers with disabilities exiting Part C where notification (consistent with any opt-out policy adopted by the State) to the SEA and LEA occurred at least 90 days prior to their third birthday for toddlers potentially eligible for Part B preschool services) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

C. Percent = [(# of toddlers with disabilities exiting Part C where the transition conference occurred at least 90 days, and at the discretion of all parties not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

Account for untimely transition planning under 8A, 8B, and 8C, including the reasons for delays.

Instructions

Indicators 8A, 8B, and 8C: Targets must be 100%.

Describe the results of the calculations and compare the results to the target. Describe the method used to collect these data. Provide the actual numbers used in the calculation.

Indicators 8A and 8C: If data are from the State’s monitoring, describe the procedures used to collect these data. If data are from State monitoring, also describe the method used to select EIS programs for monitoring. If data are from a State database, describe the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period) and how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

Indicators 8A and 8C: States are not required to report in their calculation the number of children for whom the State has identified the cause for the delay as exceptional family circumstances, as defined in 34 CFR §303.310(b), documented in the child’s record. If a State chooses to report in its calculation children for whom the State has identified the cause for the delay as exceptional family circumstances documented in the child’s record, the numbers of these children are to be included in the numerator and denominator. Include in the discussion of the data the numbers the State used to determine its calculation under this indicator and report separately the number of documented delays attributable to exceptional family circumstances.

Indicator 8A: The measurement is intended to capture those children exiting at age 3 for whom an IFSP must be developed with transition steps and services within the required timeline consistent with 34 CFR §303.209(d) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8B: Under 34 CFR §303.401(e), the State may adopt a written policy that requires the lead agency to provide notice to the parent of an eligible child with an IFSP of the impending notification to the SEA and LEA under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §303.209(b)(1) and (2) and permits the parent within a specified time period to “opt-out” of the referral. Under the State’s opt-out policy, the State is not required to include in the calculation under 8B (in either the numerator or denominator) the number of children for whom the parents have opted out. However, the State must include in the discussion of data the number of parents who opted out. In addition, any written opt-out policy must be on file with the Department of Education as part of the State’s Part C application under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §§303.209(b) and 303.401(d).

Indicator 8C: The measurement is intended to capture those children for whom a transition conference must be held within the required timeline consistent with 34 CFR §303.209(e) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8C: Do not include in the calculation but provide a separate number for those toddlers for whom the parent did not provide approval for the transition conference.

Indicators 8A, 8B, and 8C: Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in OSEP’s response for the previous SPP/APR. If the State did not ensure timely correction of the previous noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance, methods to ensure correction, and any enforcement actions that were taken.

If the State reported less than 100% compliance for the previous reporting period (e.g., for the FFY 2024 SPP/APR, the data for FFY 2023), and the State did not identify any findings of noncompliance, provide an explanation of why the State did not identify any findings of noncompliance.

If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), the explanation within each applicable indicator must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

## 8B - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 100.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data | 100.00% | 100.00% | 100.00% | 100.00% | 100.00% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

FFY 2024 SPP/APR Data

Data include notification to both the SEA and LEA

YES

| Number of toddlers with disabilities exiting Part C where notification to the SEA and LEA occurred at least 90 days prior to their third birthday for toddlers potentially eligible for Part B preschool services | Number of toddlers with disabilities exiting Part C who were potentially eligible for Part B | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 152 | 152 | 100.00% | 100% | 100.00% | Met target | No Slippage |

Number of parents who opted out

This number will be subtracted from the "Number of toddlers with disabilities exiting Part C who were potentially eligible for Part B" field to calculate the denominator for this indicator.

0

Provide reasons for delay, if applicable.

Describe the method used to collect these data.

The data collection is completed through our state’s file review process. All EI programs in Oregon receiving IDEA funds are required to participate in the Oregon Department of Education (ODE) System Performance Review & Improvement (SPR&I) system of annual accountability and performance reporting. This system focuses on procedural compliance and performance indicators identified through federal and state regulation and previous state monitoring findings. Programs conduct individual child file reviews annually to collect procedural compliance data. These data are collected on a specified number of child files determined by the State and are evenly split between Early Intervention and Early Intervention Transition. Files are selected to match the individual race/ethnicity, disability, and gender distribution for each EI program based on the December child count. Individual child procedural compliance data is collected by programs and submitted to the State electronically through the SPR&I database. The State works collaboratively with programs on comprehensive data collection, analysis, performance reporting, improvement planning, implementation, and reporting of progress. The SPR&I system provides the State with the mechanism for review of district/program policies, procedures, and systems to ensure the requirements set forth in 34 CFR §303.700-708 are met.

The SEA and LEA are notified monthly via ecWeb (the statewide EI/ECSE special education database) of all children transitioning from early intervention to early childhood special education. On the first day of every month, in ecWeb, an SEA/LEA Transition Notification report is generated and distributed to the SEA/LEA. These data comprise a list of all the EI children in Oregon who are currently in the process of transitioning to ECSE services.

Do you have a written opt-out policy? (yes/no)

NO

What is the source of the data provided for this indicator?

State monitoring

Describe the method used to select EIS programs for monitoring.

The Oregon Department of Education (ODE) uses the System Performance Review and Improvement (SPR&I) process to select Early Intervention (EI) programs for annual monitoring. All programs receiving IDEA Part C funds participate in this statewide accountability system, which focuses on procedural compliance and performance on key federal and state indicators.

Each year, programs conduct a review of individual child records based on a number set by the State. Files are divided evenly between Early Intervention and Transition from Early Intervention and are selected to reflect the program’s population by race/ethnicity, disability, and gender using data from the most recent December 1 child count.

Programs enter compliance data into the SPR&I database, including timely SEA/LEA transition notifications and reasons for not meeting the required timeline. ODE reviews these data to evaluate compliance, verify correction of noncompliance, and identify areas for improvement. Through the SPR&I process, ODE and local programs work together to use data for continuous improvement and ensure timely, high-quality transition services for children and families.

Provide additional information about this indicator (optional).

Correction of Findings of Noncompliance Identified in FFY 2023

| Findings of Noncompliance Identified | Findings of Noncompliance Verified as Corrected Within One Year | Findings of Noncompliance Subsequently Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |
| 0 | 0 | 0 | 0 |

If procedures have been adopted that permit EIS program or providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), describe how, for instances of noncompliance discovered in FFY 2023, the State verified: (1) that the source of noncompliance is correctly implementing the regulatory requirements; and, (2) each individual case of noncompliance was corrected.

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 8B - Prior FFY Required Actions

None

## 8B - OSEP Response

## 8B - Required Actions

# Indicator 8C: Early Childhood Transition

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / Effective Transition

Compliance indicator: The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

A. Developed an IFSP with transition steps and services at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday;

B. Notified (consistent with any opt-out policy adopted by the State) the State educational agency (SEA) and the local educational agency (LEA) where the toddler resides at least 90 days prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services; and

C. Conducted the transition conference held with the approval of the family at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services.

(20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Data to be taken from monitoring or State data system.

Measurement

A. Percent = [(# of toddlers with disabilities exiting Part C at age 3 who have an IFSP with transition steps and services at least 90 days, and at the discretion of all parties not more than nine months, prior to their third birthday) divided by the (# of toddlers with disabilities exiting Part C at age 3)] times 100.

B. Percent = [(# of toddlers with disabilities exiting Part C where notification (consistent with any opt-out policy adopted by the State) to the SEA and LEA occurred at least 90 days prior to their third birthday for toddlers potentially eligible for Part B preschool services) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

C. Percent = [(# of toddlers with disabilities exiting Part C where the transition conference occurred at least 90 days, and at the discretion of all parties not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B) divided by the (# of toddlers with disabilities exiting Part C who were potentially eligible for Part B)] times 100.

Account for untimely transition planning under 8A, 8B, and 8C, including the reasons for delays.

Instructions

Indicators 8A, 8B, and 8C: Targets must be 100%.

Describe the results of the calculations and compare the results to the target. Describe the method used to collect these data. Provide the actual numbers used in the calculation.

Indicators 8A and 8C: If data are from the State’s monitoring, describe the procedures used to collect these data. If data are from State monitoring, also describe the method used to select EIS programs for monitoring. If data are from a State database, describe the time period in which the data were collected (e.g., September through December, fourth quarter, selection from the full reporting period) and how the data accurately reflect data for infants and toddlers with IFSPs for the full reporting period.

Indicators 8A and 8C: States are not required to report in their calculation the number of children for whom the State has identified the cause for the delay as exceptional family circumstances, as defined in 34 CFR §303.310(b), documented in the child’s record. If a State chooses to report in its calculation children for whom the State has identified the cause for the delay as exceptional family circumstances documented in the child’s record, the numbers of these children are to be included in the numerator and denominator. Include in the discussion of the data the numbers the State used to determine its calculation under this indicator and report separately the number of documented delays attributable to exceptional family circumstances.

Indicator 8A: The measurement is intended to capture those children exiting at age 3 for whom an IFSP must be developed with transition steps and services within the required timeline consistent with 34 CFR §303.209(d) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8B: Under 34 CFR §303.401(e), the State may adopt a written policy that requires the lead agency to provide notice to the parent of an eligible child with an IFSP of the impending notification to the SEA and LEA under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §303.209(b)(1) and (2) and permits the parent within a specified time period to “opt-out” of the referral. Under the State’s opt-out policy, the State is not required to include in the calculation under 8B (in either the numerator or denominator) the number of children for whom the parents have opted out. However, the State must include in the discussion of data the number of parents who opted out. In addition, any written opt-out policy must be on file with the Department of Education as part of the State’s Part C application under IDEA section 637(a)(9)(A)(ii)(I) and 34 CFR §§303.209(b) and 303.401(d).

Indicator 8C: The measurement is intended to capture those children for whom a transition conference must be held within the required timeline consistent with 34 CFR §303.209(e) and, as such, only children between 2 years 3 months and 2 years 9 months should be included in the denominator.

Indicator 8C: Do not include in the calculation but provide a separate number for those toddlers for whom the parent did not provide approval for the transition conference.

Indicators 8A, 8B, and 8C: Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in OSEP’s response for the previous SPP/APR. If the State did not ensure timely correction of the previous noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance, methods to ensure correction, and any enforcement actions that were taken.

If the State reported less than 100% compliance for the previous reporting period (e.g., for the FFY 2024 SPP/APR, the data for FFY 2023), and the State did not identify any findings of noncompliance, provide an explanation of why the State did not identify any findings of noncompliance.

If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), the explanation within each applicable indicator must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

## 8C - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 | 87.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data | 92.16% | 92.31% | 92.36% | 92.62% | 91.84% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

FFY 2024 SPP/APR Data

Data reflect only those toddlers for whom the Lead Agency was required to conduct the transition conference, held with the approval of the family, at least 90 days, and at the discretion of all parties, not more than nine months, prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services (yes/no)

YES

| Number of toddlers with disabilities exiting Part C where the transition conference occurred at least 90 days, and at the discretion of all parties not more than nine months prior to the toddler’s third birthday for toddlers potentially eligible for Part B | Number of toddlers with disabilities exiting Part C who were potentially eligible for Part B | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 137 | 152 | 91.84% | 100% | 91.45% | Did not meet target | No Slippage |

Number of toddlers for whom the parent did not provide approval for the transition conference

This number will be subtracted from the "Number of toddlers with disabilities exiting Part C who were potentially eligible for Part B" field to calculate the denominator for this indicator.

0

Number of documented delays attributable to exceptional family circumstances

This number will be added to the "Number of toddlers with disabilities exiting Part C where the transition conference occurred at least 90 days, and at the discretion of all parties not more than nine months prior to the toddler’s third birthday for toddlers potentially eligible for Part B" field to calculate the numerator for this indicator.

2

Provide reasons for delay, if applicable.

The reasons for delay were as follows:

8 incidents of adding transition services more than nine months before the child’s third birthday. Program staff reported that this was due to insufficient staff training.

1 incident of adding transition services less than 90 days before the child’s third birthday. Program staff reported that this was due to staffing issues

4 incidents where no documentation was provided by the program for transition steps. Program staff reported that these omissions resulted from insufficient training on documentation requirements.

What is the source of the data provided for this indicator?

State monitoring

Describe the method used to select EIS programs for monitoring.

The Oregon Department of Education (ODE) uses the System Performance Review and Improvement (SPR&I) process to select Early Intervention (EI) programs for annual monitoring. All programs receiving IDEA Part C funds participate in this statewide accountability system, which focuses on procedural compliance and performance on key federal and state indicators.

Each year, programs conduct a review of individual child records based on a number set by the State. Files are divided evenly between Early Intervention and Transition from Early Intervention and are selected to reflect the program’s population by race/ethnicity, disability, and gender using data from the most recent December 1 child count.

Programs enter compliance data into the SPR&I database, including timely transition conferences and reasons for not meeting the required timeline. ODE reviews these data to evaluate compliance, verify correction of noncompliance, and identify areas for improvement. Through the SPR&I process, ODE and local programs work together to use data for continuous improvement and ensure timely, high-quality transition services for children and families.

Provide additional information about this indicator (optional).

Correction of Findings of Noncompliance Identified in FFY 2023

| Findings of Noncompliance Identified | Findings of Noncompliance Verified as Corrected Within One Year | Findings of Noncompliance Subsequently Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |
| 12 | 12 | 0 | 0 |

FFY 2023 Findings of Noncompliance Verified as Corrected

Describe how the State verified that the source of noncompliance is correctly implementing the regulatory requirements.

Of the 35 EI programs in the state, seven had findings of noncompliance. A total of twelve instances of child-specific noncompliance were identified across the seven EI programs.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition conferences were provided in accordance with federal and state requirements.

Through this review of subsequent data, the state verified that each of the seven EI programs achieved 100% compliance within one year and are correctly implementing the regulatory requirements for timely transition conferences.

Describe how the State verified that each individual case of noncompliance was corrected.

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

- The EI program submitted documentation of the correction of noncompliance for each of the twelve individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

- The state reviewed the twelve individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition conferences were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (12 of 12) incidents of noncompliance, identified across [Ex eight] regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition conferences for each child, unless the child was no longer within the jurisdiction of the EI program.

If procedures have been adopted that permit EIS program or providers to correct noncompliance prior to the State’s issuance of a finding (i.e., pre-finding correction), describe how, for instances of noncompliance discovered in FFY 2023, the State verified: (1) that the source of noncompliance is correctly implementing the regulatory requirements; and, (2) each individual case of noncompliance was corrected.

N/A

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 8C - Prior FFY Required Actions

Because the State reported less than 100% compliance for FFY 2023, the State must report on the status of correction of noncompliance identified in FFY 2023 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2024 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2023 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2024 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2023, although its FFY 2023 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2023. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

Response to actions required in FFY 2023 SPP/APR

Of the 35 EI programs in the state, seven had findings of noncompliance. A total of twelve instances of child-specific noncompliance were identified across the seven EI programs.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition conferences were provided in accordance with federal and state requirements.

Through this review of subsequent data, the state verified that each of the seven EI programs achieved 100% compliance within one year and are correctly implementing the regulatory requirements for timely transition conferences.

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

- The EI program submitted documentation of the correction of noncompliance for each of the twelve individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

- The state reviewed the twelve individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition conferences were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (12 of 12) incidents of noncompliance, identified across [Ex eight] regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition conferences for each child, unless the child was no longer within the jurisdiction of the EI program.

## 8C - OSEP Response

## 8C - Required Actions

Because the State reported less than 100% compliance for FFY 2024, the State must report on the status of correction of noncompliance identified in FFY 2024 for this indicator. When reporting on the correction of noncompliance, the State must report, in the FFY 2025 SPP/APR, that it has verified that each EIS program or provider with noncompliance identified in FFY 2024 for this indicator: (1) is correctly implementing the specific regulatory requirements (i.e., achieved 100% compliance) based on a review of updated data such as data subsequently collected through on-site monitoring or a State data system; and (2) has corrected each individual case of noncompliance, unless the child is no longer within the jurisdiction of the EIS program or provider and no outstanding corrective action exists under a State complaint or due process hearing decision for the child, consistent with OSEP QA 23-01. In the FFY 2025 SPP/APR, the State must describe the specific actions that were taken to verify the correction. If the State did not identify any findings of noncompliance in FFY 2024, although its FFY 2024 data reflect less than 100% compliance, provide an explanation of why the State did not identify any findings of noncompliance in FFY 2024. If the State did not issue any findings because it has adopted procedures that permit its EIS programs/providers to correct noncompliance prior to the State's issuance of a finding (i.e., pre-finding correction), the explanation must include how the State verified, prior to issuing a finding, that the EIS program/provider has corrected each individual case of child-specific noncompliance and is correctly implementing the specific regulatory requirements.

# Indicator 9: Resolution Sessions

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / General Supervision

Results indicator: Percent of hearing requests that went to resolution sessions that were resolved through resolution session settlement agreements (applicable if Part B due process procedures under section 615 of the IDEA are adopted). (20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Same data as used for reporting to the Department under section 618 of the IDEA, using the definitions in EDFacts file specification FS908.

Measurement

Percent = (3.1(a) divided by 3.1) times 100.

Instructions

Sampling from the State’s 618 data is not allowed.

This indicator is not applicable to a State that has adopted Part C due process procedures under section 639 of the IDEA.

Describe the results of the calculations and compare the results to the target.

States are not required to establish baselines or targets if the number of resolution sessions is less than 10. In a reporting period when the number of resolution sessions reaches 10 or greater, the State must develop baselines and targets and report them in the corresponding SPP/APR.

States may express their targets in a range (e.g., 75-85%).

If the data reported in this indicator are not the same as the State’s 618 data, explain.

States are not required to report data at the EIS program level.

## 9 - Indicator Data

Not Applicable

Select yes if this indicator is not applicable.

NO

Select yes to use target ranges.

Target Range not used

Select yes if the data reported in this indicator are not the same as the State’s data reported under Section 618 of the IDEA.

NO

Prepopulated Data

| Source | Date | Description | Data |
| --- | --- | --- | --- |
| SY 2024-25 IDEA Part C Dispute Resolution - Due Process Complaints (EDFacts file spec FS908; Data group 5031) | 11/19/2025 | 3.1 Number of resolution sessions | 0 |
| SY 2024-25 IDEA Part C Dispute Resolution - Due Process Complaints (EDFacts file spec FS908; Data group 5031) | 11/19/2025 | 3.1(a) Number resolution sessions resolved through settlement agreements | 0 |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices is included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input was gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target>= |  |  |  |  |  |
| Data |  |  |  |  |  |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target>= |  |  |

FFY 2024 SPP/APR Data

| 3.1(a) Number resolutions sessions resolved through settlement agreements | 3.1 Number of resolutions sessions | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | 0 |  |  |  | N/A | N/A |

Provide additional information about this indicator (optional)

## 9 - Prior FFY Required Actions

None

## 9 - OSEP Response

The State reported fewer than ten resolution sessions held in FFY 2024. The State is not required to provide targets until any fiscal year in which ten or more resolution sessions were held.

## 9 - Required Actions

# Indicator 10: Mediation

Instructions and Measurement

Monitoring Priority: Effective General Supervision Part C / General Supervision

Results indicator: Percent of mediations held that resulted in mediation agreements. (20 U.S.C. 1416(a)(3)(B) and 1442)

Data Source

Same data as used for reporting to the Department under section 618 of the IDEA, using the definitions in EDFacts file specification FS907.

Measurement

Percent = [(2.1(a)(i) + 2.1(b)(i)) divided by 2.1] times 100.

Instructions

Sampling from the State’s 618 data is not allowed.

Describe the results of the calculations and compare the results to the target.

States are not required to establish baselines or targets if the number of mediations is less than 10. In a reporting period when the number of mediations reaches 10 or greater, the State must develop baseline and report them in the corresponding SPP/APR.

The consensus among mediation practitioners is that 75-85% is a reasonable rate of mediations that result in agreements and is consistent with national mediation success rate data. States may express their targets in a range (e.g., 75-85%).

If the data reported in this indicator are not the same as the State’s 618 data, explain.

States are not required to report data at the EIS program level.

## 10 - Indicator Data

Select yes to use target ranges

Target Range not used

Select yes if the data reported in this indicator are not the same as the State’s data reported under Section 618 of the IDEA.

NO

Prepopulated Data

| Source | Date | Description | Data |
| --- | --- | --- | --- |
| SY 2024-25 IDEA Part C Dispute Resolution - Mediation Requests (EDFacts file spec FS907; Data group 5030) | 11/19/2025 | 2.1 Mediations held | 0 |
| SY 2024-25 IDEA Part C Dispute Resolution - Mediation Requests (EDFacts file spec FS907; Data group 5030) | 11/19/2025 | 2.1.a.i Mediations agreements related to due process complaints | 0 |
| SY 2024-25 IDEA Part C Dispute Resolution - Mediation Requests (EDFacts file spec FS907; Data group 5030) | 11/19/2025 | 2.1.b.i Mediations agreements not related to due process complaints | 0 |

Targets: Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices is included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input has been gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2005 |  |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target>= |  |  |  |  |  |
| Data |  |  | 78.26% |  |  |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target>= |  |  |

FFY 2024 SPP/APR Data

| 2.1.a.i Mediation agreements related to due process complaints | 2.1.b.i Mediation agreements not related to due process complaints | 2.1 Number of mediations held | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 0 | 0 | 0 |  |  |  | N/A | N/A |

Provide additional information about this indicator (optional)

## 10 - Prior FFY Required Actions

None

## 10 - OSEP Response

The State reported fewer than ten mediations held in FFY 2024. The State is not required to provide targets until any fiscal year in which ten or more mediations were held.

## 10 - Required Actions

# Indicator 11: State Systemic Improvement Plan

Instructions and Measurement

Monitoring Priority: General Supervision

The State’s SPP/APR includes a State Systemic Improvement Plan (SSIP) that meets the requirements set forth for this indicator.

Measurement

Results Indicator: The State’s SPP/APR includes an SSIP that is a comprehensive, ambitious, yet achievable multi-year plan for improving results for infants and toddlers with disabilities and their families. The SSIP includes each of the components described below.

Instructions

Baseline Data: The State must provide baseline data expressed as a percentage and which is aligned with the State-identified Measurable Result(s) for Infants and Toddlers with Disabilities and their Families.

Targets: In its FFY 2020 SPP/APR, due February 1, 2022, the State must provide measurable and rigorous targets (expressed as percentages) for each of the six years from FFY 2020 through FFY 2025. The State’s FFY 2025 target must demonstrate improvement over the State’s baseline data.

Updated Data: In its FFYs 2020 through FFY 2025 SPPs/APRs, due February 2022 through February 2027, the State must provide updated data for that specific FFY (expressed as percentages), and that data must be aligned with the State-identified Measurable Result(s) for Infants and Toddlers with Disabilities and their Families. In its FFYs 2020 through FFY 2025 SPPs/APRs, the State must report on whether it met its target.

Overview of the Three Phases of the SSIP

It is of the utmost importance to improve results for infants and toddlers with disabilities and their families by improving early intervention services. Stakeholders, including parents of infants and toddlers with disabilities, early intervention service (EIS) programs and providers, the State Interagency Coordinating Council, and others, are critical participants in improving results for infants and toddlers with disabilities and their families and must be included in developing, implementing, evaluating, and revising the SSIP and included in establishing the State’s targets under Indicator 11. The SSIP should include information about stakeholder involvement in all three phases.

Phase I: Analysis:

- Data Analysis;

- Analysis of State Infrastructure to Support Improvement and Build Capacity;

- State-identified Measurable Result(s) for Infants and Toddlers with Disabilities and their Families;

- Selection of Coherent Improvement Strategies; and

- Theory of Action.

Phase II: Plan (which is in addition to the Phase I content (including any updates) outlined above:

- Infrastructure Development;

- Support for EIS Program and/or EIS Provider Implementation of Evidence-Based Practices; and

- Evaluation.

Phase III: Implementation and Evaluation (which is in addition to the Phase I and Phase II content (including any updates) outlined above:

- Results of Ongoing Evaluation and Revisions to the SSIP.

Specific Content of Each Phase of the SSIP

Refer to FFY 2013-2015 Measurement Table for detailed requirements of Phase I and Phase II SSIP submissions.

Phase III should only include information from Phase I or Phase II if changes or revisions are being made by the State and/or if information previously required in Phase I or Phase II was not reported.

Phase III: Implementation and Evaluation

In Phase III, the State must, consistent with its evaluation plan described in Phase II, assess and report on its progress implementing the SSIP. This includes: (A) data and analysis on the extent to which the State has made progress toward and/or met the State-established short-term and long-term outcomes or objectives for implementation of the SSIP and its progress toward achieving the State-identified Measurable Result for Infants and Toddlers with Disabilities and Their Families (SiMR); (B) the rationale for any revisions that were made, or that the State intends to make, to the SSIP as the result of implementation, analysis, and evaluation; and (C) a description of the meaningful stakeholder engagement. If the State intends to continue implementing the SSIP without modifications, the State must describe how the data from the evaluation support this decision.

A. 	Data Analysis

As required in the Instructions for the Indicator/Measurement, in its FFYs 2020 through FFY 2025 SPP/APR, the State must report data for that specific FFY (expressed as actual numbers and percentages) that are aligned with the SiMR. The State must report on whether the State met its target. In addition, the State may report on any additional data (e.g., progress monitoring data) that were collected and analyzed that would suggest progress toward the SiMR. States using a subset of the population from the indicator (e.g., a sample, cohort model) should describe how data are collected and analyzed for the SiMR if that was not described in Phase I or Phase II of the SSIP.

B. 	Phase III Implementation, Analysis and Evaluation

The State must provide a narrative or graphic representation, (e.g., a logic model) of the principal activities, measures and outcomes that were implemented since the State’s last SSIP submission (i.e., February 3, 2025). The evaluation should align with the theory of action described in Phase I and the evaluation plan described in Phase II. The State must describe any changes to the activities, strategies, or timelines described in Phase II and include a rationale or justification for the changes. If the State intends to continue implementing the SSIP without modifications, the State must describe how the data from the evaluation support this decision.

The State must summarize the infrastructure improvement strategies that were implemented, and the short-term outcomes achieved, including the measures or rationale used by the State and stakeholders to assess and communicate achievement. Relate short-term outcomes to one or more areas of a systems framework (e.g., governance, data, finance, accountability/monitoring, quality standards, professional development and/or technical assistance) and explain how these strategies support system change and are necessary for: (a) achievement of the SiMR; (b) sustainability of systems improvement efforts; and/or (c) scale-up. The State must describe the next steps for each infrastructure improvement strategy and the anticipated outcomes to be attained during the next fiscal year (e.g., for the FFY 2024 APR, report on anticipated outcomes to be obtained during FFY 2025, i.e., July 1, 2025-June 30, 2026).

The State must summarize the specific evidence-based practices that were implemented and the strategies or activities that supported their selection and ensured their use with fidelity. Describe how the evidence-based practices, and activities or strategies that support their use, are intended to impact the SiMR by changing program/district policies, procedures, and/or practices, teacher/provider practices (e.g., behaviors), parent/caregiver outcomes, and/or child outcomes. Describe any additional data (e.g., progress monitoring data) that was collected to support the on-going use of the evidence-based practices and inform decision-making for the next year of SSIP implementation.

C. 	Stakeholder Engagement

The State must describe the specific strategies implemented to engage stakeholders in key improvement efforts and how the State addressed concerns, if any, raised by stakeholders through its engagement activities.

Additional Implementation Activities

The State should identify any activities not already described that it intends to implement in the next fiscal year (e.g., for the FFY 2024 APR, report on activities it intends to implement in FFY 2025, i.e., July 1, 2025-June 30, 2026) including a timeline, anticipated data collection and measures, and expected outcomes that are related to the SiMR. The State should describe any newly identified barriers and include steps to address these barriers.

## 11 - Indicator Data

Section A: Data Analysis

What is the State-identified Measurable Result (SiMR)?

The State Identified Measurable Result (SiMR) for infants, toddlers, and preschool children with disabilities and their families is to increase the rate of growth in social-emotional and approaches to learning skills for children with disabilities, birth through age five.  The SiMR will be measured by using the child outcome data for both C3 and B7, Outcomes A, B, C, Summary statement 1.

Has the SiMR changed since the last SSIP submission? (yes/no)

NO

Is the State using a subset of the population from the indicator (e.g., a sample, cohort model)? (yes/no)

NO

Is the State’s theory of action new or revised since the previous submission? (yes/no)

YES

Please provide a description of the changes and updates to the theory of action.

The current theory of action was revised to reflect changes in the systemic approach and for clarity and conciseness.

Please provide a link to the current theory of action.

The theory of action is posted here: https://www.oregon.gov/ode/reports-and-data/SpEdReports/Documents/2020%20APR-SPP/FY20%20Part%20C%20TOA.pdf.

Progress toward the SiMR

Please provide the data for the specific FFY listed below (expressed as actual number and percentages).

Select yes if the State uses two targets for measurement. (yes/no)

YES

Historical Data

| Part | Baseline Year | Baseline Data |
| --- | --- | --- |
| A | 2015 | 81.54% |
| B | 2015 | 61.33% |

Targets

| FFY | Current Relationship | 2024 | 2025 |
| --- | --- | --- | --- |
| Target A | Data must be greater than or equal to the target | 86.20% | 86.40% |
| Target B | Data must be greater than or equal to the target | 68.50% | 68.70% |

FFY 2024 SPP/APR Data

| Part | Numerator | Denominator | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- | --- |
| A | 2,223 | 2,556 | 85.89% | 86.20% | 86.97% | Met target | No Slippage |
| B | 1,469 | 2,407 | 63.29% | 68.50% | 61.03% | Did not meet target | Slippage |

Provide reasons for B slippage, if applicable

Slippage occurred may be attributed to lack of tiered supports to special education staff and administrators connecting the assessment tool to child outcomes data and improvement activities; Additional factors include varied implementation of quality home visiting models, limited coaching capacity to improve family or caregiver coaching, minimal improvement activities system-wide targeting cognitive, communication, and early literacy domains with this age group during routines and daily activities, and an increase in staff turnover and personnel shortages system-wide.

Provide the data source for the FFY 2024 data.

Indicator C3 and B7 Measures A1, B1, and C1 are used as the data source. Above you will find the data for A1 and B1. The data for C1 is as follows: 1868 (Numerator) / 2598 (Denominator) = 79.9% which does not meet our target of 78.6 but there is not slippage. (FFY 2023 data is 71.7%)

Please describe how data are collected and analyzed for the SiMR.

In 2015, using a national AEPS data set from typically developing children, a review team considered 90%, 85% and 80% percentile cut offs against the national data results to decide the cut off level that best reflected the State’s children in EI programs. The review team, comprised of State staff, the EI/ECSE Contractors and the EI/ECSE stakeholder group were all asked to analyze the percentile cut offs and determine the cut off level that the State should use for reporting to the EI child outcomes. The consensus was to use the 80% cut off level. This most closely represents the children who are eligible for Early Intervention programs and receive services in Oregon.

Child progress is measured using the following rubric:

If a child enters with a score below the normal range and stays the same or regresses at the next test administration, the child is categorized as (a) does not improve functioning. If the child makes progress and the ratio of how far below the normal level of development increases between test administrations, the child is categorized as (b) improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers. If the child makes progress but the ratio of how far below the normal level of development decreases between test administrations, the child is categorized as (c) improved functioning to a level nearer to the functioning of same-aged peers but did not reach it. If a child enters with a score below the normal range and increases to reach or exceed the normal range at the next test administration, the child is categorized as (d) improved functioning sufficient to reach a level comparable to same-aged peers.

If a child enters with a score at or above the normal range and maintains their score at or above the normal range at the next test administration, the child is categorized as (e) maintains functioning at or above same age peers.

In relation to the SiMR it was determined in 2015 that Summary Statement 1 for Part A and B of Indicator C3 was the most appropriate for measuring progress and effectiveness of strategies put in place to measure the impact of the coherent strategies and systemic infrastructure changes outlined in the SSIP.

Since 2015, changes to the early learning system and the relationship between the Department of Early Learning and Care (formally the Early Learning Division), the Oregon Health Authority, and the Oregon Department of Education have evolved providing families and children under five with increased opportunities for early care, home visiting, and education and behavioral supports to aid in their development. While the Oregon Department of Education remains responsible for granting funds to districts and ESDs to effectively implement IDEA, the unification of a systems approach to early learning under Raise Up Oregon and HB 3073 has required a reevaluation of the needed data to ensure systems improvements and investments are aligned, coordinated, and accessible.

Optional: Has the State collected additional data (i.e., benchmark, CQI, survey) that demonstrates progress toward the SiMR? (yes/no)

YES

Describe any additional data collected by the State to assess progress toward the SiMR.

Additional data collected by the state to assess progress towards the SiMR includes:

-ECTA Systems Framework Data

-Comprehensive System of Professional Development (CSPD Evaluation Data

-Annual Performance Indicator data on Least Restrictive Environments in Preschool

-Fidelity data from communities and programs implementing the Pyramid Model and/or the Early Childhood Inclusion Indicators.

The following data has been presented publicly at the State Interagency Coordinating Council (SICC) and can be found on the SICC website under meeting materials for the following dates:9/15/2024, 1/12/2025, and 5/10/2025. These notes can related slides can be located on the SICC Website: https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/siccmtgminutes.aspx

As described in the Phase III (1) report, three research-based measures were selected to evaluate fidelity of EC PBIS+ (otherwise known as the Pyramid Model Framework) implementation at the program and teacher levels: Early Childhood Benchmarks of Quality (BoQ), Teaching Pyramid Observation Tool (TPOT™) and The Pyramid Infant Toddler Observation Scale (TPITOS™). Collectively, these data allow for an assessment of fidelity of EC PBIS+/Pyramid Model strategies implementation by participating teachers. A description of why the TPOT was selected can be found in the State’s Phase III (1) report. To evaluate the extent to which programs are implementing Program-Wide EC PBIS+ with fidelity, participating programs collected Early Childhood Benchmarks of Quality data beginning in fall 2017. The EC-BOQ evaluates the extent to which a program has the nine critical elements and 47 benchmarks in place completely, partially in place, or not in place at all.

The National Indicators of High Quality Inclusion at the State and Community Level were also used during this cycle of the SSIP. Using the State Benchmarks of Quality, the State Indicators of High Quality Inclusion, Community Indicators and Elements of High Quality Inclusion and Program Inclusion Indicators allow the State, communities, and programs to measure progress towards implementation of this framework. A description of why the National Indicators of High Quality Inclusion was selected can be found in the State’s Phase III (1) report.

Through partnership with Oregon State University, evaluation data has been summarized through a series of briefs that can be found on the Oregon Inclusion Initiative Website: https://health.oregonstate.edu/elsi/oregon-inclusion-initiative

Additional data on impacts of implementation of the Pyramid Model and Inclusion can also be found on the Oregon Early Childhood Inclusion website at the Oregon Department of Education: https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/oeci.aspx

Did the State identify any general data quality concerns, unrelated to COVID-19, which affected progress toward the SiMR during the reporting period? (yes/no)

NO

Did the State identify any data quality concerns directly related to the COVID-19 pandemic during the reporting period? (yes/no)

NO

Section B: Implementation, Analysis and Evaluation

Please provide a link to the State’s current evaluation plan.

Oregon SSIP Part C: Evaluation Plan: https://www.oregon.gov/ode/reports-and-data/SpEdReports/Documents/2020%20APR-SPP/Evaluation%20Plan%20ssip.docx

Is the State’s evaluation plan new or revised since the previous submission? (yes/no)

YES

If yes, provide a description of the changes and updates to the evaluation plan.

The evaluation plan has been revised to include new systems improvement activities and timelines for completion.

If yes, describe a rationale or justification for the changes to the SSIP evaluation plan.

While some of the systems implementation activities continue, such as the use of Pyramid Model and the Indicators of Inclusion Frameworks, other activities have been completed and continue to evolve. To be transparent and accountable to partners across the early learning system, an updated evaluation plan was needed.

Provide a summary of each infrastructure improvement strategy implemented in the reporting period.

The State continues to guide programs to allocate IDEA funds to support implementation, training, and local level professional development activities for National Early Childhood Inclusion Indicators, and Pyramid Model. Additional discretionary funds are used for state level activities such as coordination and regional training opportunities in partnership with other states and Region 10 Head Start.

Infrastructure improvements include the following:

Strategy 1: Leverage effective staffing across the Agency and the early learning system to advance implementation of coherent strategies.

Strategy 2: Develop an improved communication and engagement strategy that includes partners and other agencies serving children and families with disabilities.

Strategy 3: Leverage General Supervision and Statewide Accountability processes, data systems, and improvement activities for Child Outcomes, Least Restrictive and Natural Environments, ensuring integrated and aligned mechanisms for evaluation.

Strategy 4: Invest in Statewide early learning capacity building efforts alongside cross-agency partners to ensure equitable access to meaningful, effective, and relevant innovations known to improve Child Outcomes, and reduce exclusionary practices.

Strategy 5: Increase coordination and alignment across agencies to ensure that efforts to improve outcomes for young children and prevent suspension and expulsion are not in competition or conflict with one another.

State staff continue to engage with national TA centers to determine the best way to proceed with expansion of these strategies and effective cross-sector investing to bring implementation efforts to scale. Support topics from WestEd, DASy and ECTA to further improve the state data system, evaluation, and integration of improvement activities into program implementation data report processes.

Describe the short-term or intermediate outcomes achieved for each infrastructure improvement strategy during the reporting period including the measures or rationale used by the State and stakeholders to assess and communicate achievement. Please relate short-term outcomes to one or more areas of a systems framework (e.g., governance, data, finance, accountability/monitoring, quality standards, professional development and/or technical assistance) and explain how these strategies support system change and are necessary for: (a) achievement of the SiMR; (b) sustainability of systems improvement efforts; and/or (c) scale-up.

During FFY 2024, Oregon achieved several short-term outcomes aligned with its SSIP infrastructure improvement strategies:

Governance & Cross-System Coordination: Expanded Oregon Early Childhood Inclusion Initiative teams from 3 to 9 communities, covering 16 counties. This strengthened governance and collaboration across agencies, supporting scale-up and sustainability.

Data Systems: Implemented the Pyramid Model Implementation Data System (PIDS) to improve fidelity monitoring and coaching support. Adoption rates and timely data submissions were tracked as measures of success.

Professional Development & Technical Assistance: Delivered statewide access to ePyramid modules and facilitated virtual series on Pyramid Model practices for EI/ECSE practitioners. Over 80% of targeted staff completed training, supporting workforce capacity and quality standards.

Quality Standards: Increased fidelity scores using Early Childhood Benchmarks of Quality (BoQ) and TPOT™ assessments in participating programs, demonstrating progress toward evidence-based practice implementation.

Stakeholder Engagement: Enhanced communication strategies, including multilingual materials and interpreter access, ensuring equitable participation in SSIP activities.

These outcomes support achievement of the SiMR by improving adult practices that directly impact children’s social-emotional development, sustainability through integrated data systems and coaching structures, and scale-up by expanding implementation teams statewide.

Did the State implement any new (newly identified) infrastructure improvement strategies during the reporting period? (yes/no)

NO

Provide a summary of the next steps for each infrastructure improvement strategy and the anticipated outcomes to be attained during the next reporting period.

For FFY 2025, Oregon will:

Expand Implementation Support: Increase the number of trained coaches and include regional technical assistance networks and trainers to sustain Pyramid Model and Inclusion Indicators; Expand implementation to include increased focus on alignment with early literacy, transformational social-emotional learning, and revised Early Learning and Kindergarten Guidelines.

Advance Data Integration: Fully operationalize PIDS and link fidelity data with child outcome data to inform continuous improvement; Launch modernized General Supervision data system, allowing areas to better measure improvement in child outcomes and access to regular education environment and receive relevant Technical Assistance from the Agency to support progress.

Strengthen Equity and Access: Continue to translate all training materials into additional languages and prioritize rural/frontier regions for TA support; Expand supports to families and differentiate guidance across audiences; support training to help partners to better understand child outcomes data and linkages to assessment tools, and improve communication through a comprehensive strategic communications plan developed by the state implementation team.

Measure Impact: Conduct annual fidelity checks and publish an equity impact report to monitor progress toward SiMR and inclusion goals.

Anticipated outcomes include statewide fidelity of Pyramid Model practices, measurable increases in inclusion rates, and improved child social-emotional outcomes as reflected in Indicator C3 and B7 Summary Statement 1.

List the selected evidence-based practices implemented in the reporting period:

Oregon Early Childhood Inclusion (Pyramid Model, Early Childhood Inclusion Indicators Initiative), Coaching and Professional Learning Communities.

Provide a summary of each evidence-based practice.

The State continued to invest in implementation of Pyramid Model, National Early Childhood Inclusion Indicators Initiative. These approaches are directly related to improving child outcomes outlined in the SiMR and have been effective in advancing child outcomes, reducing teacher stress, and supporting a comprehensive understanding of the practices and assessment tools needed to address the social-emotional needs of young children with and without disabilities.

The Pyramid Model is a conceptual framework of evidence-based practices that promote the healthy development of children’s social emotional development. The Pyramid Model builds upon a tiered system of support that addresses the needs of all, provided guidance about targeted supports that some children may need to support their learning, and identifies tools and supports for intensive interventions that may be needed for a few children in their early years.

The National Early Childhood Inclusion Indicators are the culmination of two years of deep engagement by the Early Childhood Technical Assistance Center and the National Center for Pyramid Model Innovations with key early learning partners at the national, state, and local level. The results of this outreach are a set of quality indicators that address inclusive policies and practices at the four levels of a State early care and education system: State, community, program, and early care and education environment (classroom).

Practice-Based Coaching and Professional Learning Communities, with Communities of Practice are effective and equitable strategies for enhancing adult learning through the provision of on-the job learning opportunities and feedback aligned with professional goals for practice improvement.

Provide a summary of how each evidence-based practices and activities or strategies that support its use, is intended to impact the SiMR by changing program/district policies, procedures, and/or practices, teacher/provider practices (e.g., behaviors), parent/caregiver outcomes, and/or child/outcomes.

Through implementation of the above-mentioned frameworks and classroom practices, the State utilizes practice-based coaching as the vehicle of professional development in combination with workshops, communities of practice and professional learning communities. These strategies for delivering professional development to impact and effect practice change have been identified for additional investment for improvement efforts across the State, leading regional programs to invest in additional supports to ensure staff have the skills to be effective coaches, as they lead and learn together alongside families and other caregivers.

For more information about the impact on community systems, practices, policies and procedures review the 2025 Oregon Early Childhood Inclusion Initiative Impact Report found at https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/oeci.aspx

Describe the data collected to monitor fidelity of implementation and to assess practice change.

For the Pyramid Model, the State used multiple fidelity measures to measure fidelity of implementation including State Benchmarks of Quality, Early Childhood Benchmarks of Quality, Teaching Practices Observation Tool (TPOT), Coaching Logs and Behavior Incident Reporting System data.

For completion of the Indicators for High-Quality Early Childhood Inclusion three implementing communities and the State Leadership Team gathered two data points. The State Leadership Team completed the State Indicators of High-Quality Inclusion and each community team completed the Community Indicators and Elements of High-Quality Inclusion.

Additional data was collected through survey and interview with Community and State Leadership Team participants during mid-year and end-of year events for Oregon Early Childhood Inclusion.

Data briefs and other reports can be found on the Oregon Inclusion Initiative website. (https://health.oregonstate.edu/elsi/oregon-inclusion-initiative) and on the ODE website: https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/oeci.aspx.

Describe any additional data (e.g., progress monitoring) that was collected that supports the decision to continue the ongoing use of each evidence-based practice.

Local level performance indicator data for C3, B6, and B7 data were collected in each implementing community and program. These data were shared with partners as part of the annual review process with the EI/ECSE Contractors, the Oregon Early Childhood Inclusion State Leadership Team, and the State Interagency Coordinating Council. In the data presented by the Early Childhood Coherent Strategies specialist, it was observed that accelerated growth occurred in implementation communities that used the Early Childhood Inclusion Indicators at the community level and the Indicators and Pyramid Model Framework at the Program level had remained stable, this also included factors regarding increased enrollment to pre-pandemic levels. This data was presented to SICC in January and Spring 2025.

Provide a summary of the next steps for each evidence-based practice and the anticipated outcomes to be attained during the next reporting period.

Given the results and expansion to 9 communities, ODE plans to continue shared investment in the implementation support team, which included evaluation and research staff from Oregon State University. The shared investment and expansion of the team to include a data support analyst will provide the state with more valid, reliable, and complete implementation data supporting coaches, providers, and programs with data for review by program, community, and state leadership teams.

This data will continue to inform the State Leadership Team for Oregon Early Childhood Inclusion and the Advosory Team for Every Child Belongs, a program funded and guided by the Department of Early Learning and Care.  Through a collaborative impact report, data will be shared annually and released in partnership with the State Leadership Team for High Quality Inclusion.

Results of investment in the Implementation Support Team will result in expansion of Pyramid Model Framework statewide and sustained systems coaching support within 9 regions. Plans for implementation of the inclusion indicators will follow progress and support to train regional training and technical assistance networks. This has a particular impact in rural and frontier regions of the state who have had limited access to quality training and support. This partnership will also ensure continued translation of materials into other languages for monolingual coaches and providers, ensuring an expansion of equitable access to high quality trainings, resources, and supports to the entire early learning system who serves and supports young children experiencing disability.

Does the State intend to continue implementing the SSIP without modifications? (yes/no)

NO

If no, describe any changes to the activities, strategies or timelines described in the previous submission and include a rationale or justification for the changes.

In the continued effort to ensure alignment and coherence across systems, ODE will integrate other activities from Raise Up Oregon and the ODE Accountability Framework to the SSIP in the next two years. This includes revision of the Early Learning and Kindergarten Guidelines, Early Literacy Framework, Transition to AEPS-3, Modernization of the General Supervision System for IDEA Part C and Part B, Release of Policy and Practice Briefs, Bi-annual Workforce Needs Survey and Training and Technical Assistance to support effective implementation of IDEA.

Section C: Stakeholder Engagement

Description of Stakeholder Input

The State engages stakeholders through the State Interagency Coordinating Council (SICC), collaboration with the parent training and information center (FACT Oregon), public reporting, and targeted outreach efforts. These structures support stakeholder involvement in reviewing data, setting targets, shaping improvement strategies, and monitoring progress. The State has made focused efforts to broaden participation in the SICC and to strengthen connections with Local Interagency Coordinating Councils. The State also works to improve participation in the annual Parent Survey and to ensure feedback from families informs system improvement activities.

The State collaborates with FACT, the Parent Advocacy Center, to build the capacity of diverse groups of parents in supporting the development and implementation of activities aimed at improving outcomes for infants and toddlers with disabilities and their families. Through this partnership, the State works to empower parents from a variety of backgrounds to engage in activities that enhance the quality of services and supports for children with disabilities.

To increase the diversity of parent representation on the State Interagency Coordinating Council (SICC), the State has made focused recruitment efforts. Additionally, the State has established an SICC subcommittee dedicated to the Local Interagency Coordinating Councils (LICCs), which is working to better understand the composition of these councils and ensure that feedback from the group is effectively heard and incorporated into the decision-making process.

The State has also implemented targeted strategies to improve parent response rates from families of color and those for whom English is not the first language in the annual Parent Survey. These efforts are aimed at ensuring that a wide range of voices is included in shaping the policies and practices that impact families and children with disabilities.

Additional data and input has been gathered through review of studies procured by the Department of Early Learning and Care to examine family needs and the persistent problem of exclusionary practices which indicate a high prevalence of children experiencing disability, birth to five, being asked to leave their early care and education environments.

Targeted engagement on personnel standards, the state systemic improvement plan and activities, strategies for improving access to inclusive early learning environments for children with disabilities, and updated guidance on discipline occurred throughout the reporting period. This included presentations during conferences, meetings, and advisory groups, updates to the Agency web pages, leveraging newsletters for Oregon Early Childhood Inclusion, webinars, and memorandums to district leadership and superintendents.

The State engaged with various stakeholder groups to gather feedback on the revision of the EI/ECSE personnel standards. Multiple stakeholder engagement sessions were held with EI/ECSE practitioners, community partners, and families. The State partnered with a parent information and training center, Family and Community Together (FACT) Oregon, to host a feedback session with families of children receiving EI/ECSE services. Materials were made available in Spanish and Spanish translation was provided at the family feedback session.

Describe the specific strategies implemented to engage stakeholders in key improvement efforts.

Strategies to include partners and gather feedback in key improvement efforts include diverse parent engagement including targeted recruitment to advisory groups in partnership with the governor’s office, increased availability of interpreters and translated materials as requested by parent and community members during registration for training and engagement events, partnership with higher education and the Parent Training and Information Center and Community Expansion Grant recipient to ensure bilingual and bicultural program specialists are available to support understanding of IDEA, the DEC recommended practices, and topics for engagement, engaging partners in shared professional development activities and gathering input and feedback through evaluation and follow-up, and the use of Agency newsletters for updates on initiatives, opportunities for professional development, and highlights on implementation in practice.

Additionally, the State continues to maintain ongoing partnership with the State Interagency Coordinating Council (SICC), including parent members, to continue to develop improvement strategies. These discussions with the SICC help to inform statewide improvement strategies as reflected in the SPP/APR. Topics addressed in 202 included regular legislative session updates , updates on improvement efforts for results indicators, and the development of cross-agency partnership to better align the early learning system under Raise Up Oregon, a comprehensive multi-systems plan for improving outcomes for children and families. More information about the engagement with the State Interagency Coordinating Council can be found on the SICC website: https://www.oregon.gov/ode/students-and-family/SpecialEducation/earlyintervention/Pages/sicc.aspx

Were there any concerns expressed by stakeholders during engagement activities? (yes/no)

YES

Describe how the State addressed the concerns expressed by stakeholders.

The state continues to evaluate and monitor the impacts across age groups and target investments for improvement activities to specifically address the needs identified by Part C home visitors and families entering early intervention through Part C. This has led to additional investments in professional development, supports for providers, and increased engagement in broader statewide activities addressing the quality of home visiting, statewide system development, and continuity across early learning systems of care.

Additional concerns were elevated regarding data, while improving steadily, are not enough to meet state targets or discreet enough to provide any data that would be predictive of a child’s likelyhood to experience exclusion from early learning opportunities. There is a concern that the state level data does not reflect the experience or outcomes enough to understand the impact of coherent strategies and improvement activities or draw conclusions about what is consistently working and what challenges to improvement persist.

Additional Implementation Activities

List any activities not already described that the State intends to implement in the next fiscal year that are related to the SiMR.

N/A

Provide a timeline, anticipated data collection and measures, and expected outcomes for these activities that are related to the SiMR.

N/A

Describe any newly identified barriers and include steps to address these barriers.

State budget concerns and impacts of federal policies and actions may impact progress in the next year. Currently, increased collaboration, planning, and coordination of services and supports are planned to mitigate possible impacts on children and families.

Provide additional information about this indicator (optional).

## 11 - Prior FFY Required Actions

None

## 11 - OSEP Response

The State did not provide the numerator and denominator descriptions in the FFY 2024 SPP/APR Data table.

## 11 - Required Actions

The State did not provide numerator and denominator descriptions in the FFY 2024 data table. The State must provide the required numerator and denominator descriptions for FFY 2025 in the FFY 2025 SPP/APR.

# Indicator 12: General Supervision

Instructions and Measurement

Monitoring Priority: General Supervision

Compliance indicator: This SPP/APR indicator focuses on the State lead agency’s exercise of its general supervision responsibility to monitor its Early Intervention Service (EIS) Providers and EIS Programs for requirements under Part C of the Individuals with Disabilities Act (IDEA) through the State’s reporting on timely correction of noncompliance (20 U.S.C. 1416(a) and 1435(a)(10); 34 C.F.R. §§ 303.120 and 303.700). In reporting on findings under this indicator, the State must include findings from data collected through all components of the State’s general supervision system that are used to identify noncompliance. This includes, but is not limited to, information collected through State monitoring, State database/data system dispute resolution, and fiscal management systems as well as other mechanisms through which noncompliance is identified by the State.

Data Source

The State must include findings from data collected through all components of the State’s general supervision system that are used to identify noncompliance. This includes, but is not limited to, information collected through State monitoring, State database/data system, dispute resolution, and fiscal management systems as well as other mechanisms through which noncompliance is identified by the State. Provide the actual numbers used in the calculation. Include all findings of noncompliance regardless of the specific type and extent of noncompliance.

Measurement

This SPP/APR indicator requires the reporting on the percent of findings of noncompliance corrected within one year of identification:

- # of findings of noncompliance issued the prior Federal fiscal year (FFY) (e.g., for the FFY 2024 submission, use FFY 2023, July 1, 2023 – June 30, 2024)

- # of findings of noncompliance the State verified were corrected no later than one year after the State’s written notification of findings of noncompliance

Percent = [(b) divided by (a)] times 100

Instructions

Targets must be 100%.

States are required to complete the General Supervision Data Table within the online reporting tool.

Report in Column A, the number of findings of noncompliance made in FFY 2023 (July 1, 2023 – June 30, 2024), as reported in the compliance indicator, and report in Column C1, the number of those findings which were timely corrected, as soon as possible and in no case later than one year after the State’s written notification of noncompliance. Report in Column B, the number of additional findings of noncompliance related to the compliance indicator made in FFY 2023 (July 1, 2023-June 30, 2024) and report in Column C2, the number of those additional findings related to the compliance indicator which were timely corrected, as soon as possible and in no case later than one year after the State’s written notification of noncompliance.

States may also provide additional information related to other findings of noncompliance that are not specific to the compliance indicators. This row would include reporting on all other findings of noncompliance that were not reported by the State under the compliance indicators (e.g., Results indicators (including related requirements), Fiscal, Dispute Resolution, etc.). In future years (e.g., with the FFY 2026 SPP/APR), States may be required to further disaggregate findings by results indicators (2, 3, 4, 5, 6, 9, 10, and 11), fiscal and other areas.

Provide detailed information about the timely correction of child-specific and regulatory/systemic noncompliance as noted in OSEP’s response for the previous SPP/APR. If the State did not ensure timely correction of the previous findings of noncompliance, provide information on the extent to which noncompliance was subsequently corrected (more than one year after identification). In addition, provide information regarding the nature of any continuing noncompliance and the actions that have been taken, or will be taken, to ensure the subsequent correction of the outstanding noncompliance, to address areas in need of improvement, and any sanctions or enforcement actions used, as necessary and consistent with IDEA’s enforcement provisions, the OMB Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards (Uniform Guidance), and State rules.

## 12 - Indicator Data

Historical Data

| Baseline Year | Baseline Data |
| --- | --- |
| 2023 | 100.00% |

| FFY | 2019 | 2020 | 2021 | 2022 | 2023 |
| --- | --- | --- | --- | --- | --- |
| Target | 100% | 100% | 100% | 100% | 100% |
| Data |  |  |  |  | 100.00% |

Targets

| FFY | 2024 | 2025 |
| --- | --- | --- |
| Target | 100% | 100% |

Indicator 1. Percent of infants and toddlers with Individual Family Service Plans (IFSPs) who receive the early intervention services on their IFSPs in a timely manner. (20 U.S.C. 1416(a)(3)(A) and 1442)

Findings of Noncompliance Identified in FFY 2023

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 6 | 0 | 6 | 0 | 0 |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any additional findings reported in Column B.

N/A

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

To ensure that the sources of noncompliance were correctly implementing the regulatory requirements, the State conducted additional verification activities. Through our monitoring process, a total of six instances of child-specific noncompliance were identified. Programs with noncompliance are required to complete corrective action plans to address the root cause of noncompliance. Each EI program with identified noncompliance completed and submitted subsequent file reviews in the SPR&I (Oregon's electronic monitoring system) for child records developed after the original noncompliance was corrected and corrective actions implemented.

The State reviewed these subsequent files in SPR&I and cross-checked the information in ecWeb, Oregon’s statewide EI/ECSE data system, to confirm current compliance and correct implementation of required procedures. Through this review, the State verified that all programs with previous noncompliance demonstrated sustained correction and full adherence to the regulatory requirements for timely services.

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

For FFY 2023, the State completed a comprehensive verification process to ensure timely correction of all six identified instances of individual noncompliance.

To verify correction of the identified noncompliance, the State completed the following actions:

- The Early Intervention (EI) program submitted documentation of the correction of noncompliance for each of the six individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system. The state reviewed this data as one source of information about the noncompliance correction. The State reviewed the six individual child records in EcWeb, (Oregon's Statewide Database) as a second source of data.

- In all six cases, the state verified that services were provided, although late, or the child was not longer in the program's jurisdiction. In accordance with AQ-23-01, we also verified that there were no outstanding corrective actin under a state complaint or due process hearing decision.

Indicator 7. Percent of eligible infants and toddlers with IFSPs for whom initial evaluation, initial assessment, and the initial IFSP meeting were conducted within Part C’s 45-day timeline. (20 U.S.C. 1416(a)(3)(B) and 1442)

Findings of Noncompliance Identified in FFY 2023

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 202 | 0 | 202 | 0 | 0 |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any additional findings reported in Column B.

N/A

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

The State verified per OSEP QA 23-01 that all programs with past noncompliance were correctly implementing the regulatory requirements based on updated monthly 45-day timeline data from each program. The state summarized continued new monthly CAP data for each program detailing no new cases over the 45-day timeline or only CAPs with parent delays. Subsequent individual evaluations were also reviewed by the State in EcWeb, the State IFSP database, and confirmed subsequent timely evaluations.

For FFY 2023, the programs submitted monthly corrective action plans (CAPs) to the State for any child for whom the 45-day timeline was not met. Included in the CAP that programs submitted: 1) the number of days needed to complete the referral, eligibility and initial IFSP meeting; 2) the child’s initials and birth date; 3) the specific reasons for not meeting the 45-day timeline (parent delay or program delay); 4) the corrective actions based on an analysis of the problem(s); 5) the activities planned to address each problem identified and 6) request for ODE technical assistance if desired.

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

The State verified that 100% (202/202) of the individual incidents of noncompliance in FFY 2023 were corrected within one year. All programs with noncompliance conducted the initial evaluation, assessment, and IFSP meeting, although late, for each individual child for whom the 45-day timeline was not met based on a monthly State review and approved submitted individual Corrective Action Plans (CAPs) documenting each of the 202 cases of noncompliance were corrected to 100% (consistent with OSEP QA 23-01).

The State verified as per OSEP QA 23-01 that all programs with past noncompliance were correctly implementing the regulatory requirements based on updated monthly 45-day timeline data from each program. The State summarized continued new monthly CAP data for each program detailing no new cases over the 45-day timeline or only CAPs with parent delays. Subsequent evaluations were also reviewed by the State in EcWeb, the State IFSP database, and confirmed subsequent timely evaluations.

Indicator 8A. The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

A. Developed an IFSP with transition steps and services at least 90 days (and, at the discretion of all parties, not more than nine months) prior to the toddler’s third birthday. (20 U.S.C. 1416(a)(3)(B) and 1442).

Findings of Noncompliance Identified in FFY 2023

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 10 | 0 | 10 | 0 | 0 |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any additional findings reported in Column B.

N/A

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

In FFY 2023, 93.29% (139 of 149) of Early Intervention (EI) child records reviewed for transition demonstrated that transition steps and services were developed at least 90 calendar days—and, at the discretion of the parties, up to nine months—before the child’s third birthday to support a smooth transition to preschool or other appropriate community services.

Of the 35 EI programs statewide, seven programs were issued findings of noncompliance, representing a total of ten child-specific instances of noncompliance.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition steps and services were provided in accordance with federal and state requirements.

Through this review of subsequent data, the State verified that each of the seven EI programs achieved 100% compliance within one year of identification and is now correctly implementing the regulatory requirements for timely transition planning and service provision.

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

- The EI program submitted documentation of the correction of noncompliance for each of the ten individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

- The state reviewed the ten individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition plans were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (10 of 10) incidents of noncompliance, identified across seven regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition plans with steps and services for each child, unless the child was no longer within the jurisdiction of the EI program.

Indicator 8B. The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

B.  Notified (consistent with any opt-out policy) the SEA and LEA where the toddler resides at least 90 days prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services. (20 U.S.C. 1416(a)(3)(B) and 1442)

Findings of Noncompliance Identified in FFY 2023

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 0 | 0 | 0 | 0 | 0 |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any additional findings reported in Column B.

N/A

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

N/A

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

N/A

Indicator 8C. The percentage of toddlers with disabilities exiting Part C with timely transition planning for whom the Lead Agency has:

C.  Conducted the transition conference held with the approval of the family at least 90 days (and, at the discretion of all parties, not more than nine months) prior to the toddler’s third birthday for toddlers potentially eligible for Part B preschool services. (20 U.S.C. 1416(a)(3)(B) and 1442)

Findings of Noncompliance Identified in FFY 2023

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 12 | 0 | 12 | 0 | 0 |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any additional findings reported in Column B.).

N/a

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

Of the 35 EI programs in the state, seven had findings of noncompliance. A total of twelve instances of child-specific noncompliance were identified across the seven EI programs.

To verify that each program corrected the noncompliance and was correctly implementing the regulatory requirements, the State conducted subsequent file reviews using ecWeb, Oregon’s statewide EI/ECSE data system. The State reviewed additional child records from each of the seven programs, selecting files dated after the completion of corrective actions for all children exiting Part C, to ensure that timely transition conferences were provided in accordance with federal and state requirements.

Through this review of subsequent data, the state verified that each of the seven EI programs achieved 100% compliance within one year and are correctly implementing the regulatory requirements for timely transition conferences.

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

The state completed a comprehensive verification process to ensure correction of all identified individual instances of noncompliance. The following steps were completed for correcting each case of noncompliance:

- The EI program submitted documentation of the correction of noncompliance for each of the twelve individual noncompliant IFSPs through online submission in SPR&I, Oregon’s electronic monitoring system.

- The state verified the twelve individual child records in ecWeb, Oregon’s statewide EI data system, to see if transition conferences were provided, although untimely, or the child was no longer in the program’s jurisdiction.

For FFY 2023, 100% (12 of 12) incidents of noncompliance, identified across [Ex eight] regional sites, were corrected within one year. Each program with identified noncompliance developed an IFSP that included transition conferences for each child, unless the child was no longer within the jurisdiction of the EI program.

Optional for FFY 2024, and 2025:

Other Areas - All other findings: States may report here on all other findings of noncompliance that were not reported under the compliance indicators listed above (e.g., Results indicators (including related requirements), Fiscal, Dispute Resolution, etc.).

| Column B: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Column B for which correction was not completed or timely corrected |
| --- | --- | --- |

Please explain the source (e.g., State monitoring, State database/data system, dispute resolution, fiscal, related requirements, etc.) of any findings reported in this section:

Please describe, consistent with OSEP QA 23-01, how the State verified that the source of noncompliance is correctly implementing the regulatory requirements based on updated data:

Please describe, consistent with OSEP QA 23-01, how the State verified that each individual case of noncompliance was corrected:

Total for All Noncompliance Identified (Indicators 1, 7, 8A, 8B, 8C, and Optional Areas):

| Column A: # of written findings of noncompliance identified in FFY 2023 (7/1/23 – 6/30/24) | Column B: # of any other written findings of noncompliance identified in FFY 2023 not reported in Column A (e.g., those issued based on other IDEA requirements), if applicable | Column C1: # of written findings of noncompliance from Column A that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column C2: # of written findings of noncompliance from Column B that were timely corrected (i.e., verified as corrected no later than one year from identification) | Column D: # of written findings of noncompliance from Columns A and B for which correction was not completed or timely corrected |
| --- | --- | --- | --- | --- |
| 230 | 0 | 230 | 0 | 0 |

FFY 2024 SPP/APR Data

| Number of findings of Noncompliance that were timely corrected | Number of findings of Noncompliance that were identified in FFY 2023 | FFY 2023 Data | FFY 2024 Target | FFY 2024 Data | Status | Slippage |
| --- | --- | --- | --- | --- | --- | --- |
| 230 | 230 | 100.00% | 100% | 100.00% | Met target | No Slippage |

| Percent of findings of noncompliance not corrected or not verified as corrected within one year of identification | 0.00% |
| --- | --- |

Provide additional information about this indicator (optional)

Summary of Findings of Noncompliance identified in FFY 2023 Corrected in FFY 2024 (corrected within one year from identification of the noncompliance):

| 1. Number of findings of noncompliance the State identified during FFY 2023 (the period from July 1, 2023 through June 30, 2024). | 230 |
| --- | --- |
| 2. Number of findings the State verified as timely corrected (corrected within one year from the date of written notification to the EIS program/provider of the finding) | 230 |
| 3. Number of findings not verified as corrected within one year | 0 |

Subsequent Correction: Summary of All Outstanding Findings of Noncompliance identified in FFY 2023 Not Timely Corrected in FFY 2024 (corrected more than one year from identification of the noncompliance):

| 4. Number of findings of noncompliance not timely corrected | 0 |
| --- | --- |
| 5. Number of written findings of noncompliance (Col. A) the State has verified as corrected beyond the one-year timeline ("subsequent correction") - as reported in Indicator 1, 7, 8A, 8B, 8C | 0 |
| 6a. Number of additional written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Indicator 1 | 0 |
| 6b. Number of additional written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Indicator 7 | 0 |
| 6c. Number of additional written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Indicator 8A | 0 |
| 6d. Number of additional written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Indicator 8B | 0 |
| 6e. Number of additional written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Indicator 8C | 0 |
| 6f. (optional) Number of written findings of noncompliance (Col. B) the state has verified as corrected beyond the one-year timeline (“subsequent correction”) - Other Areas - All other findings | 0 |
| 7. Number of findings not yet verified as corrected | 0 |

Subsequent correction: If the State did not ensure timely correction of previous findings of noncompliance, provide information on the nature of any continuing noncompliance and the actions that have been taken, or will be taken, to ensure the subsequent correction of the outstanding noncompliance, to address areas in need of improvement, and any sanctions or enforcement actions used, as necessary and consistent with IDEA’s enforcement provisions, the OMB Uniform Administrative Requirements, Cost Principles, and Audit Requirements for Federal Awards (Uniform Guidance), and State rules.

N/A

Correction of Findings of Noncompliance Identified Prior to FFY 2023

| Year Findings of Noncompliance Were Identified | Findings of Noncompliance Not Yet Verified as Corrected as of FFY 2023 APR | Findings of Noncompliance Verified as Corrected | Findings Not Yet Verified as Corrected |
| --- | --- | --- | --- |

## 12 - Prior FFY Required Actions

None

## 12 - OSEP Response

## 12 - Required Actions

# Certification

Instructions

Choose the appropriate selection and complete all the certification information fields. Then click the "Submit" button to submit your APR.

Certify

I certify that I am the Director of the State's Lead Agency under Part C of the IDEA, or his or her designee, and that the State's submission of its IDEA Part C State Performance Plan/Annual Performance Report is accurate.

Select the certifier’s role

Lead Agency Director

Name and title of the individual certifying the accuracy of the State's submission of its IDEA Part C State Performance Plan/Annual Performance Report.

Name:

Kara Williams

Title:

Director of Inclusive Services

Email:

kara.williams@ode.oregon.gov

Phone:

503-689-5642

Submitted on:

04/17/26  1:40:13 PM

# Determination Enclosures

## RDA Matrix

Oregon

2026 Part C Results-Driven Accountability Matrix

Results-Driven Accountability Percentage and Determination (1)

| Percentage (%) | Determination |
| --- | --- |
| 87.50% | Meets Requirements |

Results and Compliance Overall Scoring

| Section | Total Points Available | Points Earned | Score (%) |
| --- | --- | --- | --- |
| Results | 8 | 6 | 75.00% |
| Compliance | 18 | 18 | 100.00% |

2026 Part C Results Matrix

I. Data Quality

(a) Data Completeness: The percent of children included in your State’s FFY 2024 Outcomes Data (Indicator C3)

| Number of Children Reported in Indicator C3 (i.e., outcome data) | 2,880 |
| --- | --- |
| Number of Children Reported Exiting in 618 Data (i.e., 618 exiting data) | 3,771 |
| Percentage of Children Exiting who are Included in Outcome Data (%) | 76.37 |
| Data Completeness Score (please see Appendix A for a detailed description of this calculation) | 2 |

(b) Data Anomalies: Anomalies in your State’s FFY 2024 Outcomes Data

| Data Anomalies Score (please see Appendix B for a detailed description of this calculation) | 2 |
| --- | --- |

II. Child Performance

(a) Data Comparison: Comparing your State’s FFY 2024 Outcomes Data to other States’ FFY 2024 Outcomes Data

| Data Comparison Score (please see Appendix C for a detailed description of this calculation) | 1 |
| --- | --- |

(b) Performance Change Over Time: Comparing your State’s FFY 2024 data to your State’s FFY 2023 data

| Performance Change Score (please see Appendix D for a detailed description of this calculation) | 1 |
| --- | --- |

| Summary Statement Performance | Outcome A: Positive Social Relationships SS1 (%) | Outcome A: Positive Social Relationships SS2 (%) | Outcome B: Knowledge and Skills SS1 (%) | Outcome B: Knowledge and Skills SS2 (%) | Outcome C: Actions to Meet Needs SS1 (%) | Outcome C: Actions to Meet Needs SS2 (%) |
| --- | --- | --- | --- | --- | --- | --- |
| FFY 2024 | 86.97% | 40.97% | 61.03% | 35.14% | 71.96% | 34.58% |
| FFY 2023 | 86.14% | 40.01% | 63.29% | 31.68% | 71.74% | 33.32% |

(1) For a detailed explanation of how the Compliance Score, Results Score, and the Results-Driven Accountability Percentage and Determination were calculated, review "How the Department Made Determinations under Section 616(d) of the Individuals with Disabilities Education Act in 2026: Part C."

2026 Part C Compliance Matrix

| Part C Compliance Indicator (2) | Performance (%) | Full Correction of Findings of Noncompliance Identified in FFY 2023 (3) | Score |
| --- | --- | --- | --- |
| Indicator 1: Timely service provision | 97.35% | YES | 2 |
| Indicator 7: 45-day timeline | 97.81% | YES | 2 |
| Indicator 8A: Timely transition plan | 92.11% | YES | 2 |
| Indicator 8B: Transition notification | 100.00% | N/A | 2 |
| Indicator 8C: Timely transition conference | 91.45% | YES | 2 |
| Indicator 12: General Supervision | 100 | YES | 2 |
| Timely and Accurate State-Reported Data | 100.00% |  | 2 |
| Timely State Complaint Decisions | 100.00% |  | 2 |
| Timely Due Process Hearing Decisions | N/A |  | N/A |
| Longstanding Noncompliance |  |  | 2 |
| Programmatic Specific Conditions | None |  |  |
| Uncorrected identified noncompliance | None |  |  |

(2) The complete language for each indicator is located in the Part C SPP/APR Indicator Measurement Table at:

https://sites.ed.gov/idea/files/FFY2024-Part-C-SPP-APR-Reformatted-Measurement-Table.pdf

(3) This column reflects full correction, which is factored into the scoring only when the compliance data are >=90% and <95% for an indicator.

Appendix A

I. (a) Data Completeness:

The Percent of Children Included in your State's FFY 2024 Outcomes Data (Indicator C3)

Data completeness was calculated using the total number of Part C children who were included in your State’s FFY 2024 Outcomes Data (C3) and the total number of children your State reported in its FFY 2024 IDEA Section 618 data. A percentage for your State was computed by dividing the number of children reported in your State’s Indicator C3 data by the number of children your State reported exited during FFY 2024 in the State’s FFY 2024 IDEA Section 618 Exit Data.

| Data Completeness Score | Percent of Part C Children included in Outcomes Data (C3) and 618 Data |
| --- | --- |
| 0 | Lower than 34% |
| 1 | 34% through 64% |
| 2 | 65% and above |

Appendix B

I. (b) Data Quality:

Anomalies in Your State's FFY 2024 Outcomes Data

This score represents a summary of the data anomalies in the FFY 2024 Indicator 3 Outcomes Data reported by your State. Publicly available data for the preceding four years reported by and across all States for each of 15 progress categories under Indicator 3 (in the FFY 2020 – FFY 2023 APRs) were used to determine an expected range of responses for each progress category under Outcomes A, B, and C. For each of the 15 progress categories, a mean was calculated using the publicly available data and a lower and upper scoring percentage was set 1 standard deviation above and below the mean for category a, and 2 standard deviations above and below the mean for categories b through e (numbers are shown as rounded for display purposes, and values are based on data for States with summary statement denominator greater than 199 exiters). In any case where the low scoring percentage set from 1 or 2 standard deviations below the mean resulted in a negative number, the low scoring percentage is equal to 0.

If your State's FFY 2024 data reported in a progress category fell below the calculated "low percentage" or above the "high percentage" for that progress category for all States, the data in that particular category are statistically improbable outliers and considered an anomaly for that progress category. If your State’s data in a particular progress category was identified as an anomaly, the State received a 0 for that category. A percentage that is equal to or between the low percentage and high percentage for each progress category received 1 point. A State could receive a total number of points between 0 and 15. Thus, a point total of 0 indicates that all 15 progress categories contained data anomalies and a point total of 15 indicates that there were no data anomalies in all 15 progress categories in the State's data. An overall data anomaly score of 0, 1, or 2 is based on the total points awarded.

| Outcome A | Positive Social Relationships |
| --- | --- |
| Outcome B | Knowledge and Skills |
| Outcome C | Actions to Meet Needs |

| Category a | Percent of infants and toddlers who did not improve functioning |
| --- | --- |
| Category b | Percent of infants and toddlers who improved functioning but not sufficient to move nearer to functioning comparable to same-aged peers |
| Category c | Percent of infants and toddlers who improved functioning to a level nearer to same-aged peers but did not reach it |
| Category d | Percent of infants and toddlers who improved functioning to reach a level comparable to same-aged peers |
| Category e | Percent of infants and toddlers who maintained functioning at a level comparable to same-aged peers |

Expected Range of Responses for Each Outcome and Category, FFY 2024

| Outcome\ Category | Mean | StDev | -1SD | +1SD |
| --- | --- | --- | --- | --- |
| Outcome A\ Category a | 1.49 | 3.27 | -1.78 | 4.76 |
| Outcome B\ Category a | 1.29 | 2.82 | -1.52 | 4.11 |
| Outcome C\ Category a | 1.29 | 2.8 | -1.51 | 4.09 |

| Outcome\ Category | Mean | StDev | -2SD | +2SD |
| --- | --- | --- | --- | --- |
| Outcome A\ Category b | 24.44 | 9.04 | 6.36 | 42.52 |
| Outcome A\ Category c | 22.25 | 13.92 | -5.6 | 50.09 |
| Outcome A\ Category d | 26.34 | 9.71 | 6.92 | 45.76 |
| Outcome A\ Category e | 25.48 | 16.58 | -7.68 | 58.64 |
| Outcome B\ Category b | 26.03 | 9.37 | 7.29 | 44.78 |
| Outcome B\ Category c | 30.64 | 13.31 | 4.01 | 57.26 |
| Outcome B\ Category d | 29.87 | 8.22 | 13.44 | 46.31 |
| Outcome B\ Category e | 12.16 | 9.18 | -6.19 | 30.51 |
| Outcome C\ Category b | 22.37 | 9.63 | 3.1 | 41.64 |
| Outcome C\ Category c | 24.39 | 14.01 | -3.63 | 52.41 |
| Outcome C\ Category d | 32.05 | 8.74 | 14.58 | 49.53 |
| Outcome C\ Category e | 19.89 | 14.88 | -9.87 | 49.66 |

| Data Anomalies Score | Total Points Received in All Progress Areas |
| --- | --- |
| 0 | 0 through 9 points |
| 1 | 10 through 12 points |
| 2 | 13 through 15 points |

Anomalies in Your State’s FFY 2024 Outcomes Data

| Number of Infants and Toddlers with IFSP’s Assessed in your State | 2,880 |
| --- | --- |

| Outcome A — Positive Social Relationships | Category a | Category b | Category c | Category d | Category e |
| --- | --- | --- | --- | --- | --- |
| State Performance | 51 | 282 | 1,367 | 856 | 324 |
| Performance (%) | 1.77% | 9.79% | 47.47% | 29.72% | 11.25% |
| Scores | 1 | 1 | 1 | 1 | 1 |

| Outcome B — Knowledge and Skills | Category a | Category b | Category c | Category d | Category e |
| --- | --- | --- | --- | --- | --- |
| State Performance | 43 | 895 | 930 | 539 | 473 |
| Performance (%) | 1.49% | 31.08% | 32.29% | 18.72% | 16.42% |
| Scores | 1 | 1 | 1 | 1 | 1 |

| Outcome C — Actions to Meet Needs | Category a | Category b | Category c | Category d | Category e |
| --- | --- | --- | --- | --- | --- |
| State Performance | 32 | 696 | 1,156 | 712 | 284 |
| Performance (%) | 1.11% | 24.17% | 40.14% | 24.72% | 9.86% |
| Scores | 1 | 1 | 1 | 1 | 1 |

|  | Total Score |
| --- | --- |
| Outcome A | 5 |
| Outcome B | 5 |
| Outcome C | 5 |
| Outcomes A-C | 15 |

| Data Anomalies Score | 2 |
| --- | --- |

Appendix C

II. (a) Data Comparison:

Comparing Your State’s FFY 2024 Outcomes Data to Other States’ FFY 2024 Outcome Data

This score represents how your State's FFY 2024 Outcomes data compares to other States' FFY 2024 Outcomes Data. Your State received a score for the distribution of the 6 Summary Statements for your State compared to the distribution of the 6 Summary Statements in all other States. The 10th and 90th percentile for each of the 6 Summary Statements was identified and used to assign points to performance outcome data for each Summary Statement (values are based on data for States with a summary statement denominator greater than 199 exiters). Each Summary Statement outcome was assigned 0, 1, or 2 points. If your State's Summary Statement value fell at or below the 10th percentile, that Summary Statement was assigned 0 points. If your State's Summary Statement value fell between the 10th and 90th percentile, the Summary Statement was assigned 1 point, and if your State's Summary Statement value fell at or above the 90th percentile the Summary Statement was assigned 2 points. The points were added up across the 6 Summary Statements. A State can receive a total number of points between 0 and 12, with 0 points indicating all 6 Summary Statement values were at or below the 10th percentile and 12 points indicating all 6 Summary Statements were at or above the 90th percentile. An overall comparison Summary Statement score of 0, 1, or 2 was based on the total points awarded.

Summary Statement 1: Of those infants and toddlers who entered or exited early intervention below age expectations in each Outcome, the percent who substantially increased their rate of growth by the time they turned 3 years of age or exited the program.

Summary Statement 2: The percent of infants and toddlers who were functioning within age expectations in each Outcome by the time they turned 3 years of age or exited the program.

Scoring Percentages for the 10th and 90th Percentile for Each Outcome and Summary Statement, FFY 2024

| Percentiles | Outcome A SS1 | Outcome A SS2 | Outcome B SS1 | Outcome B SS2 | Outcome C SS1 | Outcome C SS2 |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | 48.11% | 35.40% | 55.43% | 29.71% | 54.53% | 33.99% |
| 90 | 79.69% | 72.29% | 81.28% | 63.82% | 82.81% | 75.29% |

| Data Comparison Score | Total Points Received Across SS1 and SS2 |
| --- | --- |
| 0 | 0 through 4 points |
| 1 | 5 through 8 points |
| 2 | 9 through 12 points |

Your State’s Summary Statement Performance FFY 2024

| Summary Statement (SS) | Outcome A: Positive Social Relationships SS1 | Outcome A: Positive Social Relationships SS2 | Outcome B: Knowledge and Skills SS1 | Outcome B: Knowledge and Skills SS2 | Outcome C: Actions to meet needs SS1 | Outcome C: Actions to meet needs SS2 |
| --- | --- | --- | --- | --- | --- | --- |
| Performance (%) | 86.97% | 40.97% | 61.03% | 35.14% | 71.96% | 34.58% |
| Points | 2 | 1 | 1 | 1 | 1 | 1 |

| Total Points Across SS1 and SS2 | 7 |
| --- | --- |

| Your State’s Data Comparison Score | 1 |
| --- | --- |

Appendix D

II. (b) Performance Change Over Time:

Comparing your State’s FFY 2024 Outcomes Data to your State’s FFY 2023 Outcomes Data

The Summary Statement percentages in each Outcomes Area from the previous year’s reporting (FFY 2023) is compared to the current year (FFY 2024) using the test of proportional difference to determine whether there is a statistically significant (or meaningful) growth or decline in child achievement based upon a significance level of p<=.05. The data in each Outcome Area is assigned a value of 0 if there was a statistically significant decrease from one year to the next, a value of 1 if there was no significant change, and a value of 2 if there was a statistically significant increase across the years. The scores from all 6 Outcome Areas are totaled, resulting in a score from 0 – 12. The Overall Performance Change Score for this results element of ‘0’, ‘1’, or ‘2’ for each State is based on the total points awarded. Where OSEP has approved a State’s reestablishment of its Indicator C3 Outcome Area baseline data the State received a score of ‘N/A’ for this element.

Test of Proportional Difference Calculation Overview

The summary statement percentages from the previous year’s reporting were compared to the current year using an accepted formula (test of proportional difference) to determine whether the difference between the two percentages is statistically significant (or meaningful), based upon a significance level of p<=.05. The statistical test has several steps. All values are shown as rounded for display purposes.

Step 1: Compute the difference between the FFY 2024 and FFY 2023 summary statements.

e.g., C3A FFY2024% - C3A FFY2023% = Difference in proportions

Step 2: Compute the standard error of the difference in proportions using the following formula which takes into account the value of the summary statement from both years and the number of children that the summary statement is based on

Sqrt[([FFY2023% * (1-FFY2023%)] / FFY2023N) + ([FFY2024% * (1-FFY2024%)] / FFY2024N)] = Standard Error of Difference in Proportions

Step 3: The difference in proportions is then divided by the standard error of the difference to compute a z score.

Difference in proportions /standard error of the difference in proportions = z score

Step 4: The statistical significance of the z score is located within a table and the p value is determined.

Step 5: The difference in proportions is coded as statistically significant if the p value is less than or equal to .05.

Step 6: Information about the statistical significance of the change and the direction of the change are combined to arrive at a score for the summary statement using the following criteria

0 = statistically significant decrease from FFY 2023 to FFY 2024

1 = No statistically significant change

2= statistically significant increase from FFY 2023 to FFY 2024

Step 7: The score for each summary statement and outcome is summed to create a total score with a minimum of 0 and a maximum of 12. The score for the test of proportional difference is assigned a score for the Indicator 3 Overall Performance Change Score based on the following cut points:

| Indicator 3 Overall Performance Change Score | Cut Points for Change Over Time in Summary Statements Total Score |
| --- | --- |
| 0 | Lowest score through 3 |
| 1 | 4 through 7 |
| 2 | 8 through highest |

| Summary Statement/ Child Outcome | FFY 2023 N | FFY 2023 Summary Statement (%) | FFY 2024 N | FFY 2024 Summary Statement (%) | Difference between Percentages (%) | Std Error | z value | p-value | p<=.05 | Score: 0 = significant decrease; 1 = no significant change; 2 = significant increase |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SS1/Outcome A: Positive Social Relationships | 2,504 | 86.14% | 2,556 | 86.97% | 0.83 | 0.0096 | 0.8650 | 0.3871 | NO | 1 |
| SS1/Outcome B: Knowledge and Skills | 2,422 | 63.29% | 2,407 | 61.03% | -2.26 | 0.0140 | -1.6227 | 0.1046 | NO | 1 |
| SS1/Outcome C: Actions to meet needs | 2,530 | 71.74% | 2,596 | 71.96% | 0.22 | 0.0126 | 0.1733 | 0.8624 | NO | 1 |
| SS2/Outcome A: Positive Social Relationships | 2,794 | 40.01% | 2,880 | 40.97% | 0.96 | 0.0130 | 0.7349 | 0.4624 | NO | 1 |
| SS2/Outcome B: Knowledge and Skills | 2,794 | 31.68% | 2,880 | 35.14% | 3.46 | 0.0125 | 2.7680 | 0.0056 | YES | 2 |
| SS2/Outcome C: Actions to meet needs | 2,794 | 33.32% | 2,880 | 34.58% | 1.26 | 0.0126 | 1.0037 | 0.3155 | NO | 1 |

| Total Points Across SS1 and SS2 | 7 |
| --- | --- |

| Your State’s Performance Change Score | 1 |
| --- | --- |

## Data Rubric

Oregon

FFY 2024 APR (1)

Part C Timely and Accurate Data -- SPP/APR Data

| APR Indicator | Valid and Reliable | Total |
| --- | --- | --- |
| 1 | 1 | 1 |
| 2 | 1 | 1 |
| 3 | 1 | 1 |
| 4 | 1 | 1 |
| 5 | 1 | 1 |
| 6 | 1 | 1 |
| 7 | 1 | 1 |
| 8A | 1 | 1 |
| 8B | 1 | 1 |
| 8C | 1 | 1 |
| 9 | 1 | 1 |
| 10 | 1 | 1 |
| 11 | 1 | 1 |
| 12 | 1 | 1 |

APR Score Calculation

| Subtotal | 14 |
| --- | --- |
| Timely Submission Points - If the FFY 2024 APR was submitted on-time, place the number 5 in the cell on the right. | 5 |
| Grand Total - (Sum of Subtotal and Timely Submission Points) = | 19 |

(1) In the SPP/APR Data table, where there is an N/A in the Valid and Reliable column, the Total column will display a 0. This is a change from prior years in display only; all calculation methods are unchanged. An N/A does not negatively affect a State's score; this is because 1 point is subtracted from the Denominator in the Indicator Calculation table for each cell marked as N/A in the SPP/APR Data table.

618 Data (2)

| Table | Timely | Complete Data | Passed Edit Check | Total |
| --- | --- | --- | --- | --- |
| Child Count/Settings Due Date: 7/30/25 | 1 | 1 | 1 | 3 |
| Exiting Due Date: 2/18/26 | 1 | 1 | 1 | 3 |
| Dispute Resolution Due Date: 11/19/25 | 1 | 1 | 1 | 3 |

618 Score Calculation

| Subtotal | 9 |
| --- | --- |
| Grand Total (Subtotal X 2.11111111) = | 19.00 |

Indicator Calculation

| A. APR Grand Total | 19 |
| --- | --- |
| B. 618 Grand Total | 19.00 |
| C. APR Grand Total (A) + 618 Grand Total (B) = | 38.00 |
| Total N/A Points in APR Data Table Subtracted from Denominator | 0 |
| Total N/A Points in 618 Data Table Subtracted from Denominator | 0.00 |
| Denominator | 38.00 |
| D. Subtotal (C divided by Denominator) (3) = | 1.0000 |
| E. Indicator Score (Subtotal D x 100) = | 100.00 |

(2) In the 618 Data table, when calculating the value in the Total column, any N/As in the Timely, Complete Data, or Passed Edit Checks columns are treated as a ‘0’. An N/A does not negatively affect a State's score; this is because 2.11111111 points are subtracted from the Denominator in the Indicator Calculation table for each cell marked as N/A in the 618 Data table.

(3) Note that any cell marked as N/A in the APR Data Table will decrease the denominator by 1, and any cell marked as N/A in the 618 Data Table will decrease the denominator by 2.11111111.

APR and 618 -Timely and Accurate State Reported Data

DATE: February 2026 Submission

SPP/APR Data

1) Valid and Reliable Data - Data provided are from the correct time period, are consistent with 618 (when appropriate) and the measurement, and are consistent with previous indicator data (unless explained).

Part C 618 Data

1) Timely –   A State will receive one point if it submits all EDFacts files associated with the IDEA Section 618 data collection to ED by the initial due date for that collection (as described in the table below).

| 618 Data Collection | EDFacts Files | Due Date |
| --- | --- | --- |
| Part C Child Count and Setting | FS902, FS903*, FS904*, FS905 | 7/30/2025 |
| Part C Exiting | FS901 | 2/18/2026 |
| Part C Dispute Resolution | FS906, FS907, FS908 | 11/19/2025 |

* if applicable

2) Complete Data – A State will receive one point if it submits data for all data elements, subtotals, totals as well as responses to all questions associated with a specific data collection by the initial due date. No data is reported as missing. No placeholder data is submitted. State-level data include data from all districts or agencies.

3) Passed Edit Check – A State will receive one point if it submits data that meets all the edit checks related to the specific data collection by the initial due date. The counts included in 618 data submissions are internally consistent within a data collection.

## Dispute Resolution

IDEA Part C

Oregon

Year 2024-25

Section A: Written, Signed Complaints

| (1) Total number of written signed complaints filed. | 2 |
| --- | --- |
| (1.1) Complaints with reports issued. | 2 |
| (1.1) (a) Reports with findings of noncompliance. | 2 |
| (1.1) (b) Reports within timelines. | 1 |
| (1.1) (c) Reports within extended timelines. | 1 |
| (1.2) Complaints pending. | 0 |
| (1.2) (a) Complaints pending a due process hearing. | 0 |
| (1.3) Complaints withdrawn or dismissed. | 0 |

Section B: Mediation Requests

| (2) Total number of mediation requests received through all dispute resolution processes. | 0 |
| --- | --- |
| (2.1) Mediations held. | 0 |
| (2.1) (a) Mediations held related to due process complaints. | 0 |
| (2.1) (a) (i) Mediation agreements related to due process complaints. | 0 |
| (2.1) (b) Mediations held not related to due process complaints. | 0 |
| (2.1) (b) (i) Mediation agreements not related to due process complaints. | 0 |
| (2.2) Mediations pending. | 0 |
| (2.3) Mediations not held. | 0 |

Section C: Due Process Complaints

| (3) Total number of due process complaints filed. | 0 |
| --- | --- |
| Has your state adopted Part C due process hearing procedures under 34 CFR 303.430(d)(1) or Part B due process hearing procedures under 34 CFR 303.430(d)(2)? | PARTB |
| (3.1) Resolution meetings (applicable ONLY for states using Part B due process hearing procedures). | 0 |
| (3.1) (a) Written settlement agreements reached through resolution meetings. | 0 |
| (3.2) Hearings fully adjudicated. | 0 |
| (3.2) (a) Decisions within timeline. | 0 |
| (3.2) (b) Decisions within extended timeline. | 0 |
| (3.3) Hearings pending. | 0 |
| (3.4) Due process complaints withdrawn or dismissed (including resolved without a hearing). | 0 |

This report shows the most recent data that was entered by:

Oregon

These data were extracted on the close date:

11/19/2025

## How the Department Made Determinations

Below is the location of How the Department Made Determinations (HTDMD) on OSEP’s IDEA Website. How the Department Made Determinations in 2026 will be posted in June 2026. Copy and paste the link below into a browser to view.

https://sites.ed.gov/idea/how-the-department-made-determinations/

## Final Determination Letter

June 16, 2026

Honorable Charlene Williams

Deputy Superintendent of Public Instruction

Oregon Department of Education

255 Capitol Street Northeast

Salem, OR 97310

Dear Deputy Superintendent Williams:

I am writing to advise you of the U.S. Department of Education’s (Department) 2026 determination under Sections 616 and 642 of the Individuals with Disabilities Education Act (IDEA). The Department has determined that Oregon  meets the requirements and purposes of Part C of the IDEA. This determination is based on the totality of Oregon's data and information, including the Federal fiscal year (FFY) 2024 State Performance Plan/Annual Performance Report (SPP/APR), other State-reported data, and other publicly available information.

Oregon's 2026 determination is based on the data reflected in Oregon's “2026 Part C Results-Driven Accountability Matrix” (RDA Matrix). The RDA Matrix is individualized for Oregon and consists of:

- a Compliance Matrix that includes scoring on Compliance Indicators and other compliance factors;

- a Results Matrix (including Components and Appendices) that include scoring on Results Elements;

- a Compliance Score and a Results Score;

- an RDA Percentage based on both the Compliance Score and the Results Score; and

- Oregon's Determination.

The RDA Matrix is further explained in a document, entitled “How the Department Made Determinations under Sections 616(d) and 642 of the Individuals with Disabilities Education Act in 2026: Part C” (HTDMD-C).

The Office of Special Education Programs (OSEP) is continuing to use both results data and compliance data in making the Department’s determinations in 2026, as it did for Part C determinations in 2016-2025. (The specifics of the determination procedures and criteria are set forth in the HTDMD-C document and reflected in the RDA Matrix for Oregon.) For 2026, the Department’s IDEA Part C determinations continue to include consideration of each State’s Child Outcomes data, which measure how children who receive Part C services are improving functioning in three outcome areas that are critical to school readiness:

- positive social-emotional skills;

- acquisition and use of knowledge and skills (including early language/communication); and

- use of appropriate behaviors to meet their needs.

Specifically, the Department considered the data quality, and the child performance levels in each State’s Child Outcomes FFY 2024 data. You may access the results of OSEP’s review of Oregon's SPP/APR and other relevant data by accessing the EDFacts Metadata and Process Systems (EMAPS) SPP/APR reporting tool using your State-specific log-on information at https://emaps.ed.gov/suite/. When you access Oregon's SPP/APR on the site, you will find, in Indicators 1 through 12, the OSEP Response to the indicator and any actions that Oregon is required to take. The actions that Oregon is required to take are in the “Required Actions” section of the indicator.

It is important for your State to review the Introduction to the SPP/APR, which may also include language in the “OSEP Response” and/or “Required Actions” sections.

Your State will also find the following important documents in the Determinations Enclosures section:

- Oregon's RDA Matrix;

- the HTDMD link;

- “2026 Data Rubric Part C,” which shows how OSEP calculated the Oregon's “Timely and Accurate State-Reported Data” score in the Compliance Matrix; and

- “Dispute Resolution 2024-2025,” which includes the IDEA Section 618 data that OSEP used to calculate the Oregon's “Timely State Complaint Decisions” and “Timely Due Process Hearing Decisions” scores in the Compliance Matrix.

As noted above, Oregon's 2026 determination is Meets Requirements. A State’s 2026 RDA Determination is Meets Requirements if the RDA Percentage is at least 80%, unless the Department has imposed Specific Conditions on the State’s last three IDEA Part C grant awards (for FFYs 2023, 2024, and 2025), and those Specific Conditions are in effect at the time of the 2026 determination.

The Department is committed to transparency, accountability, strong partnerships with States and stakeholders, high expectations, and improved outcomes for children with disabilities. To support these priorities, the Secretary is considering modifications to the factors the Department uses when making determinations, effective June 2027. Potential additional factors include graduation rates and assessment data, such as graduation rates for students with disabilities compared to all students, and Statewide assessment results of students with disabilities compared to all students. Other potential factors include longstanding noncompliance (such as OSEP-identified noncompliance that remains unresolved) as a factor in determinations.

For the FFY 2025 SPP/APR submission due on February 1, 2027, OSEP is providing the following information about the IDEA Section 618 data. The 2025-26 IDEA Section 618 Part C data submitted as of the due date will be used for the FFY 2025 SPP/APR and the 2027 IDEA Part C Results Matrix and data submitted during correction opportunities will not be used for these purposes. The 2025-26 IDEA Section 618 Part C data will automatically be prepopulated in the SPP/APR reporting platform for Part C SPP/APR Indicators 2, 5, 6, 9, and 10 (as they have in the past). States and Entities are expected to submit high-quality IDEA Section 618 Part C data that can be published and used by the Department as of the due date. States and Entities are expected to conduct data quality reviews prior to the applicable due date. OSEP expects States and Entities to take one of the following actions for all business rules that are triggered in EDPass prior to the applicable due date: 1) revise the uploaded data to address the business rule; or 2) provide a data note addressing why the uploaded data triggered the business rule. States and Entities will be unable to submit the IDEA Section 618 Part C data without taking one of these two actions. There will not be a resubmission period for the IDEA Section 618 Part C data.

As a reminder, Oregon must report annually to the public, by posting on the State lead agency’s website, on the performance of each early intervention service (EIS) program located in Oregon on the targets in the SPP/APR as soon as practicable, but no later than 120 days after Oregon's submission of its FFY 2024 SPP/APR. In addition, Oregon must:

- review EIS program performance against targets in Oregon's SPP/APR;

- determine if each EIS program “meets the requirements” of Part C, or “needs assistance,” “needs intervention,” or “needs substantial intervention” in implementing Part C of the IDEA;

- take appropriate enforcement action; and

- inform each EIS program of its determination.

Further, Oregon must make its SPP/APR available to the public by posting it on the State lead agency’s website. Within the upcoming weeks, OSEP will be finalizing a State Profile that:

- includes Oregon's determination letter and SPP/APR, OSEP attachments, and all State attachments that are accessible in accordance with Section 508 of the Rehabilitation Act of 1973; and

- will be accessible to the public via the ed.gov website.

OSEP appreciates Oregon's efforts to improve results for infants and toddlers with disabilities and their families and looks forward to working with Oregon over the next year as we continue our important work of improving the lives of children with disabilities and their families. Please contact your OSEP State Lead if you have any questions, would like to discuss this further, or want to request technical assistance.

Sincerely,

Erin McHugh

Deputy Director

Office of Special Education Programs

cc: Oregon Part C Coordinator