## ReadMe
Both tabs have the same information, just organized differently. The "Integrated" tab shows more of the cause-effect temporally between AMPC-IRST-Board work. The "Separated"tab groups all the work for each of these bodies.
Notes: | 1. over time, some of these might steps might happen faster as each group streamlines their processes
2. Much of IRST's work will be completed by INR staff between IRST meetings, with IRST providing oversight and review
3. Research questions may have subquestions, and thus could be very large projects (think RipStream - a 10 year study)
4. RFP is request for proposals
5. OAR 629-603-0200 lays out the steps of the AMP process, but this timeline illustrates how there are cyclical patterns interwoven with these steps
6. AMPC work from before May 2023 omitted for ease of reading

## Integrated
For illustrative purposes: approximations of durations of steps in AMP process (Approximations to illustrate steps, timing, and cadence)
Process | Details | # of meetings | OAR 629-603- | Sp '23 | Su '23 | Fa '23 | Wi '23-4 | Sp '24 | Su '24 | Fa '24 | Wi '24-5 | Sp '25 | Su '25 | Fa '25 | Wi '25-6 | Sp '26 | Su '26 | Fa '26 | Wi '26-7 | Sp '27 | Su '27 | Fa '27 | Wi '27-8 | Sp '28 | Su '28 | Fa '28 | Wi '28-9 | Sp '29
AMPC ID research topics |  | 1-2 | 0200(2)(a)(B)
AMPC ID Research questions, then send to IRST | e.g., 3-5 questions | 3-4 | 0200(3)
IRST charter, best available science |  | 3-5 | 0200(2)(b)
IRST draft Proposals | hone questions 1-4 | 1-2 | 0200(4)(b)
AMPC input on honed questions | questions 1-4 | 1 | 0200(4)(b)
IRST draft Proposals | Question 1 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 2 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 3 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 4 | 2-3 | 0200(4)(c)
AMPC develops research agenda |  | 2-3 | 0200(5)
AMPC Research topics & questions (as needed) |  | 1 | 0200(3)
Board vote on research agenda |  | 1 | 0200(5)(d)
AMPC Research topics & questions (as needed) | (assume this time no new questions) | 1 | 0200(3)
IRST implements research agenda | work plan | 1-2 | 0200(6)(a)
IRST implements research agenda | RFP (develop, post, award), Questions 1&2 | 3-4 | 0200(6)(b-d)
IRST implements research agenda | RFP(develop, post, award), Question 3 | 3-4 | 0200(6)(b-d)
IRST implements research agenda | Contract (develop, implement, reports to AMPC/Board), Question 1 | 3-5 | 0200(6)(f-g)
AMPC report to board re: Question 1 results |  | 2 | 0200(8)(a)
Board action on AMPC report & IRST results, Question 1 |  | 1 | 0200(8)(b)
AMPC Research topics & questions (as needed) | Questions 5 & 6 | 1 | 0200(3)
IRST draft Proposals | hone questions 5, 6 | 1-2 | 0200(4)(b)
AMPC input on honed questions | questions 5, 6 | 1 | 0200(4)(b)
IRST draft Proposals | Question 5 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 6 | 2-3 | 0200(4)(c)
AMPC refine research agenda | Note: refining what already exists, not adding new questions at this stage | 2-3 | 0200(5)
Board decision on research agenda |  | 1 | 0200(5)(d)
IRST implements research agenda | Contract (develop, implement, reports to AMPC/Board), Question 2 | 3-6 | 0200(6)(f-g)
AMPC report to board re: Question 2 results |  | 2 | 0200(8)(a)
Board action on AMPC report & IRST results, Question 2 |  | 1 | 0200(8)(b)
cycle continues for Questions 3-6+
Key:
AMPC
IRST
Board work

## Integrated simplified
| For illustrative purposes: approximations of durations of steps in AMP process (Approximations to illustrate steps, timing, and cadence) |  |  | 2023 |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
Process | Details | # of meetings | OAR 629-603- | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
AMPC ID research topics |  | 1-2 | 0200(2)(a)(B) | bar: 2023 Q2
AMPC ID Research questions, then to IRST | e.g., 3-5 questions | 3-4 | 0200(3) | bar: 2023 Q3 to 2023 Q4
IRST charter, best available science |  | 3-5 | 0200(2)(b) | bar: 2023 Q3 to 2023 Q4
IRST hones question 1 | hone questions 1-4 | 1-2 | 0200(4)(b) | bar: 2024 Q1
AMPC input Question 1 | questions 1-4 | 1 | 0200(4)(b) | bar: 2024 Q2
IRST proposal Question 1 | Question 1 | 2-3 | 0200(4)(c) | bar: 2024 Q2 to 2024 Q3
IRST draft Proposals | Question 2 | 2-3 | 0200(4)(c) | bar: 2024 Q2 to 2024 Q3
IRST draft Proposals | Question 3 | 2-3 | 0200(4)(c) | bar: 2024 Q3 to 2024 Q4
IRST draft Proposals | Question 4 | 2-3 | 0200(4)(c) | bar: 2024 Q3 to 2024 Q4
AMPC develops research agenda (Quest. 1-3) |  | 2-3 | 0200(5) | bar: 2025 Q1 to 2025 Q2
AMPC Research topics & questions (as needed) |  | 1 | 0200(3) | bar: 2025 Q1
Board: vote on research agenda (Quest. 1-3) |  | 1 | 0200(5)(d)
AMPC Research topics & questions (as needed) | (assume this time no new questions) | 1 | 0200(3) | bar: 2026 Q1
IRST implements research agenda | work plan | 1-2 | 0200(6)(a) | bar: 2025 Q4
IRST RFP, Question 1 | RFP (develop, post, award), Questions 1&2 | 3-4 | 0200(6)(b-d) | bar: 2025 Q4 to 2026 Q1
IRST implements research agenda | RFP(develop, post, award), Question 3 | 3-4 | 0200(6)(b-d) | bar: 2026 Q1 to 2026 Q2
IRST Contract, Question 1 | Contract (develop, implement, reports to AMPC/Board), Question 1 | 3-5 | 0200(6)(f-g) | bar: 2026 Q3 to 2027 Q2
AMPC report to board re: Question 1 results |  | 2 | 0200(8)(a) | bar: 2027 Q3
Board action on AMPC report & IRST results, Question 1 |  | 1 | 0200(8)(b)
AMPC Research topics & questions (as needed) | Questions 5 & 6 | 1 | 0200(3) | bar: 2027 Q1
IRST draft Proposals | hone questions 5, 6 | 1-2 | 0200(4)(b) | bar: 2027 Q2
AMPC input on honed questions | questions 5, 6 | 1 | 0200(4)(b) | bar: 2027 Q2
IRST draft Proposals | Question 5 | 2-3 | 0200(4)(c) | bar: 2027 Q2 to 2027 Q3
IRST draft Proposals | Question 6 | 2-3 | 0200(4)(c) | bar: 2027 Q2 to 2027 Q3
AMPC refine research agenda (Quest. 4+) | Note: refining what already exists, not adding new questions at this stage | 2-3 | 0200(5) | bar: 2027 Q1 to 2027 Q2
Board decision on research agenda (Quest. 4+) |  | 1 | 0200(5)(d)
IRST implements research agenda, Question 2 | Contract (develop, implement, reports to AMPC/Board), Question 2 | 3-6 | 0200(6)(f-g) | bar: 2026 Q4 to 2028 Q4
AMPC report to board re: Question 2 results |  | 2 | 0200(8)(a) | bar: 2029 Q1
Board action on AMPC report & IRST results, Question 2 |  | 1 | 0200(8)(b)
cycle continues for Questions 3-6+
Key:
AMPC
IRST
Board work

## Separated
For illustrative purposes: approximations of durations of steps in AMP process (Approximations to illustrate steps, timing, and cadence)
Process | Details | # of meetings | OAR 629-603- | Sp '23 | Su '23 | Fa '23 | Wi '23-4 | Sp '24 | Su '24 | Fa '24 | Wi '24-5 | Sp '25 | Su '25 | Fa '25 | Wi '25-6 | Sp '26 | Su '26 | Fa '26 | Wi '26-7 | Sp '27 | Su '27 | Fa '27 | Wi '27-8 | Sp '28 | Su '28 | Fa '28 | Wi '28-9 | Sp '29
AMPC ID research topics |  | 1-2 | 0200(2)(a)(B)
AMPC ID Research questions, then send to IRST | e.g., 3-5 questions | 3-4 | 0200(3)
AMPC input on honed questions |  | 1 | 0200(4)(b)
AMPC develops research agenda |  | 2-3 | 0200(5)
AMPC Research topics & questions (as needed) |  | 1 | 0200(3)
AMPC Research topics & questions (as needed) | (assume this time no new questions) | 1 | 0200(3)
AMPC report to board re: Question 1 results |  | 2 | 0200(8)(a)
AMPC Research topics & questions (as needed) | Questions 5 & 6 | 1 | 0200(3)
AMPC input on honed questions | questions 5, 6 | 1 | 0200(4)(b)
AMPC refine research agenda | Note: refining what already exists, not adding new questions at this stage | 2-3 | 0200(5)
AMPC report to board re: Question 2 results |  | 2 | 0200(8)(a)
IRST charter, best available science |  | 3-5 | 0200(2)(b)
IRST draft Proposals | hone questions 1-4 | 1-2 | 0200(4)(b)
IRST draft Proposals | Question 1 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 2 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 3 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 4 | 2-3 | 0200(4)(c)
IRST implements research agenda | work plan | 1-2 | 0200(6)(a)
IRST implements research agenda | RFP (develop, post, award), Questions 1&2 | 3-4 | 0200(6)(b-d)
IRST implements research agenda | RFP(develop, post, award), Question 3 | 3-4 | 0200(6)(b-d)
IRST implements research agenda | Contract (develop, implement, reports to AMPC/Board), Question 1 | 3-5 | 0200(6)(f-g)
IRST draft Proposals | hone questions 5-6 | 1-2 | 0200(4)(b)
IRST draft Proposals | Question 5 | 2-3 | 0200(4)(c)
IRST draft Proposals | Question 6 | 2-3 | 0200(4)(c)
IRST implements research agenda | Contract (develop, implement, reports to AMPC/Board), Question 2 | 3-6 | 0200(6)(f-g)
Board vote on research agenda |  | 1 | 0200(5)(d)
Board decision on research agenda |  | 1 | 0200(5)(d)
Board action on AMPC report & IRST results, Question 1 |  | 1 | 0200(8)(b)
Board action on AMPC report & IRST results, Question 2 |  | 1 | 0200(8)(b)
cycle continues for Questions 3-6+
Key:
AMPC
IRST
Board work