## Project Risk Register
Cost Risk* =
|  |  |  | Key# & Project Name: | [5 empty] | Total Project Cost: |  |  |  |  | Design Sched. Risk = | 0 | [9 empty] | *Cost Risk based on identified risk.
|  |  |  | TPM/RE-CP: | [5 empty] | Construction Cost: |  |  |  |  | Const. Sched. Risk = | 0 | Risk-Based Cont. =
|  |  |  | Area Manager: | [5 empty] | Project Schedule: |  |  |  |  | Total Schedule Risk = | 0
Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months | [8 empty] | Risk Response Plan |  |  |  |  | Monitor and Review
Risk No. | Date Id. | Risk Title | Phase that it impacts | Critical Path? | Nature | Detailed Description of Risk Event | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | $ Impact | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | 6 Impact | Score | Const T RR | Design T RR | Bid Date Variability | Status | Rank | Strategy | Risk Owner | Response action(s) to be taken | Date, Status, and Review Comments | Date Updated |  | Cost Percent | Cost (less than) | Schedule Percent | Schedule (less than) | Threat | Opportunity
1 |  | Metro Planning Organization (MPO) timing | Design |  | Threat | If MPO does not approve the STIP amendment (from Region buckets, planned STIP amendments) then our bid could be delayed. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Watch List |  | Accept |  | STIP amendments should be submitted 6 months in advance of PS&E to avoid impacts to bid let. Approval of amendments has not been an issue, timing can be an issue. |  |  | Negligible | 0.5% | 0 | 2% | 0 | Mitigate | Enhance
2 |  | Railroad | Design |  | Threat | Ramps within 500' of a railroad require notification to the railroad owner. Unclear how long this review timeline is. This can be 6 months to a year. If the railroad review timeline is not accounted for in the project timeline then the project may be delayed significantly. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | Program is coordinating advanced RR review at concept design and packaging ramps with rail impacts into unique projects. |  |  | Low | 1% | 0 | 4% | 0 | Avoid | Exploit
3 |  | Section 106 | Design |  | Threat | Working in historic districts and communities with old buildings. Potential capacity problem of qualified firms to do section 106 documentation. If we do not have qualified firms then project may be delayed. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Program working to modify 106 documentation requirements to better fit known profile of work scope and related risk |  |  | Moderate | 2.5% | 0 | 8% | 0 | Accept | Accept
4 |  | Mobility | Design |  | Threat | If the MAC committee is not supportive of design concepts then the project may need to be redesigned or delayed. Design teams are spending a lot of time in anticipation of MAC and preparing presentations. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Limited footprint of ramp work has resulted in a streamlined MAC review process that avoids presentations except when there are permanent impacts to reduction routes and extreme detours. |  |  | High | 5% | 0 | 12.5% | 0 | Transfer | Transfer
5 |  | Design Exception - timing | Design |  | Threat | Design exceptions take time to review and approved, if they are submitted late in the design process they may not be approved to meet the time requirements. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | Anticipated Design Exceptions should be identified at concept design, workshops to gain agreement on direction should be held prior to DAP completion, final DEs should be submitted 30 days prior to PS&E. |  |  | Extreme | 5% | 0 | 12.5% | 0
6 |  | Desgin Exception -detail | Design |  | Threat | If a design exception is submitted without sufficient supporting data then review/approval may be delayed. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | Anticipated Design Exceptions should be identified at concept design, workshops to gain agreement on direction should be held prior to DAP completion, final DEs should be submitted 30 days prior to PS&E.
7 |  | Design Execption - need | Design |  | Threat | If design exceptions are submitted and rejected, the project may be delayed to redesign or resubmit. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | Anticipated Design Exceptions should be identified at concept design, workshops to gain agreement on direction should be held prior to DAP completion, final DEs should be submitted 30 days prior to PS&E.
8 |  | 2D ADA Ramp Design | Design |  | Threat | 2D ramps don’t account for excavation and catch points at back of walk. If slopes from the ramp extend beyond ROW limits then this may trigger the need for a slope easement or Temp construction easement during construction which may cause redesign or unexpected ROW acquisition. This could potentially be mitigated with a curb at the back of walk. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Consultants must assess each ramp in order to detrmine whether the 2D approach will be sufficient. This effort includes an assessment of construction needs so is factored in upfront.
9 |  | Supply chain disruption | Construction |  | Threat | If materials are unavailable then the project may be delayed and/or the cost increased. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Continue to monitor. Utilitize advanced acquisition of materials with long lead times when deemed feasible
10 |  | Market Conditions | Construction |  | Threat | If the volume of work is greater than the contractor availability to perform it, ODOT may pay a premium or not receive bids. This may also delay project schedules as these projects are all competing for the same resources (labor, aggregate, concrete, asphalt). |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Continue to monitor. Program coordinating bid lets to spread out work as much as possible, creating some small contracts for DBE firms to bid, and developing alternative delivery projects.
11 |  | Hazmat | Construction |  | Threat | Lead paint on curbs and in soils. If soils can't be disposed in ROW then have to be hauled off. If lead is present then the project cost may increase or be delayed to test for hazardous materials. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | Lead paint should not be removed from curb. Intact paint on curb can be disposed w/o testing. All soils should be considered to be contaminated and disposed at the correct facility. Testing is done to determine the correct disposal location.
12 |  | Underground storage tanks | Construction |  | Threat | If the contractor encounters underground storage tanks then the project cost may be increase or the scheduled may be delayed to remove the tank. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept
13 |  | Batch 2 utilities | Construction |  | Threat | If we are unable to clear all batch 2 utility relocations we will have contract delays and may not be able to build all of the ramps. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept
14 |  | Batch 2 Environmental | Construction |  | Threat | If we are unable to clear all batch 2 environmental certification we will have contract delays and may not be able to build all of the ramps. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept
15 |  | Batch 2 ROW files | Construction |  | Threat | If we are unable to clear all batch 2 ROW files then we will have contract delays and may not be able to build all of the ramps. This is a high probability risk as there are a very high volume of ROW files. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | ADA Program and HQ ROW have taken significant steps to minimize and expedite ROW work, maximizing easments, V-files, and ADJCs. Achieving clearance is a timing issue, so the risk of delays should be balanced with need to get ramps into construction.
16 |  | Partner Agencies | Design |  | Opportunity | With a tight schedule, there is limited time for a lot of feedback from partner agencies. If partner agencies are not satisfied with design then it may require redesign, delaying schedule and/or increasing cost. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Accept |  | A tight timeline requires more strategic outreach to partner agencies to ensure enough time for critical feedback.
17 |  | Parking Removal Item | Design |  | Threat | State law - it is illegal to park within 20' of crosswalk. Projects with parking in urban areas may be impacted by ramp design or crosswalk upgrades. If the partner agency doesn't agree with parking removal then the project may be delayed to work through the issue. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | This can be successfullly managed with good communication and some tailored approachs that STRE has approved to meet the same level of safety as the Law would achieve: downstream vs upstream, curb extension sight distance, City ROW vs ODOT ROW....
18 |  | Ramp maintainability | Design |  | Opportunity | If either ODOT or local agency has issues with maintainability (rock mulch, landscaping) of the ramp design then the project may be delayed to redesign or work through issue. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance |  | Early and effective communication with local agencies and ODOT maintenance is crucial
19 |  | Sub-surface exploration/ signal foundation installation | Design |  | Threat | Drillers for subsurface exploration and signal foundation installation have limited availability. If drilling contractors are unavailable then the design and/or construction of the project may be delayed. This has been caused by a significant increase in drilling work. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | New geotechnical standards may reduce need for drilling by setting minimum depths requried for foundations.
20 |  | Inspection form changes | Construction |  | Opportunity | If the inspection form changes then the risk of incorrect completion of the inspection form increases. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance |  | Proper training and updates for inspectors is required.
21 |  | ADA ramp inspection competency | Construction |  | Opportunity | If ADA ramp inspectors are inexperienced, then more non-compliant ramps may be built. If construction office is not staffed to a level where inspectors can be on-site for ramp construction then more non-compliant ramps may be built. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance
22 |  | Virtual training quality | Construction |  | Opportunity | If virtual training is not high quality then the more non-compliant ramps may be built. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance
23 |  | Changing design standards | Design |  | Opportunity | If design standards are changed and have to be immediately implemented then projects may be delayed or cost increased to redesign the project |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance |  | New design standards, or new interpretations, should have a roll out schedule for implementation to minimize project impacts.
24 |  | Design Review capacity | Design |  | Threat | If ODOT reviewers are overloaded there could be extended review times |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | Continual montoring of workload is necessary.
25 |  | Contracting | Design |  | Threat | Contract and amendment review process is lengthy, making adjustments time consuming. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Mitigate |  | ADA program SOW template will be utilized, template language reviewed and pre-approved by DOJ. Modifications to language should be made with track changes and explanations for why changes are needed, both to reduce DOJ review time. OPO to seek exemption for SOW template.
26 |  | IGA | Design |  | Opportunity | Lack of signed agreements with Local Agencies could impact project schedules and designs. |  |  | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Active |  | Enhance |  | Early coordination with Local Agencies essential. If Local Agencies own ramps, they will need to take responsibility for any non-standard designs.
27 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
28 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
29 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
30 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
31 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
32 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
33 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
34 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
35 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
36 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
37 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
38 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
39 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
40 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
45 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
46 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
47 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
48 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
49 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
50 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Note on F9: If this risk did occur would it delay the critical path of the project or could it be handled concurrently with critical path activities?
Note on J9: Minimum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on L9: Maximum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on O9: Minimum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Q9: Maximum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Y9: Risk Rank Based on probability, cost, and schedule impact, this column ranks risk with 1 being the most likely & impactful risk

## Example - Project Risk Register
Cost Risk* =
|  |  |  | Key# & Project Name: |  | K12345 Example |  |  |  | Total Project Cost: | 15000000 |  |  |  | Design Sched. Risk = | 3.3 | [6 empty] | 2156468.75 |  |  | *Cost Risk based on identified risk.
|  |  |  | TPM/RE-CP: | [5 empty] | Construction Cost: | 12500000 |  |  |  | Const. Sched. Risk = | 0.8875 | Risk-Based Cont. =
|  |  |  | Area Manager: | [5 empty] | Project Schedule: | 36 |  |  |  | Total Schedule Risk = | 4.1875 | [6 empty] | 17.25%
Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months | [8 empty] | Risk Response Plan |  |  |  |  | Monitor and Review
Risk No. | Date Id. | Risk Title | Phase that it impacts | Critical Path? | Nature | Detailed Description of Risk Event | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | $ Impact | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | 6 Impact | Score | Const T RR | Design T RR | Bid Date Variability | Status | Rank | Strategy | Risk Owner | Response action(s) to be taken | Date, Status, and Review Comments | Date Updated |  | Cost Percent | Cost (less than) | Schedule Percent | Schedule (less than) | Threat | Opportunity
1 | 2020-07-01 | Design exception approval | Design | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Design phase impacts would be additional PE cost and design schedule for design/re-design. | 10% | 75 | 87.5 | 100 | 14375 | Very Low | 2 | 3 | 4 | 0.55 | Very Low | 43250 | 0 | 0.55 | Green | Active | 7 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. |  |  | Negligible | 0.5% | 75000 | 2% | 0.72 | Mitigate | Enhance
2 | 2020-07-01 | Design exception approval | Construction | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Construction phase impacts include reconstructing the ramp and lengthing the spiral. This would trigger widening of the hwy 999 o'xing structure. | 10% | 2500 | 3750 | 5000 | 687500 | High | 2 | 3 | 4 | 0.55 | Very Low | 716375 | 0.55 | 0 |  | Active | 1 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. |  |  | Low | 1% | 150000 | 4% | 1.44 | Avoid | Exploit
3 | 2020-09-10 | Bidding Climate - Volume of Work | Construction | no | Threat | High quantity of ODOT statewide projects being bid for 2022 construction may result in higher than expected bid prices due to capacity of industry and availability of contractors. | 50% | 100 | 550 | 1000 | 437500 | High | 0 | 0.005 | 0.01 | 0.00425 | Very Low | 437723.125 | 0 | 0 |  | Active | 2 | Mitigate | TPM | 1) Coordinate with Constructability Review program to engage AGC on direct project review and comment 2) Conduct evaluation of anticipated material volumes for timing of construction and perform outreach to suppliers. |  |  | Moderate | 2.5% | 375000 | 8% | 2.88 | Accept | Accept
4 | 2020-09-20 | Value Engineering study @10% design | Construction | yes | Opportunity | VE studies on average reduce project cost 20% and commonly produces construction schedule savings. If a VE study is conducted then the project cost and schedule may decrease. | 50% | 0 | 2500 | 5000 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 |  | Retired |  | Enhance | TPM | Coordinate with VE program to conduct value engineering study. | Value engineering study conducted at 10% design. 6 VE alternatives accepted for a total of $3.2 million in cost savings and 4 months of construction schedule reduction | 2021-02-08 | High | 5% | 750000 | 12.5% | 4.5 | Transfer | Transfer
5 | 2020-11-25 | High water table & stormwater facilities | Design | yes | Threat | Design deviation is being pursued for the construction of water quality and quantity facilities within a known high water table. If not approved, other off-site facilities that require ROW would need to be considered. The driver of the high-end costs are acquisitions of additional ROW to construct additional treatment facilities. In terms of schedule, an additional 12 months could be incurred for the additional ROW acquisitions. | 30% | 0 | 300 | 600 | 165000 | Moderate | 0 | 6 | 12 | 3.3 | High | 338250 | 0 | 3.3 | Red | Active | 3 | Avoid | Hydro Lead | 1) Hydro team to submit design deviation for water table depth at water quality and detention facilities. 2) ODOT and Consultant Design team to coordinate on format and information to be provided as part of design deviation information. Updates to be incorporated to facilitate reviews and approval. |  |  | Extreme | 5% | 750000 | 12.5% | 4.5
6 | 2020-11-25 | Utility Potholing | Design | yes | Threat | Potholing is currently scheduled; however, the required data for utility owners may not be received in time. The risk is that the utility owners do not complete the potholing in a timely manner to support the project design development. This will result in additional cost to the project for potholing to capture the data. | 10% | 15 | 17.5 | 20 | 2875 | Very Low | 0 | 0.5 | 1 | 0.125 | Very Low | 9437.5 | 0 | 0.125 | Green | Active | 8 | Mitigate | Utilities | 1) Utility Coordinator actively working with utilities on potholing efforts. 2) Engage in regular communication/coordination on utilities where there is a need for potholing/information.
7 | 2020-11-25 | Contract Length of Deep Foundations | Construction | no | Threat | Foundation lengths have been assumed to be a certain length and may not meet the formal recommendations being developed and to be provided regarding Geotechnical capacity. This could result in an increased foundation length, thereby increasing project costs. | 70% | 0 | 25 | 50 | 28750 | Very Low | 0 | 1 | 2 | 1.15 | Low | 89125 | 0 | 0 |  | Active | 6 | Mitigate | Geotech Lead | 1) Coordination and communication between Geotechnical and Structures for SB lanes in order to develop correct foundation lengths. 2) Once determination is made, update estimate accordingly and retire risk.
8 | 2020-11-25 | Stormwater Facility Sizing | Construction | yes | Threat | Further refinement of water quality and detention facility design may cause increases in facility cost. This could include the introduction of an additional detention facility. The risk is that the plan does not materialize as intended for the subsurface detention facility and there is a need to introduce an additional detention facility on the south side of ODOT Blvd. This item is affected by roadway design element updates, hydro resourcing, and project construction schedule. Considered construction risk only as design schedule should be able to absorb additional design. | 30% | 50 | 150 | 250 | 72500 | Very Low | 0 | 1 | 2 | 0.55 | Very Low | 101375 | 0.55 | 0 |  | Active | 5 | Mitigate | Hydro Lead | 1) Finalize roadway design including pavement sawcut lines; allow sufficient time for hydraulics design. 2) Continue to analyze and revise the tank design for the subsurface stormwater detention facility, including costs/benefits of proprietary tank vendors. 3) Explore options and seek to identify approaches to reduce the size of the tank requirements.
9 | 2020-11-25 | 1" Grind and Inlay | Construction | yes | Threat | The 1-inch grind and inlay may suffer pavement delamination during grind of partial lift of pavement or delamination of new pavement. This would be due to inadequate bond between new and existing ACP resulting in contract change orders and/or delays to repair pavement and additional traffic impacts. Delays are at the tail end of the construction season and would push a season. The recent lift of pavement was completed in 2013. Note that the project is already calling out the use of a fine milling head. | 10% | 50 | 382.5 | 715 | 90625 | Low | 0.5 | 3.75 | 7 | 0.8875 | Low | 137218.75 | 0.8875 | 0 |  | Watch List | 4 | Accept | Resident Engineer | 1) If issues emerge, use a temporary patching operation to address the issue until the next paving season.
10 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
11 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
12 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
14 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
15 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
16 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
17 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
18 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
19 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
20 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
21 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
22 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
23 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
24 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
25 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
26 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
27 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
28 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
29 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
30 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
31 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
32 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
33 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
34 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
35 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
36 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
37 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
38 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
39 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
40 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
45 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
46 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
47 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
48 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
49 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
50 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Note on F9: If this risk did occur would it delay the critical path of the project or could it be handled concurrently with critical path activities?
Note on J9: Minimum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on L9: Maximum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on O9: Minimum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Q9: Maximum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Y9: Risk Rank Based on probability, cost, and schedule impact, this column ranks risk with 1 being the most likely & impactful risk

## Guidance
Email the program with questions and/or feedback: |  | Threat Risk Response Actions
Select link >>>> | PRM@ODOT.state.or.us
|  | Avoid: | “Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact (reducing the probability of occurrence of a risk to 0%). [Risk avoidance] may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact” (PMI, 2017). “There are two types of avoidance action: (1) remove the cause of the risk (risk trigger), or (2) execute the project in a different way while still aiming to achieve project objectives. Not all risks can be avoided or eliminated, and for others this approach may be too expensive or time-consuming. However, this should be the first strategy considered for each risk and should be the primary strategy for high probability or high impact risks” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.
Proper use of this tool assumes familiarity with Project Risk Management concepts. A guide has been developed to assist users in managing projects risks:
https://www.oregon.gov/ODOT/Engineering/Pages/VE-RM.aspx
|  | Transfer: | “Transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. Risk transfer often involves payment of risk premium to the party taking on the threat. We can transfer risk through a range of actions that include, but are not limited to, the use of insurance, performance bonds, warranties, guarantees and so on. Agreements may be used to transfer ownership and liability for specified risks to another party” (PMI, 2017).
|  | Mitigate: | Take risk response action to reduce impact or probability of occurrence of a risk event. “In risk mitigation, we take action to reduce the probability of occurrence and/or impact of the threat” (PMI, 2017). This is the most common risk response strategy.
|  | Accept: | Risk acceptance acknowledges the existence of a threat, but no proactive action is taken. This strategy may be appropriate for low-priority threats, and it may also be adopted where it is not possible or cost-effective to address a threat in any other way. Acceptance can be either active or passive. “The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the threat if it occurs. Passive acceptance involves no proactive action apart from periodic review of the threat to ensure that it does not change significantly” (PMI, 2017). “Risks that are uncontrollable (no response actions are practical) are also accepted” (Hillson, 2004). Acceptance is a common strategy for risks that have a low probability of occurrence. However, accepted risks that have a very low to low probability of occurrence and very high to extreme impact on project objectives should be closely monitored, as they can have devastating consequences to a project. These occurrences are known as black swan events.
Opportunity Risk Response Actions
|  | Exploit: | The exploit strategy may be selected for the high-priority opportunities where the organization wants to ensure that the opportunity is realized. This strategy seeks to capture the benefit associated with a particular opportunity by ensuring that it definitely happens, increasing the probability of occurrence to 100%. “Examples of exploiting responses may include assigning an organization’s most talented resources to the project to reduce the time to completion, or using new technologies or technology upgrades to reduce cost and duration” (PMI, 2017). Opportunity risks that have high positive impact on project objectives, known as golden opportunities, should be exploited.
|  | Share: | Sharing involves transferring ownership of an opportunity to a third party so that it shares some of the benefit if the opportunity occurs. It is important to select the new of owner of a shared opportunity carefully so they are best able to capture the opportunity for the benefit of the project. “Risk sharing often involves payment of a risk premium to the party taking on the opportunity. Examples of sharing actions include forming risk-sharing partnerships, teams, special-purpose companies, or joint ventures” (PMI, 2017). “Transferring threats and sharing opportunities are similar in that a third party is used. Those to whom threats are transferred take on the liability and those to whom opportunities are allocated should also be allowed to share in the potential benefits” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.
|  | Enhance: | The enhance strategy is used to increase the probability and/or impact of an opportunity. Early enhancement action is often more effective than trying to improve the benefit after the opportunity has occurred. “The probability of occurrence of an opportunity may be increased by focusing attention on its causes. Where it is not possible to increase probability, an enhancement response might increase the impact by targeting factors that drive the size of the potential benefit” (PMI, 2017). “This response aims to modify the size or scope of the positive risk. We enhance the opportunity by increasing its probability, impact or both, thereby maximizing benefits realized for the project. If the probability can be increased to 100% this is effectivity an exploit response” (Hillson, 2004).
|  | Accept: | Accepting an opportunity acknowledges its existence, but we do not take proactive steps to realize it. “This strategy may be appropriate for low-priority opportunities, or those in which it is not possible or cost-effective to address an opportunity in any other way” (PMI, 2017).
“Risk +B3:N49avoidance is when the project team acts to eliminate the threat or protect the project from its impact (reducing the probability of occurrence of a risk to 0%). [Risk avoidance] may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact” (PMI, 2017). “There are two types of avoidance action: (1) remove the cause of the risk (risk trigger), or (2) execute the project in a different way while still aiming to achieve project objectives. Not all risks can be avoided or eliminated, and for others this approach may be too expensive or time-consuming. However, this should be the first strategy considered for each risk and should be the primary strategy for high probability or high impact risks” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.