## DB Program Develoment - Award
Design-Build Delivery Method 2-Step Best Value Program Development to Contract Award Process Map | [7 empty] | Index: |  | Blue = Accountable | Red = Responsible | Grey = Consulted | Orange = Informed | December 2022
Phases | Program Development Phase | Project Initiation Phase |  |  | Project Development Phase | [151 empty] | Contract Award Phase | [58 empty] | Phases
Owners | RACI Steps 1-8 | RACI Steps 9-13 | RACI Step 14 | RACI Steps 15-16 | RACI Step 17 | RACI Step 18 | RACI Step 19 | RACI Step 20 |  | RACI Steps 21-29 | RACI Step 30 | RACI Step 31 | RACI Steps 33-35 | RACI Step 36 | RACI Step 37 | RACI Step 38 | RACI Steps 40-41 | RACI Step 42 | RACI Step 43 | RACI Step 45 | RACI Step 46 | RACI Step 47 | RACI Step 48 | RACI Steps 49-50 | RACI Step 51 | RACI Step 52 | RACI Step 53 | RACI Step 54 |  | RACI Steps 56-58 | RACI Step 59 | RACI Step 60 | RACI Steps 61-62 | RACI Step 63 | RACI Step 64 | RACI Step 65 |  | RACI Step 66 | RACI Step 67 | RACI Step 68 | RACI Step 69 |  | RACI Steps 70-72 | RACI Step 73 | RACI Step 74 | RACI Steps 75-76 | RACI Step 77 | RACI Step 78 | RACI Step 79 |  | RACI Step 80 | RACI Step 81 | RACI Steps 82 | RACI Step 83 | RACI Step 84 | RACI Step 85 | RACI Steps 86-87 |  | RACI Step 88 |  | RACI Steps 89-90 | RACI Step 91 | RACI Step 92 | RACI Steps 93-94 |  | RACI Steps 96-97 | RACI Step 98 | RACI Step 99 | RACI Step 100 |  | RACI Step 101 | RACI Step 102 | RACI Steps 103-104 | RACI Step 105 | RACI Step 106 | RACI Step 107 | RACI Step 108 | RACI Step 109 | RACI Step 110 | RACI Step 111 | RACI Step 112 | RACI Step 113 | RACI Step 114 | RACI Step 115 | RACI Step 116 | RACI Step 117 | RACI Step 118 | RACI Step 119 | RACI Step 120 | RACI Step 121 | RACI Step 122 | RACI Steps 123-124 | RACI Steps 125-126 | RACI Step 127 | RACI Step 128 |  | RACI Step 129 | RACI Steps 130-131 | RACI Step 132 | RACI Step 133 | RACI Step 134 |  | RACI Step 135 | RACI Step 136 | RACI Step 137 | RACI Step 138 | RACI Step 139 | RACI Step 140 | RACI Step 141 | RACI Step 142 | RACI Step 143 | RACI Step 144 | RACI Step 145 | RACI Step 146 | RACI Step 147 |  | RACI Step 148 | RACI Step 149 | RACI Step 150 | RACI Step 151 | RACI Step 152 | RACI Step 153 | RACI Step 154 | RACI Steps 155-156 | RACI Step 157 | RACI Step 158 | RACI Step 159 | RACI Step 160 | RACI Step 161 | RACI Step 162 | RACI Step 163 | RACI Step 164 | RACI Step 165 | Optional Alternative Technical Concept (ATC) Process | RACI Step 166 | RACI Step 167 | RACI Step 168 | RACI Step 169 | RACI Step 170 | RACI Step 171 | RACI Step 172 | RACI Step 173 | RACI Step 174 | RACI Step 175 | Technical Proposal Evaluation and Scoring Process | RACI Step 176 | RACI Step 177 | RACI Step 178 | RACI Step 179 | RACI Step 180 | RACI Step 181 | RACI Step 182 | RACI Step 183 | RACI Step 184 | RACI Step 185 | RACI Step 186 | RACI Step 187 | RACI Step 188 | RACI Step 189 | RACI Step 190 | RACI Step 191 | RACI Step 192 | RACI Step 193 | RACI Step 194 | RACI Step 195 | RACI Step 196 | RACI Step 197 | RACI Step 198 | RACI Step 199 | RACI Step 200 | RACI Step 201 | RACI Step 202 | RACI Step 203 | RACI Step 204 | RACI Step 205 | RACI Step 206 | RACI Step 207 | RACI Step 208 | RACI Step 209 | RACI Step 210 | RACI Step 211 | RACI Step 212 | RACI Step 214 | RACI Step 215 | RACI Step 216 | RACI Step 217 | RACI Step 218 |  | RACI Step 219 | RACI Step 220 | RACI Step 221 | RACI Step 222 | RACI Step 223 | RACI Steps 224-225 | RACI Step 226 | RACI Step 227 | RACI Step 228 |  | RACI Step 229 | RACI Step 230 | RACI Step 231 | RACI Step 232 | RACI Steps 233-234 | RACI Step 235 | RACI Step 236 |  | RACI Step 237 | RACI Step 238 | RACI Step 239 | RACI Step 240 | RACI Step 241 | RACI Steps 242-243 | RACI Step 244 | RACI Step 245 | RACI Step 246 | Owners
Region | Delivery Method Evaluation and Selection (PD-14) (Set Tentative Dates for Solicitation Tasks with OPO) | Method Evaluation & Validation (PD-14) | Design-Build Method Concurrence Meeting (If not completed during Program Development) | Verify Concurrence | Procurement Kick-Off Meeting | Scope Refinement, Data Collection, Site and Design Investigation | Identify Risks and Develop Draft Risk Register | Conduct Risk Assessment Workshop and Update Risk Register | FFE Process | Draft FFE Documents Development | Send Draft FFE Documents to DOJ for Review and Approval |  | Finalize Draft FFE Documents | Submit Draft FFE and Supporting Documents to ODOT Director for Concurrence |  | Submit FFE and (Optional Public Hearing Notice) for Advertisement | (Optional) 2 Week Draft FFE Public Hearing Advertisement Period and Respond to Comments | (Optional) Conduct Draft FFE Public Hearing | (Optional) Respond to Draft FFE Public Hearing Comments | Finalize FFE With Optional Public Hearing Results | Send Final FFE to DOJ for Review and Approval |  | Review DOJ Comments for Final FFE Documents | Finalize FFE Documents | Send Final FFE and Supporting Documents to ODOT Director for Concurrence | ODOT Director Review and Approval Final FFE | Post Final FFE on Website | Start of 60 Day Jurisdiction Review Period of Exemption Order | Pre Solicitation Notice Process | Draft Project Pre Solicitation Notice | Send Draft Project Pre Solicitation Notice to DOJ for Review and Approval |  | Finalize Draft Project Pre Solicitation Notice | Submit Final Project Pre Solicitation Notice Requirements for Advertisement to Industry Publications | Post Final Project Pre Solicitation Notice Requirements to OPO's Website | Receive and Document Interested Firms | Primary Design and Project-Specific Contract Documents Development Process | Develop Proof of Concept Plans | Develop Basic Configuration Elements, Preliminary Design Criteria and Exceptions, Deviations and Operational Approvals, and Urban Design | Develop DB Project-Specific Performance Specifications and DB Special Provisions | Region Specifications Writer QC and Refine DB Project-Specific Performance Specifications and DB Special Provisions | Pre-Qualification Waiver and Optional Proposal Security Waver Process | Draft Project Prequalification Waiver and Optional Proposal Security Waiver | Send Draft Project Prequalification Waiver and Optional Proposal Security Waiver to DOJ for Review and Approval |  | Finalize Draft Project Prequalification Waiver and Optional Proposal Security Waiver | Submit Project Prequalification Waver and Optional Proposal Security Waver to Hwy Division Administrator or Chief Engineer for Concurrence and ODOT Director's Approval |  | Send Region Approved Project Prequalification Waver and Optional Proposal Security Waver | Draft RFQ Development Process | Draft RFQ Package Documents Project-Specific Information | Calculate and Finalize Stipend Amount for RFP | Draft RFQ Package Review and Commenting | Revise RFQ Package with Approved OPO Changes | Provide DOJ Draft RFQ Package for Review and Approval |  | Finalize RFQ Package With OPO Approved DOJ Changes | Draft RFP Development Process | Draft RFP Package Documents Project-Specific Information | Develop Project-Specific Workforce Protection Requirements With OECR | Draft RFP Package Review and Commenting | Provide Draft RFP Package to DOJ for Review and Approval |  | Finalize Draft RFP Package | SOQ and RFP Technical Proposal Evaluation and Scoring Committee Process | SOQ Evaluation Committee Scoring Members Selection | RFP Technical Proposal Evaluation Committee Scoring and Non-Scoring Members Selection | Select ATC Evaluation Committee Members | Finalize Internal Technical Proposals and ATC Evaluation and Scoring Documents and Date | Finalize RFQ Package, RFQ Advertisement, and SOQ Evaluation Process | Assemble Draft Final RFQ Package | Submit Draft Final RFQ Package to OPO | Draft Final RFQ Package Review and Commenting | Provide Draft Final RFQ Package to DOJ and FHWA for Review and Approval |  | Finalize RFQ Package Based on DOJ and FHWA Comments | DOJ Review and Approval of Final RFQ Package | FHWA Review and Approval of Final RFQ Package | Submit RFQ Ad (Business Tribune and DJC) | Release (Advertise) RFQ Package | Pre SOQ Meeting | Draft RFQ Addendums & Letters of Clarifications to Bidder Questions | Review Addendums & Letters of Clarifications | Post RFQ Addendums & Letters of Clarifications | SOQ Evaluation Committee Training | SOQ Submittals Due |  | Upload SOQs, RFQ Package Documents, Addendums, Responses to Questions, and Scoring Worksheets & Plan | Evaluate and Score SOQs | Address SOQ Evaluator Questions | Submit SOQ Scoring Worksheets | SOQ Consensus Meeting / Finalize SOQ Scores | SOQ Consensus / Final SOQ Scores Approval by OPO Procurement Official | Notify Proposers of Shortlisted Proposers | Shortlist Protest Period and Protest Resolution | Optional Proposer RFQ Debriefing Meeting Process |  | Schedule Optional RFQ Debriefing Meeting with Participants | Prepare Optional RFQ Debriefing Meeting Documents and Provided to Participants | Conduct Optional RFQ Debriefing Meeting | Prepare Optional RFQ Debriefing Meeting Summary Report and Disseminate to Meeting Participants | Project Specific Development of Contract Documents Process |  | Update Contract Documents Base Templates with Project-Specific Information | Region Specifications Writer QC and Refine Project-Specific DB Contract Documents | Coordinate with ADS Specification Engineer on Proposed Changes to Contract Documents Base Template Language | ADS Specification Engineer Concurrence of Proposed Changes to Contract Documents Base Template Language | Provide ADS Specification Engineer Draft Contract Documents for Review and Commenting | ADS Specifications Engineer Draft Project-Specific Contract Documents Review and Approval | Update Draft Project-Specific Contract Documents with ADS Approved Changes | Provide ADS Specification Engineer Revised Draft Project-Specific Contract Documents for DOJ Review and Approval | Provide DOJ Draft Project-Specific Contract Documents for Review and Approval | DOJ Review and Approval of Draft Project-Specific Contract Documents | Review DOJ Comments on Draft Project-Specific Contract Documents and Updating as Needed | Review DOJ Comments on Draft Project-Specific Contract Documents and Updating as Needed | RFP Advertisement, Proposals Scoring and Price Opening Process | Verify 60 Day Jurisdiction Review Period of Exemption Order Completed | Assemble Final RFP Package | Submit Final RFP Package to OPO | Draft RFP Package Review | Finalize Draft RFP Package | Provide Final RFP Package to DOJ and FHWA for Review and Commenting |  |  |  |  | Release RFP Package to Shortlisted Proposers | Pre-Proposal Meeting | Draft RFP Addendums & Letters of Clarifications to Bidder Questions | Review RFP Addendums & Letters of Clarifications | Provide RFP Addendums & Letters of Clarifications to DOJ Review and Approval |  | Post RFP Addendums & Letters of Clarifications |  | Proposers Request ATC One-on-One Meetings | Schedule ATC One-on-One Meetings | Conduct Pre-ATC Evaluation Training | ATC Proposer One-on-One Meetings | Proposers Submit Pre-ATCs | Determine if Pre-ATC Meet ATC Qualifying Criteria | Notify Proposers if their Pre-ATCs Meet ATC Qualifying Criteria and Can Be Submitted as Formal ATCs | Proposers Submit Formal ATCs | Review and Approve/Disapprove of Formal ATCs For Proposer Optional Inclusion in Proposals | Notify Proposers of Formal ATC Approval/Disapproval For Inclusion in Proposal |  | Technical Proposal Technical Support Evaluators and Evaluation Committee Training | RFP Price and Technical Proposal Due / Technical Proposal Opening |  | Upload Technical, RFP Package Documents, Addendums, Responses to Questions, and Scoring Worksheets & Plan | Evaluate and Score Technical Proposals | Address Evaluator Questions | Submit Technical Scoring Worksheets | Compile Scoring Sheets for Consensus Meeting | Technical Proposal Consensus Meeting / Finalize Technical Proposal Scores | Scoring Official Concurrence with Consensus / Final Consensus Scoring | Public Price Proposal Opening and Best Value Scores Calculation / Validation | Review and Post Confirmed Price Opening Results and Best Value Scores | Price Reasonableness Review | Project Engineer's Estimate Reconciliation | Issue Notice of Competitive Range (NOCR) | NOCR Protest and Response Period | Negotiations with Best Value Proposer | (OPTIONAL) Negotiate With 2nd Highest Best Value Proposer | Conform Contract Documents With Approved Addendums and DOJ Approved Changes |  |  | Issue Notice of Intent to Award (NOIA) | NOIA Protest Period and Protest Resolution |  |  | Contract Assembly | Contract Review and Sign-off by Design-Builder | Provide Contract for DOJ Award Concurrence |  |  | OTC Award Approval, if applicable | FHWA Contract Award Concurrence | Agency Award Concurrence |  |  |  |  | Document Verification (Contract, DBE From 2, Bonds and Insurance Certifications, ect.) | Agency Contract Signature Routings | Contract Execution | Issue Notice to Proceed (NTP) | Award Contract and Send Executed Contract Documents to Contractor and CAU | Optional RFP Debriefing Process |  | Determine Who Needs to Participate in the RFP Debriefing Meeting | Schedule RFP Debriefing Meeting with Participants | Prepare Draft RFP Debriefing Meeting Agenda | Review RFP Debriefing Meeting Agenda | Finalize RFP Debriefing Meeting Agenda | Prep Required Documents and Information and Disseminate with Agenda to RFP Debriefing Meeting Participants | Conduct RFP Debriefing Meeting | Prepare RFP Debriefing Meeting Summary Report and Disseminate to Meeting Participants | Optional ODOT Internal Procurement to Construction Hand-off Process | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Draft Procurement to Construction Hand-Off Meeting Agenda | Review Procurement to Construction Hand-Off Meeting Agenda | Finalize and Disseminate Procurement to Construction Hand-Off Meeting Agenda | Conduct Procurement to Construction Hand-Off Meeting | Prepare and Disseminate Procurement to Construction Hand-Off Meeting Summary | Optional ODOT Internal Post-Procurement Lessons Learned Process | Coordinate Need for Conducting a Optional Post-Procurement Lessons Learned Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Schedule Post-Procurement Lessons Learned Meeting | Draft Post-Procurement Lessons Learned Meeting Agenda | Review Post-Procurement Lessons Learned Meeting Agenda | Finalize Post-Procurement Lessons Learned Meeting Agenda | Disseminate Documents and Information to Post-Procurement Lessons Learned Meeting Participants | Conduct Post-Procurement Lessons Learned Meeting | Prepare and Disseminate Post-Procurement Lessons Learned Meeting Summary Report | Region
Alternative Delivery Services | Delivery Method Evaluation and Selection (PD-14) | Method Evaluation & Validation & Validation (PD-14) | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Verify Concurrence | Procurement Kick-Off Meeting |  | Identify Risks and Develop Draft Risk Register | Conduct Risk Assessment Workshop and Update Risk Register |  |  | Send Draft FFE Documents to DOJ for Review and Approval | [6 empty] | Conduct Draft FFE Public Hearing |  |  | Send Final FFE to DOJ for Review and Approval |  |  |  |  | ODOT Director Review and Approval Final FFE |  |  |  |  | Send Draft Project Pre Solicitation Notice to DOJ for Review and Approval | [6 empty] | Develop Proof of Concept Plans | Develop Basic Configuration Elements, Preliminary Design Criteria and Exceptions, Deviations and Operational Approvals, and Urban Design | Develop DB Project-Specific Performance Specifications and DB Special Provisions | Region Specifications Writer QC and Refine DB Project-Specific Performance Specifications and DB Special Provisions |  |  | Send Draft Project Prequalification Waiver and Optional Proposal Security Waiver to DOJ for Review and Approval |  |  |  |  | Send Region Approved Project Prequalification Waver and Optional Proposal Security Waver |  | Draft RFQ Package Documents Project-Specific Information |  | Draft RFQ Package Review and Commenting |  | Provide DOJ Draft RFQ Package for Review and Approval |  |  |  | Draft RFP Package Documents Project-Specific Information |  | Draft RFP Package Review and Commenting | Provide Draft RFP Package to DOJ for Review and Approval |  | Finalize Draft RFQ Package |  | SOQ Evaluation Committee Scoring Members Selection | RFP Technical Proposal Evaluation Committee Scoring and Non-Scoring Members Selection | Select ATC Evaluation Committee Members | RFP Technical Proposal Evaluation Committee Scoring and Non-Scoring Members Selection |  | Assemble Draft Final RFQ Package |  | Draft Final RFQ Package Review and Commenting | Provide Draft Final RFQ Package to DOJ and FHWA for Review and Approval |  | Finalize RFQ Package Based on DOJ and FHWA Comments | DOJ Review and Approval of Final RFQ Package | FHWA Review and Approval of Final RFQ Package | Submit RFQ Ad (Business Tribune and DJC) | Release (Advertise) RFQ Package | Pre SOQ Meeting | Draft RFQ Addendums & Letters of Clarifications to Bidder Questions | RFQ Review Addendums & Letters of Clarifications | Post RFQ Addendums & Letters of Clarifications | SOQ Evaluation Committee Training | SOQ Submittals Due | [5 empty] | SOQ Consensus Meeting / Finalize SOQ Scores |  | Notify Proposers of Shortlisted Proposers |  |  |  | Schedule Optional RFQ Debriefing Meeting with Participants | Prepare Optional RFQ Debriefing Meeting Documents and Provided to Participants | Conduct Optional RFQ Debriefing Meeting | Prepare Optional RFQ Debriefing Meeting Summary Report and Disseminate to Meeting Participants |  | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review of Project Contract Documents | Update Contract Documents Base Templates with Project-Specific Information |  | Coordinate with ADS Specification Engineer on Proposed Changes to Contract Documents Base Template Language | ADS Specification Engineer Concurrence of Proposed Changes to Contract Documents Base Template Language | Provide ADS Specification Engineer Draft Contract Documents for Review and Commenting | ADS Specifications Engineer Draft Project-Specific Contract Documents Review and Approval | Update Draft Project-Specific Contract Documents with ADS Approved Changes | Provide ADS Specification Engineer Revised Draft Project-Specific Contract Documents for DOJ Review and Approval | Provide DOJ Draft Project-Specific Contract Documents for Review and Approval | DOJ Review and Approval of Draft Project-Specific Contract Documents | Review DOJ Comments on Draft Project-Specific Contract Documents and Updating as Needed | Review DOJ Comments on Draft Project-Specific Contract Documents and Updating as Needed |  | Verify 60 Day Jurisdiction Review Period of Exemption Order Completed |  | Submit Final RFP Package to OPO | Draft RFP Package Review |  | Provide Final RFP Package to DOJ and FHWA for Review and Commenting |  |  |  |  | Release RFP Package to Shortlisted Proposers | Pre-Proposal Meeting | Draft RFP Addendums & Letters of Clarifications to Bidder Questions | Review RFP Addendums & Letters of Clarifications | Provide RFP Addendums & Letters of Clarifications to DOJ Review and Approval |  | Post RFP Addendums & Letters of Clarifications |  | Proposers Request ATC One-on-One Meetings | Schedule ATC One-on-One Meetings | Conduct Pre-ATC Evaluation Training | ATC Proposer One-on-One Meetings | Proposers Submit Pre-ATCs | Determine if Pre-ATC Meet ATC Qualifying Criteria | Notify Proposers if their Pre-ATCs Meet ATC Qualifying Criteria and Can Be Submitted as Formal ATCs | Proposers Submit Formal ATCs | Review and Approve/Disapprove of Formal ATCs For Proposer Optional Inclusion in Proposals | Notify Proposers of Formal ATC Approval/Disapproval For Inclusion in Proposal |  | Technical Proposal Technical Support Evaluators and Evaluation Committee Training | Price and Technical Proposal Due / Technical Proposal Opening | [6 empty] | Technical Proposal Consensus Meeting / Finalize Technical Proposal Scores | Scoring Official Concurrence with Consensus / Final Consensus Scoring | Public Price Proposal Opening and Best Value Scores Calculation / Validation | Review and Post Confirmed Price Opening Results and Best Value Scores |  |  | Issue Notice of Competitive Range (NOCR) | NOCR Protest and Response Period | Negotiations with Best Value Proposer | (OPTIONAL) Negotiate With 2nd Highest Best Value Proposer | Conform Contract Documents With Approved Addendums and DOJ Approved Changes | Provide Conformed Contract Documents to DOJ for Review and Approval |  | Issue Notice of Intent to Award (NOIA) | NOIA Protest Period and Protest Resolution |  |  | Contract Assembly |  | Provide Contract for DOJ Award Concurrence |  |  |  | FHWA Contract Award Concurrence | [7 empty] | Contract Execution | Issue Notice to Proceed (NTP) | Award Contract and Send Executed Contract Documents to Contractor and CAU |  |  | Determine Who Needs to Participate in the RFP Debriefing Meeting | Schedule RFP Debriefing Meeting with Participants | Prepare Draft RFP Debriefing Meeting Agenda | Review RFP Debriefing Meeting Agenda | Finalize RFP Debriefing Meeting Agenda | Prep Required Documents and Information and Disseminate with Agenda to RFP Debriefing Meeting Participants | Conduct RFP Debriefing Meeting | Prepare RFP Debriefing Meeting Summary Report and Disseminate to Meeting Participants |  | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Draft Procurement to Construction Hand-Off Meeting Agenda | Review Procurement to Construction Hand-Off Meeting Agenda | Finalize and Disseminate Procurement to Construction Hand-Off Meeting Agenda | Conduct Procurement to Construction Hand-Off Meeting | Prepare and Disseminate Procurement to Construction Hand-Off Meeting Summary |  | Coordinate Need for Conducting a Optional Post-Procurement Lessons Learned Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Schedule Post-Procurement Lessons Learned Meeting | Draft Post-Procurement Lessons Learned Meeting Agenda | Review Post-Procurement Lessons Learned Meeting Agenda | Finalize Post-Procurement Lessons Learned Meeting Agenda | Disseminate Documents and Information to Post-Procurement Lessons Learned Meeting Participants | Conduct Post-Procurement Lessons Learned Meeting | Prepare and Disseminate Post-Procurement Lessons Learned Meeting Summary Report | Alternative Delivery Services
ODOT Procurement Office | Delivery Method Evaluation and Selection (PD-14) (Set Tentative Dates for Solicitation Tasks with Region) (Provide Region DB Procurement Schedule Template Before Validation Meeting) | Method Evaluation & Validation & Validation (PD-14) | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Verify Concurrence | Procurement Kick-Off Meeting | Scope Refinement, Data Collection, Site and Design Investigation | Identify Risks and Develop Draft Risk Register | Conduct Risk Assessment Workshop and Update Risk Register |  | Draft FFE Documents Development (Request and Setup Virtual Hearing Platform, if applicable) | Send Draft FFE Documents to DOJ for Review and Approval | Draft FFE Documents DOJ Review and Approval | Finalize Draft FFE Documents (Test Virtual Hearing Platform, if applicable | Submit Draft FFE and Supporting Documents to ODOT Director for Concurrence | ODOT Director Review Draft FFE For Concurrence | Submit FFE and (Optional Public Hearing Notice) for Advertisement | (Optional) 2 Week Draft FFE Public Hearing Advertisement Period and Respond to Comments | Conduct Draft FFE Public Hearing | (Optional) Respond to Draft FFE Public Hearing Comments | Finalize FFE With Optional Public Hearing Results | Provide Final FFE Document to DOJ for Review and Approval | Final FFE Document DOJ Review and Approval | Review DOJ Comments for Final FFE Documents | Finalize FFE Documents | Send Final FFE and Supporting Documents to ODOT Director for Concurrence | ODOT Director Review and Approval Final FFE | Post Final FFE on Website | Start 60 Day Jurisdiction Review Period of Exemption Order |  | Draft Project Pre Solicitation Notice | Send Draft Project Pre Solicitation Notice to DOJ for Review and Approval | Draft Project Pre Solicitation Notice DOJ Review and Approval | Finalize Draft Project Pre Solicitation Notice | Submit Final Project Pre Solicitation Notice Requirements for Advertisement to Industry Publications | Post Final Project Pre Solicitation Notice Requirements to OPO's Website | Receive and Document Interested Firms |  | Develop Proof of Concept Plans | Develop Basic Configuration Elements, Preliminary Design Criteria and Exceptions, Deviations and Operational Approvals, and Urban Design | Develop DB Project-Specific Performance Specifications and DB Special Provisions |  |  | Draft Project Prequalification Waiver and Optional Proposal Security Waiver | Send Draft Project Prequalification Waiver and Optional Proposal Security Waiver to DOJ for Review and Approval | Draft Project Prequalification Waiver and Optional Proposal Security Waiver DOJ Review and Approval | Finalize Draft Project Prequalification Waiver and Optional Proposal Security Waiver | Submit Project Prequalification Waver and Optional Proposal Security Waver to Hwy Division Administrator or Chief Engineer for Concurrence and ODOT Director's Approval | ODOT HWY Division Administrator or the Chief Engineer Review and Approval of Final Project Prequalification Waiver and Optional Proposal Security Waiver | Send Region Approved Project Prequalification Waver and Optional Proposal Security Waver |  | Draft RFQ Package Documents Project-Specific Information | Calculate and Finalize Stipend Amount for RFP | Draft RFQ Package Review and Commenting | Revise RFQ Package with Approved OPO Changes | Draft RFQ Package Documents Preparation | Draft RFQ Package DOJ Review and Approval | Finalize RFQ Package With OPO Approved DOJ Changes |  | Draft RFP Package Documents Project Specific Information |  | Draft RFP Package Review and Commenting | Provide Draft RFP Package to DOJ for Review and Approval | DOJ Review and Approval of Draft RFP Package | Finalize Draft RFP Package |  | SOQ Evaluation Committee Scoring Members Selections | RFP Technical Proposal Evaluation Committee Scoring and Non-Scoring Members Selection | Select ATC Evaluation Committee Members | Finalize Internal Technical Proposals and ATC Evaluation and Scoring Documents and Date |  | Assemble Draft Final RFQ Package | Submit Draft Final RFQ Package to OPO | Draft Final RFQ Package Review and Commenting | Provide Draft Final RFQ Package to DOJ and FHWA for Review and Approval | DOJ and FHWA Draft Final RFQ Package Review and Approval | Finalize RFQ Package Based on DOJ and FHWA Comments | DOJ Review and Approval of Final RFQ Package | FHWA Review and Approval of Final RFQ Package | Submit RFQ Ad (Business Tribune and DJC) | Release (Advertise) RFQ Package | Pre SOQ Meeting | Draft RFQ Addendums & Letters of Clarifications to Bidder Questions | Review RFQ Addendums & Letters of Clarifications | Post RFQ Addendums & Letters of Clarifications | SOQ Evaluation Committee Training | SOQ Submittals Due | SOQ Responsiveness Review | Upload SOQs, RFQ Package Documents, Addendums, Responses to Questions, and Scoring Worksheets & Plan | Evaluate and Score SOQs | Address SOQ Evaluator Questions | Submit SOQ Scoring Worksheets | SOQ Consensus Meeting / Finalize SOQ Scores | SOQ Consensus / Final SOQ Scores Approval by OPO Procurement Official | Notify Proposers of Shortlisted Proposers | Shortlist Protest Period and Protest Resolution |  | Upon Proposer Request for Optional RFQ Debrief Coordinate Meeting Requirements and Timeline with Proposer | Schedule Optional RFQ Debriefing Meeting with Participants | Prepare Optional RFQ Debriefing Meeting Documents and Provided to Participants | Conduct Optional RFQ Debriefing Meeting | Prepare Optional RFQ Debriefing Meeting Summary Report and Disseminate to Meeting Participants |  |  | Update Contract Documents Base Templates with Project-Specific Information | [12 empty] | Verify 60 Day Jurisdiction Review Period of Exemption Order Completed | Assemble Final RFP Package | Submit Final RFP Package to OPO | Provide Final RFP Package to DOJ for Review and Commenting | Finalize Draft RFP Package | Provide Final RFP Package to DOJ and FHWA for Review and Commenting | DOJ and FHWA Final RFP Package Review and Approval | Finalized RFP Package | DOJ Review and Approval of Final RFP Package for Release | FHWA Review and Approval of Final RFP Package for Release | Release RFP Package to Shortlisted Proposers | Pre-Proposal Meeting | Draft RFP Addendums & Letters of Clarifications to Bidder Questions | Review RFP Addendums & Letters of Clarifications | Provide RFP Addendums & Letters of Clarifications to DOJ Review and Approval | DOJ Review and Approval of RFP Addendums & Letters of Clarifications | Post RFP Addendums & Letters of Clarifications |  | Proposers Request ATC One-on-One Meetings | Schedule ATC One-on-One Meetings | Conduct Pre-ATC Evaluation Training | ATC Proposer One-on-One Meetings | Proposers Submit Pre-ATCs | Determine if Pre-ATC Meet ATC Qualifying Criteria | Notify Proposers if their Pre-ATCs Meet ATC Qualifying Criteria and Can Be Submitted as Formal ATCs | Proposers Submit Formal ATCs | Review and Approve/Disapprove of Formal ATCs For Proposer Optional Inclusion in Proposals | Notify Proposers of Formal ATC Approval/Disapproval For Inclusion in Proposal |  | Technical Proposal Technical Support Evaluators and Evaluation Committee Training | Price and Technical Proposal Due / Technical Proposal Opening | Pass/Fail Responsiveness Check of Technical Proposals | Upload Technical, RFP Package Documents, Addendums, Responses to Questions, and Scoring Worksheets & Plan | Evaluate and Score Technical Proposals | Address Evaluator Questions | Submit Technical Proposal Scoring Worksheets | Compile Scoring Sheets for Consensus Meeting | Technical Proposal Consensus Meeting / Finalize Technical Proposal Scores | Scoring Official Concurrence with Consensus / Final Consensus Scoring | Public Price Proposal Opening and Best Value Scores Calculation / Validation | Review and Post Confirmed Price Opening Results and Best Value Scores | Price Reasonableness Review | Project Engineer's Estimate Reconciliation | Issue Notice of Competitive Range (NOCR) | NOCR Protest and Response Period | Negotiations with Best Value Proposer | (OPTIONAL) Negotiate With 2nd Highest Best Value Proposer | Conform Contract Documents With Approved Addendums and DOJ Approved Changes | Provide Conformed Contract Documents to DOJ for Review and Approval | DOJ Review and Approval of RFP Conformed Contract Documents | Issue Notice of Intent to Award (NOIA) | NOIA Protest Period and Protest Resolution | Release Proposers' Best Value Consensus Scores and Technical Proposers | Stipend Payment to Qualified Un-Successful Proposers | Contract Assembly | Contract Review and Sign-off by Design-Builder | Provide Contract for DOJ Award Concurrence | DOJ Review and Contract Award Concurrence | Send Contract Award Concurrence Request to FHWA | OTC Award Approval, if applicable | FHWA Contract Award Concurrence | Agency Award Concurrence | Issue Award Recommendation Letter | Issue Award Letter to Design-Builder | Send Contract to Design-Builder for Signature | Design-Builder review and signature for execution of Contract documents (15 Calendar Days) | Document Verification (Contract, DBE From 2, Bonds and Insurance Certifications, ect.) | Agency Contract Signature Routings | Contract Execution | Issue Notice to Proceed (NTP) | Award Contract and Send Executed Contract Documents to Contractor and CAU |  | Upon Proposer Request for Optional RFP Debriefing Meeting, Coordinate Requirements and Timeline with Proposer | Determine Who Needs to Participate in the RFP Debriefing Meeting | Schedule RFP Debriefing Meeting with Meeting Participants | Prepare Draft RFP Debriefing Meeting Agenda | Review RFP Debriefing Meeting Agenda | Finalize RFP Debriefing Meeting Agenda | Prep Required Documents and Information and Disseminate with Agenda to RFP Debriefing Meeting Participants | Conduct RFP Debriefing Meeting | Prepare RFP Debriefing Meeting Summary Report and Disseminate to Meeting Participants |  | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Draft Procurement to Construction Hand-Off Meeting Agenda | Review Procurement to Construction Hand-Off Meeting Agenda | Finalize and Disseminate Procurement to Construction Hand-Off Meeting Agenda | Conduct Procurement to Construction Hand-Off Meeting | Prepare and Disseminate Procurement to Construction Hand-Off Meeting Summary |  | Coordinate Need for Conducting a Optional Post-Procurement Lessons Learned Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Schedule Post-Procurement Lessons Learned Meeting | Draft Post-Procurement Lessons Learned Meeting Agenda | Review Post-Procurement Lessons Learned Meeting Agenda | Finalize Post-Procurement Lessons Learned Meeting Agenda | Disseminate Documents and Information to Post-Procurement Lessons Learned Meeting Participants | Conduct Post-Procurement Lessons Learned Meeting | Prepare and Disseminate Post-Procurement Lessons Learned Meeting Summary Report | ODOT Procurement Office
Project Controls Office Manager | Delivery Method Evaluation and Selection (PD-14) |  | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Verify Concurrence | [211 empty] | Project Controls Office Management
ODOT Program Development Office Manager | Delivery Method Evaluation and Selection (PD-14) |  | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Verify Concurrence | Procurement Kick-Off Meeting | [210 empty] | ODOT Program Development Office Manager
Statewide Project Delivery Manager | Delivery Method Evaluation and Selection (PD-14) |  | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Verify Concurrence | Procurement Kick-Off Meeting | [210 empty] | Statewide Project Delivery Manager
Department of Justice | Delivery Method Evaluation and Selection (PD-14) |  | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Design-Build Method Concurrence Meeting (If not previously completed during Program Development) | Procurement Kick-Off Meeting | [6 empty] | Draft FFE Documents DOJ Review and Approval | [9 empty] | Final FFE Document DOJ Review and Approval |  |  |  | ODOT Director Review and Approval Final FFE |  | Start of 60 Day Jurisdiction Review Period of Exemption Order |  |  |  | Draft Project Pre Solicitation Notice DOJ Review and Approval | [12 empty] | Draft Project Prequalification Waiver and Optional Proposal Security Waiver DOJ Review and Approval | [10 empty] | Draft RFQ Package DOJ Review and Approval | [6 empty] | DOJ Review and Approval of Draft RFP Package | [11 empty] | DOJ and FHWA Draft Final RFP Package Review and Approval |  | DOJ Review and Approval of Final RFQ Package | FHWA Review and Approval of Final RFQ Package |  |  |  |  | DOJ Review and Approval of RFQ Addendums & Letters of Clarifications | [11 empty] | Shortlist Protest Period and Protest Resolution | [7 empty] | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review of Project Contract Documents | [9 empty] | DOJ Review and Approval of Draft Project-Specific Contract Documents |  |  |  | Verify 60 Day Jurisdiction Review Period of Exemption Order Completed | [5 empty] | DOJ Final RFP Package Review and Approval |  | DOJ Final RFP Package Review and Approval for Release | [6 empty] | RFP Addendums & Letters of Clarifications to DOJ Review and Approval | [28 empty] | NOCR Protest and Response Period |  |  |  |  | DOJ Review and Approval of RFP Conformed Contract Documents |  | NOIA Protest Period and Protest Resolution | [5 empty] | DOJ Review and Contract Award Concurrence | [41 empty] | Department of Justice
ODOT Director or HWY Administrator or Chief Engineer | [13 empty] | Submit Draft FFE and Supporting Documents to ODOT Director for Concurrence | ODOT Director Review Draft FFE For Concurrence | [10 empty] | ODOT Director Review and Approval Final FFE | [21 empty] | ODOT HWY Division Administrator or the Chief Engineer Review and Approval of Final Project Prequalification Waiver and Optional Proposal Security Waiver | [167 empty] | ODOT Director
Federal Highway Administration | Delivery Method Evaluation and Selection (PD-14) | [73 empty] | DOJ and FHWA Draft Final RFP Package Review and Approval |  |  | FHWA Review and Approval of Final RFQ Package | FHWA Review and Approval of Final RFQ Package | [43 empty] | FHWA Final RFP Package Review and Approval |  |  | FHWA Final RFP Package Review and Approval for Release | [50 empty] | FHWA Review and Contract Award Concurrence | [38 empty] | Federal Highway Administration
Contract Administration Unit (CAU) | Delivery Method Evaluation and Selection (PD-14) | [102 empty] | Update Contract Documents Base Templates with Project-Specific Information | [24 empty] | Draft RFP Addendums & Letters of Clarifications to Bidder Questions | [37 empty] | Issue Notice of Intent to Award (NOIA) | [18 empty] | Issue Notice to Proceed (NTP) | Award Contract and Send Executed Contract Documents to Contractor and CAU | [11 empty] | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Draft Procurement to Construction Hand-Off Meeting Agenda | Review Procurement to Construction Hand-Off Meeting Agenda | Finalize and Disseminate Procurement to Construction Hand-Off Meeting Agenda | Conduct Procurement to Construction Hand-Off Meeting | Prepare and Disseminate Procurement to Construction Hand-Off Meeting Summary | [10 empty] | Contract Administration Unit (CAU)
Engineering and Technical Services | [37 empty] | Develop Proof of Concept Plans | Develop Basic Configuration Elements, Preliminary Design Criteria and Exceptions, Deviations and Operational Approvals, and Urban Design | Develop DB Project-Specific Performance Specifications and DB Special Provisions | Region Specifications Writer QC and Refine DB Project-Specific Performance Specifications and DB Special Provisions | [12 empty] | Finalize Design Alternatives and Proof of Concept Plans | [12 empty] | RFP Technical Proposal Evaluation Committee Scoring and Non-Scoring Members Selection | Select ATC Evaluation Committee Members | [35 empty] | Update Contract Documents Base Templates with Project-Specific Information | [31 empty] | Schedule ATC One-on-One Meetings | Conduct Pre-ATC Evaluation Training | ATC Proposer One-on-One Meetings | Proposers Submit Pre-ATCs | Determine if Pre-ATC Meet ATC Qualifying Criteria |  | Proposers Submit Formal ATCs | Review and Approve/Disapprove of Formal ATCs For Proposer Optional Inclusion in Proposals | Notify Proposers of Formal ATC Approval/Disapproval For Inclusion in Proposal | [71 empty] | Federal Highway Administration
Office Equity and Civil Rights (OECR) | Delivery Method Evaluation and Selection (PD-14) | [58 empty] | Develop Project-Specific Workforce Protection Requirements With Region | [5 empty] | SOQ Evaluation Committee Scoring Members Selection | [18 empty] | SOQ Evaluation Committee Training | [6 empty] | SOQ Consensus Meeting / Finalize SOQ Scores | [36 empty] | Draft RFP Addendums & Letters of Clarifications to Bidder Questions | [37 empty] | Issue Notice of Intent to Award (NOIA) | [18 empty] | Issue Notice to Proceed (NTP) | Award Contract and Send Executed Contract Documents to Contractor and CAU | [11 empty] | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | Draft Procurement to Construction Hand-Off Meeting Agenda | Review Procurement to Construction Hand-Off Meeting Agenda | Finalize and Disseminate Procurement to Construction Hand-Off Meeting Agenda | Conduct Procurement to Construction Hand-Off Meeting | Prepare and Disseminate Procurement to Construction Hand-Off Meeting Summary | [10 empty] | Office Equity and Civil Rights (OECR)
Project Risk Management | [7 empty] | Conduct Risk Assessment Workshop and Update Risk Register | [207 empty] | Project Risk Management
Note on DD5: Alternative Delivery Services: Per Holli, OCR changed name to Office Equity and Civil Rights. Replaced OCR with OECR.

## DB Contract Admin - Post-Con
Design-Build Delivery Method Contract Administration to Post-Construction Process Map | [21 empty] | Index: | Blue = Accountable | Red = Responsible | Grey = Consulted | Orange = Informed | December 2022
Phases | Design and Construction Management Phase | [12 empty] | Post-Construction Closeout Phase | [29 empty] | Phases
Owners |  | RACI Steps 247 | RACI Step 248 | RACI Step 249 | RACI Step 250 | RACI Step 251 | RACI Step 252 |  | RACI Step 253 | RACI Step 254 | RACI Step 255 | RACI Step 256 |  | RACI Step 257 | RACI Step 258 | RACI Step 259 |  | RACI Step 260 | RACI Step 261 |  | RACI Step 262 | RACI Step 263 | RACI Step 264 | RACI Step 265 | RACI Step 266 | RACI Step 267 | RACI Step 268 | RACI Step 269 | RACI Step 270 | RACI Step 271 | RACI Step 272 | RACI Step 273 |  | RACI Step 274 | RACI Step 275 | RACI Step 276 | RACI Step 277 | RACI Step 278 | RACI Step 279 | RACI Step 280 | RACI Step 281 | RACI Step 282 | RACI Step 283 | Owners
Region | Design and Construction Compliance Reviews and Acceptance Process | Design Development Meeting (Prior to the Commencement of Design) | Design Mobilization Meeting (Within (45) Calendar Days of NTP) | Over-the Shoulder Reviews | Definitive Design Review and Commenting and Acceptance | Interim Design Review and Commenting and Acceptance | Readiness-for-Construction Design Review and Commenting and Acceptance | Design Exceptions, Design Deviations, and Operations Approvals Review and Commenting and Approval | Design Non-Conformance Report (NCR) and Resolution | Working Plans or Working Drawings or 3D Construction Model Design Review and Commenting | As-Constructed Plans and Design-Builder Specifications Review and Commenting and Acceptance | Contract - Construction Administration and Oversight | Post-Construction Closeout Process (2nd Notification) | Track Second Notification (2nd Note) Issuance | Schedule FFE Post-Construction Reporting Requirements Discussion Meeting with Region to Take Place No Earlier Than 45 Calendar Days After 2nd Note | Meet with Region to Discuss Required Project Information for Inclusion in PM Narrative for Upcoming FFE Post-Construction Reports | Post-Construction Evaluation Reports Process (3rd Notification) | Track When ODOT Issues Third Notice and Final Payment | Provide Region FFE Post-Construction Evaluation Report Base Documents | FFE Post-Construction Evaluation Report Process | Draft FFE Post-Construction Evaluation Report | Region Provide ADS Project EA |  | Review of Draft FFE Post-Construction Evaluation Report | Revise Draft FFE Post-Construction Evaluation Report With ADS Approved Changes | Provide DOJ Draft FFE Post-Construction Evaluation Report for Review |  | Revise and Finalize Draft FFE Post-Construction Evaluation Report With ADS Approved DOJ Changes |  | Submit Final FFE Post-Construction Evaluation Report and supporting documentation to ODOT Director |  | Post Final FFE Post-Construction Evaluation Report on OPO Website Under the “Alternative Contracting” Section For Public Inspection | Post-Construction Lessons Learned Process | Draft Lessons Learned Follow Up Items List | Schedule Lessons Learned Meeting | Review of Draft Lessons Learned Follow Up Items List | Revise and Finalize Draft Lessons Learned Items List with Approved Changes | Send Attendees Final Lessons Learned Items List | Conduct Lessons Learned Follow Up | Draft Lessons Learned Follow Up Summary Report | Review of Draft Lessons Learned Follow Up Summary Report | Revise and Finalize Draft Lessons Learned Meeting Summary Report with Redline Changes | Send Attendees Final Lessons Learned Meeting Summary Report | Region
Alternative Delivery Services | [13 empty] | Track Second Notification (2nd Note) Issuance | Schedule FFE Post-Construction Reporting Requirements Discussion Meeting with Region to Take Place No Earlier Than 45 Calendar Days After 2nd Note | Meet with Region to Discuss Required Project Information for Inclusion in PM Narrative for Upcoming FFE Post-Construction Reports |  | Track When ODOT Issues Third Notice and Final Payment | Provide Region FFE Post-Construction Evaluation Report Base Documents |  | Draft FFE Post-Construction Evaluation Report | Region Provide ADS Project EA | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review | Review of Draft FFE Post-Construction Evaluation Report | Revise Draft FFE Post-Construction Evaluation Report With ADS Approved Changes | Provide DOJ Draft FFE Post-Construction Evaluation Report for Review | DOJ Review of Draft FFE Post-Construction Evaluation Report | Revise and Finalize Draft FFE Post-Construction Evaluation Report With ADS Approved DOJ Changes | Develop and Email Advanced Notification Email for the FFE Post-Construction Evaluation Report to ODOT Director | Submit Final FFE Post-Construction Evaluation Report and supporting documentation to ODOT Director | Provide OPO Copy of Final FFE Post-Construction Evaluation Report for Posting on OPO Website | Post Final FFE Post-Construction Evaluation Report on OPO Website Under the “Alternative Contracting” Section For Public Inspection |  | Draft Lessons Learned Follow Up Items List | Schedule Lessons Learned Meeting | Review of Draft Lessons Learned Follow Up Items List | Revise and Finalize Draft Lessons Learned Items List with Approved Changes | Send Attendees Final Lessons Learned Items List | Conduct Lessons Learned Follow Up | Draft Lessons Learned Follow Up Summary Report | Review of Draft Lessons Learned Follow Up Summary Report | Revise and Finalize Draft Lessons Learned Meeting Summary Report with Redline Changes | Send Attendees Final Lessons Learned Meeting Summary Report | Alternative Delivery Services
ODOT Procurement Office | [30 empty] | Provide OPO Copy of Final FFE Post-Construction Evaluation Report for Posting on OPO Website | Post Final FFE Post-Construction Evaluation Report on OPO Website Under the “Alternative Contracting” Section For Public Inspection |  |  | Schedule Lessons Learned Meeting (As needed) | Review of Draft Lessons Learned Follow Up Items List (As needed) | Revise and Finalize Draft Lessons Learned Items List with Approved Changes (As needed) |  | Conduct Lessons Learned Follow Up (AS needed) |  | Review of Draft Lessons Learned Follow Up Summary Report (AS needed) |  | Send Attendees Final Lessons Learned Meeting Summary Report (AS needed) | ODOT Procurement Office
Project Controls Office | [34 empty] | Schedule Lessons Learned Meeting (As needed) | Review of Draft Lessons Learned Follow Up Items List (As needed) | Revise and Finalize Draft Lessons Learned Items List with Approved Changes (As needed) |  | Conduct Lessons Learned Follow Up (AS needed) |  | Review of Draft Lessons Learned Follow Up Summary Report(AS needed) |  | Send Attendees Final Lessons Learned Meeting Summary Report (AS needed) | Project Controls Office Management
ODOT Program Development Office Manager | [43 empty] | ODOT Program Development Office Manager
Statewide Project Delivery Manager | [43 empty] | Statewide Project Delivery Manager
Department of Justice | [22 empty] | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review |  |  |  | DOJ Review of Draft FFE Post-Construction Evaluation Report | [16 empty] | Department of Justice
ODOT Director or HWY Administrator or Chief Engineer | [29 empty] | Submit Final FFE Post-Construction Evaluation Report and supporting documentation to ODOT Director | [13 empty] | ODOT Director
Federal Highway Administration |  |  |  |  | Definitive Design Design Exceptions Review and Commenting and Acceptance |  |  | Design Exceptions Review and Commenting and Approval | Design Non-Conformance Report (NCR) and Resolution | [34 empty] | Federal Highway Administration
Contract Administration Unit (CAU) |  | Design Development Meeting (Prior to the Commencement of Design) |  |  |  |  | Readiness-for-Construction Design Review and Commenting and Acceptance |  |  |  |  | Contract - Construction Administration and Oversight | [21 empty] | Draft Lessons Learned Follow Up Items List | Schedule Lessons Learned Meeting | Review of Draft Lessons Learned Follow Up Items List |  |  | Conduct Lessons Learned Follow Up |  | Review of Draft Lessons Learned Follow Up Summary Report |  | Send Attendees Final Lessons Learned Meeting Summary Report | Contract Administration Unit (CAU)
Engineering and Technical Services |  |  |  | Over-the Shoulder Reviews | Definitive Design Review and Commenting and Acceptance | Interim Design Review and Commenting and Acceptance | Readiness-for-Construction Design Review and Commenting and Acceptance | Design Exceptions Review and Commenting and Approval | Design Non-Conformance Report (NCR) and Resolution | Working Plans or Working Drawings or 3D Construction Model Design Review and Commenting | As-Constructed Plans and Design-Builder Specifications Review and Commenting and Acceptance |  |  | Track Second Notification (2nd Note) Issuance |  |  |  | Track When ODOT Issues Third Notice and Final Payment | [25 empty] | Federal Highway Administration
Office of Equity and Civil Rights (OECR) |  | Design Development Meeting (Prior to the Commencement of Design) |  |  |  |  | Readiness-for-Construction Design Review and Commenting and Acceptance (workforce development topics) |  |  |  |  | Contract - Construction Administration and Oversight | [21 empty] | Draft Lessons Learned Follow Up Items List | Schedule Lessons Learned Meeting | Review of Draft Lessons Learned Follow Up Items List |  |  | Conduct Lessons Learned Follow Up | Review of Draft Lessons Learned Follow Up Summary Report | Review of Draft Lessons Learned Follow Up Summary Report |  | Send Attendees Final Lessons Learned Meeting Summary Report | Office Equity and Civil Rights (OECR)
Project Risk Management | [43 empty] | Project Risk Management
For more information on the design review process, see Appendix 2 - Design Review Process Flow Chart in the Design-Build Contract Administration Manual
For more information on the design review process, see Appendix 2 - Design Review Process Flow Chart in the Design-Build Contract Administration Manual

## RFP Development (hidden)
"Best Value" Request for Proposal base template documents for Construction Manager / General Contractor Delivery Method
"Request for Proposal Process" is owned and managed by ODOT Office of Procurement. These base documents will be released to Region project teams and Innovative Delivery Services Unit during prescribed CM/GC procurement process. Region and Innovative Delivery Services Unit will coordinate with ODOT Office of Procurement in populating these required documents with project specific information and data.
Instructions and General Provisions (2 Docs)
1 | Base Instruction to Proposers (ITP) Base Document | Quality & Price Forms [11 Docs]
2 | Exhibit A - General Provisions 100s | 3 | Form Index Base Document | Process Documents [11 Docs]
|  | 4 | Acknowledgement of Receipt Base Document | 14 | CM/GC Deliverables - Preconstruction Spreadsheet Base Document
|  | 5 | Fee Percentage Form Base Document | 15 | Protocols for Interviews Base Document
|  | 6 | ICS - Certificate Regarding Ineligible Contractors & Subcontractors Base Document | 16 | Evaluation and Scoring Process, Training Plan/Presentation and Scoring Worksheets Base Document
|  | 7 | LC - Lobbying Certificate Base Document | 17 | Pre-proposal meeting Base Document
|  | 8 | Form COI Base Document | 18 | Price Opening Narrative Base Document
|  | 9 | NC - Non-Collusion Base Document | 19 | Negotiations Protocols, Process and Forms Base Document
|  | 10 | ND - Certificate Regarding Nondiscrimination Base Document | 20 | FHWA Approval to Release RFP Base Document
|  | 11 | PP- Pre-Construction Phase Services Proposal Base Document | 21 | Notice of Competitive Range Base Document
|  | 12 | Q & A Form Base Document | 22 | Best-Value Proposer Announcement Base Document
|  | 13 | Proposal Signature Page and Firm Offer Base Document | 23 | Notice of Intent of Award Base Document
|  |  |  | 24 | NTP For Pre-Construction Services Base Document
|  |  |  | 25 | Tie in ITP references to contract or GPs sections with contract and GP document language

## CM GC Contract Development (hidden)
"Best Value" Construction Contract for Construction Manager / General Contractor Delivery Method
CM/GC Contract Development Process is owned and managed by Innovative Delivery Services Unit. Innovative Delivery Services Unit will coordinate with Region, Department of Justice and ODOT Office of Procurement in populating these required documents with project specific information and data.
CM/GC Base Template and Base Early Work Amendment
1 | Sample Contract - Base Document | CM/GC Contract Exhibits- Base Documents
2 | Sample Early Work Amendment - Base Document | 3 | Exhibit A | Sample GMP Amendment to CM/GC Contract | CM/GC Contract Section 100- Base Documents
|  | 4 | Exhibit B | CM/GC Payment, Performance, and Public Works Bonds | 22 | 00110 | Organization, Conventions, Abbreviations and Definitions - Base Document
|  | 5 | Exhibit C | Required Contract Provisions for Federal Aid Construction Contracts (See C-1 through C-9) | 23 | 00120 | Bidding Requirements and Procedures - Base Document
|  | 6 | Exhibit C1 | Exhibit C1 - Required Contract Provisions for Federal-Aid Construction Contract (FHWA-1273) | 24 | 00130 | Award and Execution - Base Document
|  | 7 | Exhibit C2 | On-Site Workforce Affirmative Action Requirements for Women and Minorities on Federal-Aid Contracts - Base Documents | 25 | 00140 | Scope of Work - Base Document
|  | 8 | Exhibit C3 | Equal Employment Opportunity Contract Provisions | 26 | 00141 | Preconstruction Phase Services - Scope of Work - Base Document
|  | 9 | Exhibit C4 | Equal Employment Opportunities - Aspiration Target Contract Provisions | 27 | 00142 | Construction Services - Scope of Work - Base Document
|  | 10 | Exhibit C5 | Disadvantaged Business Enterprise (DBE) Supplemental Required Contract Provisions | 28 | 00143 | Economic Development - Base Document
|  | 11 | Exhibit C6 | Disadvantaged Business Enterprise (DBE) Supplemental Aspirational Target Contract Provisions | 29 | 00144 | Workforce and Business Equity - Base Document
|  | 12 | Exhibit C7 | Minority Business Enterprise, Women Business Enterprise, and Emerging Small Business (MWESB) Supplemental Aspirational Target Contract Provisions TBD by OCR | 30 | 00150 | Control of Work - Base Document
|  | 13 | Exhibit C8 | Federal On-the-Job / Apprenticeship Training Contract Provisions | 31 | 00160 | Source of Materials - Base Document
|  | 14 | Exhibit C9 | TERO, Environmental Justice and Other Areas TBD by OCR | 32 | 00165 | Quality of Materials - Base Document
|  | 15 | Exhibit D | Project and Program Goals - Base Document | 33 | 00170 | Legal Relations and Responsibilities- Base Document
|  | 16 | Exhibit E | Community Advisory Group Members - Base Document | 34 | 00180 | Prosecution and Progress- Base Document
|  | 17 | Exhibit F | Co-Location Requirements - Base Document | 35 | 00190 | Pricing and Measurement of Pay Quantities- Base Document
|  | 18 | Exhibit G | Insurance Requirements - Base Document | 36 | 00195 | Payment- Base Document
|  | 19 | Exhibit H | General Conditions Work - Base Document | 37 | 00196 | Payment for Extra Work- Base Document
|  | 20 | Exhibit I | Federal Wage Rate Determinations - Base Document | 38 | 00197 | Payment for Force Account Work- Base Document
|  | 21 | Exhibit ??? | ProjectWise End User Agreement | 39 | 00199 | Disagreements, Protests and Claims- Base Document
[5 empty] | 40 |  | Table of Contents- Base Document