## RACI for Design-Build
Design-Build - RACI Matrix
Task Number | TASKS | ODOT Procurement Office (OPO) | Alternative Delivery Section (ADS) | Region/Consultant | Oregon Department of Justice (DOJ ) | Project Risk Management | Office of Equity and Civil Rights (OECR) | Federal Highway Administration (FHWA) | Project Controls Office Manager (PCOM) | ODOT Director or HWY Administrator or Chief Engineer | Statewide Project Delivery Manager (SPDM) | Contract Administration Unit (CAU) | Design-Builder (DB) | Engineering and Technical Services
Alternative Delivery Evaluation Phase
1 | Perform Initial Evaluation and Screening |  | A | R
2 | Perform Formal Delivery Method Selection Tool Evaluation | I | A | R
3 | Coordinate and Facilitate Validation Meeting | C | A | R | [6 empty] | I | I
4 | OPO and ADS Provide Region DB Procurement Schedule Template Document (MS Project) | R | R | C | I
5 | Note: Project Team must include reasonable durations for ADS, OPO, DOJ, and FHWA review time. Set Dates for the following Items in the MS Project schedule: 1) Findings of Fact (FFE) Development and Optional Public Hearing 2) Final FFE 3) Sample Contract (DB Agreement, Exhibits, General Provisions, Attachments, etc.) Completion 4) Development of Request of Qualifications (RFQ) 5) Development of Request of Proposals (RFP) 6) Pre Solicitation Notice Released 7) RFQ Release 8) Pre-Statement of Qualifications (SOQ) Meeting 9) SOQs Due and Shortlisting 10) RFP Release 11) Pre-Proposal Meeting 12) Alternative Technical Concepts (ATCs) 13) Technical Proposals Due and Price Proposals Due 14) Conformed/ Execution of Contract Documents 15) Notice of Intent to Award (ITA) 16) Contract Award 17) NTP | C | C | A | I | [9 empty] | R = Responsible: Which position or department will be Responsible for completing each or a portion of a task? (Completes Task - worker) | A = Accountable: Which position or department will be Accountable, ultimately answerable for the activity or decision for major tasks and the result? This oftentimes is different than the Responsible party. (Manage Task - manager) | C = Consulted: Which positions or departments must be Consulted? Consulted parties have a say before, making decisions or tasks are completed. They are not responsible or accountable for the outcome. | I = Informed: Which positions or departments must be Informed as the tasks progress? These parties don't need to provide input during the process but must be aware of decisions made. | NOTE: If "A" is assigned to a task without an "R", then both "A" and "R" is assigned to the Position/Department for that task.
6 | Region Selection of Design-Build Alternative Selection Method for the Project (PD-14) | I | C | A
7 | ADS Provides the Region the Concurrence Letter Form (See PD-14) | I | A | C
8 | Finalize comments, signatures, and submit the Concurrence Letter to ADS for review and distribution, including schedule dates. | I | R | A
9 | Distribute MS Project Schedule for Review and Feedback | I | I | A | I |  |  | I |  |  | I | I
10 | ADS Coordinates with Region, OPO and SPD Branch, etc. for concurrence meeting (PD-14) (ADS Facilitates) | C | A | C | I |  |  |  | C |  | C
11 | Region Manager, SPD Branch and OPO Ops and Construction Manager Meeting for Concurrence of MS Project Schedule dates, Resourcing, and Method Selected | R | R | A | R |  |  | R
12 | Region Manager, SPD Branch and OPO Ops and Construction Manager Meeting for Concurrence / Non-Concurrence (PD-14) (DOJ Optional) | R | A | R | I |  | I | I | R |  | R | I
Project Development Phase
13 | Conduct Alternative Delivery / Procurement Kick-Off Meeting | R | A | R | I |  |  |  | I |  | I
14 | Set up ProjectWise folder structure with ProjectWise Admin team |  | R | C
15 | ADS Provides Region Contract Template Base Documents: 1) Sample DB Agreement and Exhibits 2) General Provisions (includes performance specifications) and Attachments. 3) Misc. Forms, steel escalation, Form SP. 4) Technical Resource List. 5) Other reference materials. | I | A | R | C
16 | OPO to coordinate with Region to collect Solicitation information for Base Documents. | A | I | R
17 | OPO drafts FFE, RFQ, and RFP | A | C | C
18 | Project Scope Refinement (Includes site investigations, site conditions, constraints, impacts and requirements (must haves), data collection | I |  | A
19 | Identify Risks and Develop Risk Register | I | I | A
20 | Conduct Risk Assessment Workshop and Update Risk Register | C | I | A |  | C
21 | Develop Risk Mitigations Strategies and Ownership | C | I | A |  | C
22 | Analysis to Identify Risks Exposures and Mitigation Strategies for Insurance Requirements with OPO Risk Compliance Analysis | A | I | R
23 | Develop Evaluation and Scoring Criteria and Weighting for RFQ | A | I | R
24 | Develop Evaluation and Scoring Criteria and Weighting for RFP | A | I | R
25 | Develop Level of Needed Proof of Conceptual Design | I | I | A | [9 empty] | C
26 | Develop Project Basic Configuration Elements | I | I | A | [9 empty] | C
27 | Define Project Elements Requiring Preliminary Design Exceptions, Design Deviations, Operations Approvals, and Interchange Approvals, as applicable. | I | C | A |  |  |  | C | [5 empty] | R
28 | Define Minimal and Performance Contract Requirements | I | C | A
Preliminary Design Development - Proof of Concept Level Plans
29 | Develop and Finalize Proof of Concept Plans | I | C | A | [9 empty] | C
30 | Develop and Finalize Basic Configuration Elements, Preliminary Design Criteria and Exceptions, Deviations and Operations Approvals, and Urban Design | I | C | A | [9 empty] | C
Prepare Project-Specific Contract Documents
31 | Develop DB Project-Specific Performance Requirements | I | C | A | [9 empty] | C
32 | Region Specifications Writer QC and Refine DB Project-Specific Performance Specifications and DB Special Provisions |  | C | A | [9 empty] | C
Project Specific Development of Contract Documents Process
33 | Request Authorization for DOJ Legal Assistance For Legal Sufficiency Review of Project-Specific Contract Documents (DB Agreement & Exhibits, DB General Provisions & Attachments, DB Standard Technical Specifications, and DB Special Provisions). |  | A |  | I
34 | Update Contract Documents Base Templates; DB Agreement & Exhibits, DB General Provisions & Attachments Contract Documents Base Templates with Project-Specific Information, including: |  | C | A
DB Agreement
DB Agreement Exhibits
DB General Provisions (including DB141)
DB General Provisions Attachment A - Engineering Data Documents and TOC
DB General Provisions Attachment B1 - DB Boilerplate Technical Special Provisions
DB General Provisions Attachment B2 - DB Special Provisions (if applicable)
DB General Provisions Attachment C - Reference Documents and TOC
| Finalize Work Locations in Contract Documents and Price Centers (Form SP) | I | C | A | [7 empty] | R
| Finalize Interim Completion Date(s) and Contract Completion Date |  | C | A | [7 empty] | R
| Establish Liquidated Damages Daily Rates |  | C | A | [7 empty] | R
| Include applicable DB Standard Technical Specifications and DB Special Provisions (See Attachment B) |  | C | A
35 | Region Specifications Writer QC and Refine Project-Specific DB Contract Documents; DB Agreement & Exhibits, General Provisions & Attachments |  | C | A
36 | Coordinate with ADS on Proposed Changes to Contract Documents Base Template Language |  | A | R
37 | ADS Concurrence of Proposed Changes to Contract Documents Base Template Language |  | A | C
38 | Provide ADS with Complete Project-Specific Contract Documents for Review and Commenting, in ProjectWise ("First Submittal package") | I | A | R
39 | ADS QA review of Complete Project-Specific Contract Documents - First Submittal package Review |  | A
40 | ADS to Provide Project Team with ADS Reviewed Project-Specific Contract Documents, in ProjectWise for Project team to address comments |  | A | R
41 | Update Project-Specific Contract Documents with ADS Approved Changes |  | C | A
42 | Provide ADS with Revised Project-Specific Contract Documents ("Revised Submittal package") | I | I | A
43 | ADS determines if "Revised" Project-Specific Contract Documents are ready for DOJ review (or repeat Project-Specific Contract Document reviews above, as required) |  | A
44 | Provide DOJ Project-Specific Contract Documents for Review | I | A | I
45 | DOJ (Legal Sufficiency) Review and/or Approval of Project-Specific Contract Documents | I | A | I | R
46 | Review DOJ Comments on Project-Specific Contract Documents and update as required |  | A | R
47 | Finalize Project-Specific Contract Documents for Inclusion in RFP Package, concurrent with or prior to start of the "RFQ and RFP Development" Phase. | I | C | A
Finding of Fact for Exemption (FFE) Process
48 | Assign FFE Order Number | A
49 | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review of Solicitation Documents (FFE Documents, Pre Solicitation Notice, Prequalification Waiver, Optional Proposal Security Waiver, and RFQ & RFP packages). | A |  |  | R
50 | Develop and Finalize Project Specific Information for FFE and optional Public Hearing Notice and documents | A |  | R
51 | Request Hearing Official Assignment and Public Hearing Date (Optional) | A |  | C
52 | Provide FFE and Optional Public Hearing Notice for DOJ review | A
53 | DOJ Review and approval of FFE documents (FFE and Optional Public Hearing Notice) | A |  |  | R
54 | Develop and Send Advanced Notification Email for FFE Concurrence Request to ODOT Director (Per ODOT Document Guidelines for Sending Requests to ODOT Director and Assistant Directors) | A |  | C
55 | Develop FFE Concurrence Request Letter to ODOT Director | A |  | C
56 | Finalize FFE Concurrence Request Letter to ODOT Director and Test Virtual Hearing Platform ‐ WebEx, if applicable | A
57 | Submit FFE with Supporting Documentation and ODOT Director FFE Concurrence Request letter to ODOT Director (Per ODOT Document Guidelines for Sending Requests to ODOT Director and Assistant Directors) | A |  | I | [5 empty] | C
58 | ODOT Director Review and Concurrence of FFE | A | [7 empty] | R
59 | Submit FFE and Optional FFE Public Hearing Notice for Advertisement, if Applicable to Industry Publications (Minimum of 2 weeks before public hearing date) | A |  | I
60 | Post FFE to OPO's Website (Industry Publications Publicizes Optional FFE Public Hearing Notice and FFE) | A
61 | 2 Week Optional FFE Public Hearing Advertisement Period | A
62 | Review and Respond to Public Comments Received During Advertisement Period | A |  | C
63 | Conduct Optional FFE Public Hearing, if applicable | A | I | R
64 | Review and Respond to Comments Received During Optional Public Hearing, if Applicable | A |  | C
65 | Develop FFE Approval Request Letter to ODOT Director | A
66 | Finalize FFE and With Optional Public Hearing Results, if Applicable | A |  | C
67 | Provide DOJ the Final FFE for Review | A | I | I
68 | DOJ Reviews the Final FFE | A |  |  | R
69 | Review and update per DOJ Comments on the FFE | A |  | I
70 | Draft Final FFE ODOT Director Approval Cover Letter to ODOT Director | A
71 | Submit FFE with Supporting Documentation and ODOT Director FFE Approval Request letter to ODOT Director (Per ODOT Document Guidelines for Sending Requests to ODOT Director and Assistant Directors) | A |  | I | [5 empty] | C
72 | ODOT Director Review and Approval of FFE | A | I | I | I |  |  |  |  | R
73 | Post Approved FFE on OPO Website Under the “Alternative Contracting” Section | A |  | I
74 | (Per ORS 279C.350 and ORS 183.484 Exemption Procedure; Appeal and ORS 183.484 Jurisdiction for Review of Orders Other Than Contested Cases) Start 60 Day Period for Jurisdiction - Public Review of the Exemption Order, Following the Date the Exemption Order was Served. Must be completed before RFP is Advertised. | A | I | I | I
75 | Per ORS 279A.161 (HB2375) Contract Administrator Role (OPO collects DOJ legal Sufficiency Review Communications for Contract Verification) | A | I | C
76 | Per ORS 279A.161 (HB2375) Contract Administrator Role (Region to Approve) | A | I | R
Project Pre Solicitation Notice Process
77 | OPO and Project Team to Coordinate on Project Pre Solicitation Notice Outreach | A |  | R
78 | Submit Project Pre Solicitation Notice Requirements for Advertisement to Industry Publications and post to OPO's website, as applicable | A |  | I
79 | Conduct outreach meeting(s), as applicable | A |  | R
Prequalification Waiver and Optional Proposal Security Waiver Process
80 | Develop Project Prequalification Waiver and Optional Proposal Security Waiver | A |  | I
81 | Submit Final Project Prequalification Waiver to Highway Division Administrator or Chief Engineer for Concurrence and ODOT Director's Approval | A |  | I | [5 empty] | C
82 | ODOT HWY Division Administrator or the Chief Engineer Review and Approval of Final Project Prequalification Waiver | A | [7 empty] | R
83 | Provide Final Proposal Security Waiver to ODOT Director for signature | A
84 | ODOT Director signature on Proposal Security Waiver | A | [7 empty] | R
85 | Provide Region Approved Project Prequalification Waiver and Optional Proposal Security Waiver | A | I | I
SOQ and RFP Technical Proposals Evaluation and Scoring Committee Process
86 | Select SOQ Evaluation Committee Scoring Members | A | C | R |  |  | C
87 | Finalize Internal SOQ Evaluation and Scoring Documents and Dates | A | C | R |  |  | C
88 | Select Technical Proposals, Technical Support Evaluators, and Evaluation Committee Scoring and Non-Scoring Members | A |  | R |  |  | I | [6 empty] | I
89 | Select ATC Evaluation Committee Members | I | C | A | [9 empty] | C
90 | Finalize Internal forms for Technical Proposal evaluation, ATC Evaluation, and Scoring Documents and Dates | A | C | I
Develop and Finalize RFQ Advertisement and SOQ Scoring Process
91 | RFQ Package Development With Project Specific Information | A | C | C
92 | Calculate and Finalize Stipend Amount | A |  | R
93 | Review RFQ Package | A | R | R
94 | Provide DOJ the RFQ Package for Review and Approval | A | I | I
95 | DOJ Review and Approval of RFQ Package | A |  |  | R
96 | Update and Finalize RFQ Package per DOJ Comments | A | I | C
97 | Provide RFQ Package to FHWA for Review | A | I | I
98 | FHWA Review and/or Concurrence of RFQ Package | A | [5 empty] | R
99 | Update per FHWA Comments and Revise RFQ Package as Needed | A | C | C
100 | DOJ review of updated RFQ Package (Repeat as needed until FHWA and DOJ approval) | A |  |  | R
101 | Provide copies of "final" RFQ Package to FHWA and DOJ | A |  |  | I |  |  | I
102 | Submit RFQ Ad (Business Tribune and DJC) | A | I | I
103 | Release (Advertise) Approved RFQ Package | A | I | I
104 | Pre-SOQ Meeting | A | I | R
105 | Develop RFQ Addendums & Letters of Clarification to Proposer Questions Chapter 6 of ODOT’s Construction Manual | A | I | R
106 | Review and Approve RFQ Addendums & Letters Clarification to Proposer Questions | A | I | C | R
107 | Post OPO and DOJ Approved RFQ Addendums & Letters Clarification to Proposer Questions | A | I | I
108 | SOQ Evaluation Committee Training | A | C | I |  |  | C
109 | SOQ Submittals Due | A | I | I
110 | Evaluate Responsiveness of SOQs Received | A |  | I
111 | Upload SOQs and Following Documents for Scoring Member Access | A |  | I
112 | RFQ Package, Addendums, Letters Clarifications, Responses to Proposer Questions, SOQ Scoring Worksheets, SOQ Evaluation Scoring Plan - Email Evaluators When Documents are Available with "Read Receipt" | A |  | I
113 | Evaluate & Score SOQs | A |  | R
114 | OPO Address Questions from SOQ Evaluators | A |  | I
115 | Submit SOQ Scoring Worksheets to OPO | A |  | R
116 | OPO Compile SOQ Scoring Worksheets for Consensus Meeting | A
117 | SOQ Consensus Meeting / Finalize SOQ Scores (Review Scoring) and Identify Shortlisted Contractors | A | I | R
118 | Prepare Summary of SOQ Consensus/Final Scoring for Procurement Official | A |  | I
119 | Scoring Official Concurrence with SOQ Consensus/Final Scoring | A |  | R
120 | Notify Proposers of Shortlist | A | I | I
121 | Shortlist Protest Period and Protest Resolution | A |  | C | R
Develop and Finalize RFP Advertisement, Proposals Scoring and Price Opening Process
122 | RFP Development With Project Specific Information | A | C | R
123 | Region and OECR Develop Workforce Protection Requirements for RFP documents, including Assigned DBE Contact Goals (one for Design and one for Construction) When Applicable Indian Preference in Employment Compliance Requirements and Preference Goal(s) | I |  | A |  |  | R
124 | Compile RFP Package (Including Sample Contract, as completed above) | A
125 | Review RFP Package | A | R | R
126 | Provide DOJ with RFP Package for Authorization for Release | A | I | I
127 | DOJ Authorization for Release Review | A |  |  | R
128 | Provide RFP Package to FHWA for Review | A | I | I
129 | Provide Pre-RFP Checklist items to FHWA for Preliminary Engineering Funds Obligation (ADS sends to OPO; OPO includes in RFP Package for FHWA) | R | A | R
130 | FHWA Concurrence Review of RFP Package | A | [5 empty] | R
131 | Review and Update per FHWA Comments on RFP Package | A | C | C
132 | DOJ review of updated RFP Package (Repeat as needed until FHWA and DOJ approval) | A |  |  | R
133 | Provide copies of "final" RFP Package to FHWA and DOJ | A |  |  | I |  |  | I
134 | DOJ Provides Authorization for Release of RFP | A | I | I | R
135 | Release (Advertise) RFP Package to Shortlisted Proposers | A | I | I
136 | Pre-Proposal Meeting | A | I | R
137 | Develop RFP Addendums & Letters of Clarification to Proposer Questions Chapter 6 of ODOT’s Construction Manual (Contract related addendums and questions go to ADS) | A | C | R |  |  | I |  |  |  |  | I
138 | Review RFP Addendums & Letters Clarification to Proposer Questions | A | I | I
139 | Provide RFP Addendums & Letters of Clarifications to DOJ Review and Approval | A | I | I
140 | DOJ Review and Approval of RFP Addendums & Letters of Clarifications | A |  |  | R
141 | Post OPO and DOJ Approved RFP Addendums & Letters Clarification to Proposer Questions | A | I | I
142 | Proposers Request ATC One-on-One Meetings (If applicable) | A | C | I | [8 empty] | R
143 | Schedule ATC One-on-One Meetings | A | C | I | [8 empty] | I | C
144 | Conduct Pre-ATC Evaluation Training | A | C | R | [9 empty] | C
145 | ATC Proposer One-on-One Meetings | A | C | R | [8 empty] | C | C
146 | Proposers Submit Pre-ATCs | A | I | I | [8 empty] | R | I
147 | Determine if Pre-ATC Meet ATC Qualifying Criteria | A | C | R | [9 empty] | I
148 | Notify Proposers if their Pre-ATCs Meet ATC Qualifying Criteria and Can Be Submitted as Formal ATCs | A | C | I
149 | Proposers Submit Formal ATCs | A | I | I | [8 empty] | R | I
150 | Review and Approve/Disapprove of Formal ATCs For Proposer Optional Inclusion in Proposals | A | C | R | [9 empty] | C
151 | Notify Proposers of Formal ATC Approval/Disapproval For Inclusion in Proposal | A | I | I | [9 empty] | I
152 | Technical Proposals Technical Support Evaluators and Evaluation Committee Training | A | C | C
153 | Technical and Price Proposals Due | A | I | I
154 | Public opening of Price Proposals | A | I | I
155 | Pass/Fail Responsiveness Check of Technical Proposals | A
156 | Upload Technical Proposals Submittals and Following Documents for Scoring Member Access | A |  | I
157 | Send RFP Package, Addendums, Letters Clarifications, Responses to Proposer Questions, Scoring Sheets, Evaluation Scoring Plan to Evaluators | A | C | I
158 | Evaluators to Evaluate and Score Technical Proposals | A |  | R
159 | Evaluators to Submit Technical Proposals Scoring Worksheets to OPO | A |  | R
160 | Compile Scoring Sheets for Consensus Meeting | A |  | I
161 | Technical Proposal Consensus Meeting / Finalize Technical Proposals Scores | A | I | R
162 | Evaluate Proposal Prices, Reasonableness Review | A | I | R
163 | Calculate Proposers' Combined Total Price Amount for Award, Per Formula Stated in RFP ITP | A
164 | Confirm Consensus Scoring via Email | A | I | R
165 | Audit and Confirm Price Proposal and Technical Proposal Scoring | A
166 | Announce Apparent Successful Proposer (Highest Combined Total Score) | A | I | I
Contract Award Phase
167 | Project Engineer's Estimate Reconciliation (Consultant) | I |  | A
168 | Conform Contract Documents With Changes by Addenda and Negotiations, Selected Proposer’s Proposals that Meet or Exceed Minimal RFP Contractual Requirements and DOJ Approved Changes (Concurrent with Tasks Prior to Agency Contract Signature Routings) | A | C | I
169 | Provide Final Conformed Contract Documents to DOJ for Review and Approval | A | I
170 | DOJ Review and Approval of Conformed Contract Documents | A |  |  | R
171 | Issue Notice of Intent to Award (NOIA) | A | I | I |  |  | I |  |  |  |  | I
172 | Finalization of Contract Documents with Best Value Proposer | A | C | R | C
173 | (OPTIONAL) If unable to reach mutually acceptable contract with Best Value Proposer Start Negotiations With 2nd Highest Best Value Proposer | A | C | R | C
174 | NOIA Protest Period and Protest Resolution | A | C | C | R
175 | Release Proposers' Best Value Consensus Scores and Technical Proposers | A
176 | Stipend Payment to Qualified Unsuccessful Proposers | A
177 | Contract Review and Sign-off by Design-Builder | A |  | I
178 | Provide Contract for DOJ Award Concurrence | A | I | I
179 | DOJ Contract Review and Award Concurrence | A |  |  | R
180 | Send Contract Award Concurrence to FHWA | A | [5 empty] | I
181 | OTC Award Approval, if applicable | C |  | A
182 | FHWA Award Concurrence Issued | A | I | I |  |  |  | R
183 | Agency Award Concurrence Issued | A |  | R
184 | Issue Award Recommendation Letter | A | I | I
185 | Issue Award Letter to Design-Builder | A | I | I
186 | Send Contract to Design-Builder for Signature | A | I | I
187 | Design-Builder review and signature for execution of Contract documents (15 Calendar Days) | A | [10 empty] | R
188 | Per ORS 279A.161 (HB2375), as Contract Administrator Role (Verify all collected DOJ advice and recommendations. Process and Submit Contract Verification Form) | A |  | R
189 | Document Verification (Contract, DBE From 2, Bonds and Insurance Certifications, etc..) | A |  | I
190 | Agency Contract Signature Routings | A |  | I
191 | Contract Execution (Milestone) | A | I | I | [8 empty] | I
192 | Issue Notice to Proceed (NTP) | A | I | I |  |  | I |  |  |  |  | I
193 | Award Contract and Send Executed Contract Documents to Contractor and CAU | A | I | I |  |  | I |  |  |  |  | C
(Optional Per Proposer Request) RFP Debriefing Meeting Process (After Completion of Notice of Intent to Award Protest Period)
194 | Upon Proposer Request for Optional RFQ/RFP Debriefing Meeting, Coordinate Requirements and Timeline with Proposer | A | [10 empty] | I
195 | Determine Who Needs to Participate in the RFQ/RFP Debriefing Meeting | A | C | C
196 | Schedule RFP Debriefing Meeting with Meeting Participants | A | I | I | [8 empty] | I
197 | Conduct RFP Debriefing Meeting | A | C | R | [8 empty] | R
(Optional) Alternative Project Delivery - ODOT Internal Procurement to Construction Hand-Off Meeting (Takes Place After Issuance of NTP)
198 | Coordinate Scheduling Optional Procurement to Construction Hand-Off Meeting | I | A | I |  |  | I |  |  |  |  | I
199 | Determine Who Needs to Participate in the Procurement to Construction Hand-Off Meeting | I | A | I |  |  | C |  |  |  |  | C
200 | Conduct Procurement to Construction Hand-Off Meeting | I | A | I |  |  | C |  |  |  |  | C
(Optional) Post-Procurement Lessons Learned Meeting (Takes Place After Optional Contractor Debrief. If Debrief is Not Held, Takes Place After Issuance of NTP)
201 | Coordinate Need for Conducting Post-Procurement Lessons Learned Meeting | R | A | C
202 | Determine Who From ODOT Needs to Participate (Region and ADS) | R | A | C
203 | Schedule Post-Procurement Lessons Learned Meeting | A | I | I
204 | Conduct Post-Procurement Lessons Learned Meeting | A | C | C
Design and Construction Management Phase
205 | Design Development Meeting (Prior to the Commencement of Design) |  |  | A |  |  | C |  |  |  |  | C
206 | Design Mobilization Meeting (See project contract for specifics) |  |  | A
207 | Over-the Shoulder Reviews (As Necessary to Ensure Continued and Uniform Consistency in the Quality and Effective Incorporation of Design Revisions into Design Documents) |  |  | A | [9 empty] | C
208 | Definitive Design Review (Plans and Specifications) - Review and Comment (each Design Unit) |  |  | A | [9 empty] | C
209 | Design Exceptions, Design Deviations, and Operations Approvals (as applicable) - Review and Commenting (each Design Unit) |  |  | R | [8 empty] | R | A
210 | Design Exceptions, Design Deviations, and Operations Approvals (as applicable) - Approval (each Design Unit) |  |  | R |  |  |  | R | [5 empty] | A
211 | Interchange Requests, if applicable (See ODOT Interchange Engineer requires FHWA approval) |  |  | R |  |  |  | A | [5 empty] | R
212 | Design Non-Conformance Report (NCR) and NCI Resolution (Definitive Design) |  |  | A |  |  |  | I | [5 empty] | C
213 | Definitive Design Review (Plans and Specifications) - Acceptance (each Design Unit) |  |  | A | [9 empty] | C
214 | Interim Design Review (Plans and Specifications) - Review and Comment, if applicable (each Design Unit) See project specific contract if this is optional or required. |  |  | A | [9 empty] | C
215 | Design Non-Conformance Report (NCR) and NCI Resolution (Interim Design) |  |  | A |  |  |  | I | [5 empty] | C
216 | Interim Design Review (Plans and Specifications) - Acceptance (each Design Unit). See project specific contract if this is optional or required. |  |  | A | [9 empty] | C
217 | Readiness-for-Construction Design Review (Plans and Specifications) - Review and Comment (each Design Unit) |  |  | A |  |  | I |  |  |  |  | I |  | C
218 | Design Non-Conformance Report (NCR) and NCI Resolution |  |  | A |  |  |  | I | [5 empty] | C
219 | Readiness-for-Construction Design Review (Plans and Specifications) - Acceptance (each Design Unit) |  |  | A |  |  | I |  |  |  |  | I |  | C
220 | Working Plans or Working Drawings or 3D Construction Model Design Review and Commenting |  |  | A | [9 empty] | C
221 | Contract - Construction Administration and Oversight |  |  | A |  |  | R |  |  |  |  | R
Post-Construction Reports Preparation Process (Issuance of Second Notification)
222 | Track Second Notification (2nd Note) Issuance |  |  | A | [9 empty] | I
223 | As-Constructed Plans Review and Commenting and Acceptance |  |  | A | [9 empty] | C
224 | Schedule FFE Post-Construction Reporting Requirements Discussion Meeting with Region to Take Place No Earlier Than 45 Calendar Days After 2nd Note |  |  | R | [7 empty] | A
225 | Meet with Region to Discuss Required Project Information for Inclusion in PM Narrative for Upcoming FFE Post-Construction Reports |  |  | R | [7 empty] | A
Post-Construction Evaluation Reports Process (Issuance of Third Notification)
226 | Track When ODOT Issues Third Notice and Final Payment |  |  | A | [7 empty] | R |  | I
227 | Provide Region FFE Post-Construction Evaluation Report Base Documents |  | I | R | [7 empty] | A
FFE Post-Construction Evaluation Report Process (Completed and Posted No Later Than 30 Calendar Days After Third Notification)
228 | Develop FFE Post-Construction Evaluation Report |  |  | R | [7 empty] | A
229 | Region Provide CAU with Project EA |  |  | A | [7 empty] | R
230 | Obtain Proper Authorization for DOJ Legal Assistance For Legal Sufficiency Review | [10 empty] | A
231 | DOJ Legal Sufficiency Review |  |  |  | R | [6 empty] | A
232 | Review of FFE Post-Construction Evaluation Report |  |  | R | [7 empty] | A
233 | Revise FFE Post-Construction Evaluation Report With CAU Approved Changes |  |  | R | [7 empty] | A
234 | Provide DOJ with FFE Post-Construction Evaluation Report for Review |  |  | I | [7 empty] | A
235 | DOJ Review of FFE Post-Construction Evaluation Report |  |  |  | R | [6 empty] | A
236 | Revise and Finalize FFE Post-Construction Evaluation Report With CAU Approved DOJ Changes |  |  | R | [7 empty] | A
237 | Develop and Email Advanced Notification Email for the FFE Post-Construction Evaluation Report to ODOT Director (Per ODOT Document Guidelines for Sending Requests to ODOT Director and Assistant Directors) | [10 empty] | A
238 | Submit Final FFE Post-Construction Evaluation Report and supporting documentation to ODOT Director as information only (Per ODOT Document Guidelines for Sending Requests to ODOT Director and Assistant Directors) |  |  | I | [5 empty] | C |  | A
239 | Provide OPO Copy of Final FFE Post-Construction Evaluation Report for Posting on OPO Website | R | I | [8 empty] | A
240 | Post Final FFE Post-Construction Evaluation Report on OPO Website Under the “Alternative Contracting” Section For Public Inspection | A | I | I | [7 empty] | I
Post-Construction Lessons Learned Meeting Process (Held After Any Litigation or Claims are Completed)
241 | Meet with Project Team to discuss contract, process or any other lessons learned during the administration of the project. |  | A | R |  |  | C |  |  |  |  | C