SP00299  (Special Provisions for the 2024 Book) 	(Bidding on or after: 12-01-23

Last updated: 05-19-23

This Section requires SP00294 when

contaminated soil or groundwater

will be encountered)

# SECTION 00299 - DECOMMISSION UNDERGROUND INJECTION CONTROL SYSTEMS

(Follow all instructions and make all edits with “Track Changes” turned on. This Section is not published in the Oregon Standard. If there are no instructions [orange text] above a subsection, paragraph, sentence, or bullet, then include it in the project, unless the item(s) that are included in the subsection, paragraph, sentence, or bullet are not required on the Project and then they should be deleted. In general do not re-number or re-letter subsections when item(s) are deleted. Delete all orange text before preparing the final document. All other modifications to this Section will require ODOT Technical Resource and State Specifications Engineer approval.)

Section 00299, which is not a Standard Specification, is included in this Project by Special Provision.

## Description

00299.00  Scope - In addition to the requirements of Section 00290, decommission underground injection control (UIC) systems according to the following Specifications.

Decommission the UIC systems indicated in Table 00299-1 below:

(Fill in the table with the required location, depth, width, description, and former use information.)

Table 00299-1

| Location/Station | Depth (feet) | Width (feet) | Description | Former Use |
| --- | --- | --- | --- | --- |

00299.03  Submittals - Provide the Engineer with the following information and documents for contaminated soil generated on this project, within 48 hours of completing or receiving them:

DEQ notifications, correspondence, permits and reports.

Reuse, recycling, and disposal receipts or other related documentation for the UIC systems.

Sample data and analytical results.

## Labor

00299.30  Personnel Qualifications - Provide contractors and workers meeting the following requirements:

An Oregon Registered Geologist (RG) or Professional Engineer (PE) who has experience decommissioning UIC systems and handling contaminated media.

(Use this bullet when the UIC system contains contamination that is known or likely to exceed DEQ cleanup standards (for example: automotive UIC systems).)

Workers  meeting the HAZWOPER training requirements of 00294.30.

## Construction

00299.40  Underground Injection Control System Decommissioning - Decommission UIC systems according to OAR 340-044-0040 and the following:

Sample UIC contents and bottom materials and characterize for disposal and DEQ UIC closure requirements, based on past use, according to 00290.20(c).

At least 30 Days before decommissioning, complete, sign and submit to DEQ and the Engineer, DEQ's UIC Registration Pre-Closure Notification Form, along with the UIC content analytical results and, if required by DEQ, a pre-closure plan stamped by a PE or RG.

Pay all UIC decommissioning fees to DEQ.

Obtain written approval from DEQ and proceed with decommissioning the UIC within the time frame specified in DEQ's approval.

(Use the following bullet when the UIC system is removed.)

Remove the UIC by excavation and backfill according to 00330.42.

Use the following two bullets when the UIC system is left in place.)

Obtain approval from DEQ and fill the UIC in place, using DEQ approved fill materials.

Backfill the excavation according to 00330.42.

Complete a closure report, signed and stamped by a PE or RG, and submit it to DEQ and the Engineer within 30 Days of finishing decommissioning work or before Second Notification whichever occurs first.

Information for decommissioning underground injection control systems is available on DEQ's Fact Sheet titled Closure of an Injection System.

(Use the following subsection .43 when contaminated soil or groundwater will be encountered.)

00299.43  Contaminated Media - Excavate, transport, and dispose of contaminated media according to Section 00294.

## Measurement

00299.80  Measurement - The quantities of decommissioned UIC systems will be measured on the unit basis.

(Use the following paragraph when contaminated soil or groundwater will be encountered.)

Excavating, transporting, and disposing of contaminated media will be measured according to 00294.80.

## Payment

00299.90  Payment - The accepted quantities of decommissioned UIC systems will be paid for at the Contract unit price, per each, for the item "Decommission Underground Injection Control Systems".

Payment will be payment in full for furnishing and placing all Materials, and for furnishing all Equipment, labor, and Incidentals necessary to complete the Work as specified.

(Use the following paragraph when contaminated soil or groundwater will be encountered.)

Excavating, transporting, and disposing of contaminated media will be paid for according to 00294.90.