## instructions
This workbook is to be used in developing a workplan for recommendations associated with the payment schedule and lack of prompt pay barrier identified by the DBE Committee. The Committee developed six recommendations related to this barrier:
1. Implement both short term and long-term project systems that track and report project payments made by ODOT and its prime firms to (sub)contractors and assess penalties for late payments. Reinforce use of systems that allow DBE firms to monitor payments.
2. ODOT commits to checking with DBE firms about how the system is working for them within three months after AASHTOWare implementation.
3. Make invoices subcontractors submit to primes visible to ODOT.
4. Add ODOT point-of-contact for DBEs to every contract and shift the follow-up with the prime from the DBE to the ODOT point-of-contact.
5. Provide a payment option other than pay-when-paid.
6. Include the topic of payments in pre-construction meeting and status check meetings that include the prime, sub(s), and construction inspector.
STEPS to complete workplan
1. Review recommendations and barrier sheet.
2. Review information on recommendation 1 tab, row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
3. Review information on recommendation 2 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
4. Review information on recommendation 3 tab, row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
5. Review information on recommendation 4 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
6. Review information on recommendation 5 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
7. Review information on recommendation 6 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
8. In step 1, include names, contact information, and roles for ODOT team members who are key to advancing each recommendation.
9. In step 2, provide clear descriptions of each milestone, including what decision will be made at each milestone, who will make that decision, and the outcome of that decision. Add activities necessary to complete each action to complete the recommendation.
10. In step 3, include any collaborators in the partners column.
11. In step 4, provide realistic timelines for completion of each activity and action.
12. In column 1, add actions that will be necessary to complete the recommendations, including activities for each.
13. As you add actions, include those in your barriers and recommendations change log.
14. Repeat steps 8 through 13 for recommendations 2 through 5.
15. Fill out additional information as your clarify you process.

## recommendation 1
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 1 Implement both short term and long-term project systems that track and report project payments made by ODOT and its prime firms to (sub)contractors and assess penalties for late payments. Reinforce use of systems that allow DBE firms to monitor payments.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: According to feedback from DBEs at 5/19/23 meeting, publicize to both prime and subcontractors about the existing prompt payment specifications requiring subs to be paid within 10 days from the date a prime receives payment from ODOT. | Diponker Mukherjee - SME - DBE/OECR Adriane McKinney - SME - ODOT Web Team Kevin Cassidy - SME - OPO Summer Guthrie - SME - CAU | * Work with ODOT web team to develop an additional OECR "Resources" website (link to it from OECR and CAU webpages, others?) *Plan for publicizing the website once created. | ODOT Contract Administration Unit (CAU) ODOT Office of Equity and Civil Rights (OECR) | 6 months
| Action 2: According to 5/19/23 DBE suggestion, provide education and resources for primes and subs on a variety of issues related to payment and subcontracting. | Diponker Mukherjee - SME - DBE/OECR Adriane McKinney - SME - ODOT Web Team Kevin Cassidy - SME - OPO Summer Guthrie - SME - CAU | Suggestions for including on the proposed OECR "Resources" website: *Best practices for successful subcontracting (keeping in mind the subcontract relationship is between prime and subs). *Develop and provide a list of commonly required forms and documents subs must submit to qualify for payment. *Where subs can find information pertinent to payment in ODOT's Electronic Document Management System (EDMS; and possibly other places, for example, the Construction Contracts Status Report). *How subs can find out about the Pre-Construction meetings for contracts. *How subs can get access to ODOT's EDMS and where to access the Contract Documents in ODOT's EDMS (dependent on Recommendation 5, Action 5). *How subs can access or request the prime's contract with OPO. *Who subs can reach out to for help related to prompt payments on their subcontracts. * 12 month schedule of upcoming projects. | OECR Small Business Navigators OECR Field Coordinators Department of Justice (DOJ) ODOT Contract Administration ODOT Procurement Office (OPO) ODOT eConstruction & AASHTOWare (AWP) System Administration Team OECR Web Page Owners | 6 months
| Action 3: Investigate this recommendation's suggestion of the possibility of ODOT assessment of penalties to the primes for late payments to subs. | Summer Guthrie will consult with the Contract Administration Engineer and State Construction Materials Engineer. |  | Industry ODOT Management Federal Highway Administration (FHWA) DOJ | After consultation within Contract Administration, it appears this suggestion is essentially recommending liquidated damages. Assessment of liquidated damages must be supported by monetary damage (cost) to the Agency or the traveling public. This scenario does not meet those criteria. 00170.10 addresses Required Payments by Contractors and, under subsection (d), includes the following language and remedy “The Agency has no obligation to pay these Entities, and ODOT will not normally do so, but will refer them to the Contractor and the Contractor's Surety.” Any changes to the part 00100’s of the specifications require DOJ approval. Additional discussion of this item should involve DOJ and ODOT management. The Subcontract is where the enforceable terms exist to protect the subcontractor’s interests.
| Action 4: Investigate 5/19/23 DBE suggestion that ODOT consult with WSDOT regarding programs and tools they have implemented to improve prompt payment. | Diponker Mukherjee - SME - OECR | TBD | Other state agencies | TBD
| Action 5: According to this recommendation's suggestion, implement systems to be able to track and report contract payments. | Diponker Mukherjee - SME - DBE/OECR James Myers - SME - OECR Reporting Summer Guthrie - SME - CAU | * Work with AWP Team to ensure adequate and accessible prompt payment reporting and analysis is available from ODOT's data systems, including AWP. |  | Data should be available to report out of AASHTOWare by January 2024. This data will be limited to the few contracts let toward the end of 2023 which will have the AWP specifications included, and there will only be potentially one or two payment cycles worth of information in AWP by January of 2024, assuming implementation of AWP continues on schedule. Reports for the initial implementation of AWP are close to being finalized. Any additional reporting desired would need to go through the process for request, approval, and then development - at this time unable to speak to the possible timeline on this item. However, reporting using data from AWP will be possible using ODOT's other data querying systems, such as PowerBI.
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 2
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 2 ODOT commits to checking with DBE firms about how the system is working for them within three months after AASHTOWare implementation.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Implement long term AASHTOWare (AWP) use. | ODOT eConstruction & AWP Team | Program launch for Construction and Materials modules currently scheduled for October 2023 | ODOT Office of Equity and Civil Rights (OECR; has been using AWP already) | AWP implementation date will be confirmed or delayed by end of June 2023 based on the results of recent system testing which are currently being analyzed by ODOT.
| Action 2: According to this recommendation's suggestion, ODOT will check with DBE subcontractors to see how the AWP system is working for them, specifically in regard to prompt payment. | OECR Small Business Navigators OECR Field Coordinators | *Primes and Subs will begin entering data in AWP upon implementation for projects let with the AWP specifications in the Contract (currently predicted to be contracts bid sometime in or after September 2023) *What is currently intended to be monthly prompt payment reporting will only be able to be generated from the system after at least one payment cycle is complete in AWP (dependent on Recommendation 1, Action 5). *Subcontractors will be able to "ratify" contract payments within AWP. | ODOT Resident Engineers, RE-CPs, and Consultant Project Managers ODOT OECR Representatives ODOT Contract Administration (CAU) Industry (Primes and Subcontractors) | First Quarter of 2024 would be a reasonable time frame to check in with DBE subs. WIth the exception of current OECR data in AWP, construction data in AWP will be limited to the few contracts let toward the end of 2023 which will have the AWP specifications included. OECR provided clarification that the previous reference to subcontractors' "ratification" of payments in AWP correlates with this recent statement from the AWP newsletter: "Payments – Prompt Payments allows for all subcontractors to verify when they were paid ensuring compliance with the allotted days and, if passed, will be in Prompt Payment Discrepancy report."
[Action 3]
[Action 4]
[Action 5]
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 3
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 3 Make invoices subcontractors submit to primes visible to ODOT.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Include subcontractors, as appropriate under regulatory requirements and the contract, in the payment estimate process according to the abilities of the subcontractor role in AASHTOWare (AWP). | TBD | Note: Until AWP configuration is finalized, it is important to keep in mind that changes to the system may still occur. About AWP: *Implementation of AWP will allow users (including subs) to input data and submit documents tailored to the "role" of the user (for example, "subcontractor" is a role). *Visibility of entered or submitted information and documents in AWP will also be dependent on the "role" of the user. * The Subcontractor "role" will be able to see some progress payment data. *Subcontractors will be able to "ratify" contract payments within AWP. (See Recommendation 2, Action 2) | ODOT Procurement ODOT Contract Administration (CAU) ODOT eConstruction & AWP Team Federal Highway Administration (FHWA) Department of Justice (DOJ) | AWP implementation date will be confirmed or delayed by end of June 2023 based on the results of recent system testing which are currently being analyzed by ODOT to address the recommendation
| Action 2: Investigate this recommendation's suggestion to make invoices subcontractors submit to primes visible to ODOT. | TBD | Pending resolution of Recommendation 5, Action 1 |  | Note: The current potential solution to the issue of prompt payment is found in Recommendation 5, Action 1. It may not be necessary to explore this suggestion if the draft concept specification 'Advance Allowance for Subcontracted Work' is implemented because that draft specification currently contains language that would require receipt by the Engineer of a "written request for advance allowance," which would likely be or include an invoice from the subcontractor.
[Action 3]
[Action 4]
[Action 5]
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 4
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 4 Add ODOT point-of-contact for DBEs to every contract and shift the follow-up with the prime from the DBE to the ODOT point-of-contact.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: OECR has hired Small Business Navigators to assist subcontractors as a point-of-contact on prompt pay matters. | Small Business Navigators - SME - OECR | Onboarding Small Business Navigators | ODOT Contract Administration ODOT Financial Services | OECR Small Business Navigators were hired May 2023, and will begin to provide active support available on or around August 2023.
[Action 2]
[Action 3]
[Action 4]
[Action 5]
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 5
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 5 Provide a payment option other than pay-when-paid.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: According to 5/19/23 discussion and positive feedback, DBE subs present would like ODOT to pursue implementation of draft concept specification 'Advance Allowance for Subcontracted Work,' the current effort ODOT has been working on which would provide a payment option other than pay-when-paid. | Summer Guthrie - SME - CAU | *Discuss status with State Construction Materials Engineer and Contract Administration representatives. | ODOT Contract Administration (CAU) ODOT Procurement Office (OPO) ODOT Financial Services Associated General Contractors ODOT Industry Leadership Team Department of Justice (DOJ) | Complete investigation into status within 3 months.
| Action 2: According to 5/19/23 presentation by OECR, DBE subs present would like ODOT to investigate % advance payment specification implemented by Illinois DOT as a possibility for ODOT to consider. | Diponker Mukherjee - OECR DBE Program Manager | TBD | ODOT Office of Equity and Civil Rights (OECR) | TBD Note: ODOT currently does not make partial payments for unit priced Pay Item Work, only for Lump Sum Pay Items.
| Action 3: Investigate 5/19/23 DBE suggestion that subs should be able to get paid when their work is complete and accepted even if the payment to the prime is held up due to something that is the responsibility of the prime. | Summer Guthrie - SME - CAU | *Consult with others in Construction and Contract Administration who have previously worked on prompt payment to determine if this suggestion has already been discussed and is not a viable option. | Industry ODOT Management FHWA DOJ | Complete investigation into status within 3 months. Note: The current potential solution to the issue of prompt payment is found in Action 1 of this recommendation. It may not be necessary to explore this suggestion if the draft concept specification 'Advance Allowance for Subcontracted Work' is implemented.
| Action 4: Investigate 5/19/23 DBE suggestion about the possibility of ODOT implementation of an incentive/disincentive (I/D) for prime in regard to prompt payment to subs. | Jaime Viramontes - SME - PCO Kevin Cassidy- SME - OPO Summer Guthrie - SME- CAU | *CAU will consult with others in Construction and Contract Administration who have previously worked on prompt payment to determine if this suggestion has already been discussed and is not a viable option. *Clarify with workgroup if this action item would more accurately be stated that it is desired there be some form of penalty when primes don't meet the current prompt pay requirements. | ODOT Contract Administration (CAU) ODOT Procurement Office (OPO) ODOT Project Controls Office (PCO) Industry ODOT Management FHWA DOJ | Consultation within Contract Administration found the following: The FHWA Core Curriculum gives specific criteria for the use of I/D provisions and (p. 110) states "The use of I/D provisions should be restricted to critical projects where it is essential to minimize traffic delays." I/D provisions relate to time. Contract Administration is unsure I/D can apply to something like the prompt payment requirement. To Contract Administration’s knowledge incentives/disincentives are based on road user costs. Any changes to the part 00100’s of the specifications require DOJ approval. Additional discussion of this item should involve FHWA and DOJ. The OPO and PCO representatives listed under Roles on this item have not yet had a chance to review and comment on it. The information gathered by CAU will be shared with OPO and PCO. Note: The current potential solution to the issue of prompt payment is found in Action 1 of this recommendation. It may not be necessary to explore this suggestion if the draft concept specification 'Advance Allowance for Subcontracted Work' is implemented.
| Action 5: Investigate the 5/19/23 DBE suggestion that ODOT should add requirements to contracts with primes to require certain things of primes' subcontracts with subs (specific suggestions made in the meeting were: primes not withholding retainage from subs if ODOT not withholding retainage from primes, including the subs bid sheet terms in the subcontract, releasing retainage to each sub when the sub's work is complete and accepted by ODOT). | Summer Guthrie - SME - CAU | *Consult with others in Construction and Contract Administration who have previously worked on prompt payment to determine if any of these suggestions have already been discussed and are not viable options. | Industry ODOT Management FHWA DOJ | Complete investigation into status within 6 months. Under Terms of Subcontracts (00180.21(d)) ODOT currently doesn’t require anything beyond what is legally required. Note: Withholding of retainage must comply with escrow laws. Is the question about retainage better asked "Are primes complying with escrow laws? And, if not, what are ODOT's options for recourse, if any?"
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 6
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 4: Prompt Pay, Recommendation 6 Include the topic of payments in pre-construction meeting and status check meetings that include the prime, sub(s), and construction inspector.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Investigate this recommendation's suggestion that ODOT Include the topic of payments at Pre-Construction meetings. | Summer Guthrie - CAU | *Discuss with ODOT Resident Engineers and OECR Field Coordinators, others at ODOT. | ODOT Resident Engineers, RE-CPs, and Consultant Project Managers ODOT Contract Administration (CAU) | The Construction Manual Chapter 11, Section 11-2 addresses the requirements of the Pre-Construction Conference, specifically discussing progress payments is already the expectation with the language “Objectives to be accomplished during the Pre-Con include: … Informing the Contractor of procedures for consent to subcontracts, progress payments and timing.” Complete investigation within 3 months.
| Action 2: Investigate 5/19/23 DBE suggestion that ODOT make it a requirement to Invite DBEs and Subcontractors to Pre-Construction meetings. | Summer Guthrie - CAU | *Discuss with ODOT Resident Engineers and OECR Field Coordinators, others at ODOT. | ODOT Resident Engineers, RE-CPs, and Consultant Project Managers ODOT Contract Administration OECR Small Business Navigators and Field Coordinators | Although not a requirement, the Construction Manual Chapter 11, Section 11-2 addresses invitation of subcontractors to the Pre-Construction Meeting with the language “Persons who should attend a Pre-Con include: … Key personnel from the Contractor and its Subcontractors.” This would likely only reach the disclosed first-tier subcontractors as this meeting typically happens within 30 days of Notice-to-Proceed. Complete investigation within 6 months.
| Action 3: Investigate this recommendation's suggestion about possibility of ODOT implementing status check meetings regarding prompt payment. | Small Business Navigators, OECR - SME | Onboarding Small Business Navigators | ODOT Contract Administration ODOT Financial Services | TBD
| Action 4: According to 5/19/23 DBE suggestion, ODOT investigate creating a process for subs to request prime's contract from OPO so subs can see what is required of the prime regarding payment obligations. | Marie Wright/ Kevin Cassidy - SME - OPO | Determine what is already available and what steps would be needed to implement something new. Add info to new OECR resource page. | OECR Web Page Owners ODOT Procurement Office (OPO) - Carolee Will | Complete within 3 months.
| Action 5: According to 5/19/23 DBE feedback, ODOT will investigate the Special Provisions and Contract Plans being put in a Doc Express drawer the subs have access to. | Summer Guthrie - SME - CAU | *Discuss with Contract Administration and ODOT eConstruction. |  | Complete investigation within 3 months. According to 6/6/23 discussion between CAU and ODOT's eConstruction and AASHTOWare (AWP) Team Lead, there will be a separate drawer structure in Doc Express for AWP projects. The team is currently working on that reconfiguration. This suggestion was well received and will be considered. Would subcontractors requiring a copy of the final contract documents for a project prior to signing a subcontract be a viable remedy in addition to this action item?
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan