## instructions
This workbook is to be used in developing a workplan for recommendations associated with the low-bid contracting barrier identified by the DBE Committee. The Committee developed two recommendations related to this barrier:
1. Create more contracting processes that waive the lowest bid requirements, maybe other criteria, including best value or “lowest and best” to provide for contracting flexibility needed to allow DBE firms to compete.
2. Modify the mentor-protégé program for the partnership to center on small firms winning more work after competing.
STEPS to complete workplan
1. Review recommendations and barrier paper.
2. Review information on recommendation 1 tab, row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
3. Review information on recommendation 2 tab row 5, partners in column E, and actions in column B to confirm they match. Make any edits to correct errors.
4. In step 1, include names, contact information, and roles for ODOT team members who are key to advancing each recommendation.
5. In step 2, provide clear descriptions of each milestone, including what decision will be made at each milestone, who will make that decision, and the outcome of that decision. Add activities necessary to complete each action to complete the recommendation.
6. In step 3, include any collaborators in the partners column.
7. In step 4, provide realistic timelines for completion of each activity and action.
8. In column 1, add actions that will be necessary to complete the recommendations, including activities for each.
9. As you add actions, include those in your barriers and recommendations change log.
10. Repeat steps 4 through 9 for recommendation 2.
11. Fill out additional information as your clarify you process.

## recommendation 1
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 6: Bundled A&E and Construction Contracts, Recommendation 1 Explore ways for ODOT Project Delivery and/or other relevant departments to unbundle more projects
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Contact other State Departments of Transportation to understand how they address the barrier created by bundling. | Statewide Project Delivery Branch or region - make contact with DOTs and identify barrier actions | 1. Select DOTs to contact - WSDOT, at at least two others. 2. Summarize and evaluate results 3. Identify potential solutions related to bundling and add to list of action | DOTs - willing to respond to questions about bundling FHWA - DBE contact for ideas - Chris Woods | Summer 2023
| Action 2: Explore establishing a target percentage of STIP projects that are exclusively in the Tier A Full Service Price Agreement for Architectural and Design Services. | Statewide Project Delivery Branch - evaluate data, define and set target Statewide Project Delivery Branch - plan, implement and monitor | 1. Define the calculation of the target percentage and how it will be applied. 2 Assess the capacity of the workforce 3. Evaluate data on sizes of design projects likely to be delivered using the FSPA. 4. Set target percentage 5. Prepare the implementation/ communications plan for action (including DBE partners) 6. Implement and monitor for compliance and impact. | ODOT Procurement Office - American Council of Engineering Companies - assist with communication to consultants FHWA | End of 2023
| Action 3: Explore establishing a target percentage of STIP projects that will be bid with a construction value of less than $1M. | DBE firms or other DBE organizations - to validate the threshold for max construction value Statewide Project Delivery Branch and regions - evaluate data, define and set target Statewide Project Delivery Branch - plan, implement and monitor | 1. Establish the max size of projects - likely $1M max 2. Define the calculation of the target percentage and how it will be applied. 3. Evaluate data on sizes of construction projects in the current STIP. 4. Set target percentage 5. Prepare the implementation/ communications plan for action (including DBE partners) 6. Implement and monitor for compliance and impact. | ODOT Procurement Office - American Council of Engineering Companies - assist with communication to consultants FHWA | End of 2023
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 2
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 6: Bundled A&E and Construction Contracts, Recommendation 2 Explore opportunities for Agency use of other (alternative) contracting methods that may offer DBE certified firms access to smaller work packages.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Explore Construction Manager/General Contractor (CM/GC) contracting. | Alternative Delivery Services (ADS) ODOT Procurement Office Office of Equity and Civil Rights | The CM/GC method allows for smaller early work amendments and flexibilities in work packages. This contracting method (on ODOT contracts) also requires an approved diversity and subcontracting plan. Work has already begun by ADS on this action. | Federal Highway Administration | Summer 2024
| Action 2: Explore single function Indefinate Delivery/Indefinate Quantity (ID/IQ) contracting. | Alternative Delivery Services (ADS) ODOT Procurement Office Office of Equity and Civil Rights | The ID/IQ method creates opportunities for smaller single function work to be contracted in a specific geographical location. Project sizes are smaller, routine, specialized, simple work. Work has already begun by ADS on this action. | Federal Highway Administration | Summmer 2024
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan

## recommendation 3
This worksheet is designed to be used digitally and will grow with your entries.
Barrier 6: Bundled A&E and Construction Contracts, Recommendation 3 Explore ways for ODOT to incentivize and/or penalize prime firms for how they unbundle or bundle contracts.
| Plan Components | Step 1 Roles and Responsibilities List team members, their roles, and responsibilities | Step 2 Activities and Milestones List activities & outputs/milestones | Step 3 Other Potential Partners List other agencies or individuals that may be involved | Step 4 Timelines and Duration Identify timelines for each action and activity
| Action 1: Explore incentives for prime consultants to not eliminate or reduce DBE services on A&E projects during solicitation. | This action was determined to be similar/same as an action identified by the low-bid contracting work group . The low-bid work group agreed to take the lead on the exploration of this action. | See activities and milestones of low-bid contracting work group |  | See timelines and durations of low-bid contracting work group
| Action 2: Explore incentives for prime contractors to not eliminate or reduce DBE services on construction projects when bidding. For example - implement incentives for prime contractors to allow DBE firms to exercise direct control and authority over the work of their own employees and equipment consistent with the FHWA requirement of Commercially Useful Function (CUF)). | This action was determined to be similar/same as an action identified by the low-bid contracting work group . The low-bid work group agreed to take the lead on the exploration of this action. | See activities and milestones of low-bid contracting work group |  | See timelines and durations of low-bid contracting work group
[Insert new rows above as needed]
Step 1
Step 2
Step 3
Step 4
Plan