## Sheet1
PE-CE OUTSOURCED REPORT
AS OF: December 23 2025
FOR REGION(S): Region 1
FOR ADMIN ID(S): ODOT, ODOT/LOCAL
Report Contact:PMO
FOR COUNTY(S): ALL
FOR KEY NUMBER(S): ALL
FOR DBE GOAL: All
STIP-FP Data |  | MSP Data | [8 empty] | Programmed STIP-FP Data | [5 empty] | Calculation | MSP Data |  | CRCT
Key # |  | Project Name |  |  | PCS Region | ODOT Lead | Outsourced PE | PE Outsourced Discipline | Outsourced CE | CE Outsourced Discipline | Project Description | Admin By | County | Work Type | PE/PL Programmed Budget | Total Programmed Project Budget | Anticipated RFP Release Time | Kick-off Meeting Date | Bid Let Date | Anticipated DBE Goal
23636 |  | US30B: (N Lombard St) N Delaware Ave - N Denver Ave |  |  | Region 1 | BACHMAN JENNIFER | 60% | PI Support, Geo Design, Noise, Traffic Signal/Illumination, Geo Exploration, Roadway, Access Management, Environmental, Traffic ITS, Right of Way, Traffic Control - Analysis &amp; Design, Utilities, Pavements, Specifications, Permits, Bridge, Graphics, 3D Visualization/Animation, Traffic Other, Hydro Design | No |  | Upgrade curb ramps and add and redesign bike lanes for the safety of all roadway users along Lombard St between Delaware and Denver. From Boston to Lancaster the project will reconfigure the roadway to three lanes, adding bike lanes. At Denver, the project will implement a variety of safety improvements and upgrade the traffic signal. | ODOT | MULTNOMAH | BIKPED | 2821715.36 | 3724663.36 |  | 2026-01-07 17:00 | 2028-09-07 17:00 | 0.00%
23771 |  | OR224 & OR213 curb ramps (Happy Valley & Mulino) |  |  | Region 1 | LAM Canh | F/S |  | CA/CEI |  | Construct curb ramps to meet compliance with the Americans with Disabilities Act (ADA) standards. | ODOT | CLACKAMAS | ADAP | 900000 | 2090000 |  | 2025-10-13 17:00 | 2026-09-22 17:00 | TBD: 0 – 22%
Report Total: 2

## Sheet2
About this report Report name: PE-CE Outsourced Report Purpose: To provide forecasted outsourced work to industry partners. This report is posted to the external ODOT Procurement website weekly. Definitions and filters: Anticipated DBE goal shows the range of possible DBE goal percentages if the goal has not yet been entered in the source system. Filter(s): Projects show on this report according to the following: PE & CE or just PE outsourced: Project will be on the report for 12 months before the PDT kick off date until 3 months after the PDT kick off date. Or until the project has gone to bid through OregonBuys. Just CE outsourced: Project will be on the report for 9 months before the bid let date until 1 month after the bid let date. Or until the project has gone to bid through OregonBuys. Anticipated RFP Release Time calculation: PE & CE or just PE Outsourced: PDT Kick off - 140 days Just CE outsourced: PS&E Submittal date - 180 days Data sources: RMS, STIP, CivilRights