## qryMonthlyConstructionContracts
ACTIVE CONSTRUCTION PROJECTS
(Projects fall off this report 3 months after Final Payment)
strContractNo | Key_PCS | strFederalAid | Project | County | Region | FirstNameLast | strContractorName | dtmAdvertised | Let Date | dtmAward | Contractor'sBid | ContractorPaidtoDate | EstCompletionDate | dtmFNote | dtmSNote | dtmTNote | dtmFinalEst
C15134 | 18873 | S001(475) | I-5: California State Line - Ashland Paving | Jackson | 3 | Shon Heern | Carter & Company, Inc. | 2019-02-21 | 2019-04-18 | 2019-05-01 | 23435983.65 | 28973807.77 |  | 2019-06-20 | 2023-10-30 | 2025-10-31
C15168 | 20109 | S009(494) | US101: Yaquina Bay Bridge | Lincoln | 2 | Steve Schultz | Wildish Standard Paving Co. | 2019-09-26 | 2019-11-14 | 2019-12-09 | 26095255.06 | 25955597.08 |  | 2020-08-06 | 2024-03-12 | 2025-03-03
C15177 | 18578 | S045(054) | OR38: Umpqua River (Scottsburg) Bridge Replacement | Douglas | 3 | Josh Lonie | Hamilton Construction Co. (Oregon) | 2019-10-10 | 2019-11-21 | 2019-12-26 | 39455231.8 | 44894080.72 |  | 2020-02-06 | 2023-10-25
C15206 | 21216 | S049(006) | US395: Big Stick Creek - Alkali Lake | Various | 4 | Tom Feeley | LTM Inc. dba Knife River (MDU) | 2020-06-25 | 2020-07-23 | 2020-08-04 | 10881875.41 | 14548235.12 |  | 2020-09-28 | 2022-10-26 | 2023-12-25
C15215 | 22112 | S026(166) | US26 Curb Ramps (Sandy) | Clackamas | 1 | Eric Bortvedt | Moore Excavation, Inc. | 2020-08-20 | 2020-09-10 | 2020-09-24 | 1625763.5 | 1763216.6 |  | 2021-03-26 | 2023-05-31 | 2025-03-25
C15217 | 18848 | 5245(013) | US101: SE 32nd Street - SE 35th Street (Newport) | Lincoln | 2 | Steve Schultz | James W. Fowler Company | 2020-10-29 | 2020-11-19 | 2020-12-07 | 3644377.58 | 4014375.72 |  | 2021-02-25 | 2021-11-09 | 2023-11-03 | 2025-09-18
C15218 | 18611 | 1 S091(082) | OR99W: Mcdougall Jct - McDonald Way | Yamhill | 2 | Scott Nelson | Roy L. Houck Construction LLC | 2020-09-10 | 2020-10-01 | 2020-10-21 | 9045115.49 | 10910820.54 |  | 2021-01-07 | 2022-07-12
C15222 | 20149 | S062(042) | OR126: Florence-Eugene Shoulder Widening | Lane | 2 | Shane Prohaska | JAL Construction, Inc. | 2020-09-17 | 2020-10-08 | 2020-10-23 | 2384389.37 | 2538948.54 |  | 2021-02-08 | 2022-01-13 | 2022-09-27 | 2025-09-18
C15227 | 20442 | S004(221) | US197: The Dalles (Columbia River) Bridge | Wasco | 4 | Riley Skov | Hamilton Construction Co. (Oregon) | 2020-09-24 | 2020-11-12 | 2021-01-07 | 32946675.2 | 36018563.65 |  | 2021-02-24 | 2024-06-11
C15238 | 20433 | S015(036) | OR126: Willamette River WB Bridge | Lane | 2 | Shane Prohaska | F D Thomas, Inc. | 2020-10-08 | 2020-11-05 | 2020-11-23 | 3813117.5 | 3877967.61 |  | 2021-03-22 | 2022-07-11 | 2023-04-27 | 2025-09-18
C15239 | 17882 | 2105(000) | OR99W: 1st St - Parks Drive (Dundee) | Yamhill | 2 | Scott Nelson | Kerr Contractors Oregon, Inc. | 2020-10-08 | 2020-11-12 | 2020-12-10 | 8050945 | 8327774.05 |  | 2021-01-29 | 2022-09-30
C15240 | 21296 | SA00(182) | Southern Oregon Seismic Bridge Retrofit | Douglas & Josephine | 3 | Mike Hawkins | HP Civil, Inc | 2020-10-08 | 2020-11-05 | 2020-11-19 | 12716724.38 | 14419126.05 |  | 2021-01-20 | 2024-03-29 | 2025-01-14 | 2025-09-18
C15245 | 20122 | S150(012) | OR221: Michigan City Ln - Edgewater St (W Salem) | Polk | 2 | Scott Nelson | Emery & Sons Construction Group | 2020-10-22 | 2020-11-12 | 2020-12-10 | 6418039 | 7117223.23 |  | 2021-02-02 | 2022-08-13 | 2025-05-22
C15246 | 20530 | S006(163) | I-84: Meacham - Kamela Paving & Umatilla County Signals | Umatilla | 5 | Josh McCullough | Knife River Corp - Mountain West | 2020-10-15 | 2020-12-03 | 2020-12-16 | 36435836 | 40932264.88 |  | 2021-02-23 | 2023-08-24
C15248 | 21254 | SA00(154) | US395 & OR140 (Lakeview) ADA Curb Ramps | Lake | 4 | Tom Feeley | Marcum & Sons LLC | 2020-10-15 | 2020-11-05 | 2020-12-16 | 3717253.35 | 3697597.17 |  | 2021-05-05 | 2023-11-02 | 2024-07-26
C15255 | 19071 | S001(483) | I-5 Rose Quarter Development | Multnomah | 1 | Carolyn Heniges | Hamilton and Sundt (Joint Venture) |  |  | 2020-11-06 | 9986270 | 13383392.81
C15258 | 19389 | S483(000) | OR18 McMinnville Spur: South Yamhill River Bridge | Yamhill | 2 | Scott Nelson | Wildish Standard Paving Co. | 2020-12-24 | 2021-01-28 | 2021-02-23 | 24923317.56 | 29029445.83 |  | 2021-05-03 | 2024-12-10
C15259 | 18664 | S051(003) | OR551 at Ehlen Road | Marion | 2 | Scott Nelson | K & E Excavating, Inc. | 2021-01-07 | 2021-02-04 | 2021-02-25 | 3949945 | 4438565.08 |  | 2021-04-15 | 2022-10-20 | 2025-01-14 | 2025-09-18
C15262 | 18731 | 3970(028) | OR140: Brett Way Extension (K Falls) | Klamath | 4 | Tom Feeley | Rocky Mountain Construction LLC | 2021-01-07 | 2021-02-04 | 2021-02-23 | 9117867.3 | 8511677.07 |  | 2021-05-10
C15268 | 22115 | SA00(354) | OR211 & OR224 Curb Ramps (Molalla & Estacada) | Clackamas | 1 | Dave Davies | Carter & Company, Inc. | 2021-02-11 | 2021-03-04 | 2021-03-18 | 1888430.54 | 1715665.76 |  | 2021-05-17 | 2023-05-31 | 2025-07-16
C15276 | 18311 | C067(110) | Durham Rd/Upper Boones Ferry Rd: OR99W - I-5 | Washington | 1 | Kevin Christiansen | Brown Contracting, Inc. | 2021-04-01 | 2021-04-22 | 2021-05-11 | 633888 | 645846.8 |  | 2021-09-10 | 2022-05-20 | 2025-06-25 | 2025-11-20
C15292 | 21229 | S004(227) | US97 and US20 Bend North Corridor | Deschutes | 4 | Zachary Davis | Kiewit Construction Company | 2021-11-18 | 2022-06-09 | 2022-06-09 | 102619100 | 103611812.41 |  | 2022-06-29 | 2024-12-06 | 2025-08-28
C15294 | 20223 | SA00(185) | West Lane County Curve Warning Upgrades | Lane | 2 | Mike Hawkins | Gage It Construction, LLC | 2021-07-08 | 2021-07-29 | 2021-08-17 | 1399941.5 | 1250306.86 |  | 2021-11-11 | 2022-09-09 | 2023-11-13 | 2025-09-18
C15295 | 20093 | S081(077) | OR99E: Enhanced Pedestrian Crosswalk (Woodburn) | Marion | 2 | Scott Nelson | Brown Contracting, Inc. | 2021-07-08 | 2021-07-29 | 2021-08-17 | 178023 | 186205.15 |  | 2022-01-18 | 2022-05-05 | 2025-01-27 | 2026-11-14
C15296 | 20535 | S004(219) | US97: OR58 - California Border | Klamath | 4 | Tom Feeley | Hamilton Construction Co. (Oregon) | 2021-07-08 | 2021-09-02 | 2021-09-20 | 24374705.23 | 27305453.65 |  | 2022-03-16 | 2025-10-30
C15298 | 18841 | S144(026) | OR217: OR10 - OR99W | Washington | 1 | Rick Smith | Kerr Contractors Oregon, Inc. | 2021-07-08 | 2021-08-26 | 2021-09-20 | 110081488.22 | 115068521.54 |  | 2022-01-11 | 2025-10-31
C15303 | 20423 | S102(037) | OR47: Nehalem River Bridge Project | Columbia | 2 | Mike Williams | Stellar J. Corporation | 2021-07-29 | 2021-09-02 | 2021-09-21 | 1995941 | 1791025.48 |  | 2022-01-31 | 2022-10-29 | 2022-12-31 | 2025-11-14
C15307 | 20162 | S063(037) | OR99: Coleman Ck (Phoenix) | Jackson | 3 | Richard Zeedyk | Stellar J. Corporation | 2021-09-02 | 2021-09-23 | 2021-10-08 | 3680210.56 | 3565167.63 |  | 2022-01-26 | 2022-11-08 | 2024-11-05
C15309 | 21191 | S031(014) | US20: Safety Upgrades (Albany to Corvallis) | Benton | 2 | Dave Davies | HP Civil, Inc | 2021-09-02 | 2021-09-30 | 2021-10-21 | 8799718.37 | 10301942.56 |  | 2021-12-03 | 2024-09-09
C15310 | 18745 | 6765(007) | OR214: Johna Lane - Fenne Lane (Silverton) | Marion | 2 | Scott Nelson | Brown Contracting, Inc. | 2021-09-02 | 2021-09-23 | 2021-10-14 | 842823 | 993655.47 |  | 2022-03-03 | 2022-09-15 | 2025-08-06
C15315 | 20214 | S072(012) | Mission St. 17th Street - I-5 North Ramps (Salem) | Marion | 2 | Dave Davies | HP Civil, Inc | 2021-09-16 | 2021-10-07 | 2021-10-28 | 645728.85 | 693096.11 |  | 2022-09-09 | 2022-12-31 | 2023-10-19 | 2025-11-20
C15316 | 20203 | S009(504) | US101 @ Perkins Lane Intersection Improvements | Clatsop | 2 | Jayson Buchholz | Cat Works LLC | 2021-09-23 | 2021-10-14 | 2021-11-05 | 1657880.8 | 1566381.42 |  | 2022-06-28 | 2023-07-26 | 2025-02-05
C15318 | 21591 | C019(180) | Old Hwy 99N: Oakland Bridge and Melrose Rd: Conn Ford Bridge | Douglas | 3 | Josh Lonie | Farline Bridge Inc | 2021-09-23 | 2021-10-28 | 2021-11-19 | 22624680.25 | 23140688.1 |  | 2022-01-24 | 2024-12-06
C15319 | 22318 | SA00(426) | Region 2 Signal Improvements Area 1 and 3 | Various | 2 | Dave Davies | Diamond Testing | 2021-09-02 | 2021-09-23 | 2021-10-14 | 719960.55 | 666846.14 |  | 2022-02-07 | 2022-12-06 | 2023-10-05 | 2025-09-18
C15321 | 21235 | S091(092) | OR99W: W. 1st Ave - Enid Rd | Lane | 2 | Shane Prohaska | Riverbend Construction, Inc | 2021-09-30 | 2021-10-21 | 2021-11-04 | 4586183.53 | 5346596.61 |  | 2022-07-26 | 2023-11-13 | 2025-01-28
C15324 | 20125 | S009(489) | US101: Youngs Bay Bridge - Neptune Dr | Clatsop | 2 | Jayson Buchholz | Granite Construction Co | 2021-09-30 | 2021-10-21 | 2021-11-22 | 2769769 | 3069529.42 |  | 2022-04-18 | 2023-06-23 | 2025-03-18
C15326 | 20189 | SA00(268) | Region 2 (North) Curve Warning Upgrades | Various | 2 | Eric Bortvedt | Coral Construction Co. | 2021-10-07 | 2021-10-28 | 2021-11-22 | 1746504 | 1448694.87 |  | 2022-06-01 | 2022-08-24 | 2023-12-18 | 2025-09-18
C15327 | 20128 | S009(509) | US101: Ecola Creek - Arcadia Beach | Clatsop | 2 | Jayson Buchholz | LTM, Inc. dba Knife River Materials | 2021-10-07 | 2021-10-28 | 2021-11-16 | 4340663.94 | 4841826.42 |  | 2022-03-07 | 2023-05-25 | 2025-06-09
C15328 | 20142 | S161(021) | OR211 @ Canby Marquam Hwy | Clackamas | 2 | Scott Nelson | Aaken Corporation | 2021-10-14 | 2021-11-04 | 2021-11-23 | 511561.5 | 517059.53 |  | 2022-06-21 | 2022-10-18 | 2025-04-01
C15329 | 19062 | S001(497) | I-5: Aurora - Donald Interchange (Exit 278) Phase 1(A) | Marion | 2 | Scott Nelson | K & E Excavating, Inc. | 2021-10-14 | 2021-11-18 | 2021-12-13 | 8776736 | 9404308.85 |  | 2022-02-10 | 2023-10-20
C15333 | 22410 | S001(547) | I-5: Emergency Fence Repair | Jackson | 3 | Richard Zeedyk | Mountain Sky Inc | 2021-11-11 | 2021-12-02 | 2021-12-16 | 1195876.4 | 1109262.84 |  | 2022-04-12 | 2022-11-09 | 2025-01-31 | 2025-11-14
C15336 | 20499 | S010(053) | OR82: Bear Creek (Wallowa River) Bridge | Wallowa | 5 | Josh McCullough | HP Civil, Inc | 2021-11-18 | 2021-12-16 | 2022-01-24 | 14640732.05 | 14945002.39 |  | 2022-03-02 | 2024-10-01 | 2025-04-14
C15338 | 22391 | SA00(409) | US20/OR228 Curb Ramps (Sweet Home) | Linn | 2 | Paul Tappana | Wildish Construction Co. | 2021-11-18 | 2021-12-09 | 2021-12-22 | 4586124.6 | 5109094.05 |  | 2022-03-14 | 2024-04-19 | 2025-01-21
C15340 | 22389 | SA00(401) | OR99/I-5 Curb Ramps | Jackson | 3 | Spenser Hays | Granite Construction Co | 2021-11-18 | 2021-12-09 | 2021-12-30 | 4797797 | 5546749.4 |  | 2022-03-21 | 2023-07-21 | 2025-10-27
C15341 | 20094 | S092(063) | US30 @ Graham Creek MP 65.08 - 65.25 | Columbia | 2 | Jayson Buchholz | Legacy Contracting, Inc | 2021-11-18 | 2021-12-09 | 2022-01-12 | 2419745 | 3343349.36 |  | 2022-04-20 | 2024-09-19
C15343 | 22209 | SA00(365) | Klamath, Lake, Deschutes, Crook and Wasco County Curb Ramps | Klamath | 4 | Kevin Christiansen | Granite Construction Co | 2021-11-25 | 2022-01-13 | 2022-02-24 | 9920920 | 9449140.72 |  | 2022-04-18 | 2023-09-29 | 2025-05-30
C15346 | 20445 | S153(008) | OR153: Salt Creek (Ash Swale) Bridge | Yamhill | 2 | Scott Nelson | Carter & Company, Inc. | 2021-12-09 | 2022-01-13 | 2022-02-01 | 7598226.02 | 8088320.1 |  | 2022-03-26 | 2023-11-16
C15348 | 21684 | S002(241) | I-84: Multnomah Falls - Toothrock Tunnel - Cascade Locks | Multnomah | 1 | Amer Hmidan | Kerr Contractors Oregon, Inc. | 2021-12-16 | 2022-01-20 | 2022-03-03 | 16184573.4 | 18614988.43 |  | 2022-04-05 | 2023-06-30 | 2025-10-13
C15350 | 20208 | S092(060) | US30: NW Kittridge Ave to NW Bridge Ave | Multnomah | 1 | Jamie Miller | Kerr Contractors Oregon, Inc. | 2022-01-06 | 2022-02-03 | 2022-02-17 | 5171925 | 3750203.04 |  | 2022-04-20 | 2024-01-12
C15351 | 20447 | S102(035) | OR47: West Fork Dairy Creek Bridge | Washington | 2 | Jason Kelly | Legacy Contracting, Inc | 2022-01-13 | 2022-02-03 | 2022-02-24 | 3979376 | 4174618.17 |  | 2022-05-05 | 2023-06-29 | 2025-10-13
C15352 | 22392 | SA00(418) | OR47/Territorial Rd Curb Ramps (Carlton/Veneta) | Yamhill | 2 | Paul Tappana | Brown Contracting, Inc. | 2022-01-13 | 2022-02-03 | 2022-02-17 | 3282230 | 3913113.44 |  | 2022-06-16 | 2023-11-21 | 2025-07-16
C15354 | 20092 | S047(118) | US26 at Mendenhall Creek MP 45.45 to 45.71 | Washington | 2 | Brian Bierwagen | Legacy Contracting, Inc | 2022-01-20 | 2022-02-10 | 2022-03-07 | 5035022.5 | 4723242.26 |  | 2022-05-23 | 2024-06-20
C15355 | 20242 | S226(002) | OR99: Urban Upgrade (Cottage Grove) | Lane | 2 | Shane Prohaska | Suulutaaq Inc | 2022-01-20 | 2022-02-10 | 2022-03-03 | 4176081.7 | 4584311.12 |  | 2022-08-01 | 2023-10-13 | 2025-04-16
C15358 | 21323 | S009(503) | US101: Garrison Slough - Cemetery Lp Rd (Port Orford) | Curry | 3 | Don Duey | Tidewater Contractors, Inc. | 2022-01-27 | 2022-02-17 | 2022-03-03 | 4347789 | 4438592.65 |  | 2022-08-03 | 2024-07-12 | 2025-02-03
C15359 | 22387 | SA00 (456) | US101/OR38 Curb Ramps | Douglas | 3 | Don Duey | Brown Contracting, Inc. | 2022-01-27 | 2022-02-17 | 2022-03-03 | 4223986 | 5018765.61 |  | 2022-05-25 | 2024-02-08 | 2024-10-25 | 2025-11-14
C15360 | 21707 | S123(024) | US30B: St Johns (Willamette River) Bridge | Multnomah | 1 | Rick Smith | Wildish Standard Paving Co. | 2022-02-03 | 2022-03-03 | 2022-03-15 | 8443792.56 | 12783308.01 |  | 2022-09-06
C15362 | 20362 | SA00(291) | US26: SE Kelso Rd - Frog Lake Sno Park Sec | Clackamas | 1 | Riley Skov | Dirt and Aggregate Interchange, Inc. | 2022-02-10 | 2022-03-03 | 2022-03-24 | 953333 | 916158.99 |  | 2022-07-29 | 2022-10-20 | 2024-02-12 | 2025-11-14
C15364 | 21261 | S069(022) | OR569: Green Hill Rd. - Coburg Rd. (Eugene) | Lane | 2 | Shane Prohaska | Wildish Construction Co. | 2022-02-10 | 2022-03-24 | 2022-05-06 | 17284807.95 | 17330601.94 |  | 2022-08-01 | 2024-10-29
C15367 | 18751 | S058(027) | OR99E: American Drive to SCL (Halsey) Phase 1 | Linn | 2 | Steve Schultz | Wildish Construction Co. | 2022-02-24 | 2022-03-24 | 2022-04-11 | 9914058.29 | 11489061.76 |  | 2022-08-08 | 2025-07-07
C15370 | 22400 | SA00(457) | OR7/I-84/US30 Curb Ramps (Baker City) | Baker | 5 | Chad Maxwell | Wildish Standard Paving Co. | 2022-03-03 | 2022-03-24 | 2022-04-28 | 11758937.26 | 12234864.36 |  | 2022-05-17 | 2023-10-05 | 2024-08-28
C15371 | 20339 | SA00(176) | East Systemic Signals and Illumination (ODOT) | Clackamas | 1 | Amer Hmidan | Northeast Electric, LLC | 2022-03-24 | 2022-04-14 | 2022-05-11 | 3646858 | 3550496.14 |  | 2022-11-14 | 2023-07-19 | 2024-05-15
C15372 | 20335 | SA00(186) | Central Systemic Signals and Illumination (ODOT) | Multnomah | 1 | Jamie Miller | Wildish Construction Co. | 2022-06-23 | 2022-07-14 | 2022-08-04 | 3805544.95 | 3963253.99 |  | 2023-02-21 | 2024-11-20
C15375 | 22468 | S123(027) | OR10 (Wash Co) & OR99E (Milwaukie-Oregon City) Curb Ramps | Washington | 1 | Dave Davies | M J Hughes Construction, Inc. | 2022-03-10 | 2022-03-31 | 2022-04-14 | 3293526.97 | 3246981.25 |  | 2022-05-23 | 2023-05-15 | 2025-08-29
C15376 | 22122 | SA00(434) | Central Oregon Curb Ramps - Phase 2 | Various | 4 | Kevin Christiansen | Brown Contracting, Inc. | 2022-03-17 | 2022-04-07 | 2022-06-02 | 6622800 | 6323860.77 |  | 2022-07-18 | 2024-05-17
C15381 | 22401 | SA00(446) | Umatilla County Curb Ramps (Pendleton) | Umatilla | 5 | Chad Maxwell | Moreno & Nelson Construction | 2022-03-31 | 2022-04-21 | 2022-05-20 | 6582563.86 | 6887630.62 |  | 2022-06-27 | 2023-07-14 | 2024-07-28 | 2025-09-18
C15384 | 22394 | S081(081) | OR99E: Curb Ramps (Hubbard) | Marion | 2 | Dave Davies | Carter & Company, Inc. | 2022-04-14 | 2022-05-05 | 2022-05-19 | 1023717.37 | 1076480.52 |  | 2022-07-25 | 2023-09-07 | 2025-07-29
C15388 | 22393 | SA00(419) | OR99/OR99W/OR99E Curb Ramps | Various | 2 | Dave Davies | Corpac Construction Company | 2022-05-12 | 2022-06-02 | 2022-06-09 | 6442305 | 6803784.01 |  | 2022-08-18 | 2024-03-15 | 2025-10-17
C15392 | 20256 | S021(019) | OR140 at OR66 Intersection Improvements | Klamath | 4 | Tom Feeley | LaDuke Construction LLC | 2022-06-23 | 2022-07-14 | 2022-08-04 | 4617977.03 | 4328542.75 |  | 2022-10-10 | 2023-11-14 | 2024-10-04 | 2025-09-18
C15394 | 22398 | SA00(451) | Umatilla/Morrow County Curb Ramps | Umatilla | 5 | Kevin Christiansen | Nelson Construction Corp dba Moreno and Nelson Co. | 2022-06-23 | 2022-07-14 | 2022-08-11 | 9652155.1 | 10671429.99 |  | 2023-02-06 | 2024-10-11 | 2025-08-13
C15395 | 18775 | S081(072) | OR99E: MP 20.35 - SW Berg Parkway (Canby) | Clackamas | 1 |  | K & E Excavating, Inc. | 2022-06-23 | 2022-08-04 | 2022-08-30 | 11976347.76 | 19184369.75 |  | 2022-11-18 | 2025-06-06
C15397 | 18733 | S009(484) | US101: Ave A - Ave K (Seaside) Sec | Clatsop | 2 | Dave Davies | Big River Construction, Inc. | 2022-06-30 | 2022-07-28 | 2022-08-26 | 6789101.8 | 7249720.96 |  | 2022-11-03 | 2024-08-29 | 2025-07-10
C15400 | 22467 | S064(063) | I-205: I-5 to OR213, Phase 1A | Clackamas | 1 | Christopher Aguon | Kiewit Construction Company | 2021-12-02 | 2022-03-01 | 2022-05-17 | 445870790.78 | 439071449.57 |  | 2022-05-31
C15402 | 21514 | S033(065) | US20: Philomath Couplet | Benton | 2 | Steve Schultz | Corpac Construction Company | 2022-06-30 | 2022-07-28 | 2022-09-16 | 13966205.85 | 13739296.48 |  | 2022-11-28 | 2024-11-11
C15403 | 22518 | SA00(452) | I-84: Cascade Locks - Arlington Sign Upgrades | Wasco | 5 | Dave Davies | Coral Construction Co. | 2022-07-28 | 2022-08-18 | 2022-09-14 | 7883556 | 8949399.11 |  | 2023-06-13 | 2024-08-16 | 2025-04-29
C15404 | 20429 | S001(530) | I-5 Conn over Corp (Cottage Grove) | Lane | 2 | Shane Prohaska | HP Civil, Inc | 2022-07-28 | 2022-08-18 | 2022-09-08 | 1939796.98 | 1843147.3 |  | 2022-12-01 | 2023-06-14
C15405 | 21029 | 4700(076) | Foothill Rd: Delta Waters to Dry Creek | Jackson | 3 | Shane Javernick | LTM, Inc. dba Knife River Materials | 2022-08-04 | 2022-09-15 | 2022-10-04 | 6658671.34 | 6358382.87 |  | 2023-01-23 | 2024-11-04
C15407 | 20011 | S017(016) | US20: Tumalo - Cooley Rd (Bend) | Deschutes | 4 | Bill Martin | Marcum & Sons LLC | 2022-08-11 | 2022-09-08 | 2022-09-20 | 18741544.8 | 18289809.45 |  | 2022-10-17 | 2023-11-14 | 2025-04-28
C15408 | 20486 | S001(522) | I-5 over 26th Avenue Bridge | Multnomah | 1 | Jamie Miller | HP Civil, Inc |  | 2022-10-06 | 2022-10-17 | 11097122.18 | 11119819.44 |  | 2023-04-18 | 2024-12-02
C15409 | 20185 | S063(039) | OR99: I-5 to Scenic Ave | Jackson | 3 | Richard Zeedyk | LTM, Inc. dba Knife River Materials | 2022-08-25 | 2022-09-15 | 2022-10-04 | 3447281.66 | 3226932.03 |  | 2022-12-13 | 2023-10-24 | 2024-03-08
C15411 | 20435 | S091(090) | OR99W: I-5 - McDonald St Section | Washington | 1 | Neil Waibel | Knife River Corporation - NW (MDU) | 2022-09-08 | 2022-10-13 | 2022-12-01 | 26174331.54 | 24987974.89 |  | 2023-04-17 | 2024-11-27
C15413 | 19836 | C009(076) | Columbia County Emergency Slide Repairs | Columbia | 2 |  | Tapani, Inc | 2022-09-29 | 2022-10-20 | 2022-11-17 | 1349000 | 1337238.03 |  | 2023-02-28 | 2023-05-31
C15414 | 19840 | C009(077) | Columbia County Emergency Culvert Replacements | Columbia | 2 | Eric Bortvedt | Tapani, Inc | 2022-10-06 | 2022-10-27 | 2022-12-01 | 3449000 | 3525370.88 |  | 2023-05-30 | 2023-10-12
C15415 | 19231 | 4700(076) | Foothill Rd Corridor Project | Jackson | 3 | Richard Zeedyk | LTM, Inc. dba Knife River Materials | 2022-09-29 | 2022-11-17 | 2022-12-15 | 56432118.75 | 57568537.36 |  | 2023-02-16
C15416 | 20067 | S009(497) | US101: Moolack Landslide Repair MP 135.7 - 136.31 | Lincoln | 2 | Steve Schultz | Jesse Rodriguez Construction LLC | 2022-09-29 | 2022-10-20 | 2022-11-03 | 1037833 | 1021272.35 |  | 2023-01-10 | 2023-09-06 | 2025-05-15
C15417 | 18749 | 5210(009) | OR219: Edgewood Dr - Aldercrest Dr | Yamhill | 2 | Mike Williams | The Saunders Company Inc | 2022-09-29 | 2022-10-20 | 2022-12-01 | 1928000 | 2014953.69 |  | 2023-09-11 | 2024-10-14
C15419 | 20410 | S002(234) | I-84: I-205 - Marine Drive Section | Multnomah | 1 | Amer Hmidan | Kerr Contractors Oregon, Inc. | 2022-10-13 | 2022-11-10 | 2022-12-23 | 13247388 | 13355390.44 |  | 2023-03-28 | 2024-09-04
C15420 | 20519 | 3490(012) | US30 (Cascade Ave.) at Rand Rd (Hood River) | Hood River | 1 | Riley Skov | Wildish Standard Paving Co. | 2022-10-27 | 2022-11-17 | 2022-12-01 | 2087734.77 | 2107531.89 |  | 2023-02-03 | 2024-11-12 | 2025-11-10
C15422 | 21540 | S001(535) | I-5: Goshen - Cottage Grove | Lane | 2 | Shon Heern | Wildish Construction Co. | 2022-11-03 | 2022-12-01 | 2022-12-15 | 7489198.03 | 7567259.7 |  | 2023-04-23 | 2024-10-21 | 2025-09-17
C15423 | 21966 | S440(005) | OR205: Junction of Steens Hwy - Roaring Springs Ranch | Harney | 5 | Petr Lovasik | High Desert Aggregate & Paving, Inc. | 2022-11-17 | 2022-12-08 | 2022-12-21 | 5553591 | 5640267.6 |  | 2023-04-26 | 2023-09-19 | 2025-04-09
C15426 | 21898 | SA00(473) | Baker & Union Counties Traffic Signal Safety Improvements | Union | 5 | Josh McCullough | Ross Brandt Electric, Inc | 2022-12-22 | 2023-01-12 | 2023-02-06 | 1985804 | 1885001 |  | 2023-08-14 | 2024-06-13 | 2025-01-07
C15428 | 21538 | S227(020) | I-105: Willamette R - Pacific Hwy. | Lane | 2 | Shane Prohaska | Riverbend Construction, Inc | 2023-02-02 | 2023-03-02 | 2023-03-16 | 5109321.05 | 4566128.78 |  | 2023-07-24 | 2024-07-24 | 2024-11-22
C15429 | 22302 | S031(017) | US20: Conifer Blvd to Merloy Ave | Benton | 2 | Dave Davies | North Santiam Paving Co. | 2022-12-29 | 2023-01-19 | 2023-02-09 | 4759849.2 | 4874356.73 |  | 2023-04-04 | 2023-12-08 | 2025-07-21
C15430 | 20688 | S210(022) | OR34: Van Buren Bridge (Corvallis) | Various | 2 | Steve Schultz | Hamilton Construction Co. (Oregon) | 2023-01-05 | 2023-02-23 | 2023-03-13 | 61391555.7 | 55113209.62 |  | 2023-04-24
C15431 | 21543 | S015(039) | OR126: Greenwood Dr - Vida | Lane | 2 | Shane Prohaska | Riverbend Construction, Inc | 2023-01-26 | 2023-02-16 | 2023-02-27 | 2298724.2 | 2425223.51 |  | 2023-06-05 | 2023-09-12 | 2024-10-30
C15432 | 21230 | SA00(259) | US20/OR201: Burns to Ontario | Various | 5 |  | Marcum & Sons LLC | 2023-01-19 | 2023-02-16 | 2023-03-03 | 11963039 | 12941169.66 |  | 2023-05-24
C15433 | 21675 | S001(546) | I-5: North Ashland - South Ashland | Jackson | 3 | Tim Fletcher | Rocky Mountain Construction LLC | 2023-01-19 | 2023-02-16 | 2023-03-02 | 8949849 | 8387476.63 |  | 2023-05-22 | 2023-12-22
C15434 | 21795 | S006(174) | I-84: Benson Creek and Moores Hollow Interchange | Malheur | 5 |  | Wildish Standard Paving Co. | 2023-01-19 | 2023-03-02 | 2023-04-27 | 6086047.48 | 6245134.47 |  | 2023-07-17 | 2024-11-25
C15435 | 20478 | S160(056) | OR213 at MP 15.71 (Toliver Rd) | Clackamas | 1 | Amer Hmidan | Kerr Contractors Oregon, Inc. | 2023-01-19 | 2023-02-09 | 2023-03-08 | 3848295 | 3728439.92 |  | 2023-06-06 | 2023-09-29 | 2025-03-04
C15436 | 21539 | S001(537) | I-5: N. Santiam - Kuebler | Marion | 2 | Scott Nelson | Knife River Corporation - NW (MDU) | 2023-02-09 | 2023-03-02 | 2023-03-17 | 4862764.47 | 5033480.96 |  | 2023-06-19 | 2024-05-23
C15438 | 22523 | SA00(474) | OR18: Newberg-Dundee Bypass (Phase 2a) | Yamhill | 2 |  | Wildish Standard Paving Co. | 2024-08-22 | 2024-09-24 | 2024-10-25 | 39200252.27 | 12613454.83 |  | 2025-02-17
C15439 | 21794 | S006(173) | I-84: Bridges over OR237 (North Powder Interchange) | Union | 5 | Dave Davies | HP Civil, Inc | 2023-02-23 | 2023-03-16 | 2023-05-10 | 4927292.06 | 5399436.37 |  | 2023-09-25 | 2024-10-23
C15443 | 21374 | S091(097) | OR99W: Orrs Corner Road - Clow Corner Road | Polk | 2 | Scott Nelson | Emery & Sons Construction Group | 2023-03-02 | 2023-03-30 | 2023-04-20 | 7858985.06 | 7813222.18 |  | 2023-06-06 | 2025-10-30
C15444 | 22446 | SA00(439) | Grant County Curb Ramps | GRANT | 5 | Chad Maxwell | Western United Civil Group LLC | 2023-03-09 | 2023-04-13 | 2023-05-04 | 4381678.5 | 4351117.8 |  | 2023-10-30 | 2024-10-18 | 2025-04-09
C15445 | 22290 | S060(003) | Southern Oregon Seismic Bridge Retrofit (Phase 3) | Jackson | 3 | Mike Hawkins | Carter & Company, Inc. | 2023-03-09 | 2023-03-30 | 2023-04-10 | 9171773.29 | 9515676.81 |  | 2023-11-28
C15446 | 22445 | SA00(438) | Burns & Hines Curb Ramps | Harney | 5 | Chad Maxwell | Wildish Construction Co. | 2023-03-16 | 2023-04-06 | 2023-05-18 | 9466018 | 8978477.96 |  | 2023-09-25 | 2025-08-07
C15447 | 22447 | SA00(440) | Jordan Valley/Ontario/Huntington/Adrian Curb Ramps | Various | 5 | Chad Maxwell | HP Civil, Inc | 2023-03-30 | 2023-04-20 | 2023-05-18 | 7117363.05 | 7032160.47 |  | 2023-10-23 | 2024-09-19 | 2025-07-21
C15448 | 21599 | S026(165) | US26: Salmon River - Zigzag | Clackamas | 1 | Amer Hmidan | Brix Paving Company | 2023-03-30 | 2023-04-27 | 2023-05-25 | 6748709 | 6661143.71 |  | 2023-07-25 | 2023-12-14
C15449 | 21177 | S068(031) | OR213 (82nd Ave): SE Foster Rd - SE Thompson Rd | Multnomah | 1 | Amer Hmidan | Kerr Contractors Oregon, Inc. | 2023-04-24 | 2023-05-25 | 2023-07-13 | 15462614 | 14304230.55 |  | 2023-10-09 | 2025-08-05
C15450 | 22520 | S004(235) | US97: Dover Ln - Bear Dr Safety Improvements | Jefferson | 4 | Bill Martin | Taylor Northwest LLC | 2023-05-11 | 2023-06-01 | 2023-06-14 | 1613646.8 | 1598191.14 |  | 2023-07-24 | 2023-10-15 | 2025-03-17
C15451 | 22469 | S081(083) | US30BY Curb Ramps (Portland) | Multnomah | 1 | Eric Bortvedt | Wildish Construction Co. | 2023-05-11 | 2023-06-01 | 2023-06-13 | 1175570.02 | 1004233.39 |  | 2023-09-18 | 2024-02-02
C15454 | 17270 | C000(047) | 40 Mile Loop: Blue Lake Park - Sundial Rd | Multnomah | 1 | Peter Coffman | K & E Excavating, Inc. | 2023-08-22 | 2023-07-13 | 2023-07-25 | 2476792 | 2497640.37 |  | 2023-10-09 | 2024-06-13 | 2025-02-25
C15456 | 22609 | S029(037) | OR8: East Lane (Cornelius) | Washington | 1 |  | Wildish Construction Co. | 2023-06-22 | 2023-07-13 | 2023-08-01 | 645697 | 628792.44 |  | 2023-10-13 | 2024-04-25 | 2025-05-08
C15457 | 22437 | SA00(430) | US101/OR241/OR540 Curb Ramps (Coos Bay/North Bend) | Coos | 3 | Eric Bortvedt | Brown Contracting, Inc. | 2023-06-29 | 2023-07-27 | 2023-08-08 | 3397323 | 3340712.49 |  | 2023-10-24 | 2024-06-14
C15459 | 22225 | S242(012) | OR242: McKenzie Pass Pavement Preservation | Deschutes | 4 |  | Knife River Corporation - NW (MDU) | 2023-07-27 | 2023-08-17 | 2023-08-28 | 4205745 | 4185176.38 |  | 2024-03-08 | 2024-11-01 | 2025-04-29
C15460 | 19327 | 7365(014) | Fanno Crk Trail: Woodward Pk - Bonita Rd/85th Ave - Tu | Washington | 1 |  | Farline Bridge Inc | 2023-07-27 | 2023-08-17 | 2023-08-31 | 7575939.05 | 7531094.98 |  | 2023-11-15
C15461 | 21649 | S006(172) | I-84: Exit 216 East Bound Off-Ramp | Umatilla | 5 |  | Michael A. Becker General Contractor Inc | 2023-08-10 | 2023-08-31 | 2023-09-13 | 3561208.2 | 3716855.81 |  | 2024-02-27 | 2024-11-18 | 2025-10-28
C15462 | 21644 | S002(240) | I-84:US197-The Dalles, Rufus and Arlington Bridges | Gilliam | 4 |  | Wildish Construction Co. | 2024-04-25 | 2024-05-16 | 2024-06-12 | 14901911.65 | 8553737.39 |  | 2024-09-26
C15463 | 20428 | S031(015) | US20: Willamette R (Ellsworth St) Bridge | Benton | 2 | Steve Schultz | Wildish Standard Paving Co. | 2023-08-24 | 2023-09-14 | 2023-09-22 | 4535395.02 | 4512266.29 |  | 2023-12-29 | 2024-10-18 | 2025-04-14
C15464 | 22519 | SA00(453) | I-84: Arlington - Pendleton and I-82 Sign Upgrades | Various | 5 | Dave Davies | Knife River Corporation - NW (MDU) | 2023-08-24 | 2023-09-14 | 2023-10-09 | 6169000 | 5481798.34 |  | 2024-02-12
C15465 | 21778 | SA00(381) | City of Springfield Signal Enhancements | Lane | 2 | Scott Mansur | Northstar Electrical | 2023-08-31 | 2023-09-21 | 2023-10-05 | 1340000 | 1305774.74 |  | 2024-04-23 | 2025-01-27
C15466 | 21583 | S092(067) | US30: EB Larson Rd. - Longview Bridge Queue Warning System | Columbia | 2 | Jayson Buchholz | Northeast Electric, LLC | 2023-08-31 | 2023-09-21 | 2023-10-04 | 1258000 | 1318921.61 |  | 2024-01-08 | 2024-06-21
C15467 | 19835 | C057(079) | Crystal Creek (Miami - Foley) Br | Tillamook | 2 | Kevin Timmins | HP Civil, Inc | 2023-08-31 | 2023-09-21 | 2023-10-10 | 2478659.14 | 2469162.74
C15469 | 21641 | S456(026) | US95: Idaho State Line - McDermitt | Malheur | 5 | Petr Lovasik | High Desert Aggregate & Paving, Inc. | 2023-09-14 | 2023-10-12 | 2023-10-20 | 12948660 | 13248940.05 |  | 2024-03-20 | 2025-08-14
C15470 | 21666 | S067(008) | Pendleton Signal Upgrade Project Phase II | Umatilla | 5 |  | HP Civil, Inc | 2023-07-14 | 2023-10-05 | 2023-10-26 | 1558695.33 | 1757629.89 |  | 2024-06-11 | 2024-11-14 | 2025-10-27
C15471 | 19833 | C057(075) | Dick Creak Bridge (Bayocean Rd) Tillamook | Tillamook | 2 | Kevin Timmins | Farline Bridge Inc | 2023-09-14 | 2023-10-05 | 2023-10-26 | 1031042.86 | 990680.99 |  | 2024-08-05 | 2024-09-30
C15472 | 21447 | 6960(055) | City of Springfield Signal Enhancements | Lane | 2 |  | Northstar Electrical | 2023-09-21 | 2023-10-12 | 2023-10-24 | 696745.2 | 706592.82 |  | 2024-05-28 | 2024-08-08 | 2025-04-21
C15473 | 21875 | SA00(393) | Eastern Oregon Roadside Traffic & Weather Cameras | Various | 5 |  | HP Civil, Inc | 2023-09-21 | 2023-10-12 | 2023-11-01 | 2892013.13 | 2892515.75 |  | 2024-11-13 | 2025-08-26
C15474 | 22612 | SA00(598) | Jackson County curb ramps, phase 2A | Jackson | 3 |  | Brown Contracting, Inc. | 2023-09-21 | 2023-10-12 | 2023-10-26 | 1393182 | 1488368.16 |  | 2023-12-20 | 2024-07-16 | 2025-09-22
C15475 | 19929 | S001(505) | I-5: Kuebler Blvd to Delaney Rd widening | Marion | 2 | Shon Heern | K & E Excavating, Inc. | 2024-04-18 | 2024-05-23 | 2024-06-18 | 38270523.02 | 27490341.27 |  | 2024-08-28
C15476 | 21645 | S300(003) | OR206: Rock Creek Bridge | Gilliam | 4 |  | Marcum & Sons LLC | 2023-09-28 | 2023-10-19 | 2023-11-01 | 3685499.07 | 3505291.44 |  | 2024-02-21
C15477 | 21162 | S004(216) | US97: Lower Bridge Way - NW 10th St (Terrebonne) | Deschutes | 4 |  | Knife River Corporation - NW (MDU) | 2024-04-11 | 2024-05-09 | 2024-05-22 | 27182656.1 | 16213667.08 |  | 2024-07-15
C15478 | 21224 | S047(119) | US26: Little Humbug Creek Bridge | Clatsop | 2 |  | Farline Bridge Inc | 2023-09-28 | 2023-10-19 | 2023-11-01 | 4119314.62 | 3575623.12 |  | 2024-04-02 | 2025-05-01
C15479 | 21615 | SA00(375) | Washington County Safety, Bike and Pedestrian Improvements | Washington | 1 |  | Aaken Corporation | 2023-09-28 | 2023-10-19 | 2023-11-06 | 1548521 | 1535493.14 |  | 2024-02-23 | 2025-02-11 | 2025-10-06
C15480 | 20209 | S015(037) | OR126B @ 54th St. (Springfield) | Lane | 2 |  | Wildish Construction Co. | 2023-09-28 | 2023-10-19 | 2023-11-08 | 1360766.05 | 1278259.74 |  | 2024-04-15 | 2024-12-19
C15481 | 21452 | SA00(289) | Southern Oregon Seismic Slopes Stability | Jackson | 3 | Karen Tatman | LTM Inc | 2023-09-28 | 2023-10-26 | 2023-11-09 | 6293773 | 6040037.33 |  | 2024-01-30 | 2024-11-11
C15482 | 20522 | S123(023) | US30 at Bridge Ave Ramps | Multnomah | 1 |  | Conway Construction Company | 2023-09-28 | 2023-10-19 | 2023-11-16 | 2257099 | 2226563.32 |  | 2023-12-18 | 2024-05-06 | 2025-06-26
C15483 | 21727 | SA00(387) | US101 Frontage Road: Ben Jones (Rocky Creek) Bridg | Lincoln | 2 | Steve Schultz | Stellar J. Corporation | 2023-10-26 | 2023-11-16 | 2023-12-05 | 4097145 | 4503412 |  | 2024-04-08 | 2024-12-19 | 2025-10-29
C15484 | 20268 | S041(031) | US26: Harwood Ave - Combs Flat Rd (Prineville) | Crook | 4 |  | Cascade Civil Corp | 2023-10-12 | 2023-11-16 | 2023-11-28 | 7028383.86 | 7040623.97 |  | 2024-01-10 | 2024-11-22
C15485 | 21408 | S060(002) | OR99: Rogue Valley Intersection Improvements | Various Highways | 3 |  | LTM Inc | 2023-10-26 | 2023-11-16 | 2023-12-04 | 858994.5 | 881250.6 |  | 2024-01-31 | 2024-05-14 | 2025-01-23
C15486 | 21647 | S053(039) | US26: Wapinita Junction - Warm Springs River | Wasco | 4 |  | Granite Construction Co | 2023-11-09 | 2023-12-07 | 2023-12-22 | 8234234 | 8670634.37 |  | 2024-05-29 | 2024-09-26 | 2025-04-30
C15487 | 22384 | S063(042) | OR99: Glenwood - Coleman Creek | Jackson | 3 |  | LTM Inc | 2023-11-09 | 2023-12-07 | 2023-12-27 | 10611703.4 | 8096035.78 |  | 2024-05-20
C15489 | 21597 | S047(122) | US26: Glencoe Rd - Cornelius Pass Rd | Washington | 1 |  | Kerr Contractors Oregon, Inc. | 2023-11-16 | 2023-12-14 | 2023-12-29 | 6426337 | 6718325.12 |  | 2024-04-01 | 2024-12-20
C15490 | 21537 | S281(013) | OR281 at Orchard Rd (Hood River) | Hood River | 1 |  | James Dean Construction, Inc. | 2023-11-16 | 2023-12-07 | 2023-12-21 | 797363 | 692558.17 |  | 2024-02-26 | 2024-06-05 | 2025-09-22
C15491 | 21655 | SA00(460) | All Roads Transportation Safety Intersection Upgrades | Various | 4 |  | Brown Contracting, Inc. | 2023-11-23 | 2023-12-14 | 2023-12-22 | 598888 | 638695.03 |  | 2024-06-17 | 2024-10-22 | 2025-06-17
C15493 | 23458 | S123(028) | US30BY Curb Ramps, Phase 1 | Multnomah | 1 | Eric Bortvedt | Wildish Construction Co. | 2023-11-23 | 2023-12-21 | 2024-01-11 | 7046627.52 | 5538524.44 |  | 2024-03-26 | 2025-03-14
C15494 | 20167 | S041(030) | OR126: Redmond - Powell Butte | Deschutes | 4 |  | Marcum & Sons LLC | 2023-12-07 | 2024-01-11 | 2024-01-26 | 8279904.93 | 7172769.37 |  | 2024-02-27
C15495 | 21542 | S162(061) | OR22: Big Cliff Dam - Mongold Slide | Marion | 2 |  | North Santiam Paving Co. | 2023-12-21 | 2024-02-01 | 2024-02-14 | 5029958.5 | 5280486.69 |  | 2024-03-26 | 2024-08-23
C15496 | 21731 | S164(009) | OR164: Jefferson (Santiam River) Bridge | Marion | 2 |  | Carter & Company, Inc. | 2023-12-21 | 2024-01-11 | 2024-01-30 | 5487717.17 | 5618110.09 |  | 2024-04-24
C15497 | 21894 | SA00(475) | Malheur County Traffic Signal Safety Improvements | Harney | 5 |  | HP Civil, Inc | 2024-01-04 | 2024-01-25 | 2024-02-12 | 592300 | 599991.46 |  | 2024-06-03 | 2024-06-08 | 2025-03-13
C15498 | 22505 | S001(554) | I-5: Aurora Donald Interchange (Exit 278) Phase 2 | MARION | 2 | Nick Donnelly | HP Civil, Inc | 2023-12-28 | 2024-02-22 | 2024-03-14 | 53281187.94 | 35693530.23 |  | 2024-05-23
C15499 | 22358 | S007(088) | US20: Corridor Culvert Repairs Phase 2 | Various | 5 |  | Whitaker Construction Co. Inc | 2024-01-11 | 2024-02-01 | 2024-02-22 | 1244210.2 | 1110391.2 |  | 2025-07-28 | 2025-08-28
C15500 | 21717 | SA00(521) | Rogue Valley Rural Intersection Improvements | Various | 3 |  | Aaken Corporation | 2024-01-11 | 2024-02-01 | 2024-02-22 | 910141.5 | 912183.25 |  | 2024-05-13 | 2024-10-04
C15501 | 22072 | S017(019) | US20 at N. Locust Ave. Intersection | Deschutes | 4 |  | Marcum & Sons LLC | 2024-01-18 | 2024-02-08 | 2024-02-14 | 3983245.29 | 4019723.02 |  | 2024-02-29 | 2025-05-08
C15502 | 22508 | S001(550) | I-5: Halsey to Lane County Line | LINN | 2 |  | Riverbend Construction, Inc |  | 2024-02-29 | 2024-03-18 | 15588575 | 16623530.59 |  | 2024-05-14 | 2025-09-15
C15503 | 21549 | S033(066) | US20: Eddyville - Cline Hill | Lincoln | 2 |  | Knife River Corporation - NW (MDU) | 2024-01-18 | 2024-02-08 | 2024-02-22 | 3016259.36 | 2926625.37 |  | 2024-05-12 | 2024-08-22 | 2025-07-08
C15504 | 21738 | S015(041) | OR126: Blue River Bridge | Lane | 2 | Nick Donnelly | HP Civil, Inc | 2024-01-18 | 2024-02-08 | 2024-03-05 | 1554126.27 | 1692404.49 |  | 2024-04-26 | 2024-09-23 | 2025-05-08
C15505 | 23483 | S009(533) | US101: Reedsport Lane Reconfiguration | Douglas | 3 |  | Brown Contracting, Inc. | 2024-02-08 | 2024-02-29 | 2024-03-14 | 569459.2 | 558919.33 |  | 2024-05-06 | 2024-10-31 | 2025-03-21
C15506 | 21711 | S026(168) | OR35: US26 Overcrossing Bridge | Clackamas | 1 |  | Hamilton Construction Co. (Oregon) | 2024-02-08 | 2024-02-29 | 2024-03-14 | 1793422 | 1746860.47 |  | 2024-06-17 | 2025-04-24
C15507 | 20190 | SA00(312) | Region 2 (Central & S) Curve Warning Upgrades | Various | 2 | Eric Bortvedt | Cartello Construction Inc | 2024-02-15 | 2024-03-07 | 2024-03-14 | 848603 | 689479 |  | 2024-07-08 | 2025-04-01
C15508 | 21489 | S007(083) | US20: 3rd St - Purcell (Greenwood, Bend) | Deschutes | 4 |  | K & E Excavating, Inc. | 2024-02-15 | 2024-03-07 | 2024-03-21 | 3284606 | 4625299.63 |  | 2024-06-11 | 2025-06-30
C15509 | 21761 | S001(548) | I-5 northbound: Santiam Overflow Bridge | Marion | 2 |  | Carter & Company, Inc. | 2024-02-15 | 2024-03-07 | 2024-03-20 | 971525.25 | 873347.29 |  | 2024-06-16 | 2024-10-01
C15510 | 22515 | S018(058) | OR58: Eagle Creek to Salt Creek Tunnel | Lane | 2 |  | Wildish Construction Co. | 2024-02-22 | 2024-03-14 | 2024-04-15 | 3798561.11 | 3813312.5 |  | 2024-08-08 | 2024-10-16 | 2025-01-27
C15511 | 21643 | S066(023) | US30: (10th St) /Hughes- Cedar St Upgrades (Baker) | Baker | 5 |  | Moreno & Nelson Construction | 2024-02-22 | 2024-03-14 | 2024-04-01 | 8177488 | 7764929.51 |  | 2024-05-23
C15512 | 21676 | SA00(352) | OR99/OR238/OR62: Big X Intersection (Medford) | Jackson | 3 |  | LTM Inc | 2024-02-29 | 2024-03-28 | 2024-05-08 | 15889987.2 | 15361221.5 |  | 2024-07-08 | 2025-10-31
C15513 | 22423 | C011(076) | Sandy Creek Rd at Mile Point 2.70 | Coos | 3 |  | Carter & Company, Inc. | 2024-03-07 | 2024-03-28 | 2024-04-15 | 1421588 | 1378446.47 |  | 2024-05-20 | 2024-09-30 | 2025-11-05
C15514 | 20376 | SA00(196) | West Systemic Signals and Illumination | Various | 1 |  | Northstar Electrical | 2024-03-07 | 2024-03-28 | 2024-04-15 | 4046033 | 3953805.97 |  | 2024-09-25
C15515 | 18735 | 0315(018) | OR202: Dresden St to 4th St (Astoria) | Clatsop | 2 | Jayson Buchholz | Big River Construction, Inc. | 2024-03-07 | 2024-03-28 | 2024-04-23 | 4449246.35 | 4645648.86 |  | 2024-06-11 | 2025-02-25
C15516 | 21564 | S091(104) | OR99W: Theona Dr. (Eugene) | Lane | 2 |  | Wildish Construction Co. | 2024-03-14 | 2024-04-04 | 2024-04-30 | 192072 | 164141.41 |  | 2024-07-08 | 2024-08-02 | 2025-04-21
C15517 | 22001 | C041(032) | South Beaver Creek Road: South Fork Beaver Creek | Lincoln | 2 | Mike Williams | JAL Construction, Inc. | 2024-03-14 | 2024-04-04 | 2024-04-22 | 1538942 | 1619408.46 |  | 2024-06-20 | 2024-10-15
C15518 | 21613 | S100(069) | US30: Sandy River - OR35 | Various | 1 |  | Coral Construction Co. | 2024-03-21 | 2024-04-11 | 2024-05-01 | 443346 | 411561.06 |  | 2024-07-01 | 2024-09-26
C15519 | 21545 | S215(004) | OR126: Linn County Line - Old McKenzie Highway | Lane | 2 |  | Knife River Corporation - NW (MDU) | 2024-03-21 | 2024-04-11 | 2024-04-22 | 5219362.12 | 5209160.09 |  | 2024-06-24 | 2025-06-23
C15520 | 22560 | SA00(507) | Umatilla County curb ramps (Pendleton) phase 2 | Umatilla | 5 |  | Brown Contracting, Inc. | 2024-03-28 | 2024-04-18 | 2024-05-09 | 5892302 | 5818462.28 |  | 2024-07-11
C15521 | 20252 | S009(508) | US101: Urban Upgrade (Garibaldi) | Tillamook | 2 |  | K & E Excavating, Inc. | 2024-03-28 | 2024-04-25 | 2024-05-21 | 8105524.6 | 8034046.69 |  | 2024-08-14 | 2025-09-19
C15522 | 23429 | SA00(617) | Umatilla/Morrow County curb ramps phase 2A | VARIOUS | 5 |  | Nelson Construction Corp dba Moreno and Nelson Co. | 2024-03-28 | 2024-04-25 | 2024-05-10 | 3663663 | 3611858 |  | 2025-01-13 | 2025-09-30
C15523 | 21774 | S035(085) | OR42: Endicott, Middle Fork Coquille and Hoffman | Coos | 3 |  | HP Civil, Inc | 2024-04-04 | 2024-04-25 | 2024-05-06 | 1753462.22 | 1814862.98 |  | 2024-06-28 | 2024-10-08 | 2025-11-10
C15524 | 21878 | S006(177) | I-84: LaGrande-Baker City Sign Upgrades | Baker | 5 |  | HP Civil, Inc | 2024-04-04 | 2024-04-25 | 2024-05-21 | 2540038.33 | 2455771.88 |  | 2024-07-24 | 2025-09-19
C15525 | 21781 | S002(246) | I-84: Ruckel Creek Culvert | Hood River | 1 |  | Wildish Construction Co. | 2024-04-04 | 2024-04-25 | 2024-05-14 | 424140.01 | 379572.4 |  | 2024-07-01 | 2024-08-26 | 2025-09-24
C15526 | 22434 | S009(521) | US101 Curb Ramps (Lincoln City/Lincoln Beach) | Lincoln | 2 |  | Brown Contracting, Inc. | 2024-04-11 | 2024-05-02 | 2024-05-22 | 10823238 | 6820498.63 |  | 2024-08-21
C15527 | 20548 | S006(170) | I-82 and I-84: Umatilla - Pendleton Concrete Pavement Repair | Umatilla | 5 |  | HP Civil, Inc | 2024-04-18 | 2024-05-16 | 2024-06-06 | 13165582.61 | 13563536 |  | 2024-10-08
C15528 | 22776 | S004(239) | US97: Redmond-Bend Phase 2 | Deschutes | 4 |  | Marcum & Sons LLC | 2024-05-16 | 2024-06-06 | 2024-06-25 |  |  |  | 2024-10-01 | 2024-10-31 | 2025-06-26
C15529 | 23165 | C067(124) | Tualatin River/South Rd Bridge (Washington Co) | Washington | 2 |  | Cascade Civil Corp | 2024-05-16 | 2024-06-06 | 2024-06-24 | 1266335.92 | 1339739.15 |  | 2024-08-12 | 2025-01-08
C15530 | 21553 | S001(538) | I-5: Salem - Albany | Various | 2 |  | Carter & Company, Inc. | 2024-05-16 | 2024-06-06 | 2024-06-28 | 2648007.06 | 2568421.73 |  | 2024-10-03 | 2025-10-17
C15531 | 21393 | 6960(053) | Mill Street: A Street to Centennial Boulevard (Spr | Lane | 2 |  | K & E Excavating, Inc. | 2024-05-16 | 2024-06-13 | 2024-07-08 | 11292639 | 10612534.47 |  | 2024-09-05
C15532 | 23568 | SA00(640) | OR223/OR99W curb ramps (Dallas/Rickreall), phase 1 | POLK | 2 | Paul Tappana | Carter & Company, Inc. | 2024-05-16 | 2024-06-06 | 2024-07-02 | 2022263.54 | 1874821.75 |  | 2024-11-20
C15533 | 22435 | SA00(466) | OR47/OR8/US30 Curb Ramps | Various | 2 |  | Brown Contracting, Inc. | 2024-05-23 | 2024-06-13 | 2024-07-05 | 7430880 |  |  | 2024-09-16
C15536 | 23029 | SA00(671) | Northwest Oregon 2024-2027 ADA curb ramp design build | VARIOUS | 2 |  | K & E Excavating, Inc. | 2024-12-01 | 2024-09-16 | 2025-06-09 | 82246258 | 11765998.89
C15537 | 21255 | SA00(167) | US26/OR213/OR8 Curb Ramps | Various | 1 |  | Brown Contracting, Inc. | 2024-06-20 | 2024-07-11 | 2024-08-06 | 423324 |  |  | 2025-02-25 | 2025-06-06
C15538 | 21617 | S029(036) | OR8: SE Brookwood Ave - OR217 | Washington | 1 | Eric Bortvedt | Aaken Corporation | 2024-07-04 | 2024-07-25 | 2024-08-16 | 1985982 | 1171626.65 |  | 2025-02-10
C15539 | 21602 | S001(540) | I-5: Marquam Bridge - SW Terwilliger Blvd | Multnomah | 1 |  | Carter & Company, Inc. | 2024-07-25 | 2024-08-15 | 2024-08-29 | 3045292 | 1895795.4 |  | 2025-03-10
C15540 | 22020 | 6365(006) | Stewart Park Road: South Umpqua River Bridge (Roseburg) | Douglas | 3 |  | Carter & Company, Inc. | 2024-08-08 | 2024-08-29 | 2024-09-20 | 4482950 | 4356766.57
C15541 | 20539 | S0006(169) | I-84 Frontage Road: Meacham Creek & UPRR | Umatilla | 5 |  | Oregon State Bridge Construction Inc | 2024-08-15 | 2024-09-12 | 2024-10-01 | 6576278.7 |  |  | 2025-03-24
C15542 | 21873 | S012(031) | OR86: Fish Creek | Baker | 5 |  | Marcum & Sons LLC | 2024-08-22 | 2024-09-12 | 2024-10-01 | 2389131.5 | 2343463.21 |  | 2025-02-24 | 2025-10-16
C15543 | 21552 | S031(016) | US20: Harrison Blvd. (Corvallis) | Benton | 2 | Steve Schultz | Knife River Corporation - NW (MDU) | 2024-08-22 | 2024-09-12 | 2024-09-24 | 2964432.7 | 2768030.14 |  | 2025-02-17
C15544 | 21546 | S009(2524) | US101: SE 40th St. - SE 123rd St. | Lincoln | 2 |  | Kerr Contractors Oregon, Inc. | 2024-08-22 | 2024-09-12 | 2024-10-02 | 3667316.56 | 3594523.84 |  | 2025-06-09 | 2025-08-27
C15545 | 21637 | SA00(332) | OR281, OR282 and OR35 Signs, Signals and Lighting | Hood River | 1 |  | HP Civil, Inc | 2024-08-29 | 2024-09-19 | 2024-10-08 | 385677.22 | 384462.32 |  | 2025-01-30 | 2025-04-21 | 2025-11-10
C15546 | 21572 | S072(014) | OR99EB: D St. - Union St. | Marion | 2 |  | HP Civil, Inc | 2024-08-29 | 2024-09-19 | 2024-10-01 | 1249254.14 | 1622005.69 |  | 2025-01-19 | 2025-09-30
C15547 | 21706 | S100(068) | US30: Bridal Veil Falls Bridge | Multnomah | 1 |  | HP Civil, Inc | 2024-09-05 | 2024-09-26 | 2024-10-23 | 882417.77 | 1074878.37 |  | 2024-12-17 | 2025-04-28
C15548 | 22621 | S100(070) | US30 Curb Ramps (Hood River) | Hood River | 1 | Eric Bortvedt | Cascade Civil Corp | 2024-09-05 | 2024-09-26 | 2024-10-09 | 2204725.1 | 2489010.85 |  | 2024-11-12 | 2025-09-29
C15549 | 22458 | 0315(020) | Astoria Riverwalk Trail Lighting | Clatsop | 2 |  | Big River Construction, Inc. | 2024-09-05 | 2024-09-26 | 2024-10-11 | 534934 | 573637.2 |  | 2025-01-03 | 2025-03-25
C15550 | 21766 | S002(238) | I-84: EB McCord Creek Bridge Replacement | Multnomah | 1 |  | Legacy Contracting, Inc | 2024-09-12 | 2024-10-31 | 2024-12-11 | 20365237.86 | 6668098.89 |  | 2025-02-20
C15551 | 21698 | S009(520) | US101: Anderson Rockfall | Curry | 3 | Don Duey | Rock Supremacy LLC | 2024-09-12 | 2024-10-03 | 2024-11-07 | 2141084.88 | 2039854.27 |  | 2025-02-13 | 2025-05-23 | 2025-10-23
C15552 | 20329 | S003(016) | OR43: Willamette Dr at Marylhurst Dr (West Linn) Sec. | Clackamas | 1 |  | Corpac Construction Company | 2024-09-12 | 2024-10-10 | 2024-11-04 | 1631797.45 | 1402856.97 |  | 2025-01-30
C15553 | 21587 | SA00(519) | Sign Replacements (NW Oregon) (21-24) | Clatsop | 2 |  | HP Civil, Inc | 2024-09-19 | 2024-10-10 | 2024-10-18 | 309356.66 | 302108.3 |  | 2025-01-08 | 2025-03-12 | 2025-09-09
C15554 | 20328 | C067(120) | OR8 Corridor Safety & Access to Transit II | Washington | 1 |  | Brown Contracting, Inc. | 2024-09-19 | 2024-10-10 | 2024-10-31 | 677248 | 634444.47 |  | 2024-12-05 | 2025-06-30
C15555 | 20261 | S009(513) | US101: Parkview Dr - Lucky Ln (Brookings) Section | Curry | 3 |  | Tidewater Contractors, Inc. | 2024-09-19 | 2024-10-10 | 2024-10-24 | 3143165 | 2794913.91 |  | 2025-02-26 | 2025-09-10
C15556 | 21756 | S002(242) | US20: Central Oregon Hwy Culverts Corridor Project | Various | 4 |  | K & E Excavating, Inc. | 2024-09-19 | 2024-10-10 | 2024-10-24 | 1136409 | 793234.2 |  | 2025-03-10
C15557 | 21616 | SA00(385) | OR99W: OR217 - SW Sunset Blvd & US30B: Kerby - 162 | Various | 1 | Jason Kelly | Brown Contracting, Inc. | 2024-09-26 | 2024-10-17 | 2024-11-06 | 869169.76 | 709427.5 |  | 2025-02-24 | 2025-06-20
C15558 | 21577 | SA00(396) | Curve Warning Upgrades (NW Oregon) | Various | 2 |  | Cartello Construction Inc | 2024-10-03 | 2024-10-24 | 2024-11-05 | 748309.5 | 527348.32 |  | 2025-03-11 | 2025-09-16
C15559 | 18235 | 3055(010) | Allen Creek Road Improvements | Josephine | 3 |  | HP Civil, Inc | 2024-09-26 | 2024-10-24 | 2024-11-06 | 6014411.06 | 2996548.78 |  | 2025-01-27
C15560 | 21574 | SA00(377) | Rumble Strips (Unit 1 NW Oregon) (2024) | Various | 2 |  | HP Civil, Inc | 2024-09-26 | 2024-10-17 | 2024-10-31 | 1985876.37 | 1679267.44 |  | 2025-06-04
C15561 | 21776 | S009(525) | US101: Floras Creek and Willow Creek bridges | Curry | 3 |  | Cascade Civil Corp | 2024-09-26 | 2024-10-17 | 2024-10-30 | 2774375 |  |  | 2025-02-17 | 2025-08-04
C15562 | 21677 | S035(083) | OR42: Lookingglass Creek to I-5 (Winston) | Douglas | 3 |  | Rocky Mountain Construction LLC | 2024-09-26 | 2024-10-31 | 2024-11-13 | 11966966.96 |  |  | 2025-02-17
C15563 | 21760 | S131(003) | OR131: Tillamook River Bridge | Tillamook | 2 |  | Abhe & Svoboda, Inc. | 2024-09-26 | 2024-10-31 | 2024-11-14 | 1177150 | 899431.24 |  | 2025-06-06
C15564 | 22517 | SA00(469) | I-84: Tower Road - Stanfield | Various | 5 |  | High Desert Aggregate & Paving, Inc. | 2024-10-03 | 2024-11-07 | 2024-12-02 | 13837090 |  |  | 2025-03-10 | 2025-10-24
C15566 | 22383 | S012(032) | OR86: Guardrail Upgrades Final Phase | Baker | 5 |  | Railco LLC | 2024-10-03 | 2024-10-24 | 2024-11-08 | 3398398 | 2425183.06 |  | 2025-05-12
C15567 | 22557 | S018(059) | OR58: Salt Creek Bridge (MP 42.93) | Lane | 2 |  | Hamilton Construction Co. (Oregon) | 2024-11-07 | 2024-12-12 | 2025-01-02 | 13799118.48 | 7317980.63 |  | 2025-02-18
C15568 | 21178 | S026(130) | US26 (Powell Blvd): SE 99th Ave - East City Limits | Multnomah | 1 |  | Moore Excavation, Inc. | 2024-11-07 | 2024-12-17 | 2025-01-10 | 64434239.7 |  |  | 2025-03-25
C15569 | 22611 | S240(010) | OR540/OR241 ADA Curb Ramps (Coos Bay) Proj. | Coos | 3 |  | Brown Contracting, Inc. | 2024-11-21 | 2024-12-12 | 2025-01-06 | 444144.14 | 288293.18 |  | 2025-03-10 | 2025-04-21 | 2025-06-17
C15570 | 22431 | SA00(448) | OR141/OR217 Curb Ramps | Washington | 1 |  | Carter & Company, Inc. | 2024-11-28 | 2024-12-19 | 2025-01-09 | 3285042.7 | 3045357.71 |  | 2025-02-20
C15571 | 21598 | S171(051) | OR224: SE 17th Ave - SE Rusk Road Sec | Clackamas | 1 |  | Wildish Construction Co. | 2024-12-05 | 2025-01-09 | 2025-02-05 |  |  |  | 2025-05-05
C15572 | 22442 | SA00(495) | Sisters and Bend Curb Ramps | Deschutes | 4 | Bill Martin | Brown Contracting, Inc. | 2025-05-15 | 2025-06-05 | 2025-06-18 | 2792423 | 32610.9 |  | 2025-09-15
C15573 | 21773 | S241(008) | OR241: Chandler (Coos River) Bridge | Coos | 3 |  | Abhe & Svoboda, Inc. | 2024-12-26 | 2025-01-30 | 2025-02-13 | 7288400 | 0
C15574 | 23612 | SA00(785) | Portland Metro Area 2024-2027 ADA Curb Ramps Phase 1 | Clackamas | 1 | Eric Bortvedt | Brown Contracting, Inc. | 2024-12-26 | 2025-01-16 | 2025-01-30 | 5995823 | 1551064.91 |  | 2025-07-20
C15575 | 23225 | C059(051) | US730/US395 Umatilla County Signal Safety Improvem | Umatilla | 5 |  | Brown Contracting, Inc. | 2024-12-26 | 2025-01-16 | 2025-01-30 | 247505 | 236319.51 |  | 2025-06-09 | 2025-07-10 | 2025-10-01
C15576 | 23539 | S063(044) | OR99: Transit Signal Upgrades | JACKSON | 3 |  | Northstar Electrical Contractors Inc | 2025-01-02 | 2025-01-23 | 2025-02-04 | 249500 | 95592.9 |  | 2025-08-25
C15577 | 21699 | S001(541) | I-5: Southern Oregon Wrong Way Driver Mitigation | Various | 3 |  | Gage It Construction, LLC | 2025-01-02 | 2025-01-23 | 2025-02-14 | 2410806.9 | 1376467.66 |  | 2025-04-10
C15579 | 22325 | C059(050) | Thorne Hollow Road: Umatilla River Bridge | Umatilla | 5 |  | HP Civil, Inc | 2025-01-09 | 2025-01-30 | 2025-02-13 | 3597771.94 | 2401141.53 |  | 2025-06-16
C15580 | 00031 | SA00(546) | OR47: Messing Creek Bridge (MIST) | Columbia | 3 |  | M J Hughes Construction, Inc. | 2025-01-09 | 1982-12-16 | 2025-02-18 | 2237750.85 | 2206062.95 |  | 2025-04-09
C15581 | 21719 | S035(084) | OR42: US101 to Cedar Point Rd | Coos | 3 |  | LTM Inc | 2025-01-09 | 2025-02-20 | 2025-03-13 | 11768225.02 | 9746575.92 |  | 2025-06-02
C15582 | 23430 | SA00(797) | Umatilla/Morrow County curb ramps phase 2B | Various | 5 |  | Brown Contracting, Inc. | 2025-01-16 | 2025-02-06 | 2025-02-27 | 2598823 | 687309.92 |  | 2025-07-08
C15584 | 21601 | SA00(608) | Portland Metro and Surrounding Areas Variable Mess | Various | 1 |  | Aaken Corporation | 2025-01-16 | 2025-02-06 | 2025-02-21 | 391831 | 359441
C15585 | 22438 | SA00(458) | Jackson County Curb Ramps, Phase 2 | Jackson | 3 |  | HP Civil, Inc | 2025-01-23 | 2025-02-20 | 2025-03-21 | 4489334.33 | 2023641.77 |  | 2025-05-20
C15587 | 22558 | S041(032) | OR126 and US26 curb ramps (Redmond/Prineville) | Various | 4 |  | Cascade Civil Corp | 2025-02-06 | 2025-03-06 | 2025-03-19 | 5687256.5 | 1362668.48 |  | 2025-04-21
C15588 | 23635 | S004(242) | US97: Yew Ave (Redmond) to Quarry Ave Section | Deschutes | 4 |  | Marcum & Sons LLC | 2025-02-06 | 2025-02-27 | 2025-03-28 | 2647955.18 | 2664464.86 |  | 2025-06-09 | 2025-10-10
C15589 | 20331 | 3490(013) | May Street Elevated Sidewalk Replacement | Hood River | 1 |  | Stellar J. Corporation | 2025-02-06 | 2025-02-27 | 2025-03-25 | 1667169.69 | 311358.94 |  | 2025-06-02
C15590 | 23524 | 6710(007) | Ice Age Drive: Oregon St SW Kahlke Ln (Tonquin) | Washington | 1 |  | Canby Excavating | 2025-02-13 | 2025-03-20 | 2025-04-17 | 10130321 | 2087478.21 |  | 2025-06-03
C15591 | 22620 | S004(238) | US97: Chiloquin BR - OR39: Hwy 50 SB over Hwy 4 NB BR | Klamath | 4 |  | Cascade Civil Corp | 2025-02-27 | 2025-03-20 | 2025-04-08 | 1887566.5 | 1801064.1 |  | 2025-05-30 | 2025-12-07
C15592 | 22511 | S027(014) | OR34: Roadside Barrier Upgrades | Various | 2 |  | Knife River Corporation - NW (MDU) | 2025-03-06 | 2025-03-27 | 2025-04-17 | 2927117.7 | 2150609.45 |  | 2025-06-09
C15594 | 22647 | S141(011) | OR141 (SW Hall Blvd): SW Spruce St - SW Hemlock St | Washington | 1 |  | Brown Contracting, Inc. | 2025-03-27 | 2025-03-27 | 2025-04-16 | 997623 | 860916.21 |  | 2025-05-29 | 2025-10-31
C15595 | 21762 | S015(040) | OR126B: Westbound Springfield (Willamette River) | Lane | 2 |  | Carter & Company, Inc. | 2025-03-13 | 2025-04-03 | 2025-04-28 | 1585000.17 | 0 |  | 2025-10-21
C15596 | 23685 | SA00(805) | North Powder/Richland/Halfway curb ramps | VARIOUS | 5 | Chad Maxwell | Eastern Oregon Contracting | 2025-03-20 | 2025-04-17 | 2025-05-23 | 3503690.94 | 933462.36 |  | 2025-09-15
C15597 | 20110 | S009(495) | US101: Depoe Bay Bridge | Lincoln | 2 |  | Carter & Company, Inc. | 2025-03-20 | 2025-05-01 | 2025-05-22 | 8179851.54 | 0
C15598 | 21128 | S092(061) | US30: Watson Rd - Hoge Ave | Multnomah | 1 |  | HP Civil, Inc | 2025-03-27 | 2025-04-17 | 2025-05-05 | 377780 | 0 |  | 2025-08-25 | 2025-10-15
C15599 | 22555 | SA00(486) | OR223/OR99W curb ramps (Dallas/Rickreall) | Polk | 2 | Paul Tappana | R & R General Contractors | 2025-03-27 | 2025-04-17 | 2025-05-13 | 1869000 | 395854.13 |  | 2025-08-18
C15601 | 21674 | S001(549) | I-5: Monument Dr - N. Grants Pass | Josephine | 3 |  | LTM Inc | 2025-04-17 | 2025-05-22 | 2025-06-05 | 16316649.25 |  |  | 2025-09-24
C15602 | 23638 | S064(068) | I-205 Sunnybrook Blvd - Stafford Rd Bus on Shoulde | CLACKAMAS | 1 |  | Brown Contracting, Inc. | 2025-05-01 | 2025-05-22 | 2025-05-30 | 1123321 | 1061421.82 |  | 2025-07-25 | 2025-10-31
C15603 | 18758 | S029(027) | OR8 Operational Improvements | Washington | 1 |  | Brown Contracting, Inc. | 2025-05-15 | 2025-06-05 | 2025-06-30 | 1202232.34 |  |  | 2025-11-03
C15604 | 21718 | S045(454) | OR38: Hinsdale Slough Culvert | Douglas | 3 |  | Carter & Company, Inc. | 2025-06-05 | 2025-06-26 | 2025-07-21 | 322522.5
C15605 | 23692 | SA00(803) | Portland Metro area 2024-2027 ADA curb ramps, phas | WASHINGTON | 1 | Eric Bortvedt | Carter & Company, Inc. | 2025-06-05 | 2025-06-26 | 2025-07-08 | 4529684.77 |  |  | 2025-10-13
C15606 | 23767 | SR05(002) | Myrtle Point/Gold Beach/Brookings/Roseburg curb ramps | VARIOUS | 3 | Paul Tappana | HP Civil, Inc | 2025-07-31 | 2025-08-28 | 2025-09-24 | 2309828.88
C15609 | 23551 | SA00(672) | ODOT Fleet Charging Equipment | STATEWIDE | 4 |  | HP Civil, Inc | 2025-09-04 | 2025-09-25 | 2025-10-09 | 949561.11
C15610 | 23737 | SA00(808) | OR99W/OR153 curb ramps (Amity) | YAMHILL | 2 |  | Interlaken, Inc. | 2025-08-07 | 2025-09-11 | 2025-09-19 | 1379229 | 0
C15611 | 22421 | SA00(436) | Cornelius Pass Hwy: US26 to US30 ITS Improvements | Various | 1 |  | HP Civil, Inc | 2025-08-21 | 2025-09-11 | 2025-09-29 | 1404492.77
C15612 | 23734 | SA00(813) | Portland Metro area 2024-2027 ADA curb ramps, phas | MULTNOMAH | 1 | Eric Bortvedt | Carter & Company, Inc. | 2025-08-21 | 2025-09-18 | 2025-10-09 | 4568023.76
C15613 | 22509 | S037(034) | OR6: Roadside Barrier Upgrades | Various | 2 | Anita Eaton | Carter & Company, Inc. | 2025-08-21 | 2025-09-18 | 2025-10-13 | 6940927.88
C15614 | 22556 | S157(004) | OR18B curb ramps (Willamina/Sheridan) | Various | 2 |  | Brown Contracting, Inc. | 2025-08-21 | 2025-09-11 | 2025-09-26 | 2523423
C15615 | 22773 | S002(253) | I-84: I-5 - Hood River | VARIOUS | 1 |  | Aaken Corporation |  | 2025-10-02 | 2025-11-19 | 722820
C15616 | 22919 | SA00(600) | I-84: Farewell Bend - N. Fork Jacobsen Gulch | Malhuer | 5 |  | HP Civil, Inc |  | 2025-10-30 | 2025-11-26 | 33220273.22
C15617 | 22504 | S002(248) | I-84: Corbett Interchange - Multnomah Falls Phase | Multanoma | 1 |  | Moore Excavation, Inc. |  | 2025-10-02 | 2025-11-20 | 731873.5
C15618 | 23763 | SA00(824) | Portland Metro area 2024-2027 ADA curb ramps, phas | VARIOUS | 1 | Eric Bortvedt | Interlaken, Inc. |  | 2025-10-30 | 2025-12-02 | 4991306
C15621 | 22938 | S001(561) | I-5: Cottage Grove - Martin Creek | Lane | 2 |  | Wildish Construction Co. |  | 2025-10-30 | 2025-11-25 | 8382601.78
C15622 | 22994 | S006(182) | I-84: Roadway Illumination project | VARIOUS | 5 |  | Northstar Electrical Contractors Inc |  | 2025-10-30 | 2025-11-13 | 448660
C15624 | 23755 | SA00(830) | Eastern Oregon 2024-2027 ADA curb ramps, phase 2 | UMATILLA | 5 |  | Moreno & Nelson Construction |  | 2025-10-30 | 2025-11-12 | 3466664.01
K14409 | 14409 | STP-5900(273) | NE Marine Drive Path: NE 112th Ave - NE 185th Ave | Multnomah | 1 | Winston Sandino | Just Bucket Excavating, Inc. |  | 2018-07-04 | 2018-12-21 |  |  |  | 2019-06-03 | 2020-10-21 | 2021-03-01
K16075 | 16075 | STIP-S000(949) | Greenhill Road Rail Xing Safety Project (Eugene) | Lane | 2 | Jim Steers | Wildish Construction Co. |  | 2015-10-15 | 2016-01-28 |  |  |  | 2016-05-05 | 2016-09-30 | 2017-10-02
K16283 | 16283 | C003(041) | Oak Cr - SW Campus Way (Irish Bend) Covered Br #03C30 | Benton | 2 | Bruce Moser | 3 Kings Environmental |  | 2020-03-16 | 2020-06-12 |  |  |  | 2020-07-07 | 2021-01-21 | 2021-06-08
K16587 | 16587 | STP-7515(006) | Delaney Rd Sidewalks & Bikelanes | Marion | 2 | Steve Preszler | KSH Construction LLC |  | 2016-12-29 | 2017-01-30 |  |  |  | 2017-03-28 | 2018-03-27 | 2018-10-25
K17267 | 17267 |  | Twenties Bikeway: NE Lombard - SE Harney Drive | Multnomah | 1 | Rich Newlands | Brown Contracting, Inc. |  | 2016-03-03 | 2017-05-30 |  |  |  | 2016-08-08 | 2017-06-30 | 2019-09-04
K17268 | 17268 | STP-5900(251) | Red Electric Trail: SW Bertha - SW Vermont | Multnomah | 1 | Tim Doherty | M J Hughes Construction, Inc. |  | 2020-12-02 | 2021-02-15 |  |  |  | 2021-03-02 | 2022-12-15 | 2023-10-05
K17312 | 17312 | C047(103) | Traffic Signal Interconnects (Marion County) | Marion | 2 | Steve Preszler | Diamond Testing |  | 2022-02-07 | 2021-12-07 |  |  |  | 2022-02-09 | 2023-11-08
K17408 | 17408 | C005(099) | Pudding River (Whiskey Hill Road) Bridge #01559 | Clackamas | 2 | Stan Monte | Farline Bridge Inc |  | 2015-09-30 | 2016-05-05 |  |  |  | 2016-05-24 | 2017-07-19 | 2018-11-13
K17417 | 17417 | STP-C043(044) | North Santiam River (Stayton-Scio Rd) Bridge | Linn | 2 | Danieal Malone | Legacy Contracting, Inc |  | 2014-12-12 | 2015-02-17 |  |  |  | 2015-02-23 | 2017-05-17 | 2018-04-20
K17472 | 17472 | STP-S000(703) | St Louis Road Rail X'ing Safety Project (Marion) | Marion | 2 |  | K & E Excavating, Inc. |  | 2017-02-20 | 2017-03-15 |  |  |  | 2017-04-25 | 2017-05-30 | 2018-01-10
K17881 | 17881 | C005(101) | SE 122nd Ave & 132nd Ave: Sidewalk Connections | Clackamas | 1 | Bob Knorr | M J Hughes Construction, Inc. |  | 2016-08-08 | 2017-01-04 |  |  |  | 2017-02-27 | 2018-08-21 | 2019-01-07
K17994 | 17994 | 6490(108) | 12th St: (McGilchrist to Fairview) SB Widening | Marion | 2 | John Echeverri | M L Houck Construction Co. |  | 2018-05-15 | 2018-05-04 |  |  |  | 2018-05-17 | 2018-11-12 | 2021-03-03
K18001 | 18001 | S000(899) | Clackamas County Regional Freight ITS Project | Clackamas | 1 | Carl Olson | Diamond Testing |  | 2022-04-28 | 2022-03-31 |  |  |  | 2022-11-17 | 2023-06-21 | 2025-04-23
K18019 | 18019 | C051(098) | Arata Road: 223rd - 238th (Fairview/Wood Village) | Multnomah | 1 | Sara Jeffrey | Wildish Standard Paving Co. |  | 2017-09-28 | 2018-01-08 |  |  |  | 2018-05-04 | 2020-10-30 | 2022-09-12
K18020 | 18020 | C051(103) | Sandy Blvd: 230th Ave - 238th Dr (Wood Village) | Multnomah | 1 | Sara Jeffrey | Kodiak Pacific Construction Co. |  | 2017-05-05 | 2017-07-24 |  |  |  | 2018-03-01 | 2018-10-26 | 2020-04-29
K18021 | 18021 | 5900(253) | East Portland Active Transportation to Transit | Multnomah | 1 | Elizabeth Tillstrom | Brix Paving Company |  | 2018-09-27 | 2018-12-11 |  |  |  | 2019-04-29 | 2020-09-14 | 2021-06-25
K18022 | 18022 | STP-5900(287) | Foster Road Streetscape: SE 50th - SE 84th | Multnomah | 1 | Dan Layden | Wildish Standard Paving Co. |  | 2018-09-27 | 2018-05-10 |  |  |  | 2018-06-15 | 2019-06-14 | 2021-03-09
K18023 | 18023 |  | Burgard/Lombard @ North Time Oil Road Intersection | Multnomah | 1 | Jason Shepard | Wildish Standard Paving Co. | 2017-10-02 | 2017-02-04 | 2018-01-18 |  |  |  | 2018-02-05 | 2018-08-17 | 2020-09-28
K18123 | 18123 | STP-C047(076) | Brown Rd: Arizona Ave - San Francisco Ave (Salem) | Marion | 2 | Steve Preszler | M L Houck Construction Co. |  | 2014-01-09 | 2015-08-11 |  |  |  | 2015-09-09 | 2017-10-21 | 2017-10-24
K18147 | 18147 | C051(097) | NW Cornelius Pass Rd: US30 - NW Kaiser Rd | Multnomah | 1 | Alma Pradeepan | Wildish Standard Paving Co. |  | 2019-04-30 | 2019-04-12 |  |  |  | 2019-06-25 | 2020-10-30 | 2022-04-06
K18212 | 18212 | 6490(093) | Summer Street: Mill Creek Bridge #470218 (Salem) | Marion | 2 | Brian Vinson | Banzer Construction Company |  | 2014-06-17 | 2014-06-17 |  |  |  | 2014-08-18 | 2014-10-15 | 2015-03-03
K18213 | 18213 | ER-6490(095) | Winter St: Shelton Ditch Bridge #470405 (Salem) | Marion | 2 | Troy Thomson | HP Civil, Inc |  | 2014-03-27 | 2015-01-06 |  |  |  | 2015-06-08 | 2016-03-23 | 2017-05-02
K18308 | 18308 | STP-5900(283) | N/NE Columbia Blvd Traffic/Transit Signal Upgrade | Multnomah | 1 | Bikram Raghubansh | Brown Contracting, Inc. |  | 2020-07-04 | 2020-12-07 |  |  |  | 2021-01-20 | 2022-07-22 | 2023-06-26
K18316 | 18316 | 5900(313) | SW Barbur Blvd: SW Caruthers St - SW Capitol Hwy | Various | 1 | Bikram Raghubansh | Standard Utility Contractors, Inc. |  | 2023-02-07 | 2023-02-13 |  |  |  | 2023-04-10 | 2023-09-29
K18410 | 18410 | C047(077) | Silverton Rd: Little Pudding River Br Replacement | Marion | 2 | Steve Preszler | Farline Bridge Inc |  | 2019-12-25 | 2020-11-19 |  |  |  | 2021-03-26 | 2022-06-30 | 2023-09-19
K18416 | 18416 | 5900(262) | Springwater Trail Gap: SE Umatilla - SE 13th Ave | Multnomah | 1 | John Wilson | Pacific Excavation Inc |  | 2018-03-30 | 2018-12-04 |  |  |  | 2019-02-19 | 2019-10-14 | 2020-02-25
K18698 | 18698 | BRO-C043(045) | Old Salem Rd: Truax Creek Bridge Replacement | Linn | 2 | Danieal Malone | HP Civil, Inc |  | 2016-12-25 | 2017-10-17 |  |  |  | 2017-11-10 | 2018-09-21 | 2019-08-09
K18750 | 18750 | C047(082) | Hayesville Dr NE Happy Dr - Fuhrer St Bike/Ped Impvs | Marion | 2 | Shane Ottosen Jr | Carter & Company, Inc. |  | 2022-07-04 | 2022-07-13 |  |  |  | 2022-10-21
K18792 | 18792 | STP-2385(093) | South Bank Path: Knickerbocker Bridge to Walnut St | Lane | 2 | Patrick Cox | 2G ConstructionSTIP_ProjectsSTIP_Projects | 2016-05-18 | 2016-07-22 | 2016-08-05 |  |  |  | 2016-08-29 | 2017-03-14 | 2017-05-10
K18814 | 18814 | STP-5900(284) | Connected Cully | Multnomah | 1 | Kaitlin Littleford | Just Bucket Excavating, Inc. |  | 2020-09-18 | 2021-02-10 |  |  |  | 2021-03-22 | 2023-11-23 | 2024-03-27
K18833 | 18833 | C051(107) | NE 238th Dr: NE Halsey St - NE Glisan St | Multnomah | 1 | Sara Jeffrey | Goodfellow Bros., Inc. |  | 2020-07-04 | 2020-12-29 |  |  |  | 2021-02-26 | 2022-06-03 | 2023-01-20
K18856 | 18856 | 2385(095) | Amazon Active Corridor: Martin Street - 33rd St. | Lane | 2 | Bryan Root | Wildish Construction Co. |  | 2018-09-17 | 2018-09-21 |  |  |  | 2018-10-10 | 2020-01-08 | 2020-04-03
K18859 | 18859 | 2385(091) | Jessen Multiuse Path: Ohio Street - Beltline | Lane | 2 | Katie Markwitz | Brown Contracting, Inc. |  | 2017-09-30 | 2017-12-28 |  |  |  | 2018-04-17 | 2019-04-24 | 2019-07-23
K18860 | 18860 | STP-C039(076) | Bob Straub Pkwy: Mt. Vernon Road Intersection | Lane | 2 |  | Wildish Construction Co. |  | 2016-11-21 | 2017-01-31 |  |  |  | 2017-04-24 | 2017-06-29 | 2017-09-01
K19120 | 19120 | 3125(055) | SE 242nd/Hogan: NE Burnside - E Powell (Gresham) | Multnomah | 1 | Mike Green | Raimore Construction |  | 2022-08-25 | 2022-08-25 |  |  |  | 2022-11-03 | 2023-10-09
K19234 | 19234 | 6490(111) | Brown RD NE: San Francisco - Sunnyview, Sidewalks An | Marion | 2 | Julie Tichbourne | M L Houck Construction Co. |  | 2019-04-16 | 2019-05-01 |  |  |  | 2019-05-28 | 2020-03-16 | 2021-04-13
K19279 | 19279 | STP-3125(056) | Sandy Blvd: NE 181st Ave to East Gresham City Limits | Multnomah | 1 | Will Jones | Goodfellow Bros., Inc. |  | 2020-09-18 | 2020-11-10 |  |  |  | 2021-03-09 | 2021-11-10 | 2024-04-03
K19297 | 19297 | STP-5900(292) | East Portland Access to Employment and Education | Multnomah | 1 | Mauricio Juarez | Kodiak Pacific Construction Co. |  | 2020-12-01 | 2020-10-28 |  |  |  | 2020-12-04 | 2023-01-05
K19303 | 19303 | 5900(296) | N. Going to the Island Freight Project | Multnomah | 1 | Willie Rotich | Tice Electric Company |  | 2019-07-04 | 2020-01-08 |  |  |  | 2020-05-19 | 2020-11-04 | 2021-06-29
K19641 | 19641 | C005(102) | Canby (M J Lee) Ferry Bank Stabilization and ITS P | Clackamas | 1 | Joel Howie | Diamond Testing | 2023-01-25 | 2023-03-08 | 2023-05-11 |  |  |  | 2023-08-28 | 2024-05-10
K19722 | 19722 | 5900(282) | HSIP 2016 Signalized Improvements (Portland) | Multnomah | 1 | Nicole Peirce | Brown Contracting, Inc. |  | 2018-08-30 | 2019-04-19 |  |  |  | 2019-10-01 | 2019-12-19 | 2020-08-13
K19723 | 19723 | 5900(281) | HSIP City of Portland Bikeped | Multnomah | 1 | John Wilson | Brown Contracting, Inc. |  | 2018-09-01 | 2009-01-15 |  |  |  | 2019-06-12 | 2020-01-09 | 2021-07-07
K19740 | 19740 | C047(079) | Lancaster Dr/Macleay Rd Traffic Signal Upgrade | Marion | 2 | Shane Ottosen Jr | Brown Contracting, Inc. |  | 2019-09-01 | 2019-09-05 |  |  |  | 2020-01-02 | 2020-07-29 | 2022-06-30
K19773 | 19773 | 2385(098) | South Willamette Street Enhancement (Eugene) | Lane | 2 | Patrick Cox | Wildish Construction Co. |  | 2019-12-25 | 2020-05-27 |  |  |  | 2020-07-13 | 2022-01-13 | 2022-09-12
K19794 | 19794 | STP-5900(289) | SE 122nd Ave: Johnson Creek Bridge Replacements | Multnomah | 1 | Cameron Glasgow | Cascade Bridge | 2018-01-19 | 2018-04-26 | 2018-05-18 |  |  |  | 2018-07-02 | 2019-05-06 | 2020-06-12
K20165 | 20165 | 2385(100) | 13th Ave: Willamette St. to Alder St. (Eugene) | Lane | 2 | Bryan Root | Wildish Construction Co. |  | 2019-09-01 | 2019-10-28 |  |  |  | 2020-02-07 | 2020-10-14 | 2021-03-23
K20204 | 20204 | 6490(115) | Broadway St. @ Pine St. (Salem) | Marion | 2 | Kyle Cochran | Riverbend Construction, Inc |  | 2022-07-04 | 2023-01-30 |  |  |  | 2023-06-15 | 2024-06-14
K20206 | 20206 | 2385(104) | River Rd. @ Irving Rd. (City of Eugene) | Lane | 2 | Jordan Vesper | Wildish Construction Co. |  | 2022-07-04 | 2023-02-02 |  |  |  | 2023-03-20
K20216 | 20216 | 2385(102) | City of Eugene Signal Enhancements | Various | 2 | Bryan Root | Wildish Construction Co. |  | 2020-09-30 | 2021-02-05 |  |  |  | 2021-06-28 | 2022-02-22 | 2022-06-22
K20294 | 20294 | 2385(109) | Coburg Rd:Ferry St RR Br & Willamette R Br (Eugene) | Various | 2 | Mike Hawkins | HP Civil, Inc |  | 2022-02-07 | 2022-02-07 |  |  |  | 2022-02-28 | 2023-06-09
K20333 | 20333 | 5900(302) | Seventies Neighborhood Greenway | Multnomah | 1 | Tim Bowers | Interlaken, Inc. |  | 2022-12-21 | 2022-12-19 |  |  |  | 2023-03-06 | 2024-04-01
K20382 | 20382 | STP-C051(112) | Morrison Street: Willamette River (Morrison) Br | Multnomah | 1 | Ken Huntley | Southern Road and Bridge, LLC |  | 2020-09-30 | 2021-07-12 |  |  |  | 2021-11-18 | 2024-02-21 | 2024-10-24
K20738 | 20738 | 6490(126) | Hilfiker Ln SE at Commercial St SE (Salem) | Marion | 2 | John Echeverri | Carter & Company, Inc. |  | 2023-07-04 | 2023-12-04
K20740 | 20740 | 3850(017) | River Rd: Shangri-La Ave to Wheatland Rd (Keizer) | Marion | 2 | Steven Tjoelker | Northstar Electrical |  | 2022-04-01 | 2023-03-07 |  |  |  | 2023-10-10
K20743 | 20743 | C047(092) | Hollywood Dr: Silverton Rd to Greenfield Ln (Salem) | Marion | 2 | Mark Foster | Gelco Construction Co. |  | 2022-07-04 | 2022-11-30 |  |  |  | 2023-02-21 | 2023-11-20 | 2025-06-03
K20745 | 20745 | C047(088) | Lancaster Dr: Center St to Monroe Ave (Salem) | Marion | 2 | Mark Foster | Gelco Construction Co. |  | 2022-07-04 | 2022-11-07 |  |  |  | 2023-02-21 | 2024-06-28 | 2025-01-10
K21107 | 21107 | C051(11) | Newberry Road at MP 0.5 | Multnomah | 1 | Storm Beck | Tapani, Inc | 2018-10-23 | 2018-09-27 | 2018-11-02 |  |  |  | 2019-02-13 | 2019-04-17 | 2020-03-05
K21159 | 21159 | 2385(107) | Eugene Enhanced Walking Network | Lane | 2 | Bryan Root | Riverbend Construction, Inc |  | 2022-07-04 | 2022-11-18 |  |  |  | 2023-03-22 | 2024-11-05 | 2025-02-07
K21164 | 21164 | 2385(103) | High Street Protected Bikeway (Eugene) | Lane | 2 | Bryan Root | Brown Contracting, Inc. |  | 2022-07-04 | 2023-03-29 |  |  |  | 2023-05-17 | 2024-04-16
K21168 | 21168 | C039(083) | Howard Elementary & Colin Kelly MS Traffic Congest | Lane | 2 | Steve Templin | Riverbend Construction, Inc | 2022-09-30 | 2022-07-04 | 2022-12-07 |  |  |  | 2023-03-20 | 2023-12-05 | 2024-03-19
K21195 | 21195 | STP-3125(059) | East Multnomah County Road Connections ITS Project | Multnomah | 1 | Jim Gelhar | Northeast Electric, LLC |  | 2020-12-24 | 2020-11-23 |  |  |  | 2021-01-14 | 2022-01-14 | 2023-05-17
K21221 | 21221 | ER-C005(109) | 232nd Drive at MP 0.3 | Clackamas | 1 | Mike Ward | NTA Contracting Inc |  | 2021-06-21 | 2021-07-12 |  |  |  | 2021-11-29 | 2022-04-08
K21378 | 21378 | 2385(108) | 8th Avenue Streetscape and Bikeway | Lane | 2 | Rachel Love | Wildish Construction Co. | 44970 | 44746 | 45033 |  |  |  | 45062 |  | 45630
K21407 | 21407 | 5900(309) | OR99W/SW Barbur Blvd Area: Sidewalk Infill (Portla | Multnomah | 1 | Gary Brittle | Kodiak Pacific Construction Co. |  | 44823 | 44768 |  |  |  | 44879
K21446 | 21446 | 1580(055) | NW Buchanan Ave, NW 11th Street (Corvallis) | Benton | 2 | Josh Bjornstedt | Emery & Sons Construction Group |  | 43650 | 43979 |  |  |  | 44018 | 44040 | 44121
K21448 | 21448 | C043(052) | One Horse Slough (Brewster Road) Bridge (Linn Coun | Linn | 2 | Danieal Malone | H A McCoy Engineering & Surveying LLC |  | 43938 | 43929 |  |  |  | 44004 | 44113 | 44264
K21496 | 21496 | 5900(312) | NE Airport Way Arterial Corridor management | Multnomah | 1 | Bikram Raghubansh | Tice Electric Company |  | 44825 | 44865 |  |  |  | 44833 | 45096 | 45205
K21515 | 21515 | 2385(111) | South Bank Shared Use Path | Lane | 2 | Love Rachel | Brown Contracting, Inc. | 44216 | 44016 | 44186 |  |  |  | 44244 | 44503 | 44677
K21887 | 21887 | 6490(130) | McGilchrist Street SE at 22nd Ave SE (Salem) | Marion | 2 | William Kuenzi | Carter & Company, Inc. |  | 45107 | 45107 |  |  |  | 45202 | 45670
K22493 | 22493 | C047(107) | Marion County Ferry Boat Program (Phase 3a) | Various | 2 | Steve Preszler | HP Civil, Inc |  | 44746 | 44921 |  |  |  | 45106
Updated December 8, 2025