## Project Risk Register
Cost Risk* =
|  |  |  | Key# & Project Name: | [5 empty] | Total Project Cost: |  |  |  |  | Design Sched. Risk = | 0 | [9 empty] | *Cost Risk based on identified risk.
|  |  |  | TPM/RE-CP: | [5 empty] | Construction Cost: |  |  |  |  | Const. Sched. Risk = | 0 | Risk-Based Cont. =
|  |  |  | Area Manager: | [5 empty] | Project Schedule: |  |  |  |  | Total Schedule Risk = | 0
Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months | [8 empty] | Risk Response Plan |  |  |  |  | Monitor and Review
Risk No. | Date Id. | Risk Title | Phase that it impacts | Critical Path? | Nature | Detailed Description of Risk Event | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | $ Impact | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | 6 Impact | Score | Const T RR | Design T RR | Bid Date Variability | Status | Rank | Strategy | Risk Owner | Response action(s) to be taken | Date, Status, and Review Comments | Date Updated |  | Cost Percent | Cost (less than) | Schedule Percent | Schedule (less than) | Threat | Opportunity
1 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | Negligible | 0.5% | 0 | 2% | 0 | Mitigate | Enhance
2 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | Low | 1% | 0 | 4% | 0 | Avoid | Exploit
3 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | Moderate | 2.5% | 0 | 8% | 0 | Accept | Accept
4 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | High | 5% | 0 | 12.5% | 0 | Transfer | Transfer
5 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | Extreme | 5% | 0 | 12.5% | 0
6 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
7 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
8 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
9 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
10 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
11 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
12 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
14 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
15 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
16 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
17 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
18 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
19 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
20 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
21 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
22 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
23 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
24 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
25 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
26 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
27 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
28 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
29 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
30 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
31 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
32 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
33 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
34 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
35 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
36 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
37 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
38 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
39 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
40 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
45 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
46 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
47 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
48 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
49 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
50 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Note on F9: If this risk did occur would it delay the critical path of the project or could it be handled concurrently with critical path activities?
Note on J9: Minimum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on L9: Maximum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on O9: Minimum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Q9: Maximum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Y9: Risk Rank Based on probability, cost, and schedule impact, this column ranks risk with 1 being the most likely & impactful risk

## Example - Project Risk Register
Cost Risk* =
|  |  |  | Key# & Project Name: |  | K12345 Example |  |  |  | Total Project Cost: | 15000000 |  |  |  | Design Sched. Risk = | 3.3 | [6 empty] | 2156468.75 |  |  | *Cost Risk based on identified risk.
|  |  |  | TPM/RE-CP: | [5 empty] | Construction Cost: | 12500000 |  |  |  | Const. Sched. Risk = | 0.8875 | Risk-Based Cont. =
|  |  |  | Area Manager: | [5 empty] | Project Schedule: | 36 |  |  |  | Total Schedule Risk = | 4.1875 | [6 empty] | 17.25%
Risk Identification | [7 empty] | Cost Impact - In Thousands |  |  |  |  | Schedule Impact - In Months | [8 empty] | Risk Response Plan |  |  |  |  | Monitor and Review
Risk No. | Date Id. | Risk Title | Phase that it impacts | Critical Path? | Nature | Detailed Description of Risk Event | Probability | Min $ | Most Likely $ | Max $ | Expected Value $ | $ Impact | Min 6 | Most Likely 6 | Max 6 | Expected Value 6 | 6 Impact | Score | Const T RR | Design T RR | Bid Date Variability | Status | Rank | Strategy | Risk Owner | Response action(s) to be taken | Date, Status, and Review Comments | Date Updated |  | Cost Percent | Cost (less than) | Schedule Percent | Schedule (less than) | Threat | Opportunity
1 | 2020-07-01 | Design exception approval | Design | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Design phase impacts would be additional PE cost and design schedule for design/re-design. | 10% | 75 | 87.5 | 100 | 14375 | Very Low | 2 | 3 | 4 | 0.55 | Very Low | 43250 | 0 | 0.55 | Green | Active | 7 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. |  |  | Negligible | 0.5% | 75000 | 2% | 0.72 | Mitigate | Enhance
2 | 2020-07-01 | Design exception approval | Construction | yes | Threat | The project assumes design exception approval for substandard super-elevation of 13% and a substandard spiral length of 200' for the Exit 400 SB off ramp. If the design exception is not granted the ramp would have to be reconstructed to a max 12% super-elevation for a 2-lane ramp and a min. spiral length of 240'. This would be a substanstial increase in the projects scope. Construction phase impacts include reconstructing the ramp and lengthing the spiral. This would trigger widening of the hwy 999 o'xing structure. | 10% | 2500 | 3750 | 5000 | 687500 | High | 2 | 3 | 4 | 0.55 | Very Low | 716375 | 0.55 | 0 |  | Active | 1 | Avoid | Roadway Designer | 1) Conduct pre-coordination with SPDB to obtain buy-off to minimize the likelihood of rejection. 2) Provide updates/coordination with SPDB as design progresses. 3) Document necessary information regarding Design Exceptions to facilitate communications/understanding. 4) Manage internal resources to ensure timelines for submittals can be achieved. |  |  | Low | 1% | 150000 | 4% | 1.44 | Avoid | Exploit
3 | 2020-09-10 | Bidding Climate - Volume of Work | Construction | no | Threat | High quantity of ODOT statewide projects being bid for 2022 construction may result in higher than expected bid prices due to capacity of industry and availability of contractors. | 50% | 100 | 550 | 1000 | 437500 | High | 0 | 0.005 | 0.01 | 0.00425 | Very Low | 437723.125 | 0 | 0 |  | Active | 2 | Mitigate | TPM | 1) Coordinate with Constructability Review program to engage AGC on direct project review and comment 2) Conduct evaluation of anticipated material volumes for timing of construction and perform outreach to suppliers. |  |  | Moderate | 2.5% | 375000 | 8% | 2.88 | Accept | Accept
4 | 2020-09-20 | Value Engineering study @10% design | Construction | yes | Opportunity | VE studies on average reduce project cost 20% and commonly produces construction schedule savings. If a VE study is conducted then the project cost and schedule may decrease. | 50% | 0 | 2500 | 5000 | 0 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 |  | Retired |  | Enhance | TPM | Coordinate with VE program to conduct value engineering study. | Value engineering study conducted at 10% design. 6 VE alternatives accepted for a total of $3.2 million in cost savings and 4 months of construction schedule reduction | 2021-02-08 | High | 5% | 750000 | 12.5% | 4.5 | Transfer | Transfer
5 | 2020-11-25 | High water table & stormwater facilities | Design | yes | Threat | Design deviation is being pursued for the construction of water quality and quantity facilities within a known high water table. If not approved, other off-site facilities that require ROW would need to be considered. The driver of the high-end costs are acquisitions of additional ROW to construct additional treatment facilities. In terms of schedule, an additional 12 months could be incurred for the additional ROW acquisitions. | 30% | 0 | 300 | 600 | 165000 | Moderate | 0 | 6 | 12 | 3.3 | High | 338250 | 0 | 3.3 | Red | Active | 3 | Avoid | Hydro Lead | 1) Hydro team to submit design deviation for water table depth at water quality and detention facilities. 2) ODOT and Consultant Design team to coordinate on format and information to be provided as part of design deviation information. Updates to be incorporated to facilitate reviews and approval. |  |  | Extreme | 5% | 750000 | 12.5% | 4.5
6 | 2020-11-25 | Utility Potholing | Design | yes | Threat | Potholing is currently scheduled; however, the required data for utility owners may not be received in time. The risk is that the utility owners do not complete the potholing in a timely manner to support the project design development. This will result in additional cost to the project for potholing to capture the data. | 10% | 15 | 17.5 | 20 | 2875 | Very Low | 0 | 0.5 | 1 | 0.125 | Very Low | 9437.5 | 0 | 0.125 | Green | Active | 8 | Mitigate | Utilities | 1) Utility Coordinator actively working with utilities on potholing efforts. 2) Engage in regular communication/coordination on utilities where there is a need for potholing/information.
7 | 2020-11-25 | Contract Length of Deep Foundations | Construction | no | Threat | Foundation lengths have been assumed to be a certain length and may not meet the formal recommendations being developed and to be provided regarding Geotechnical capacity. This could result in an increased foundation length, thereby increasing project costs. | 70% | 0 | 25 | 50 | 28750 | Very Low | 0 | 1 | 2 | 1.15 | Low | 89125 | 0 | 0 |  | Active | 6 | Mitigate | Geotech Lead | 1) Coordination and communication between Geotechnical and Structures for SB lanes in order to develop correct foundation lengths. 2) Once determination is made, update estimate accordingly and retire risk.
8 | 2020-11-25 | Stormwater Facility Sizing | Construction | yes | Threat | Further refinement of water quality and detention facility design may cause increases in facility cost. This could include the introduction of an additional detention facility. The risk is that the plan does not materialize as intended for the subsurface detention facility and there is a need to introduce an additional detention facility on the south side of ODOT Blvd. This item is affected by roadway design element updates, hydro resourcing, and project construction schedule. Considered construction risk only as design schedule should be able to absorb additional design. | 30% | 50 | 150 | 250 | 72500 | Very Low | 0 | 1 | 2 | 0.55 | Very Low | 101375 | 0.55 | 0 |  | Active | 5 | Mitigate | Hydro Lead | 1) Finalize roadway design including pavement sawcut lines; allow sufficient time for hydraulics design. 2) Continue to analyze and revise the tank design for the subsurface stormwater detention facility, including costs/benefits of proprietary tank vendors. 3) Explore options and seek to identify approaches to reduce the size of the tank requirements.
9 | 2020-11-25 | 1" Grind and Inlay | Construction | yes | Threat | The 1-inch grind and inlay may suffer pavement delamination during grind of partial lift of pavement or delamination of new pavement. This would be due to inadequate bond between new and existing ACP resulting in contract change orders and/or delays to repair pavement and additional traffic impacts. Delays are at the tail end of the construction season and would push a season. The recent lift of pavement was completed in 2013. Note that the project is already calling out the use of a fine milling head. | 10% | 50 | 382.5 | 715 | 90625 | Low | 0.5 | 3.75 | 7 | 0.8875 | Low | 137218.75 | 0.8875 | 0 |  | Watch List | 4 | Accept | Resident Engineer | 1) If issues emerge, use a temporary patching operation to address the issue until the next paving season.
10 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
11 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
12 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
13 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
14 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
15 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
16 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
17 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
18 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
19 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
20 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
21 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
22 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
23 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
24 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
25 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
26 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
27 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
28 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
29 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
30 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
31 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
32 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
33 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
34 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
35 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
36 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
37 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
38 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
39 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
40 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
41 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
42 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
43 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
44 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
45 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
46 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
47 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
48 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
49 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
50 | [8 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0
Note on F9: If this risk did occur would it delay the critical path of the project or could it be handled concurrently with critical path activities?
Note on J9: Minimum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on L9: Maximum cost impact, as compared to the base estimate, in thousands if the risk where to occur
Note on O9: Minimum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Q9: Maximum schedule impact, as compared to the base estimate, in thousands if the risk where to occur
Note on Y9: Risk Rank Based on probability, cost, and schedule impact, this column ranks risk with 1 being the most likely & impactful risk

## Guidance
Email the program with questions and/or feedback: |  | Threat Risk Response Actions
Select link >>>> | PRM@ODOT.state.or.us
|  | Avoid: | “Risk avoidance is when the project team acts to eliminate the threat or protect the project from its impact (reducing the probability of occurrence of a risk to 0%). [Risk avoidance] may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact” (PMI, 2017). “There are two types of avoidance action: (1) remove the cause of the risk (risk trigger), or (2) execute the project in a different way while still aiming to achieve project objectives. Not all risks can be avoided or eliminated, and for others this approach may be too expensive or time-consuming. However, this should be the first strategy considered for each risk and should be the primary strategy for high probability or high impact risks” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.
Proper use of this tool assumes familiarity with Project Risk Management concepts. A guide has been developed to assist users in managing projects risks:
https://www.oregon.gov/ODOT/Engineering/Pages/VE-RM.aspx
|  | Transfer: | “Transfer involves shifting ownership of a threat to a third party to manage the risk and to bear the impact if the threat occurs. Risk transfer often involves payment of risk premium to the party taking on the threat. We can transfer risk through a range of actions that include, but are not limited to, the use of insurance, performance bonds, warranties, guarantees and so on. Agreements may be used to transfer ownership and liability for specified risks to another party” (PMI, 2017).
|  | Mitigate: | Take risk response action to reduce impact or probability of occurrence of a risk event. “In risk mitigation, we take action to reduce the probability of occurrence and/or impact of the threat” (PMI, 2017). This is the most common risk response strategy.
|  | Accept: | Risk acceptance acknowledges the existence of a threat, but no proactive action is taken. This strategy may be appropriate for low-priority threats, and it may also be adopted where it is not possible or cost-effective to address a threat in any other way. Acceptance can be either active or passive. “The most common active acceptance strategy is to establish a contingency reserve, including amounts of time, money, or resources to handle the threat if it occurs. Passive acceptance involves no proactive action apart from periodic review of the threat to ensure that it does not change significantly” (PMI, 2017). “Risks that are uncontrollable (no response actions are practical) are also accepted” (Hillson, 2004). Acceptance is a common strategy for risks that have a low probability of occurrence. However, accepted risks that have a very low to low probability of occurrence and very high to extreme impact on project objectives should be closely monitored, as they can have devastating consequences to a project. These occurrences are known as black swan events.
Opportunity Risk Response Actions
|  | Exploit: | The exploit strategy may be selected for the high-priority opportunities where the organization wants to ensure that the opportunity is realized. This strategy seeks to capture the benefit associated with a particular opportunity by ensuring that it definitely happens, increasing the probability of occurrence to 100%. “Examples of exploiting responses may include assigning an organization’s most talented resources to the project to reduce the time to completion, or using new technologies or technology upgrades to reduce cost and duration” (PMI, 2017). Opportunity risks that have high positive impact on project objectives, known as golden opportunities, should be exploited.
|  | Share: | Sharing involves transferring ownership of an opportunity to a third party so that it shares some of the benefit if the opportunity occurs. It is important to select the new of owner of a shared opportunity carefully so they are best able to capture the opportunity for the benefit of the project. “Risk sharing often involves payment of a risk premium to the party taking on the opportunity. Examples of sharing actions include forming risk-sharing partnerships, teams, special-purpose companies, or joint ventures” (PMI, 2017). “Transferring threats and sharing opportunities are similar in that a third party is used. Those to whom threats are transferred take on the liability and those to whom opportunities are allocated should also be allowed to share in the potential benefits” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.
|  | Enhance: | The enhance strategy is used to increase the probability and/or impact of an opportunity. Early enhancement action is often more effective than trying to improve the benefit after the opportunity has occurred. “The probability of occurrence of an opportunity may be increased by focusing attention on its causes. Where it is not possible to increase probability, an enhancement response might increase the impact by targeting factors that drive the size of the potential benefit” (PMI, 2017). “This response aims to modify the size or scope of the positive risk. We enhance the opportunity by increasing its probability, impact or both, thereby maximizing benefits realized for the project. If the probability can be increased to 100% this is effectivity an exploit response” (Hillson, 2004).
|  | Accept: | Accepting an opportunity acknowledges its existence, but we do not take proactive steps to realize it. “This strategy may be appropriate for low-priority opportunities, or those in which it is not possible or cost-effective to address an opportunity in any other way” (PMI, 2017).
“Risk +B3:N49avoidance is when the project team acts to eliminate the threat or protect the project from its impact (reducing the probability of occurrence of a risk to 0%). [Risk avoidance] may be appropriate for high-priority threats with a high probability of occurrence and a large negative impact” (PMI, 2017). “There are two types of avoidance action: (1) remove the cause of the risk (risk trigger), or (2) execute the project in a different way while still aiming to achieve project objectives. Not all risks can be avoided or eliminated, and for others this approach may be too expensive or time-consuming. However, this should be the first strategy considered for each risk and should be the primary strategy for high probability or high impact risks” (Hillson, 2004). Avoidance action should be taken on risks that have a high probability of occurrence and a high impact on project objectives.