## Overview
DETERMINING HOW A FEDERALLY FUNDED LOCAL PUBLIC AGENCY (LPA) PROJECT WILL BE DELIVERED IN OREGON
See the Project Readiness Checklist from the USDOT Grant Application Resources page at: https://www.transportation.gov/grants/dot-navigator/project-readiness-checklist-dot-discretionary-grant-applicants
- Complete the transportation planning process to set your project up for success.
- Plan for how the environmental review and permitting requirements will be met. Consider your project’s civil rights compliance and equity considerations and outcomes.
- Ensure you can secure the non-federal share according to the program’s requirements identified in the notice of funding opportinity ("NOFO").
- Ensure your organization has sound project management systems and sufficient staffing.
- Develop a clear plan for project financing and management of the grant.
- Determine how you will handle ROW. Will the recipient use ODOT's ROW policies or develop their own acquisition management plan?
This workbook has four sections.
1. Overview
2. Fed Disc. Project Delivery Flow
3. Experience Matrix
4. Checklist
Use the information from the Experience Matrix and Federal Discretionary Project Delivery Flow to fill out the Checklist.
The Experience Matrix should be used to help determine the level of staff experience with the nine potential areas of support needed.

## Experience Matrix
Experience Matrix with Delivering Federal Projects |  |  |  |  | column width = 40
Area | Experience |  |  |  | row height = 90
| None | Little | Moderate | High
Contracting – Architectural/ Engineering (A/E) Consultant | Never delivered a Federal Aid project. | Had experience with non-federal aid funds. Or partnered, on projects with federal aid funds, but never led the process. | Have delivered a federal aid project through ODOT as part of the ODOT Delivered Local Agency Project (ODLAP). | Certified local public agency.
23 CFR 172
Civil Rights | Never delivered a Federal Aid project. | Have a basic knowledge of Civil Rights but never/infrequently delivered a Federal Aid Project. Rely heavily on partners, consultants, and ODOT. | Adopts the ODOT process and confers with ODOT Civil Rights office on Civil Rights issues (Title VI/Limited English Proficiency, DBE, ADA and complaint investigations) | Have its own Civil Rights officer that completes and updates its plans (Title VI/Limited English Proficiency, and ADA Transition Plan), ensures DBE Program compliance on LPA's federal projects, investigates complaints/ submits to the Oregon DOT
49 CFR 26
NEPA | Never delivered a Federal Aid project. | Have familiarity with NEPA, but never/infrequently delivered a Federal Aid Project. Rely heavily on partners or consultants. | Have occasionally and successfully delivered Federal Aid Projects. No environmental compliance specialists on staff. Rely on ODOT or A/E consultants to perform this duty. | Have routinely and successfully delivered Federal Aid Projects. Have environmental compliance specialists on staff to support project compliance efforts and/or have A/E consultants perform this duty.
23 CFR 771
Utility Relocation | Never delivered a Federal Aid project. | Have experience in relocating utilities under Oregon State laws. | Have experience in relocating utilities under Oregon State laws and have worked with Oregon DOT to relocate utilities from the rights-of-way needed for a federal aid project. | Have routinely relocated utilities under Oregon State laws for its projects. Have relocated utilities for a federal aid project. Have utility engineers or staff knowledgeable in utility relocations.
23 CFR 645
Railroad | Never delivered a Federal Aid project. | Have experience in cooperating with railroads on past projects. | Have worked with the Oregon DOT to negotiate required railroad agreements on roadway projects. The work was performed with LPA staff and/or A/E consultants. | Have routinely cooperated with railroads to accomplish its projects. Have engineers or staff knowledgeable in railroads requirements.
23 CFR 646
Right-of-Way (ROW) | Never delivered a Federal Aid project. | Have experience in acquiring right-of-way or other properties under ORS 35. | Have worked with the Oregon DOT to deliver right-of-way for a federal aid project. The work was performed with LPA staff and/or A/E consultants. The agency routinely acquires property under ORS 35 in its roadway or other departments. The agency has real estate professionals available to assist. | Have routinely acquired right-of-way under ORS 35 for roadway projects. Have real estate staff knowledgeable in federal aid right-of-way requirements.
23 CFR 710
Contracting – Construction | Never delivered a Federal Aid project. | Have familiarity, but never delivered a Federal Aid Project without ODOT’s assistance. | Have occasionally and successfully delivered Federal Aid Projects. Have staff with some experience in contracting. | Have routinely and successfully delivered Federal Aid Projects. Have staff with a high level of experience in contracting.
23 CFR 630 (preconstruction procedures) , 633 (required contract provisions), 635 (construction and maintenance), 636 (design build contracting)
Materials Testing | Never delivered a Federal Aid project. | Have qualified products from certified suppliers (qualified products list) or catalog cuts supporting delivered products. | Have manufactured products from certified suppliers and certification with a quality system plan (not a full quality assurance plan). | Have full-field statistical testing, a quality assurance plan, and an independent assurance testing system.
23 CFR 637
Inspection (Quality/ Quantity) | No inspection staff / No inspection staff – acceptance of quantities from contractor | No inspection at the source; all inspections performed at the project site / Occasional checks of project site quantities | Occasional quality assurance inspection at the source / Major items or major deliveries are checked to assure quantities are verified | Full quality assurance inspection at the source for all fabricated materials / All work is measured, calculated and paid for with supporting documentation and verified by agency inspection
23 CFR 637

## Checklist-Form (734-5440)
Determining How a Project Will Be Delivered
A. Local Public Agency Information
Local Public Agency (LPA)
LPA Address
Is your LPA a Certified Agency?
Primary Contact for the Discretionary Grant
Name
Title
Phone Number
E-mail Address
B. Project Information
Type of Project |  | Road | Bridge |  | Bike/Ped | Transit | Other
Describe Project
C. Financial Management
Accounting: Is LPA’s accounting system (a) automated, (b) manual, or (c) combination?
Federal Requirements: To meet the requirements of 2 CFR 200 Subparts D and E for federal-aid awards, does LPA have a financial management system that provides for all of the following (a.-g.)? |  | Yes | No
If not, please explain whether the LPA is willing and able to bring its financial management system into compliance with 2 CFR 200 Subparts D and E within a reasonable time (prior to executing grant agreement). | IF NO, TYPE EXPLANATION HERE REPLACING THIS TEXT
a. Identification of all federal awards received and expended and the federal programs under which they were received.
b. Accurate, current, and complete disclosure of the financial results of each federal award or program.
c. Records that adequately identify the source and application of funds for federally funded activities.
d. Effective control over, and accountability for, all funds, property, and other assets.
e. Comparison of expenditures with budget amounts for each federal award.
f. Written procedures to implement the requirements of 2 CFR 200.305 Payment.
g. Written procedures for determining allowable costs in accordance with Subpart E.
Single Audit Act Compliance: Does the LPA comply with the Single Audit Act? If yes, when was the last Single Audit conducted? If there were findings, what were they? |  | Yes | No | IF YES, TYPE EXPLANATION HERE BY REPLACING TEXT
Federal Audits: Has the LPA been audited by the Federal government in the prior three years? If yes, when and were there any findings? |  | Yes | No | IF YES, TYPE EXPLANATION HERE BY REPLACING TEXT
Indirect Costs: The LPA has an approved indirect cost allocation plan and rates for overhead rates? |  | Yes | No
D. Agency Experience
How many FHWA-funded projects does the local agency have at one time?
Staff Experience with: (Use the Experience Matrix to help make these determinations)*
Contracting – Architectural/Engineering (A/E) Consultant |  | None | Little |  | Moderate | High | N/A
Civil Rights |  | None | Little |  | Moderate | High | N/A
NEPA |  | None | Little |  | Moderate | High | N/A
Utility Relocation |  | None | Little |  | Moderate | High | N/A
Railroad |  | None | Little |  | Moderate | High | N/A
Rights-of-Way (ROW) |  | None | Little |  | Moderate | High | N/A
Contracting – Construction |  | None | Little |  | Moderate | High | N/A
Materials Testing |  | None | Little |  | Moderate | High | N/A
Inspection (Quality/Quantity) |  | None | Little |  | Moderate | High | N/A
*If rank none or little in multiple categories, consider asking ODOT or a certified agency to deliver your project.
E. Project Support
Support Needed to Meet Federal-Aid Requirements: (Explain the support needed)**
Contracting – Architectural/Engineering (A/E) Consultant
Civil Rights
NEPA
Utility Relocation
Railroad
Rights-of-Way (ROW)
Contracting – Construction
Materials Testing
Inspection (Quality/Quantity)
How does the LPA want this project to be delivered? |  | ODOT Delivered Local Agency Project (ODLAP)
By a Certified Agency on behalf of LPA (COBO)
LPA Certified Agency
Local Agency Federal Direct (for federal discretionary grants)
ODOT Form (734-5440) rev. 07/23/24
**If ODOT agrees to provide support services on a Local Agency Federal Direct project, the LPA and ODOT shall enter into a project agreement that clarifies ODOT support activities and the anticipated cost. The LPA will be required to provide advance funding, by phase, for ODOT's costs. A deposit payment schedule for the advanced funding may be negotiated between ODOT and the LPA. Since the LPA may only seek reimbursement from FHWA once work has been performed, the advance funding will be locally funded. ODOT will provide the LPA with a cost breakdown for costs incurred for which the LPA may then seek reimbursement from FHWA.