Utilities Coordination

Training Scenarios & Resources

CUG Annual Meeting

December 4, 2025

Scenario Discussion Points for Participants

Project Scenario:

KN01234 Main Street Improvements, Mytown, OR

- Project includes roadway reconstruction and sidewalk widening on a local road or street.

- Acme Telecom Inc. obtained property rights in the project area prior to project.

- ABC Power & Light Co. is located in the public right of way under a local permit or franchise agreement.

Issue 1: Determining Eligibility for Reimbursement

- Is Mytown eligible for federal reimbursement for either of these utilities’ relocation costs?

- Which LAG Sec. C, Chapter 11 subsection(s) support(s) your answer?

- What else might Mytown’s Utility Coordinator need to know to determine eligibility for reimbursement?

Issue 2: Utility Coordination Activities

- What are the likely coordination actions Mytown will need to take prior to PS&E with these utilities?

  - For ABC Power & Light Co. what notifications will be needed?

  - For Acme Telecom Inc. what notifications will be needed?

  - What other elements/activities are likely needed with Acme, assuming the Mytown agrees they are reimbursable?

- Which LAG Sec. C, Chapter 11 subsection(s) support(s) your answer?

- Which other resource(s) might you need to consult to answer this question?

Issue 3: Quality Control for PS&E

- Prior to final PS&E submittal to ODOT, what type of ODOT approval is needed for utility coordination?

- Which LAG Sec. C, Chapter 11 subsection(s) support(s) your answer?

- Based on the following, what issues might the State Utility Liaison request Mytown to resolve prior to signing the Utility Certification form?

- Assume original project facts above.

- Also assume both Acme Telecom Inc. and ABC Power & Light Co. have conflicts and are the only utilities identified for the project.

- “ABC Lights” - the only utility listed under 00150.50(f) Utility Information (No Anticipated Relocations). No contact info shown for ABC Lights.

- Acme Telecom Inc.’s Time Requirements Letter - relocate by August 30, 2026.

- Acme Telecom Inc. - the only utility listed under 00150.50(g) Utility Information (Anticipated Relocations). Contact info is complete, and the estimated completion date is shown as August 30, 2025.

- What issues may be of concern about how the specifications are written?

- What issues may be of concern regarding relocation timing?

Resource Links:

- Local Agency Guidelines Manual, Chapter 11

- ODOT Utility Relocation Manual

- Utility Certification (form 734-5162)

- ODOT 2024 Boilerplate Special Provisions