## Instructions
Planning Level Rough Order of Magnitude (PROM) Instructions |  | Version # | Author | Date | Changes
|  | 1 | Leia Kagawa | 2026-08-26 | Original Version
1 | Create a project tab by copying the "Template" tab
2 | Complete cream colored tabs for rows 1- 6
See ODOT's TransGIS to verify Region
3 | For each component, select a component type in column B, then project component in column C.
See "Components" tab for component descriptions
4 | Complete ROW acquisition cells in columns D & E if applicable or known.
Increase Utility / ROW/ Access Management Risk if unknown.
5 | Indicate Risk factors
See "Risk Worksheet" tab for risk examples
Note: | Add up to 200 components for a project.
Multiples of a single component may be required for a project, see component descriptions.
This tool is not intended for Major-Projects (base year floor >$100,000).
This tool is based off 5-year ODOT bid data and is to be updated yearly.
This tool calculates a rough order of magnitude, not a cost estimate.
This tool does not take the place of an Engineer's Estimate.
See Methodology for more information.

## Template
Planning Project: | [20 empty] | 2026 | [5 empty] | Calc. Factor | 0.056 | 8 | 1.2
Region |  | County |  | Project # | [15 empty] | CE | 0 | 0 |  |  |  |  | Region Cost Factor |  | 10 | 1.25
Planning Horizon |  | Urban Population |  | Total Risk Factor | 1.35 | [14 empty] | PE CE CC | 0 | 0 |  |  |  |  | County Cost Factor |  | 12 | 1.3
Base Year (BY) | 2026 | Future Year (FY) |  | CE Only? | No | [14 empty] | Sum Base Cost | 0 | [5 empty] | Population Cost Factor | 0.056 | 14 | 1.35
Total Cost (BY): (2026 dollars) |  |  | ( dollars) | [23 empty] | BI Year | 2026 | 16 | 1.4
Submitter |  |  |  | Report Date | 2026-08-26 | [21 empty] | AGR | 3.5% | 18 | 1.45
[27 empty] | # Components | 24 | 20 | 1.5
Component # | Type | Component | ROW Type | Required Acres | Complexity Risk | Utility / ROW / AM Risk | Environmental Risk | Estimate Confidence / Scope Creep Risk | ITS or Bridge Preservation | Est. ROW Cost | Risk Factor | 2026 Adjusted Component Construction Cost plus 25% | 2026 PE CE CC | Est. Compexity Contingency | Est. Utility / ROW / AM Contingency | Est. Environmental Contingency | Est. Estimate / Scope Creep Contingency | Est. ITS / Bridge Pres. Contingency | ROW Cost/Acre | Component Baseline U/C | Future Adj CE | Future Adj PE CE CC | Total (Straight) Risk % | Complex Risk % | Utility/ROW AM Risk % | Enviro Risk % | Confident / Scope Creep Risk % | ITS / Bridge Pres Risk % | Risk Adjusted Baseline | Weighted Risk $
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
[5 empty] | Moderate | Moderate | Moderate | Moderate | No | 0 |  |  |  | 0 | 0 | 0 | 0 | n/a | 0 |  |  |  | 16% | 4% | 4% | 4% | 4% | 0% | 0
Note on AO1: Averages ODOT Region, County, and Urban Population factors. Note: that the Region factor is given double weight.
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Region 6 = Statewide
Note on C3: n/a assumes rural up to <80 miles from a major city
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Weighted average of component risk
Note on A4: Or Fiscal Year (submitted)
Note on C4: Anticipated Construction Year
Note on D4: For CIP, 9 years shall be used for estimating purposes
Note on E4: Construction Engineering (CE) Only?
Note on F6: Defaults to today's date, user may override
Note on F9: Moderate = Default
Note on G9: Moderate = Default
Note on H9: Moderate = Default
Note on I9: Moderate = Default
Note on F10: Moderate = Default
Note on G10: Moderate = Default
Note on H10: Moderate = Default
Note on I10: Moderate = Default
Note on F11: Moderate = Default
Note on G11: Moderate = Default
Note on H11: Moderate = Default
Note on I11: Moderate = Default
Note on F12: Moderate = Default
Note on G12: Moderate = Default
Note on H12: Moderate = Default
Note on I12: Moderate = Default
Note on F13: Moderate = Default
Note on G13: Moderate = Default
Note on H13: Moderate = Default
Note on I13: Moderate = Default
Note on F14: Moderate = Default
Note on G14: Moderate = Default
Note on H14: Moderate = Default
Note on I14: Moderate = Default
Note on F15: Moderate = Default
Note on G15: Moderate = Default
Note on H15: Moderate = Default
Note on I15: Moderate = Default
Note on F16: Moderate = Default
Note on G16: Moderate = Default
Note on H16: Moderate = Default
Note on I16: Moderate = Default
Note on F17: Moderate = Default
Note on G17: Moderate = Default
Note on H17: Moderate = Default
Note on I17: Moderate = Default
Note on F18: Moderate = Default
Note on G18: Moderate = Default
Note on H18: Moderate = Default
Note on I18: Moderate = Default
Note on F19: Moderate = Default
Note on G19: Moderate = Default
Note on H19: Moderate = Default
Note on I19: Moderate = Default
Note on F20: Moderate = Default
Note on G20: Moderate = Default
Note on H20: Moderate = Default
Note on I20: Moderate = Default
Note on F21: Moderate = Default
Note on G21: Moderate = Default
Note on H21: Moderate = Default
Note on I21: Moderate = Default
Note on F22: Moderate = Default
Note on G22: Moderate = Default
Note on H22: Moderate = Default
Note on I22: Moderate = Default
Note on F23: Moderate = Default
Note on G23: Moderate = Default
Note on H23: Moderate = Default
Note on I23: Moderate = Default
Note on F24: Moderate = Default
Note on G24: Moderate = Default
Note on H24: Moderate = Default
Note on I24: Moderate = Default
Note on F25: Moderate = Default
Note on G25: Moderate = Default
Note on H25: Moderate = Default
Note on I25: Moderate = Default
Note on F26: Moderate = Default
Note on G26: Moderate = Default
Note on H26: Moderate = Default
Note on I26: Moderate = Default
Note on F27: Moderate = Default
Note on G27: Moderate = Default
Note on H27: Moderate = Default
Note on I27: Moderate = Default
Note on F28: Moderate = Default
Note on G28: Moderate = Default
Note on H28: Moderate = Default
Note on I28: Moderate = Default
Note on F29: Moderate = Default
Note on G29: Moderate = Default
Note on H29: Moderate = Default
Note on I29: Moderate = Default
Note on F30: Moderate = Default
Note on G30: Moderate = Default
Note on H30: Moderate = Default
Note on I30: Moderate = Default
Note on F31: Moderate = Default
Note on G31: Moderate = Default
Note on H31: Moderate = Default
Note on I31: Moderate = Default
Note on F32: Moderate = Default
Note on G32: Moderate = Default
Note on H32: Moderate = Default
Note on I32: Moderate = Default
Note on F33: Moderate = Default
Note on G33: Moderate = Default
Note on H33: Moderate = Default
Note on I33: Moderate = Default
Note on F34: Moderate = Default
Note on G34: Moderate = Default
Note on H34: Moderate = Default
Note on I34: Moderate = Default
Note on F35: Moderate = Default
Note on G35: Moderate = Default
Note on H35: Moderate = Default
Note on I35: Moderate = Default
Note on F36: Moderate = Default
Note on G36: Moderate = Default
Note on H36: Moderate = Default
Note on I36: Moderate = Default
Note on F37: Moderate = Default
Note on G37: Moderate = Default
Note on H37: Moderate = Default
Note on I37: Moderate = Default
Note on F38: Moderate = Default
Note on G38: Moderate = Default
Note on H38: Moderate = Default
Note on I38: Moderate = Default
Note on F39: Moderate = Default
Note on G39: Moderate = Default
Note on H39: Moderate = Default
Note on I39: Moderate = Default
Note on F40: Moderate = Default
Note on G40: Moderate = Default
Note on H40: Moderate = Default
Note on I40: Moderate = Default
Note on F41: Moderate = Default
Note on G41: Moderate = Default
Note on H41: Moderate = Default
Note on I41: Moderate = Default
Note on F42: Moderate = Default
Note on G42: Moderate = Default
Note on H42: Moderate = Default
Note on I42: Moderate = Default
Note on F43: Moderate = Default
Note on G43: Moderate = Default
Note on H43: Moderate = Default
Note on I43: Moderate = Default
Note on F44: Moderate = Default
Note on G44: Moderate = Default
Note on H44: Moderate = Default
Note on I44: Moderate = Default
Note on F45: Moderate = Default
Note on G45: Moderate = Default
Note on H45: Moderate = Default
Note on I45: Moderate = Default
Note on F46: Moderate = Default
Note on G46: Moderate = Default
Note on H46: Moderate = Default
Note on I46: Moderate = Default
Note on F47: Moderate = Default
Note on G47: Moderate = Default
Note on H47: Moderate = Default
Note on I47: Moderate = Default
Note on F48: Moderate = Default
Note on G48: Moderate = Default
Note on H48: Moderate = Default
Note on I48: Moderate = Default
Note on F49: Moderate = Default
Note on G49: Moderate = Default
Note on H49: Moderate = Default
Note on I49: Moderate = Default
Note on F50: Moderate = Default
Note on G50: Moderate = Default
Note on H50: Moderate = Default
Note on I50: Moderate = Default
Note on F51: Moderate = Default
Note on G51: Moderate = Default
Note on H51: Moderate = Default
Note on I51: Moderate = Default
Note on F52: Moderate = Default
Note on G52: Moderate = Default
Note on H52: Moderate = Default
Note on I52: Moderate = Default
Note on F53: Moderate = Default
Note on G53: Moderate = Default
Note on H53: Moderate = Default
Note on I53: Moderate = Default
Note on F54: Moderate = Default
Note on G54: Moderate = Default
Note on H54: Moderate = Default
Note on I54: Moderate = Default
Note on F55: Moderate = Default
Note on G55: Moderate = Default
Note on H55: Moderate = Default
Note on I55: Moderate = Default
Note on F56: Moderate = Default
Note on G56: Moderate = Default
Note on H56: Moderate = Default
Note on I56: Moderate = Default
Note on F57: Moderate = Default
Note on G57: Moderate = Default
Note on H57: Moderate = Default
Note on I57: Moderate = Default
Note on F58: Moderate = Default
Note on G58: Moderate = Default
Note on H58: Moderate = Default
Note on I58: Moderate = Default
Note on F59: Moderate = Default
Note on G59: Moderate = Default
Note on H59: Moderate = Default
Note on I59: Moderate = Default
Note on F60: Moderate = Default
Note on G60: Moderate = Default
Note on H60: Moderate = Default
Note on I60: Moderate = Default
Note on F61: Moderate = Default
Note on G61: Moderate = Default
Note on H61: Moderate = Default
Note on I61: Moderate = Default
Note on F62: Moderate = Default
Note on G62: Moderate = Default
Note on H62: Moderate = Default
Note on I62: Moderate = Default
Note on F63: Moderate = Default
Note on G63: Moderate = Default
Note on H63: Moderate = Default
Note on I63: Moderate = Default
Note on F64: Moderate = Default
Note on G64: Moderate = Default
Note on H64: Moderate = Default
Note on I64: Moderate = Default
Note on F65: Moderate = Default
Note on G65: Moderate = Default
Note on H65: Moderate = Default
Note on I65: Moderate = Default
Note on F66: Moderate = Default
Note on G66: Moderate = Default
Note on H66: Moderate = Default
Note on I66: Moderate = Default
Note on F67: Moderate = Default
Note on G67: Moderate = Default
Note on H67: Moderate = Default
Note on I67: Moderate = Default
Note on F68: Moderate = Default
Note on G68: Moderate = Default
Note on H68: Moderate = Default
Note on I68: Moderate = Default
Note on F69: Moderate = Default
Note on G69: Moderate = Default
Note on H69: Moderate = Default
Note on I69: Moderate = Default
Note on F70: Moderate = Default
Note on G70: Moderate = Default
Note on H70: Moderate = Default
Note on I70: Moderate = Default
Note on F71: Moderate = Default
Note on G71: Moderate = Default
Note on H71: Moderate = Default
Note on I71: Moderate = Default
Note on F72: Moderate = Default
Note on G72: Moderate = Default
Note on H72: Moderate = Default
Note on I72: Moderate = Default
Note on F73: Moderate = Default
Note on G73: Moderate = Default
Note on H73: Moderate = Default
Note on I73: Moderate = Default
Note on F74: Moderate = Default
Note on G74: Moderate = Default
Note on H74: Moderate = Default
Note on I74: Moderate = Default
Note on F75: Moderate = Default
Note on G75: Moderate = Default
Note on H75: Moderate = Default
Note on I75: Moderate = Default
Note on F76: Moderate = Default
Note on G76: Moderate = Default
Note on H76: Moderate = Default
Note on I76: Moderate = Default
Note on F77: Moderate = Default
Note on G77: Moderate = Default
Note on H77: Moderate = Default
Note on I77: Moderate = Default
Note on F78: Moderate = Default
Note on G78: Moderate = Default
Note on H78: Moderate = Default
Note on I78: Moderate = Default
Note on F79: Moderate = Default
Note on G79: Moderate = Default
Note on H79: Moderate = Default
Note on I79: Moderate = Default
Note on F80: Moderate = Default
Note on G80: Moderate = Default
Note on H80: Moderate = Default
Note on I80: Moderate = Default
Note on F81: Moderate = Default
Note on G81: Moderate = Default
Note on H81: Moderate = Default
Note on I81: Moderate = Default
Note on F82: Moderate = Default
Note on G82: Moderate = Default
Note on H82: Moderate = Default
Note on I82: Moderate = Default
Note on F83: Moderate = Default
Note on G83: Moderate = Default
Note on H83: Moderate = Default
Note on I83: Moderate = Default
Note on F84: Moderate = Default
Note on G84: Moderate = Default
Note on H84: Moderate = Default
Note on I84: Moderate = Default
Note on F85: Moderate = Default
Note on G85: Moderate = Default
Note on H85: Moderate = Default
Note on I85: Moderate = Default
Note on F86: Moderate = Default
Note on G86: Moderate = Default
Note on H86: Moderate = Default
Note on I86: Moderate = Default
Note on F87: Moderate = Default
Note on G87: Moderate = Default
Note on H87: Moderate = Default
Note on I87: Moderate = Default
Note on F88: Moderate = Default
Note on G88: Moderate = Default
Note on H88: Moderate = Default
Note on I88: Moderate = Default
Note on F89: Moderate = Default
Note on G89: Moderate = Default
Note on H89: Moderate = Default
Note on I89: Moderate = Default
Note on F90: Moderate = Default
Note on G90: Moderate = Default
Note on H90: Moderate = Default
Note on I90: Moderate = Default
Note on F91: Moderate = Default
Note on G91: Moderate = Default
Note on H91: Moderate = Default
Note on I91: Moderate = Default
Note on F92: Moderate = Default
Note on G92: Moderate = Default
Note on H92: Moderate = Default
Note on I92: Moderate = Default
Note on F93: Moderate = Default
Note on G93: Moderate = Default
Note on H93: Moderate = Default
Note on I93: Moderate = Default
Note on F94: Moderate = Default
Note on G94: Moderate = Default
Note on H94: Moderate = Default
Note on I94: Moderate = Default
Note on F95: Moderate = Default
Note on G95: Moderate = Default
Note on H95: Moderate = Default
Note on I95: Moderate = Default
Note on F96: Moderate = Default
Note on G96: Moderate = Default
Note on H96: Moderate = Default
Note on I96: Moderate = Default
Note on F97: Moderate = Default
Note on G97: Moderate = Default
Note on H97: Moderate = Default
Note on I97: Moderate = Default
Note on F98: Moderate = Default
Note on G98: Moderate = Default
Note on H98: Moderate = Default
Note on I98: Moderate = Default
Note on F99: Moderate = Default
Note on G99: Moderate = Default
Note on H99: Moderate = Default
Note on I99: Moderate = Default
Note on F100: Moderate = Default
Note on G100: Moderate = Default
Note on H100: Moderate = Default
Note on I100: Moderate = Default
Note on F101: Moderate = Default
Note on G101: Moderate = Default
Note on H101: Moderate = Default
Note on I101: Moderate = Default
Note on F102: Moderate = Default
Note on G102: Moderate = Default
Note on H102: Moderate = Default
Note on I102: Moderate = Default
Note on F103: Moderate = Default
Note on G103: Moderate = Default
Note on H103: Moderate = Default
Note on I103: Moderate = Default
Note on F104: Moderate = Default
Note on G104: Moderate = Default
Note on H104: Moderate = Default
Note on I104: Moderate = Default
Note on F105: Moderate = Default
Note on G105: Moderate = Default
Note on H105: Moderate = Default
Note on I105: Moderate = Default
Note on F106: Moderate = Default
Note on G106: Moderate = Default
Note on H106: Moderate = Default
Note on I106: Moderate = Default
Note on F107: Moderate = Default
Note on G107: Moderate = Default
Note on H107: Moderate = Default
Note on I107: Moderate = Default
Note on F108: Moderate = Default
Note on G108: Moderate = Default
Note on H108: Moderate = Default
Note on I108: Moderate = Default
Note on F109: Moderate = Default
Note on G109: Moderate = Default
Note on H109: Moderate = Default
Note on I109: Moderate = Default
Note on F110: Moderate = Default
Note on G110: Moderate = Default
Note on H110: Moderate = Default
Note on I110: Moderate = Default
Note on F111: Moderate = Default
Note on G111: Moderate = Default
Note on H111: Moderate = Default
Note on I111: Moderate = Default
Note on F112: Moderate = Default
Note on G112: Moderate = Default
Note on H112: Moderate = Default
Note on I112: Moderate = Default
Note on F113: Moderate = Default
Note on G113: Moderate = Default
Note on H113: Moderate = Default
Note on I113: Moderate = Default
Note on F114: Moderate = Default
Note on G114: Moderate = Default
Note on H114: Moderate = Default
Note on I114: Moderate = Default
Note on F115: Moderate = Default
Note on G115: Moderate = Default
Note on H115: Moderate = Default
Note on I115: Moderate = Default
Note on F116: Moderate = Default
Note on G116: Moderate = Default
Note on H116: Moderate = Default
Note on I116: Moderate = Default
Note on F117: Moderate = Default
Note on G117: Moderate = Default
Note on H117: Moderate = Default
Note on I117: Moderate = Default
Note on F118: Moderate = Default
Note on G118: Moderate = Default
Note on H118: Moderate = Default
Note on I118: Moderate = Default
Note on F119: Moderate = Default
Note on G119: Moderate = Default
Note on H119: Moderate = Default
Note on I119: Moderate = Default
Note on F120: Moderate = Default
Note on G120: Moderate = Default
Note on H120: Moderate = Default
Note on I120: Moderate = Default
Note on F121: Moderate = Default
Note on G121: Moderate = Default
Note on H121: Moderate = Default
Note on I121: Moderate = Default
Note on F122: Moderate = Default
Note on G122: Moderate = Default
Note on H122: Moderate = Default
Note on I122: Moderate = Default
Note on F123: Moderate = Default
Note on G123: Moderate = Default
Note on H123: Moderate = Default
Note on I123: Moderate = Default
Note on F124: Moderate = Default
Note on G124: Moderate = Default
Note on H124: Moderate = Default
Note on I124: Moderate = Default
Note on F125: Moderate = Default
Note on G125: Moderate = Default
Note on H125: Moderate = Default
Note on I125: Moderate = Default
Note on F126: Moderate = Default
Note on G126: Moderate = Default
Note on H126: Moderate = Default
Note on I126: Moderate = Default
Note on F127: Moderate = Default
Note on G127: Moderate = Default
Note on H127: Moderate = Default
Note on I127: Moderate = Default
Note on F128: Moderate = Default
Note on G128: Moderate = Default
Note on H128: Moderate = Default
Note on I128: Moderate = Default
Note on F129: Moderate = Default
Note on G129: Moderate = Default
Note on H129: Moderate = Default
Note on I129: Moderate = Default
Note on F130: Moderate = Default
Note on G130: Moderate = Default
Note on H130: Moderate = Default
Note on I130: Moderate = Default
Note on F131: Moderate = Default
Note on G131: Moderate = Default
Note on H131: Moderate = Default
Note on I131: Moderate = Default
Note on F132: Moderate = Default
Note on G132: Moderate = Default
Note on H132: Moderate = Default
Note on I132: Moderate = Default
Note on F133: Moderate = Default
Note on G133: Moderate = Default
Note on H133: Moderate = Default
Note on I133: Moderate = Default
Note on F134: Moderate = Default
Note on G134: Moderate = Default
Note on H134: Moderate = Default
Note on I134: Moderate = Default
Note on F135: Moderate = Default
Note on G135: Moderate = Default
Note on H135: Moderate = Default
Note on I135: Moderate = Default
Note on F136: Moderate = Default
Note on G136: Moderate = Default
Note on H136: Moderate = Default
Note on I136: Moderate = Default
Note on F137: Moderate = Default
Note on G137: Moderate = Default
Note on H137: Moderate = Default
Note on I137: Moderate = Default
Note on F138: Moderate = Default
Note on G138: Moderate = Default
Note on H138: Moderate = Default
Note on I138: Moderate = Default
Note on F139: Moderate = Default
Note on G139: Moderate = Default
Note on H139: Moderate = Default
Note on I139: Moderate = Default
Note on F140: Moderate = Default
Note on G140: Moderate = Default
Note on H140: Moderate = Default
Note on I140: Moderate = Default
Note on F141: Moderate = Default
Note on G141: Moderate = Default
Note on H141: Moderate = Default
Note on I141: Moderate = Default
Note on F142: Moderate = Default
Note on G142: Moderate = Default
Note on H142: Moderate = Default
Note on I142: Moderate = Default
Note on F143: Moderate = Default
Note on G143: Moderate = Default
Note on H143: Moderate = Default
Note on I143: Moderate = Default
Note on F144: Moderate = Default
Note on G144: Moderate = Default
Note on H144: Moderate = Default
Note on I144: Moderate = Default
Note on F145: Moderate = Default
Note on G145: Moderate = Default
Note on H145: Moderate = Default
Note on I145: Moderate = Default
Note on F146: Moderate = Default
Note on G146: Moderate = Default
Note on H146: Moderate = Default
Note on I146: Moderate = Default
Note on F147: Moderate = Default
Note on G147: Moderate = Default
Note on H147: Moderate = Default
Note on I147: Moderate = Default
Note on F148: Moderate = Default
Note on G148: Moderate = Default
Note on H148: Moderate = Default
Note on I148: Moderate = Default
Note on F149: Moderate = Default
Note on G149: Moderate = Default
Note on H149: Moderate = Default
Note on I149: Moderate = Default
Note on F150: Moderate = Default
Note on G150: Moderate = Default
Note on H150: Moderate = Default
Note on I150: Moderate = Default
Note on F151: Moderate = Default
Note on G151: Moderate = Default
Note on H151: Moderate = Default
Note on I151: Moderate = Default
Note on F152: Moderate = Default
Note on G152: Moderate = Default
Note on H152: Moderate = Default
Note on I152: Moderate = Default
Note on F153: Moderate = Default
Note on G153: Moderate = Default
Note on H153: Moderate = Default
Note on I153: Moderate = Default
Note on F154: Moderate = Default
Note on G154: Moderate = Default
Note on H154: Moderate = Default
Note on I154: Moderate = Default
Note on F155: Moderate = Default
Note on G155: Moderate = Default
Note on H155: Moderate = Default
Note on I155: Moderate = Default
Note on F156: Moderate = Default
Note on G156: Moderate = Default
Note on H156: Moderate = Default
Note on I156: Moderate = Default
Note on F157: Moderate = Default
Note on G157: Moderate = Default
Note on H157: Moderate = Default
Note on I157: Moderate = Default
Note on F158: Moderate = Default
Note on G158: Moderate = Default
Note on H158: Moderate = Default
Note on I158: Moderate = Default
Note on F159: Moderate = Default
Note on G159: Moderate = Default
Note on H159: Moderate = Default
Note on I159: Moderate = Default
Note on F160: Moderate = Default
Note on G160: Moderate = Default
Note on H160: Moderate = Default
Note on I160: Moderate = Default
Note on F161: Moderate = Default
Note on G161: Moderate = Default
Note on H161: Moderate = Default
Note on I161: Moderate = Default
Note on F162: Moderate = Default
Note on G162: Moderate = Default
Note on H162: Moderate = Default
Note on I162: Moderate = Default
Note on F163: Moderate = Default
Note on G163: Moderate = Default
Note on H163: Moderate = Default
Note on I163: Moderate = Default
Note on F164: Moderate = Default
Note on G164: Moderate = Default
Note on H164: Moderate = Default
Note on I164: Moderate = Default
Note on F165: Moderate = Default
Note on G165: Moderate = Default
Note on H165: Moderate = Default
Note on I165: Moderate = Default
Note on F166: Moderate = Default
Note on G166: Moderate = Default
Note on H166: Moderate = Default
Note on I166: Moderate = Default
Note on F167: Moderate = Default
Note on G167: Moderate = Default
Note on H167: Moderate = Default
Note on I167: Moderate = Default
Note on F168: Moderate = Default
Note on G168: Moderate = Default
Note on H168: Moderate = Default
Note on I168: Moderate = Default
Note on F169: Moderate = Default
Note on G169: Moderate = Default
Note on H169: Moderate = Default
Note on I169: Moderate = Default
Note on F170: Moderate = Default
Note on G170: Moderate = Default
Note on H170: Moderate = Default
Note on I170: Moderate = Default
Note on F171: Moderate = Default
Note on G171: Moderate = Default
Note on H171: Moderate = Default
Note on I171: Moderate = Default
Note on F172: Moderate = Default
Note on G172: Moderate = Default
Note on H172: Moderate = Default
Note on I172: Moderate = Default
Note on F173: Moderate = Default
Note on G173: Moderate = Default
Note on H173: Moderate = Default
Note on I173: Moderate = Default
Note on F174: Moderate = Default
Note on G174: Moderate = Default
Note on H174: Moderate = Default
Note on I174: Moderate = Default
Note on F175: Moderate = Default
Note on G175: Moderate = Default
Note on H175: Moderate = Default
Note on I175: Moderate = Default
Note on F176: Moderate = Default
Note on G176: Moderate = Default
Note on H176: Moderate = Default
Note on I176: Moderate = Default
Note on F177: Moderate = Default
Note on G177: Moderate = Default
Note on H177: Moderate = Default
Note on I177: Moderate = Default
Note on F178: Moderate = Default
Note on G178: Moderate = Default
Note on H178: Moderate = Default
Note on I178: Moderate = Default
Note on F179: Moderate = Default
Note on G179: Moderate = Default
Note on H179: Moderate = Default
Note on I179: Moderate = Default
Note on F180: Moderate = Default
Note on G180: Moderate = Default
Note on H180: Moderate = Default
Note on I180: Moderate = Default
Note on F181: Moderate = Default
Note on G181: Moderate = Default
Note on H181: Moderate = Default
Note on I181: Moderate = Default
Note on F182: Moderate = Default
Note on G182: Moderate = Default
Note on H182: Moderate = Default
Note on I182: Moderate = Default
Note on F183: Moderate = Default
Note on G183: Moderate = Default
Note on H183: Moderate = Default
Note on I183: Moderate = Default
Note on F184: Moderate = Default
Note on G184: Moderate = Default
Note on H184: Moderate = Default
Note on I184: Moderate = Default
Note on F185: Moderate = Default
Note on G185: Moderate = Default
Note on H185: Moderate = Default
Note on I185: Moderate = Default
Note on F186: Moderate = Default
Note on G186: Moderate = Default
Note on H186: Moderate = Default
Note on I186: Moderate = Default
Note on F187: Moderate = Default
Note on G187: Moderate = Default
Note on H187: Moderate = Default
Note on I187: Moderate = Default
Note on F188: Moderate = Default
Note on G188: Moderate = Default
Note on H188: Moderate = Default
Note on I188: Moderate = Default
Note on F189: Moderate = Default
Note on G189: Moderate = Default
Note on H189: Moderate = Default
Note on I189: Moderate = Default
Note on F190: Moderate = Default
Note on G190: Moderate = Default
Note on H190: Moderate = Default
Note on I190: Moderate = Default
Note on F191: Moderate = Default
Note on G191: Moderate = Default
Note on H191: Moderate = Default
Note on I191: Moderate = Default
Note on F192: Moderate = Default
Note on G192: Moderate = Default
Note on H192: Moderate = Default
Note on I192: Moderate = Default
Note on F193: Moderate = Default
Note on G193: Moderate = Default
Note on H193: Moderate = Default
Note on I193: Moderate = Default
Note on F194: Moderate = Default
Note on G194: Moderate = Default
Note on H194: Moderate = Default
Note on I194: Moderate = Default
Note on F195: Moderate = Default
Note on G195: Moderate = Default
Note on H195: Moderate = Default
Note on I195: Moderate = Default
Note on F196: Moderate = Default
Note on G196: Moderate = Default
Note on H196: Moderate = Default
Note on I196: Moderate = Default
Note on F197: Moderate = Default
Note on G197: Moderate = Default
Note on H197: Moderate = Default
Note on I197: Moderate = Default
Note on F198: Moderate = Default
Note on G198: Moderate = Default
Note on H198: Moderate = Default
Note on I198: Moderate = Default
Note on F199: Moderate = Default
Note on G199: Moderate = Default
Note on H199: Moderate = Default
Note on I199: Moderate = Default
Note on F200: Moderate = Default
Note on G200: Moderate = Default
Note on H200: Moderate = Default
Note on I200: Moderate = Default
Note on F201: Moderate = Default
Note on G201: Moderate = Default
Note on H201: Moderate = Default
Note on I201: Moderate = Default
Note on F202: Moderate = Default
Note on G202: Moderate = Default
Note on H202: Moderate = Default
Note on I202: Moderate = Default
Note on F203: Moderate = Default
Note on G203: Moderate = Default
Note on H203: Moderate = Default
Note on I203: Moderate = Default
Note on F204: Moderate = Default
Note on G204: Moderate = Default
Note on H204: Moderate = Default
Note on I204: Moderate = Default
Note on F205: Moderate = Default
Note on G205: Moderate = Default
Note on H205: Moderate = Default
Note on I205: Moderate = Default
Note on F206: Moderate = Default
Note on G206: Moderate = Default
Note on H206: Moderate = Default
Note on I206: Moderate = Default
Note on F207: Moderate = Default
Note on G207: Moderate = Default
Note on H207: Moderate = Default
Note on I207: Moderate = Default
Note on F208: Moderate = Default
Note on G208: Moderate = Default
Note on H208: Moderate = Default
Note on I208: Moderate = Default
NOTE:
Base Cost Estimates include estimated Project Engineering, Construction Administration, and General Construction Contingency costs.
This tool is not intended for Major-projects with minimum Base Year total costs exceeding $100,000,000.
Have a mega-project or don't see a component you need?
Contact: ODOTCostEstimating@odot.oregon.gov

## Components
https://ordot-my.sharepoint.com/personal/leia_kagawa_odot_oregon_gov/Documents/Planning_Cost_Estimating_Tool/[Typical_Sections.xlsx]Project Components'! |  |  |  |  | 2026-08-26 | 8 | 24 | 10 | 18 | 18 | 15 | 8 | 1
[6 empty] | Bike_Ped | Bridge | Hydraulics | Intersection | Pavement | Roadway | Utility
Description | TYPE | Cost | Full Description | Row # |  | Bike_Ped | Bridge | Hydraulics | Intersection | Pavement | Roadway | Utility
Stormsewer (≤ 0.5 mile) | Utility | 875110.96 | New 18" pipe for storm sewer facilities for up to 0.5 miles on both sides of the highway | 4 |  | RRFB w/out Median Refuge | Bridge Prep (No diversion bridge) | Channel/Stream Re-alignment | Add Single Right Turn Lane (Slow) | Pavement Preservation General (≤1 mi: 1-lane) | Traffic Separator (100') | Stormsewer (≤ 0.5 mile)
Sanitary (≤ 0.5 mile) | Utility | 1694158.19 | 18" pipe for sanitary sewer facilities for up to 0.5 miles on both sides of the highway | 5 |  | RRFB w/ Median Refuge | Deck Rehabilitation (Single lane, ≤100ft) | Culvert Renewal / Rehabilitation (<36") | Add Single Right Turn Lane (Fast) | Pavement Preservation Urban (≤1 mi: 2-Shoulders) | Guardrail (250') | Sanitary (≤ 0.5 mile)
Potable Water (≤ 0.5 mile) | Utility | 590300.01 | 18" pipe for potable water facilities for up to 0.5 miles on both sides of the highway | 6 |  | Multi-Use Path (500') | Deck Rehabilitation (Single lane, ≤ 500ft) | Culvert Renewal / Rehabilitation (≥36") | Right Turn Acceleration Lane | Pavement Preservation Rural (≤1 mi: 2-Shoulders) | Soundwall (0.25 mi) | Potable Water (≤ 0.5 mile)
Railroad Crossing Rehabilitation (2-lanes) | Utility | 163672.26 | Accounts for the improvement of a railroad crossing and includes 100' asphalt in both direction tie-ins, pavement markings and signs. | 7 |  | Separate Sidewalk (500') | Deck Rehabilitation (Single lane, ≤1000ft) | Bank Protection | Restripe for Left Turn Lane | Pavement Rehabilitation General (≤1 mi: 1-lane) | Median Cable Barrier (3 MI) | Railroad Crossing Rehabilitation (2-lanes)
Railroad Crossing Rehabilitation (4-lanes) | Utility | 327344.52 | Accounts for the improvement of a railroad crossing and includes 100' asphalt in both direction tie-ins, pavement markings and signs. | 8 |  | Curb-line Sidewalk (500') | Bridge Replacement (Single lane, ≤100ft) | Culvert Replacement (≤ 10' Deep) | Add Single Left Turn Lane | Pavement Rehabilitation Urban (≤1 mi: 2-Shoulders) | Median Concrete Barrier (3 MI) | Railroad Crossing Rehabilitation (4-lanes)
Channel/Stream Re-alignment | Hydraulics | 140319.73 | Assumes major channel re-alignment includes streambed enhancement | 9 |  |  | Bridge Replacement (Single lane, ≤ 500ft) | Culvert Replacement (> 10' Deep) | Channelized Left Turn Lane with Median | Pavement Rehabilitation Rural (≤1 mi: 2-Shoulders) | New Variable Message Signs
Culvert Renewal / Rehabilitation (<36") | Hydraulics | 214746.94 | Installing a new internal lining system within an existing structure to restore hydraulic capacity, improve structural integrity, and extend service life while minimizing disruption to surrounding infrastructure. | 10 |  |  | Bridge Replacement (Single lane, ≤1000ft) | Structural Culvert Replacement | T-Intersection Left Turn Bypass | Pavement Preservation Freeway (≤1 mi: 2-Shoulders) | Replace Variable Message Signs
Culvert Renewal / Rehabilitation (≥36") | Hydraulics | 418053.88 | Installing a new internal lining system within an existing structure to restore hydraulic capacity, improve structural integrity, and extend service life while minimizing disruption to surrounding infrastructure. | 11 |  |  | Box Culvert Replacement |  | Restricted Crossing U-Turn (R-Cut) | Pavement Rehabilitation Freeway (≤1 mi: 2-Shoulders) | Street Illumination (≤100ft)
Bank Protection | Hydraulics | 224275 | Adds Bank Protection and Streambed Enhancement (Typically required for Box Culvert / Bridge projects) | 12 |  |  | Bridge Rail Retrofit (≤ 500 ft) |  | Median U-Turn (MUT) | Recessed Pavement Markers RPM (≤1 mi: 1-line) | Fence (100')
Bridge Prep (No diversion bridge) | Bridge | 329214.05 | Bridge removal, detour, containment, class 2 prep, membrane, joints (may need diversion bridge with temp access) | 13 |  |  | Bridge Protective Screening (350 Feet) |  | Roundabout (Single Lane) | Pavement Preservation Interchange Ramps (1-side: Exit & Entrance) | Wildlife Fence (≤ 500)
Deck Rehabilitation (Single lane, ≤100ft) | Bridge | 205380.52 | Deck rehabilitation using hydro-demolition involves the removal of deteriorated concrete with high-pressure water jets to preserve sound material and reinforcement, followed by surface preparation and placement of new concrete to restore structural integrity and extend service life. A single lane for a bridge up to 100'. Add multiple of this component for multiple lanes, and 300' total of Mill/Fill. Example: 3-lane bridge requires 3x of this component | 14 |  |  | Bridge Rehab - Paint (≤ 100 ft) |  | Roundabout (Double Lane) | Pavement Rehabilitation Interchange Ramps (1-side: Exit & Entrance) | Striping 1-lane (≤3 mi)
Deck Rehabilitation (Single lane, ≤ 500ft) | Bridge | 1026902.61 | Deck rehabilitation using hydro-demolition involves the removal of deteriorated concrete with high-pressure water jets to preserve sound material and reinforcement, followed by surface preparation and placement of new concrete to restore structural integrity and extend service life. A single lane for a bridge up to 500'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. Example: 3-lane bridge requires 3x of this component | 15 |  |  | Bridge Overlay, non-structural 1-lane (≤ 100 ft) |  | Transverse Rumble Strips | Full Reconstruction (≤ 0.25 MI 1-lane) | New Signs (≤ 100)
Deck Rehabilitation (Single lane, ≤1000ft) | Bridge | 2043612.96 | Deck rehabilitation using hydro-demolition involves the removal of deteriorated concrete with high-pressure water jets to preserve sound material and reinforcement, followed by surface preparation and placement of new concrete to restore structural integrity and extend service life. A single lane for a bridge up to 1000'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. Example: 3-lane bridge requires 3x of this component | 16 |  |  | Bridge Overlay, non-structural 1-lane (≤ 500 ft) |  | Dynamic Warning Signs | Rural Highway Widening (≤ 0.25 MI)
Bridge Replacement (Single lane, ≤100ft) | Bridge | 1876050.71 | A single lane for a bridge up to 100'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended) Example: 3-lane bridge requires 3x of this component | 17 |  |  | Bridge Strengthening |  | New Signal Installation | Add Passing Lane
Bridge Replacement (Single lane, ≤ 500ft) | Bridge | 9006050.71 | A single lane for a bridge up to 500'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended.) Example: 3-lane bridge requires 3x of this component | 18 |  |  | New Bridge (Single lane, ≤100ft) |  | Replace Signal | New 1-lane road (≤0.25 mi)
Bridge Replacement (Single lane, ≤1000ft) | Bridge | 17918550.71 | A single lane for a bridge up to 1000'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended.) Example: 3-lane bridge requires 3x of this component | 19 |  |  | New Bridge (Single lane, ≤ 500ft)
Box Culvert Replacement | Bridge | 2979613.63 | Construct new box culvert, includes temporary road and access. Assumes 3-lanes and 300' total of mill/fill. (Adding a components for Bank Protection recommended.) | 20 |  |  | New Bridge (Single lane, ≤1000ft)
Bridge Rail Retrofit (≤ 500 ft) | Bridge | 417310.29 | Bridge rail retrofit includes saw-cutting, near surface rebar repair, and new bridge rail bridge demolition | 21 |  |  | Bridge Overlay, structural 1-lane (≤ 100 ft)
Bridge Protective Screening (350 Feet) | Bridge | 201586.05 | Constructs fall-protection / anti-throw screens on bridges | 22 |  |  | Bridge Overlay, structural 1-lane (≤ 500 ft)
Bridge Rehab - Paint (≤ 100 ft) | Bridge | 1665000 | Bridge painting for bridges up to 100' | 23 |  |  | Bridge Rehabilitation - Mechanical / Electrical
Bridge Overlay, non-structural 1-lane (≤ 100 ft) | Bridge | 45865.63 | Non-structural bridge overlays (PPC or ACWS) for 1-lane for bridges up to 100'. And striping and add as many of this item to equate the number of lanes. | 24 |  |  | Substructure Rehabilitation (1 bent)
Bridge Overlay, non-structural 1-lane (≤ 500 ft) | Bridge | 229328.17 | Non-structural bridge overlays (PPC or ACWS) for 1-lane for bridges up to 500'. And striping and add as many of this item to equate the number of lanes. | 25
Pavement Preservation General (≤1 mi: 1-lane) | Pavement | 151675 | Up to 1-mile 3" mill/fill for 1-lane Includes longitudinal pavement markings. (Needs shoulder components. Add multiples of this component as needed. May need utility items if in an urban setting) | 26
Pavement Preservation Urban (≤1 mi: 2-Shoulders) | Pavement | 191030.92 | Up to 1-mile URBAN 3" mill/fill for 2-shoulders Includes crosswalk markings and bike legends (May need sidewalk infill, signals, RRFBs, etc.) | 27
Pavement Preservation Rural (≤1 mi: 2-Shoulders) | Pavement | 174925 | Up to 1-mile RURAL 3" mill/fill for 2-shoulders | 28
Pavement Rehabilitation General (≤1 mi: 1-lane) | Pavement | 257175 | Up to 1-mile 5" mill/fill for 1-lane Includes longitudinal pavement markings. (Needs shoulder components. Add multiples of this component as needed. May need utility items if in an urban setting) | 29
Pavement Rehabilitation Urban (≤1 mi: 2-Shoulders) | Pavement | 296530.92 | Up to 1-mile URBAN 5" mill/fill for 2-shoulders Includes crosswalk markings and bike legends (May need sidewalk infill, signals, RRFBs, concrete barrier) | 30
Pavement Rehabilitation Rural (≤1 mi: 2-Shoulders) | Pavement | 280425 | Up to 1-mile RURAL 5" mill/fill for 2-shoulders (May need cable barrier) | 31
Pavement Preservation Freeway (≤1 mi: 2-Shoulders) | Pavement | 174925 | Up to 1-mile FREEWAY 3" mill/fill for 2-shoulders Includes Rumble strips (May need Recessed Pavement Markers and Interchange Ramp components) | 32
Pavement Rehabilitation Freeway (≤1 mi: 2-Shoulders) | Pavement | 283800 | Up to 1-mile FREEWAY 5" mill/fill for 2-shoulders Includes Rumble strips (May need Recessed Pavement Markers and Interchange Ramp components) | 33
Recessed Pavement Markers RPM (≤1 mi: 1-line) | Pavement | 1950 | Up to 1-mile of Recessed Pavement Markers (RPM). (Add multiples of this component as needed) | 34
Pavement Preservation Interchange Ramps (1-side: Exit & Entrance) | Pavement | 1592876.04 | 3" mil/fill for 1-exit and 1-entrance FREEWAY ramps. Typical Interchange Spacing: Urban=3-miles, Rural=6-miles | 35
Pavement Rehabilitation Interchange Ramps (1-side: Exit & Entrance) | Pavement | 1698376.04 | 5" mil/fill for 1-exit and 1-entrance FREEWAY ramps. Typical Interchange Spacing: Urban=3-miles, Rural=6-miles | 36
Full Reconstruction (≤ 0.25 MI 1-lane) | Pavement | 308724.33 | Up to 0.25 mile Full dig out or 1-lane, Assumes 12" Agg, 10" ACP. (May need to add utility items & sidewalk infill if in an urban environment.) | 37
Rural Highway Widening (≤ 0.25 MI) | Pavement | 179296.04 | RURAL shoulder widening. Assumes added 8' added with striping and ditch work. Assumes no curbs | 38
Add Passing Lane | Pavement | 1765419.67 | Adds a passing lane approximately 1.25 mile long plus tapers & Ditch | 39
New 1-lane road (≤0.25 mi) | Pavement | 176541.97 | Construction a new bed for a new road for a single lane for up to 0.25 miles. Includes a ditch on one side of the road. Add as many of this item to equate the length of road | 40
Add Single Right Turn Lane (Slow) | Intersection | 621800.96 | Adds an new right turn lane, for speed limits ≤35 mph. Includes building an ADA Ramp (may need ROW) | 41
Add Single Right Turn Lane (Fast) | Intersection | 844900.69 | Adds an new right turn lane, for speed limits ≤55 mph. Includes building an ADA Ramp (may need ROW) | 42
Right Turn Acceleration Lane | Intersection | 583407.62 | Adds right turn Acceleration Lane | 43
Restripe for Left Turn Lane | Intersection | 6780.56 | Restripes an existing through lane into a left turn lane includes legends. | 44
Add Single Left Turn Lane | Intersection | 844900.69 | Adds a new left turn lane for speed limits ≤55 mph. Assumes widening to the right and land shifts (not separated highway) | 45
Channelized Left Turn Lane with Median | Intersection | 1062983.08 | Adds a channelized left turn lane with median according to HDM 500-24 | 46
T-Intersection Left Turn Bypass | Intersection | 1176926.92 | Assumes high speed highway with narrow median (<40'). Includes concrete barrier. | 47
Restricted Crossing U-Turn (R-Cut) | Intersection | 1808360.24 | Install Restricted Crossing U-Turn at grade separated highway | 48
Median U-Turn (MUT) | Intersection | 1808360.24 | Assumes segment between minor streets in median and 2-lanes in each direction, separated highway and requires an acceleration lane. May need con signals at each U-turn depending on volumes. | 49
Roundabout (Single Lane) | Intersection | 2576998.86 | Single-lane Roundabout on Highway. Assumes ≤55 mph, 4 legs, illuminated. Includes 300 feet 3" mill/fill per approach | 50
Roundabout (Double Lane) | Intersection | 6365573.86 | Double-lane Roundabout on Highway. Assumes ≤55 mph, 4 legs, illuminated. Includes 300 feet 3" mill/fill per approach | 51
Transverse Rumble Strips | Intersection | 27671.52 | Intersection improvement for RURAL unsignalized intersection, with stops required for minor legs. Transverse rumble strips, and large stop signs for 1-approaches (May need flashing stop light. Multiples of this component may be necessary) | 52
Dynamic Warning Signs | Intersection | 174884.64 | Intersection Improvement for RURAL unsignalized intersection, with stops required for minor legs. Dynamic flashing warning signs. (Multiples of this component may be necessary) | 53
New Signal Installation | Intersection | 633675 | Signal installation only. (no paving) | 54
Replace Signal | Intersection | 750507.18 | Replace an existing signal, includes temporary signal and paving. | 55
RRFB w/out Median Refuge | Bike_Ped | 216200 | An enhanced pedestrian crossing with push button Rectangular Rapid Flashing Beacon across a road with a pedestrian refuge (crosswalk markings not included) | 56
RRFB w/ Median Refuge | Bike_Ped | 246400 | An enhanced pedestrian crossing with push button Rectangular Rapid Flashing Beacon across a road with a median refuge (crosswalk markings not included) | 57
Multi-Use Path (500') | Bike_Ped | 36181.9 | Assumes 12' asphalt, includes excavation. | 58
Separate Sidewalk (500') | Bike_Ped | 75377.49 | 5' Sidewalk Infill, assumes 4' separation. Includes excavation | 59
Curb-line Sidewalk (500') | Bike_Ped | 109655.74 | 5' Sidewalk Infill. Includes Curb and Gutter. Includes excavation | 60
Traffic Separator (100') | Roadway | 6768.32 | Up to 100' of Mountable Curb to separate lanes of traffic. | 61
Guardrail (250') | Roadway | 16609.53 | Adds new guardrail | 62
Soundwall (0.25 mi) | Roadway | 2273621.56 | Construct a sound wall (Typical length for 1 interchange corner is 0.25 miles) | 63
Median Cable Barrier (3 MI) | Roadway | 2058947.83 | Construct new Median Cable Barrier at a median separated highway | 64
Median Concrete Barrier (3 MI) | Roadway | 3502211.53 | Construct new Median Concrete Barrier | 65
New Variable Message Signs | Roadway | 692217.44 | Add new Variable Message sign with structure, typically accompanies variable speed/warning sign | 66
Replace Variable Message Signs | Roadway | 49557.27 | Replace existing variable message sign only. Includes incidental conduits. NO STRUCTURES | 67
Street Illumination (≤100ft) | Roadway | 31695.83 | Adds Illumination in an urban environment. Assumes moderately accessible electricity. Increase Utility risk if not in an urban environment. | 68
Fence (100') | Roadway | 11360.39 | Adds new or replacement of fence | 69
Wildlife Fence (≤ 500) | Roadway | 10247.84 | Adds new or replacement of wildlife fencing. | 70
Striping 1-lane (≤3 mi) | Roadway | 66097.87 | Intended for restriping projects. Assumes thermoplastic for 2 lanes, no RPMs and no stripe removal. | 71
New Signs (≤ 100) | Roadway | 68395.44 | Installation of up to 100 new signs. Assumes average signs as 4'x4' | 72
Bridge Strengthening | Bridge | 200735.91 | Near Surface Mounted Carbon Fiber Reinforced Polymer Strengthening | 73
New Bridge (Single lane, ≤100ft) | Bridge | 1782500 | A single lane for a bridge up to 100'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended) Example: 3-lane bridge requires 3x of this component | 74
New Bridge (Single lane, ≤ 500ft) | Bridge | 8912500 | A single lane for a bridge up to 500'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended.) Example: 3-lane bridge requires 3x of this component | 75
New Bridge (Single lane, ≤1000ft) | Bridge | 17825000 | A single lane for a bridge up to 1000'. Add multiple of this component for multiple lanes. Includes 300' total of Mill/Fill and bridge approaches. (Adding a components for Temporary bridges/access and Bank Protection recommended.) Example: 3-lane bridge requires 3x of this component | 76
Bridge Overlay, structural 1-lane (≤ 100 ft) | Bridge | 109391.41 | Structural bridge overlays for 1-lane for bridges up to 100'. And striping and add as many of this item to equate the number of lanes. | 77
Bridge Overlay, structural 1-lane (≤ 500 ft) | Bridge | 546957.05 | Structural bridge overlays for 1-lane for bridges up to 500'. And striping and add as many of this item to equate the number of lanes. | 78
Bridge Rehabilitation - Mechanical / Electrical | Bridge | 1000000 | Rehabilitate the mechanical and/or electrical components of a bridge | 79
Culvert Replacement (≤ 10' Deep) | Hydraulics | 109856.67 | Remove and replace an existing culvert with a culvert that is installed less than or equal to 10' deep. This is the default culvert replacement if you do not know the replacement depth. Not Box Culvert. (May require a new lane component for widening and/or channel/stream re-alignment) | 80
Culvert Replacement (> 10' Deep) | Hydraulics | 267438.6 | Remove and replace an existing culvert with a culvert that is more than 10' deep. Not Box Culvert. (May require a new lane component for widening and/or channel/stream re-alignment) | 81
Structural Culvert Replacement | Hydraulics | 512754.73 | Remove and replace an existing culvert/s with a structural plate culvert. This culvert is considered a bridge structure. Not box culvert. (May Require a new lane component for widening and/or channel/stream re-alignment) | 82
Substructure Rehabilitation (1 bent) | Bridge | 160000 | Rehabilitating bridge substructure. Methods may include: rehabilitating/strengthening caps, columns, foundations, piles, footings, or corrosion protection. | 83
Note on A42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove blank
Note on A43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove blank
Note on A59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove space

## Indices (hidden)
REGION |  | Planning Horizon |  |  |  |  | COUNTY | [8 empty] | CITY |  |  |  | Risk Percentages |  |  |  | Risk Factors |  | ITS or BP
Reg # | Factor |  |  | Low | High | 2013 AASHTO Practical Guide to Cost Estimating | County | Group# | Factor | Group # | Factor | Residential | Commercial/Industrial | Farm/Forest | Other / Unknown | Population | Pop Max | Factor | 7/5/25 BOLI |  |  |  | old | 8 | 1.2
1 | 0.044 | <5 years | 0 | -0.1 | 0.25 |  | Baker | 12 | 0.028 | 1 | 0.025 | 664001 | 466001 | 8002 | 27001 | Range Bottom | 0 | 0.022 |  | Negligible | 1% | 1 | 5% | 10 | 1.25 | No
2 | -0.031 | ≥5 years | 5 | -0.3 | 0.5 |  | Benton | 3 | -0.134 | 2 | -0.16 | 664001 | 466000 | 8000 | 27000 | < 3000 | 3000 | 0.022 |  | Very Low | 4% | 2 | 10% | 12 | 1.3 | Yes
3 | -0.02 | ≥10 years | 10 | -0.4 | 1 |  | Clackamas | 1 | 0.025 | 3 | -0.134 | 664000 | 466000 | 8000 | 27000 | < 7000 | 7000 | -0.096 |  | Low | 9% | 3 | 15% | 14 | 1.35
4 | -0.012 | ≥20 years | 20 | -0.5 | 2 |  | Clatsop | 10 | 0.706 | 4 | -0.051 | 664000 | 466000 | 8000 | 27000 | < 12000 | 12000 | -0.028 |  | Moderate | 16% | 4 | 25% | 16 | 1.4
5 | 0.014 |  | 15 | -0.4 | 1 |  | Columbia | 10 | 0.706 | 5 | -0.126 | 664000 | 466000 | 7999 | 27000 | < 25000 | 25000 | -0.027 |  | High | 25% | 5 | 35% | 18 | 1.45
6 | 0 |  | 25 | -0.5 | 2 |  | Coos | 11 | 0.567 | 6 | -0.074 | 664000 | 466000 | 8000 | 27000 | < 50000 | 50000 | -0.084 |  | Very High | 36% | 6 | 50% | 20 | 1.5
[7 empty] | Crook | 5 | -0.126 | 7 | -0.051 | 664000 | 465999 | 7999 | 26999 | < 70000 | 70000 | -0.017
[7 empty] | Curry | 11 | 0.567 | 8 | 0.145 | 663999 | 465999 | 7999 | 26999 | < 120000 | 120000 | 0.036
[7 empty] | Deschutes | 5 | -0.126 | 9 | -0.07 | 663999 | 466001 | 7999 | 27000 | ≥ 120000 | 99999999 | -0.054
[7 empty] | Douglas | 4 | -0.051 | 10 | 0.706 | 664000 | 466001 | 8001 | 27001 | n/a | n/a | 0.056
[7 empty] | Gilliam | 12 | 0.028 | 11 | 0.567 | 664000 | 465999 | 8000 | 27000 |  |  |  |  | 2019 Guide to Managing Project Risks for ODOT STIP
[7 empty] | Grant | 12 | 0.028 | 12 | 0.028 | 663999 | 465999 | 7999 | 26999
[7 empty] | Harney | 8 | 0.145 |  | AVG Cost: | 664000 | 466000 | 8000 | 27000
[7 empty] | Hood River | 6 | -0.074
[7 empty] | Jackson | 4 | -0.051
[7 empty] | Jefferson | 5 | -0.126
[7 empty] | Josephine | 4 | -0.051
[7 empty] | Klamath | 9 | -0.07
[7 empty] | Lake | 8 | 0.145
[7 empty] | Lane | 3 | -0.134
[7 empty] | Lincoln | 10 | 0.706
[7 empty] | Linn | 3 | -0.134
[7 empty] | Malheur | 8 | 0.145
[7 empty] | Marion | 2 | -0.16
[7 empty] | Morrow | 9 | -0.07
[7 empty] | Multnomah | 1 | 0.025
[7 empty] | Polk | 2 | -0.16
[7 empty] | Sherman | 6 | -0.074 | [10 empty] | 2017 ODOT Risk Management Practices and Recommendations to Support TAMP
[7 empty] | Tillamook | 10 | 0.706
[7 empty] | Umatilla | 7 | -0.051
[7 empty] | Union | 7 | -0.051
[7 empty] | Wallowa | 7 | -0.051
[7 empty] | Wasco | 6 | -0.074
[7 empty] | Washington | 1 | 0.025
[7 empty] | Wheeler | 12 | 0.028
[7 empty] | Yamhill | 2 | -0.16
[7 empty] | Various | 0 | 0
Note on D1: AASHTO
Note on Z1: TBD
Note on AC1: TBD
Note on AF1: TBD
Note on B2: 11/14/2025 Round to thousandths
Note on O2: 11/14/2025 Round to thousandths
Note on W2: 11/14/2025 Round to thousandths
Note on A8: STATEWIDE
Note on W12: BOLI average between ≤30 to <80mi AVG(100%,102%,109%,104%,112%,105%)

## Risk Worksheet
Project Name: |  |  | Name: |  |  | 1.2 | Negligible | Max Score | Rating
Project #: |  |  | Title: |  |  |  |  | 8 | 1.2 | Negligible
ProjectWise Link: |  |  | Date: |  |  |  |  | 10 | 1.25 | Very Low
Date: |  |  | Agency/Consultant: |  |  |  |  | 12 | 1.3 | Low
[8 empty] | 14 | 1.35 | Moderate
1 | 2 | 3 | 4 | 5 | 6 | Enter 1-6 | Comments | 16 | 1.4 | High
Complexity | [7 empty] | 18 | 1.45 | Very High
Minimal complexity; routine maintenance, no changes. Basic "1R pave only" on flat sites. Risks easily mitigated. | Low complexity; minor improvements, limited scope. Basic "1R" with additions like signage. Risks predictable, low-impact. | 3R Preservation. Basic complexity; some enhancements, straightforward. Light minor rehabilitation. Risks from minor uncertainties. | 4R Rural Modernization. Single Span Bridges. Average complexity; multiple elements need planning. Mid-range "3R" with modernization. Risks from interdependencies. | Elevated complexity; significant upgrades, technical hurdles. Approaches "4R" with bridges. High risk variability. | Extreme complexity; full modernization, interdependent challenges. Full 4R with complex bridges, multi-stages. Multifaceted risks. |  |  | 20 | 1.5 | Very, Very High
Utility / Right of Way (ROW) / Access Management (AM)
No ROW, no const. easements, access management exemption. No utilities affected. Minimal overall risks | Minimal ROW/easements; few minor utilities; simple access changes. Low coordination, predictable risks. | Some ROW/easements; routine utilities; moderate access mods. Standard processes, minor delays possible. | Multiple ROW parcels/easements; multi-utilities; planned access changes. Increased coordination, potential conflicts. | Significant urban ROW/easements; complex utilities; major access controls. High acquisition/delays, stakeholder risks. | Metro area, urban ROW, significant access management. Extensive utilities/relocations. Potential legal risks.
Environmental Factors | [7 empty] | 1
Project within developed ROW. No environmental impacts or permits needed. Minimal risks. | Minor work in low-sensitivity areas. Basic permits, negligible impacts. Predictable risks. | Shoulder work, categorical exclusion. Routine permits, minor environmental reviews. Low risks. | Minimal in-water work, pre-identified archaeology/historic sites. Planned permits, moderate impacts. | Significant regulated areas, in-water work, archaeology/historic sites. Complex permits, high mitigation needs. | Extensive regulated area/in-water work (e.g., drilled shafts), hazardous materials, archaeological/historic sites. Extreme permits, major risks. |  |  | 2
Estimating Confidence / Scope Creep | [7 empty] | 3
Maintenance/rural pave only. High confidence, negligible scope creep or schedule uncertainty; no stakeholder involvement to alter scope. | Detailed scope, estimate & risk understanding; actual pavement widths used. Very low creep or schedule slips; minimal stakeholder influence. | Clear problem statement and solution, limited leverage opportunities. Low creep risk, minor schedule uncertainty; low stakeholder potential to change scope. | 20+ ADA ramps present, unidentified staging. Moderate scope creep potential, some schedule uncertainty; moderate stakeholder involvement risks. | Approx quantities, extensive lump sums, non-metro urban/unclear scope. High creep and schedule uncertainty; high stakeholder-driven changes. | Long delivery timeline, extensive lump sums, metro urban/unclear scope. Very high creep, major schedule uncertainty; extensive stakeholder involvement to alter scope. |  |  | 4
Scope Creep / Change | [7 empty] | 5
Rural Pave Only |  | Clear Problem Statement Limited Leverage Opportunities | ADA Ramps Present Unidentified Staging | Non Metro: Urban Project / Unclear Scope | Metro: Urban Project / Unclear Scope |  |  | 6
Scoping Risk Worksheet Purpose
The purpose of this Scoping Risk Worksheet is to take a consistent approach when applying a risk factor to the construction estimate of each project and to document those risks and assumptions in a single document. Although the spreadsheet has a built in calculator and estimates a risk factor between 20% and 50% each Region has the ability to adjust these numbers as they see fit. This risk factor will replace the "contingency" item in our Scoping Estimates. As a reminder, any transportation project estimated to cost at least $15 million and go before the OTC for approval in the STIP must have a Benefit-Cost Analyusis complete (Link Below)
Benefit-Cost-Analysis Operational Notice
Scoping Risk Worksheet Process
The Scoping Risk form is intended to be completed at the conclusion of the scoping process, once the initial scoping estimate is prepared. The risk form should be completed with input from technical resources and project delivery leadership within the regions. The proposed risk number should then be utilized as a factor multiplied against the total construction estimate to achieve the final scoping amount for construction. The intent would be to include this risk factor on a scoping summary page, scoping estimate, or other equivalent document, and to not list this as the contingency factor on the designer's estimate. The contingency factor on the designer's estimate can and should remain the 3.5%. This method will also provide a process forward regarding identifying a risk factor at Preliminary Plans, DAP, etc. in lieu of just having the roadway designer assume contingency numbers at each milestone. Considerations by all parties preparing scoping estimates (roadway, bridge, geo, etc.) should be reviewed so that each group is not applying additional contingency factors to their specific estimates thus multiplying the risk factor unnecessarily.
Form Instructions
1. Enter Project Name and Projectwise Scoping Folder Number
2. Enter detailed assumptions and potential risks in the comment section of each of the 5 categories.
3. Enter a numerical value in the far right column corresponding to each of the Risk Factors. Enter 4 for Red, 3 for Orange, 2 for Yellow, and 1 for Green.
4. The spreadsheet will automatically format the color based on the number you entered and provide a total risk value in the "Risk Factor" cell at the bottom right of the sheet.
5. Review the Risk Factor assigned to determine if it is indeed reflective of the project. The minimum risk factor applied will remain 1.2 or 20% even if all items are in green. The maximum risk factor calculated will be 1.5 or 50%. These are suggested ranges and can be adjusted on a case by case basis.
6. Complete the information at the bottom of form identifying who completed the document.

## ODOTinflation (hidden)
ODOT Inflation Calculator (internal only)
Index Last Updated | 2026-03-11
Extracted | 2026-05-04
Bid Year Base | 2026 | Based on prototype's 2024 Bid-Data, shall use 2025/6 in production
Estimated AGR(5yr) | 3.2% | For <5 year project horizons Average Increase from Bid Base Year to +5 | 2026 | 2031
Estimated AGR(10yr) | 3.5% | For ≥5 year project horizons Average Increase from Bid Base Year to +10 | 2026 | 2034
Estimated AGR(20yr) | 3.533% | For ≅20 year project horizons Calculated based on linear regression calculation to 20 year protection | 2046
| Index from 2026 | Increase
2015 | 0.6728
2016 | 0.6749
2017 | 0.6962
2018 | 0.7301
2019 | 0.7455
2020 | 0.7503
2021 | 0.8247
2022 | 0.908
2023 | 0.9291
2024 | 0.9449
2025 | 0.9755
2026 | 1 | 0.0245
2027 | 1.0305 | 0.0305
2028 | 1.0644 | 0.0339
2029 | 1.0981 | 0.0337
2030 | 1.133 | 0.0349
2031 | 1.1694 | 0.0364
2032 | 1.207 | 0.0376
2033 | 1.2451 | 0.0381
2034 | 1.2841 | 0.039
2046 | 1.7066 | 0.0356 * x -71.155 | 0.035612 | -71.1548