## Instructions
HB-5202 Behavioral Health Housing Investment: Quarterly Report Instructions (July 1 - September 30, 2023)
Grant Program Objectives: | House Bill 5202 appropriates money for distribution to community mental health programs (CMHP) and related administrative support in OHA. The goals of this funding are to provide an array of supported housing and residential treatment, relieve bottlenecks in the continuum of care, and address health inequities and housing access disparities.
Eligible Program Activities: | Each of the following are eligible program activities and Grant funds may be expended for the costs of such activities, if such costs are in accordance with Recipient’s budget approved by OHA. a. Repurpose or build new secure residential treatment facilities, residential treatment homes, adult foster homes, supported housing units, and supportive housing units. b. Operational and administrative costs to manage housing. c. Housing support services. d. Planning, coordination, siting, purchasing buildings/land (pre-build or renovation activities). e. Subsidies for short-term shelter beds. f. Long-term rental assistance. g. Outreach and engagement items such as food or clothing to meet immediate needs for houseless individuals.
Quarterly Reporting Information: |  | Report Period | Report Start Date | Report End Date | Report Due Date:
Grantees are required to prepare and electronically submit written quarterly reports that describe the grant activities for the quarter. These reports are due 30 days after fiscal quarter-end except for the Q4 report, which is due 50 days after quarter-end. Please see table to the right for dates. |  | Q1 (Jul 1 - Sep 30) | 2023-07-01 | 2023-09-30 | 2023-10-30
|  | Q2 (Oct 1 - Dec 31) | 2023-10-01 | 2023-12-31 | 2024-01-30
|  | Q3 (Jan 1 - Mar 31) | 2023-01-01 | 2023-03-31 | 2023-04-30
|  | Q4 (Apr 1 - Jun 30) | 2023-04-01 | 2023-06-30 | 2023-08-20
Data Fields & Cell Colors |  | Cell Color |  | Information
Please note that this file uses color coding to indicate what cells/fields require updates and which are formula driven or auto-populated. |  | Blue shaded cells |  | Blue shaded cells require input by the individual completing this form.
|  | Gray shaded cells |  | Gray shaded cells contain links, formulas, or references and do not need to be edited.
Please send completed reports and any questions to: SDOH.HB5202@odhsoha.oregon.gov
Tab 1: Expenditure Report Form
Section: | Data Field: | Field Type | Instructions/Notes:
A. Grantee Information | Community Mental Health Program | Formula Driven | Your Organization Name will auto-populate from the manual entry of your Grant Agreement #. Please notify us if there is any incorrect information.
| Grant Agreement Number | Manual Entry | Please enter your Grant Agreement Number. Note, by entering your Grant Agreement #, this will auto-populate the following cells: Community Mental Health Program, Contact Name, Contact Phone Number, and Contact Email. If you are not able to find your Grant Agreement Number, please reach out to our team.
| Contact Name, Phone Number & Email | Formula Driven | Your organization contact information will auto-populate based on your entered Grant Agreement #. The contact information in these cells will be the point-of-contact that our team member may reach out to if we have any questions regarding your report.
| Date of Report | Manual Entry | Please enter the date this report was completed.
| Prepared By | Manual Entry | Please enter the name of the individual who is completing this report. Note, the same individual can be the main point of contact and report preparer.
| OHA Reviewed By | Manual Entry | Please disregard this cell (for internal use only). The OHA team will enter the name of the reviewer of this package for documentation purposes.
| Construction Complete: | Drop-down Selection | Please indicate if the construction is complete for your project from the drop-down list. This will grey out cells in Section B. and Section C., dependent on the answer selected.
B. Budget & Expenditures Information | Total Funding Provided | Formula Driven | This row will auto-populate the current approved budget based on the entered Grant Agreement #. Note, these budgets are the latest our team has in our records; if these amounts are incorrect, please reach out to our team.
| Previous Amount Expended | Formula Driven | This row will auto-populate the current spend to date based on the entered Grant Agreement # and the Quarterly Expenditure Reports received by our team; if these amounts are incorrect, please reach out to our team.
| Month 1 - Month 3 | Manual Entry | Please enter the amount spent in each month for each of the applicable budget categories. Note, the form will show the applicable month based on the Reporting Period. (I.E. Reporting Period Q1 2023 will show January 2023, February 2023, and March 2023).
| Total Expenditures this Quarter | Formula Driven | This row will auto-sum the three month's expenditures for each budget category.
| Total Funding Remaining | Formula Driven | This row will auto-populate the remaining funds for each budget category based on the Total Funding Provided, Previous Amount Expended, and Prior Quarter Spend.
C. Expenditure Descriptions | Budget Categories 1 - 7 | Manual Entry | Please enter detailed descriptions for each line-item expenditure over $1,000 within each budget category.
Tab 2: Progress Report Form
Section: | Data Field: | Field Type | Instructions/Notes:
A. Project Information | Project Name | Formula Driven | This column will auto-populate with each of your Grant Agreement's projects from the most recently approved Exhibit D. If any of these projects are missing, incorrect, or need to be updated, please reach out to our team for support.
| Project Start Date | Formula Driven / Manual Entry | The grey fields will auto-populate with each of your Grant Agreement's Project Start Dates from the most recent Quarterly Expenditure Report received by our team. If any of these dates are missing, incorrect, or need to be updated, please provide the correct date in the blue field below.
| Estimated Project Completion Date | Formula Driven | The grey fields will auto-populate with each of your Grant Agreement's Estimated Project Completion Dates from the most recent Quarterly Expenditure Report received by our team. If any of these dates are missing, incorrect, or need to be updated, please provide the correct date in the blue field below.
| Initial Date of Occupancy | Formula Driven | The grey fields will auto-populate with the Initial Date of Occupancy for each of the projects in your Grant Agreement. These dates are from the most recent Quarterly Expenditure Report received by our team. If any of these dates are missing, incorrect, or need to be updated, please provide the correct date in the blue field below.
| New Number of Beds/Units | Formula Driven | The grey fields will auto-populate with the New Number of Beds/Units for each of the projects in your Grant Agreement (resulting from 5202 funds). These values are from the most recent Quarterly Expenditure Report received by our team. If any of these values are missing, incorrect, or need to be updated, please provide the correct amount in the blue field below.
| Rationale for Updated Values | Manual Entry | Please provide rationale for any updates and/or changes made to Project Start Date, Estimated Project Completion Date, Initial Date of Occupancy, and/or Number of Beds/Units in Section A.
B. Project Progress Information | Project Progress Summary | Manual Entry | Please provide a summary of progress on funding deliverables and project activities, where applicable.
| Accomplishments & Upcoming Action Items | Manual Entry | Please provide a summary on accomplishments milestones and upcoming action items, where applicable.
| Barrier Summary | Manual Entry | Please describe barriers to any project deliverables, where applicable.
| Mitigation Strategies | Manual Entry | Please provide strategies to overcome barriers identified above, where applicable.
| Success Story & Recommendations | Manual Entry | Please consider sharing a success story with us as well as any recommendations or areas where OHA can provide additional support, where applicable.
Tab 3: Certification
Section: | Data Field: | Field Type | Instructions/Notes:
A. Certificate | Authorized Agent Signature | Manual Entry | Please electronically sign this form by typing in name. Note, Authorized Agent should be the grant program responsible party or their designee.
| Authorized Agent Title | Manual Entry | Please provide the title of the Authorized Agent certifying this report.
| Date | Manual Entry | Please provide the date the Authorized Agent completed this certification.
Updated: Sept. 2023

## 1. Expenditure Report Form
HB-5202 Behavioral Health Housing Investment: Quarterly Expenditure Report (July 1 - September 30, 2023)
A. Grantee Information | [5 empty] | Please only populate data in blue shaded cells.
Community Mental Health Program: | Adapt Integrated Health (Douglas) |  | Grant Agreement Number: | 177734 |  | Grey shaded cells contain links, formulas or functions.
Contact Name: | Grayson Bly |  | Date of Report: |  |  | Report Period: | Q1 2024 (Jul 1 - Sep 30)
Contact Phone Number: | 541-672-2691 |  | Prepared By: |  |  | Report Due Date: | 2023-10-30
Contact Email: | graysonb@adaptoregon.org |  | OHA Reviewed By: |  |  | Construction Complete?
B. Budget & Expenditures Information
Budget Category | Repurpose Or Build New Secure Residential Treatment Facilities, etc. | Operational and Administrative Costs To Manage Housing | Housing Support Services | Planning, Coordination, Siting, Purchasing Buildings/Land (Pre-Build Or Renovation Activities) | Subsidy For Short Term Shelter Beds | Long Term Rental Assistance | Outreach And Engagement Items To Meet Immediate Needs For Houseless Individuals | Total
Total Funding Provided | 2325000 | 50000 | 267853 | 300000 | 0 | 360000 | 5584 | 3308437
Previous Amount Expended | 2325000 | 8379 | 0 | 0 | 0 | 0 | 0 | 2333379
2023-07-01 | [7 empty] | 0
2023-08-01 |  |  |  |  | 40000 |  |  | 40000
2023-09-01 | [7 empty] | 0
Total Expenditures this Quarter | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 40000
Total Funding Remaining | 0 | 41621 | 267853 | 300000 | -40000 | 360000 | 5584 | 935058
C. Expenditure Descriptions: Please enter detailed descriptions for each line-item expenditure over $1,000 within each budget category. (if applicable)
Expenditure Description Example | The $10,000 in reported long-term rental assistance expenditures was used to help provide 8 individuals with 1-bedroom housing units at an average cost of $1,250 per unit. These individuals moved into the units during the first week of January 2023 and assistance will be provided for 6 months.
Repurpose or Build New Secure Residential Treatment Facilities, etc.
Operational and Administrative Costs to manage housing
Housing support services
Planning, coordination, siting, purchasing buildings/land (pre-build or renovation activities)
Subsidy for short term shelter beds
Long term rental assistance
Outreach and engagement items such as food or clothing to meet immediate needs for houseless individuals
Updated: Sept. 2023

## 2. Progress Report Form
HB-5202 Behavioral Health Housing Investment: Quarterly Progress Report (July 1 - September 30, 2023)
| Grantee Information | [9 empty] | Please only populate data in blue shaded cells.
| Community Mental Health Program: | Adapt Integrated Health (Douglas) |  |  |  | Grant Agreement Number: | 177734 | Reporting Period: | Q1 2024 (Jul 1 - Sep 30) |  | Grey shaded cells contain links, formulas or functions.
| A. Project Information |  |  |  |  | B. Project Progress Information
NOTE: If you are requesting to update your project's Start Date, Estimated Completion Date, Initial Date of Occupancy, or Bed/Unit Capacity, please ensure that the 5202 Team is aware by emailing the SDOH 5202 Shared Inbox at SDOH.HB5202@odhsoha.oregon.gov so they can discuss possible changes with you.
Project ID | Project Name & Description: | Project Start Date: | Estimated Project Completion Date: | Initial Date of Occupancy: | New Bed/Unit Capacity upon Project Completion (resulting from 5202 funds) | If any updated values were provided in Columns D - G, please provide a narrative and rationale for each update: | Please provide a summary of progress on funding deliverables and project activities. | Please provide a summary on accomplishments milestones and upcoming action items. | Please describe barriers to any project deliverables. | Please provide strategies to overcome the identified barriers. | Please use the space below to share a success story / positive outcome as a result of this funding. Please also provide any recommendations to the SDOH team on how we can better support you.
| Example Project: Apartment Complex Acquisition & Renovation | 2023-04-01 | 2023-10-15 | 2023-11-01 | 10 | Due to supply chain delays, construction is behind schedule, and will likely result in a later than anticipated completion date. | With the property acquisition having recently been completed, we are currently beginning renovation work and making steady progress in alignment with our project plan. | The first part of our renovation plan is to complete the necessary plumbing, electrical, and utility repairs. | We currently do not have any foreseen barriers but if the renovation repairs take longer than expected that may impact our estimated completion date. | Our organization will create a plan of action and coordinate with the SDOH team if barriers that impact our completion and occupancy dates do arise. | Through this funding we will be able to create 10 net-new beds for the community. Once the renovations have been completed and the facility is occupied we can provide personal accounts and stories.
177734-0-1 | Building Purchase and Renovation - Repurpose/Build New Facility | 2022-11-22 | 2024-06-01 | N/A | 50
1 | If any of these values have changed, please provide the updated value:
177734-0-2 | Administrative Oversight and Project Management - Operational and Administrative Costs | N/A | N/A | N/A | N/A
1 | If any of these values have changed, please provide the updated value:
177734-0-3 | Two Full-Time Employees - Housing Support Services | N/A | N/A | N/A | N/A
1 | If any of these values have changed, please provide the updated value:
177734-0-4 | Senior Level Staff Member and Project Manager - Planning, Coordinating, and Purchasing | N/A | N/A | N/A | N/A
1 | If any of these values have changed, please provide the updated value:
177734-0-5 | Rental Funds for 18 months for 10 Individuals - Long Term Rental Assistance | N/A | N/A | N/A | N/A
1 | If any of these values have changed, please provide the updated value:
177734-0-6 | New Supplies that Cannot be Donated - Outreach and Engagement | N/A | N/A | N/A | N/A
1 | If any of these values have changed, please provide the updated value:
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0
0 | 0
0

## 3. Certification
HB-5202 Behavioral Health Housing Investment: Quarterly Progress Report (July 1 - September 30, 2023)
Report Information
Organization: | Adapt Integrated Health (Douglas) |  |  | Grant Agreement Number: | 177734
Report Period: | Q1 2024 (Jul 1 - Sep 30) |  | Please email completed reports to: | SDOH.HB5202@odhsoha.oregon.gov
A. Certificate
I certify to the best of my knowledge and belief that the report is true, complete and accurate, and the expenditures, disbursements and cash receipts are for the purposes and objectives set forth in the terms and conditions of the grant award. I am aware that any false, fictitious or fraudulent information, or the omission of any material fact, may subject me to criminal, civil or administrative penalties for fraud, false statements, false claims or otherwise. (2 CFR 200.415)
Authorized Agent Signature: |  | Authorized Agent Title: |  | Date:

## Data Entry Import
*"OHA Reviewed By" and "Construction Complete" at end*
| Indicative Data | [7 empty] | First Month Spend | [6 empty] | Second Month Spend | [6 empty] | Third Month Spend | [6 empty] | Spend Descriptions | [6 empty] | Certification
| Report Period | CMHP Name | Grant Agreement Number | Contact Name | Contact Phone | Contact Email | Prepared by | Date of Report | Repurpose/Build New Facility | Operational and Administrative Costs | Housing Support Services | Planning, Coordinating, and Purchasing | Short Term Bed Subsidy | Long Term Rental Assistance | Outreach and Engagement | Repurpose/Build New Facility | Operational and Administrative Costs | Housing Support Services | Planning, Coordinating, and Purchasing | Short Term Bed Subsidy | Long Term Rental Assistance | Outreach and Engagement | Repurpose/Build New Facility | Operational and Administrative Costs | Housing Support Services | Planning, Coordinating, and Purchasing | Short Term Bed Subsidy | Long Term Rental Assistance | Outreach and Engagement | Repurpose/Build New Facility | Operational and Administrative Costs | Housing Support Services | Planning, Coordinating, and Purchasing | Short Term Bed Subsidy | Long Term Rental Assistance | Outreach and Engagement | Authorized Agent Signature | Authorized Agent Title | Certification Date | OHA Reviewed By | Construction Complete?
Copy this row --> | Q1 2024 (Jul 1 - Sep 30) | Adapt Integrated Health (Douglas) | 177734 | Grayson Bly | 541-672-2691 | graysonb@adaptoregon.org | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
*Revision rationale at end*
Progress Report Form | Grant Agreement Number | Reporting Period | Project ID | Project Name | Project Start Date: | Estimated Project Completion Date: | Initial Date of Occupancy: | Number of Beds/Units (if applicable): | Please provide a summary of progress on funding deliverables and project activities. | Please provide a summary on accomplishments milestones and upcoming action items. | Please describe barriers to any project deliverables. | Please provide strategies to overcome the identified barriers. | Please use the space below to share a success story / positive outcome as a result of this funding. Please also provide any recommendations to the SDOH team on how we can better support you. | If any updated values were provided in Columns D - G, please provide a narrative and rationale for each update
Copy these rows --> | 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-1 | Building Purchase and Renovation - Repurpose/Build New Facility |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-2 | Administrative Oversight and Project Management - Operational and Administrative Costs |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-3 | Two Full-Time Employees - Housing Support Services |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-4 | Senior Level Staff Member and Project Manager - Planning, Coordinating, and Purchasing |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-5 | Rental Funds for 18 months for 10 Individuals - Long Term Rental Assistance |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 177734 | Q1 2024 (Jul 1 - Sep 30) | 177734-0-6 | New Supplies that Cannot be Donated - Outreach and Engagement |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Smartsheet Export
Begin Paste here --> | Primary Column | Short Grant Agreement Number | Grant Agreement Number | Grantee Name | County | Total NTE | NTE vs Budget Variance | Repurpose/Build New Facility | Operational and Administrative Costs | Housing Support Services | Planning, Coordinating, and Purchasing | Short Term Bed Subsidy | Long Term Rental Assistance | Outreach and Engagement | Total Reported Expenditures | Repurpose/Build New Facility Spend to Date | Operational and Administrative Costs Spend to Date | Housing Support Services Spend to Date | Planning, Coordinating, and Purchasing Spend | Short Term Bed Subsidy Spend to Date | Long Term Rental Assistance Spend to Date | Outreach and Engagement Spend to Date
|  | 177734 | 177734-0 | Adapt Integrated Health | Douglas | 3308437 | 0 | 2325000 | 50000 | 267853 | 300000 | 0 | 360000 | 5584 | 2333379 | 2325000 | 8379 | 0 | 0 | 0 | 0 | 0
|  | 177735 | 177735-0 | Adapt Integrated Health | Curry | 1883183 | 0 | 1386000 | 30000 | 133927 | 150000 | 0 | 180000 | 3256 | 10253 | 7710 | 2543 | 0 | 0 | 0 | 0 | 0
|  | 177680 | 177680-0 | Benton County Health Department Behavioral Health Division | Benton | 2780841.48 | 0 | 0 | 0 | 350841.48 | 0 | 0 | 2400000 | 30000 | 6182 | 0 | 0 | 0 | 0 | 0 | 6182 | 0
|  | 177770 | 177770-0 | BestCare Treatment Services | Jefferson | 3021010.34 | 0 | 330010.34 | 200000 | 200000 | 2291000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177751 | 177751-0 | Center for Human Development | Union | 1570015.85 | -0.85 | 501661 | 63815 | 192268 | 17700 | 106018 | 670400 | 18153 | 137215.48 | 0 | 9318.3 | 19651.4 | 0 | 10407.08 | 95703.92 | 2134.78
|  | 177736 | 177736-0 | Clackamas County Behavioral Health Division | Clackamas | 4704837 | 0.17 | 0 | 730000 | 0 | 3924837.17 | 0 | 0 | 50000 | 14196.61 | 0 | 14196.61 | 0 | 0 | 0 | 0 | 0
|  | 177670 | 177670-0 | Clatsop County Behavioral Healthcare | Clatsop | 2353924.99 | 0 | 1778924.99 | 200000 | 0 | 375000 | 0 | 0 | 0 | 180305.9 | 78924.99 | 53914.32 | 0 | 47466.59 | 0 | 0 | 0
|  | 177716 | 177716-0 | Columbia Community Mental Health | #NO MATCH | 2524129 | 0 | 1703342 | 74617 | 746170 | 0 | 0 | 0 | 0 | 141818.18 | 132193.18 | 9625 | 0 | 0 | 0 | 0 | 0
|  | 177737 | 177737-0 | Community Counseling Solutions | Umatilla | 7138703.53 | 0 | 6126983.53 | 250000 | 30000 | 120000 | 238160 | 338560 | 35000 | 1921804.37 | 1847843.81 | 23286.91 | 30000 | 0 | 0 | 17989.65 | 2684
|  | 177671 | 177671-0 | Coos County Health & Wellness | Coos | 2762431.29 | 0 | 2712431.29 | 0 | 0 | 50000 | 0 | 0 | 0 | 179582.19 | 129582.19 | 0 | 0 | 50000 | 0 | 0 | 0
|  | 177672 | 177672-0 | Deschutes County | Deschutes | 3901470.64 | 0 | 2850000 | 51470.64 | 0 | 150000 | 850000 | 0 | 0 | 58400 | 0 | 0 | 0 | 0 | 58400 | 0 | 0
|  | 177726 | 177726-0 | Jackson County Behavioral Health Services | #NO MATCH | 4165649.82 | 0 | 3292114.82 | 0 | 0 | 873535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177698 | 177698-0 | Klamath Basin Behavioral Health | Klamath | 2637875.63 | 0 | 1847255.63 | 0 | 0 | 790620 | 0 | 0 | 0 | 174312.75 | 0 | 0 | 0 | 174312.75 | 0 | 0 | 0
|  | 177674 | 177674-0 | Lake County Health District | Lake | 1487041.4 | 0 | 750000 | 0 | 0 | 701041.4 | 0 | 0 | 36000 | 360.22 | 0 | 0 | 0 | 0 | 0 | 0 | 360.22
|  | 177675 | 177675-0 | Lane County | #NO MATCH | 6907194.83 | 0 | 6100000 | 400000 | 357194.83 | 50000 | 0 | 0 | 0 | 327782.14 | 0 | 0 | 327782.14 | 0 | 0 | 0 | 0
|  | 177687 | 177687-0 | Lifeways Inc | Malheur | 1638524 | 0 | 1638524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177676 | 177676-0 | Lincoln County Health and Human Services | #NO MATCH | 2597926 | 0 | 0 | 27000 | 0 | 2550000 | 0 | 0 | 20926 | 12766 | 0 | 0 | 0 | 9750 | 3016 | 0 | 0
|  | 177747 | 177747-0 | Linn County | #NO MATCH | 2687000 | 0 | 2500000 | 137000 | 10000 | 0 | 40000 | 0 | 0 | 199063.5 | 119597.79 | 39465.71 | 0 | 0 | 40000 | 0 | 0
|  | 177688 | 177688-0 | Marion County Health and Human Services | Marion | 6318421 | 0 | 2735000 | 1640761 | 942580 | 265000 | 50000 | 434640 | 250440 | 977904.56 | 788970.82 | 150764.74 | 0 | 32719.5 | 0 | 3172 | 2277.5
|  | 177689 | 177689-0 | Mid Columbia Center for Living | Wasco | 4079544 | 0 | 3200000 | 289544 | 80000 | 0 | 350000 | 0 | 160000 | 9968 | 0 | 9968 | 0 | 0 | 0 | 0 | 0
|  | 177677 | 177677-0 | Multnomah County Health Department | #NO MATCH | 9715230.97 | -1 | 3665379.97 | 593124 | 1206726 | 4000000 | 0 | 0 | 250000 | 4797720.11 | 749999 | 47721.11 | 0 | 4000000 | 0 | 0 | 0
|  | 177684 | 177684-0 | New Directions Northwest, Inc. | Baker | 1449518.73 | 0 | 0 | 166961.49 | 72800 | 1092000 | 10000 | 55757.24 | 52000 | 514878.04 | 0 | 58517.11 | 42717.92 | 385557.24 | 2263.82 | 24376.99 | 1444.96
|  | 177685 | 177685-0 | Options for Southern Oregon’s Behavioral Health | #NO MATCH | 3072811.95 | 0 | 1350000 | 78488 | 143520 | 1408803.95 | 36000 | 36000 | 20000 | 513703.01 | 0 | 0 | 0 | 513107.1 | 595.91 | 0 | 0
|  | 177690 | 177690-0 | Polk County Health Services | Polk | 2456371.85 | 0 | 2456371.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177713 | 177713-0 | Symmetry Care | Harney | 1400000 | 0 | 472524.25 | 250000 | 300000 | 252475.75 | 0 | 25000 | 100000 | 520762.64 | 214478.83 | 48793.98 | 0 | 252475.75 | 0 | 5000 | 14.08
|  | 177679 | 177679-0 | Tillamook Family Counseling Center | Tillamook | 1741064.65 | -5999.65 | 1350000 | 245700 | 0 | 139365 | 0 | 0 | 0 | 29997.04 | 3116 | 19863.79 | 0 | 7017.25 | 0 | 0 | 0
|  | 177692 | 177692-0 | Wallowa Valley Center for Wellness | Wallowa | 1426957 | 0 | 1406825 | 20132 | 0 | 0 | 0 | 0 | 0 | 1234642 | 1214510 | 20132 | 0 | 0 | 0 | 0 | 0
|  | 178501 | 178501-0 | Warm Springs | Warm Springs | 1500000 | -50229 | 200000 | 0 | 0 | 1200000 | 0 | 49771 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177694 | 177694-0 | Washington County Department of Health and Human Services | #NO MATCH | 5931316.61 | 1 | 5931317.61 | 0 | 0 | 0 | 0 | 0 | 0 | 2008111.22 | 2008111.22 | 0 | 0 | 0 | 0 | 0 | 0
|  | 177708 | 177708-0 | Yamhill County Health and Human Services | Yamhill | 2828947 | 0 | 0 | 1335000 | 180000 | 1255000 | 0 | 0 | 58947 | 40391.2 | 0 | 0 | 0 | 40391.2 | 0 | 0 | 0
|  | 177685 | 177685-0 | Options for Southern Oregon’s Behavioral Health | #NO MATCH | 3072811.95 | 0 | 1350000 | 78488 | 143520 | 1408803.95 | 36000 | 36000 | 20000 | 513703.01 | 0 | 0 | 0 | 513107.1 | 595.91 | 0 | 0

## Data Validation
Grantee Information Selected: | Selection | Short Name | Quarter | Year | Timeframe | Reporting Period | Due Date | First Month | Second Month | Third Month | County | County Formal Name | # of Clients | Project Type | Project Status | Short Grant Agreement Number | Grant Agreement Number | Grantee Name | Short Name | ID | Name | Contact Name | Contact Phone | Contact Email | Grantee Name | AdaptCurry | 177735 | [6 empty] | 177735-0-1 | Hammond House Purchase - Repurpose/Build New Facility | 177735-0
Grantee: | Adapt Integrated Health (Douglas) | AdaptDouglas | Q | 2022 | Oct 1 - Dec 31 | Q2 2022 (Oct 1 - Dec 31) | 2023-01-30 | 2022-10-01 | 2022-11-01 | 2022-12-01 | Baker | Baker County | N/A - 0 | Secure Residential Treatment Facilities | Not Started | 177735 | 177735-0 | Adapt Integrated Health (Curry) | AdaptCurry | AdaptCurryID | AdaptCurryName | Grayson Bly | 541-672-2691 | graysonb@adaptoregon.org | Adapt Integrated Health (Curry) |  | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177735-0-2 | Apartment Complex Purchase - Repurpose/Build New Facility | Hammond House Purchase
Grant Agreement Number: | 177735-0 | AdaptDouglasID | Q1 | 2023 | Jan 1 - Mar 31 | Q3 2023 (Jan 1 - Mar 31) | 2023-05-15 | 2023-01-01 | 2023-02-01 | 2023-03-01 | Benton | Benton County | 1 | Residential Treatment Homes | Less than 50% Complete | 177734 | 177734-0 | Adapt Integrated Health (Douglas) | AdaptDouglas | AdaptDouglasID | AdaptDouglasName | Grayson Bly | 541-672-2691 | graysonb@adaptoregon.org | Adapt Integrated Health (Douglas) | 177735-0-1 | Hammond House Purchase | Repurpose/Build New Facility | Repurpose/Build New Facility - Hammond House Purchase | 2023-05-01 | 2024-03-01 | 2024-03-15 | 4 | 177735-0-3 | Administrative Oversight and Project Management - Operational and Administrative Costs | Apartment Complex Purchase
Short Grant Agreement Number: | 177734 | AdaptDouglasID | Q2 | 2023 | Apr 1 - Jun 30 | Q4 2023 (Apr 1 - Jun 30) | 2023-08-20 | 2023-04-01 | 2023-05-01 | 2023-06-01 | Clackamas | Clackamas County | 2 | Adult Foster Homes | More than 50% Complete | 177680 | 177680-0 | Benton County Health Department Behavioral Health Division | Benton | BentonID | BentonName | N/A | N/A | N/A | Benton County Health Department Behavioral Health Division | 177735-0-2 | Apartment Complex Purchase | Repurpose/Build New Facility | Repurpose/Build New Facility - Apartment Complex Purchase | 2023-08-01 | 2024-08-01 | 2024-08-15 | 12 | 177735-0-4 | Full-Time Employee - Housing Support Services |  | Administrative Oversight and Project Management
Short Name: | AdaptDouglas |  | Q3 | 2023 | Jul 1 - Sep 30 | Q1 2024 (Jul 1 - Sep 30) | 2023-10-30 | 2023-07-01 | 2023-08-01 | 2023-09-01 | Clatsop | Clatsop County | 3 | Supported Housing Units |  | 177770 | 177770-0 | BestCare Treatment Services | BestCare | BestCareID | BestCareName | Rhonda Navarra | 541-504-1995 | rhodan@bestcaretreatment.org | BestCare Treatment Services | 177735-0-3 | Administrative Oversight and Project Management | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Oversight and Project Management |  |  |  |  | 177735-0-5 | Senior Level Staff Member and Project Manager - Planning, Coordinating, and Purchasing |  | Full-Time Employee
Short Name & ID: | AdaptDouglasID |  | Q4 | 2023 | Oct 1 - Dec 31 | Q2 2024 (Oct 1 - Dec 31) | 2024-01-30 | 2023-10-01 | 2023-11-01 | 2023-12-01 | Columbia | Columbia County | 4 | Supportive Housing Units |  | 177751 | 177751-0 | Center for Human Development | CHD | CHDID | CHDName | Kory Escobar | 541-962-8805 | gthompson@chdinc.org | Center for Human Development | 177735-0-4 | Full-Time Employee | Housing Support Services | Housing Support Services - Full-Time Employee |  |  |  |  | 177735-0-6 | Rental Funds for Five Individuals - Long Term Rental Assistance |  | Senior Level Staff Member and Project Manager
Category & Project Name: | AdaptDouglasName |  | Q1 | 2024 | Jan 1 - Mar 31 | Q3 2024 (Jan 1 - Mar 31) | 2024-04-30 | 2024-01-01 | 2024-02-01 | 2024-03-01 | Coos | Coos County | 5 |  |  | 177736 | 177736-0 | Clackamas County Behavioral Health Division | Clackamas | ClackamasID | ClackamasName | Mary Rumbaugh | 503-406-7005 | maryrum@clackamas.us | Clackamas County Behavioral Health Division | 177735-0-5 | Senior Level Staff Member and Project Manager | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Senior Level Staff Member and Project Manager |  |  |  |  | 177735-0-7 | New Medical Supplies and Clothing - Outreach and Engagement |  | Rental Funds for Five Individuals
Contact: | Grayson Bly |  | Q2 | 2024 | Apr 1 - Jun 30 | Q4 2024 (Apr 1 - Jun 30) | 2024-08-20 | 2024-04-01 | 2024-05-01 | 2024-06-01 | Crook | Crook County | 6 |  |  | 177670 | 177670-0 | Clatsop County Behavioral Healthcare | Clatsop | ClatsopID | ClatsopName | Amy Baker | 503-939-1857 | amyb@clatsopbh.org | Clatsop County Behavioral Healthcare | 177735-0-6 | Rental Funds for Five Individuals | Long Term Rental Assistance | Long Term Rental Assistance - Rental Funds for Five Individuals |  |  |  |  | 177734-0-1 | Building Purchase and Renovation - Repurpose/Build New Facility |  | New Medical Supplies and Clothing
Contact Phone: | 541-672-2691 |  | Q3 | 2024 | Jul 1 - Sep 30 | Q1 2025 (Jul 1 - Sep 30) | 2024-10-30 | 2024-07-01 | 2024-08-01 | 2024-09-01 | Curry | Curry County | 7 |  |  | 177716 | 177716-0 | Columbia Community Mental Health | Columbia | ColumbiaID | ColumbiaName | Todd Jacobson | 503-438-2201 | toddj@ccmh1.com | Columbia Community Mental Health | 177735-0-7 | New Medical Supplies and Clothing | Outreach and Engagement | Outreach and Engagement - New Medical Supplies and Clothing |  |  |  |  | 177734-0-2 | Administrative Oversight and Project Management - Operational and Administrative Costs
Contact Email: | graysonb@adaptoregon.org |  | Q4 | 2024 | Oct 1 - Dec 31 | Q2 2025 (Oct 1 - Dec 31) | 2025-01-30 | 2024-10-01 | 2024-11-01 | 2024-12-01 | Deschutes | Deschutes County | 8 |  |  | 177737 | 177737-0 | Community Counseling Solutions | CCS | CCSID | CCSName | Matt Bergstrom | 541-571-1439 | matt.bergstrom@ccsemail.org | Community Counseling Solutions | [8 empty] | 177734-0-3 | Two Full-Time Employees - Housing Support Services
|  |  | Q1 | 2025 | Jan 1 - Mar 31 | Q3 2025 (Jan 1 - Mar 31) | 2025-04-30 | 2025-01-01 | 2025-02-01 | 2025-03-01 | Douglas | Douglas County | 9 |  |  | 177671 | 177671-0 | Coos County Health & Wellness | Coos | CoosID | CoosName | David Geels | 541-266-6738 | david.geels@chw.coos.or.us | Coos County Health & Wellness | AdaptDouglas | 177734 | [6 empty] | 177734-0-4 | Senior Level Staff Member and Project Manager - Planning, Coordinating, and Purchasing
| ProjectIDs: |  | Q2 | 2025 | Apr 1 - Jun 30 | Q4 2025 (Apr 1 - Jun 30) | 2025-08-20 | 2025-04-01 | 2025-05-01 | 2025-06-01 | Gilliam | Gilliam County | 10 |  |  | 177672 | 177672-0 | Deschutes County | Deschutes | DeschutesID | DeschutesName | Holly Harris | 541-322-7508 | holly.harris@deschutes.org | Deschutes County |  | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177734-0-5 | Rental Funds for 18 months for 10 Individuals - Long Term Rental Assistance
177734-0-1 | 177734-0-1 | [9 empty] | Grant | Grant County | 11 |  |  | 177726 | 177726-0 | Jackson County Behavioral Health Services | Jackson | JacksonID | JacksonName | Jenn Inman | 541-774-7921 | inmanjk@jacksoncounty.org | Jackson County Behavioral Health Services | 177734-0-1 | Building Purchase and Renovation | Repurpose/Build New Facility | Repurpose/Build New Facility - Building Purchase and Renovation | 2022-11-22 | 2024-06-01 |  | 50 | 177734-0-6 | New Supplies that Cannot be Donated - Outreach and Engagement
177734-0-2 | 1 | [9 empty] | Harney | Harney County | 12 |  |  | 177698 | 177698-0 | Klamath Basin Behavioral Health | Klamath | KlamathID | KlamathName | Jennifer Hill | 541-883-1030 | jhill@kbbh.org | Klamath Basin Behavioral Health | 177734-0-2 | Administrative Oversight and Project Management | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Oversight and Project Management |  |  |  |  | 177680-0-1 | TBD - Housing Support Services
177734-0-3 | 177734-0-2 | [9 empty] | Hood River | Hood River County | 13 |  |  | 177674 | 177674-0 | Lake County Health District | Lake | LakeID | LakeName | Kristi Albertson | (406) 471-7680 | kalbertson@lakehealthdistrict.org | Lake County Health District | 177734-0-3 | Two Full-Time Employees | Housing Support Services | Housing Support Services - Two Full-Time Employees |  |  |  |  | 177680-0-2 | Rental Funds for 8 years for 10 Individuals - Long Term Rental Assistance
177734-0-4 | 1 | [9 empty] | Jackson | Jackson County | 14 |  |  | 177675 | 177675-0 | Lane County | Lane | LaneID | LaneName | Risa Holden | 541-513-4600 | rholden@sheltercare.org | Lane County | 177734-0-4 | Senior Level Staff Member and Project Manager | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Senior Level Staff Member and Project Manager |  |  |  |  | 177680-0-3 | Outreach and Engagement - Outreach and Engagement
177734-0-5 | 177734-0-3 | [9 empty] | Jefferson | Jefferson County | 15 |  |  | 177687 | 177687-0 | Lifeways Inc | Lifeways | LifewaysID | LifewaysName | Steve Jensen | 541-823-9005 | sjensen@lifeways.org | Lifeways Inc | 177734-0-5 | Rental Funds for 18 months for 10 Individuals | Long Term Rental Assistance | Long Term Rental Assistance - Rental Funds for 18 months for 10 Individuals |  |  |  |  | 177770-0-1 | New Facility Construction (Jefferson) - Repurpose/Build New Facility
177734-0-6 | 1 | [9 empty] | Josephine | Josephine County | 16 |  |  | 177676 | 177676-0 | Lincoln County Health and Human Services | Lincoln | LincolnID | LincolnName | Marie Laper/Lori Allen | 541-265-0581 | mlaper@co.lincoln.or.us / lallen@co.lincoln.or.us | Lincoln County Health and Human Services | 177734-0-6 | New Supplies that Cannot be Donated | Outreach and Engagement | Outreach and Engagement - New Supplies that Cannot be Donated |  |  |  |  | 177770-0-2 | Administrative Costs (Jefferson) - Operational and Administrative Costs
| 177734-0-4 | [9 empty] | Klamath | Klamath County | 17 + |  |  | 177747 | 177747-0 | Linn County | Linn | LinnID | LinnName | Tanya Thompson | 541-967-3866 (2304) | tthompson@co.linn.or.us | Linn County | [8 empty] | 177770-0-3 | Expansion of Exceptional Needs Care Coordination Capacity (Jefferson) - Housing Support Services
| 1 | [9 empty] | Lake | Lake County |  |  |  | 177688 | 177688-0 | Marion County Health and Human Services | Marion | MarionID | MarionName | Nike Neuvenheim | 503-576-4611 | nneuvenheim@co.marion.or.us | Marion County Health and Human Services | Benton | 177680 | [6 empty] | 177770-0-4 | Land Purchase (Jefferson) - Planning, Coordinating, and Purchasing
| 177734-0-5 | [9 empty] | Lane | Lane County |  |  |  | 177689 | 177689-0 | Mid Columbia Center for Living | MCCL | MCCLID | MCCLName | Al Barton | 541-296-5452 | abarton@mccfl.org | Mid Columbia Center for Living |  | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177770-0-5 | New Facility Construction (Crook) - Repurpose/Build New Facility
| 1 | [9 empty] | Lincoln | Lincoln County |  |  |  | 177677 | 177677-0 | Multnomah County Health Department | Multnomah | MultnomahID | MultnomahName | Desiree Batiste | 971-325-6409 | desiree.batiste@multco.us | Multnomah County Health Department | 177680-0-1 | TBD | Housing Support Services | Housing Support Services - TBD |  |  |  |  | 177770-0-6 | Administrative Costs (Crook) - Operational and Administrative Costs
| 177734-0-6 | [9 empty] | Linn | Linn County |  |  |  | 177684 | 177684-0 | New Directions Northwest, Inc. | New | NewID | NewName | Judy Lind | 541-523-7400 | jlind@ndninc.org | New Directions Northwest, Inc. | 177680-0-2 | Rental Funds for 8 years for 10 Individuals | Long Term Rental Assistance | Long Term Rental Assistance - Rental Funds for 8 years for 10 Individuals |  |  |  |  | 177770-0-7 | Expansion of Exceptional Needs Care Coordination Capacity (Crook) - Housing Support Services
| 1 | [9 empty] | Malheur | Malheur County |  |  |  | 177685 | 177685-0 | Options for Southern Oregon’s Behavioral Health | Options | OptionsID | OptionsName | Karla McCafferty | 541-476-2373 | kmccafferty@optionsonline.org | Options for Southern Oregon’s Behavioral Health | 177680-0-3 | Outreach and Engagement | Outreach and Engagement | Outreach and Engagement - Outreach and Engagement |  |  |  |  | 177770-0-8 | Land Purchase (Crook) - Planning, Coordinating, and Purchasing
| 0 | [9 empty] | Marion | Marion County |  |  |  | 177690 | 177690-0 | Polk County Health Services | Polk | PolkID | PolkName | Jennifer Lief | 503-623-9289 | lief.jennifer@co.polk.or.us | Polk County Health Services | [8 empty] | 177751-0-1 | Supportive and Transitional Housing - Repurpose/Build New Facility
| 0 | [9 empty] | Morrow | Morrow County |  |  |  | 177713 | 177713-0 | Symmetry Care | Symmetry | SymmetryID | SymmetryName | Chris Siegner | 541.573.8376 | csiegner@symmetrycareinc.com | Symmetry Care | BestCare | 177770 | [6 empty] | 177751-0-2 | Housing Coordinator and Administrative Costs - Operational and Administrative Costs
| 0 | [9 empty] | Multnomah | Multnomah County |  |  |  | 177679 | 177679-0 | Tillamook Family Counseling Center | Tillamook | TillamookID | TillamookName | Frank Hanna-Williams | 503-815-5414 | frankhw@tfcc.org | Tillamook Family Counseling Center |  | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177751-0-3 | Case Management Employees and Support Training - Housing Support Services
| 0 | [9 empty] | Polk | Polk County |  |  |  | 177692 | 177692-0 | Wallowa Valley Center for Wellness | Wallowa | WallowaID | WallowaName | Chantay Jett | 206-371-1497 | chantay.jett@wvcenterforwellness.org | Wallowa Valley Center for Wellness | 177770-0-1 | New Facility Construction (Jefferson) | Repurpose/Build New Facility | Repurpose/Build New Facility - New Facility Construction (Jefferson) |  |  |  | 16 | 177751-0-4 | Establish Housing Advisory Committee and Need Assessment/Planning Process - Planning, Coordinating, and Purchasing
| 0 | [9 empty] | Sherman | Sherman County |  |  |  | 178501 | 178501-0 | Warm Springs | Warm | WarmID | WarmName | Caroline M. Cruz | 541-615-0140 | caroline.cruz@wstribes.org | Warm Springs | 177770-0-2 | Administrative Costs (Jefferson) | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Costs (Jefferson) |  |  |  |  | 177751-0-5 | Emergency Hotel Vouchers - Short Term Bed Subsidy
| 0 | [9 empty] | Tillamook | Tillamook County |  |  |  | 177694 | 177694-0 | Washington County Department of Health and Human Services | Washington | WashingtonID | WashingtonName | Kristin Burke | 503-846-4563 | kristin_burke@washingtoncountyor.gov | Washington County Department of Health and Human Services | 177770-0-3 | Expansion of Exceptional Needs Care Coordination Capacity (Jefferson) | Housing Support Services | Housing Support Services - Expansion of Exceptional Needs Care Coordination Capacity (Jefferson) |  |  |  |  | 177751-0-6 | Rental, Deposit, and Utility Assistance - Long Term Rental Assistance
| 0 | [9 empty] | Umatilla | Umatilla County |  |  |  | 177708 | 177708-0 | Yamhill County Health and Human Services | Yamhill | YamhillID | YamhillName | Lindsey Manfrin | 503-434-7525 | manfrinl@co.yamhill.or.us | Yamhill County Health and Human Services | 177770-0-4 | Land Purchase (Jefferson) | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Land Purchase (Jefferson) |  |  |  |  | 177751-0-7 | Outreach and Engagement - Outreach and Engagement
| 0 | [9 empty] | Union | Union County | [13 empty] | 177770-0-5 | New Facility Construction (Crook) | Repurpose/Build New Facility | Repurpose/Build New Facility - New Facility Construction (Crook) |  |  |  | 16 | 177736-0-5 | Property Purchase - Repurpose/Build New Facility
| 0 | [9 empty] | Wallowa | Wallowa County | [13 empty] | 177770-0-6 | Administrative Costs (Crook) | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Costs (Crook) |  |  |  |  | 177736-0-6 | Operational and Administrative Costs - Operational and Administrative Costs
| 0 | [9 empty] | Wasco | Wasco County | [13 empty] | 177770-0-7 | Expansion of Exceptional Needs Care Coordination Capacity (Crook) | Housing Support Services | Housing Support Services - Expansion of Exceptional Needs Care Coordination Capacity (Crook) |  |  |  |  | 177736-0-7 | Partner with HACC to Access SH Services - Housing Support Services
| 0 | [9 empty] | Washington | Washington County | [13 empty] | 177770-0-8 | Land Purchase (Crook) | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Land Purchase (Crook) |  |  |  |  | 177736-0-8 | Pursue Rent-to-Own or Purchase - Planning, Coordinating, and Purchasing
| 0 | [9 empty] | Wheeler | Wheeler County | [21 empty] | 177736-0-9 | Outreach and Engagement Services - Outreach and Engagement
| 0 | [9 empty] | Yamhill | Yamhill County | [13 empty] | CHD | 177751 | [6 empty] | 177670-0-1 | Build Permanent Supportive Housing and Clinic - Repurpose/Build New Facility
| 0 | [25 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177670-0-2 | Vacant Land Purchase - Planning, Coordinating, and Purchasing
| 0 | [24 empty] | 177751-0-1 | Supportive and Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive and Transitional Housing |  |  |  |  | 177670-0-3 | Staff for Transitional Housing - Operational and Administrative Costs
| 0 | [24 empty] | 177751-0-2 | Housing Coordinator and Administrative Costs | Operational and Administrative Costs | Operational and Administrative Costs - Housing Coordinator and Administrative Costs |  |  |  |  | 177670-0-4 | Renovate Apartments in Clinic Building - Repurpose/Build New Facility
| 0 | [24 empty] | 177751-0-3 | Case Management Employees and Support Training | Housing Support Services | Housing Support Services - Case Management Employees and Support Training |  |  |  |  | 177716-0-1 | Transitional Supportive Housing - Repurpose/Build New Facility
| 0 | [24 empty] | 177751-0-4 | Establish Housing Advisory Committee and Need Assessment/Planning Process | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Establish Housing Advisory Committee and Need Assessment/Planning Process |  |  |  |  | 177716-0-2 | Transitional Supportive Housing - Repurpose/Build New Facility
| 0 | [24 empty] | 177751-0-5 | Emergency Hotel Vouchers | Short Term Bed Subsidy | Short Term Bed Subsidy - Emergency Hotel Vouchers |  |  |  |  | 177716-0-3 | Crisis Stabilization Center - Repurpose/Build New Facility
| 0 | [24 empty] | 177751-0-6 | Rental, Deposit, and Utility Assistance | Long Term Rental Assistance | Long Term Rental Assistance - Rental, Deposit, and Utility Assistance |  |  |  |  | 177716-0-4 | TBD - Operational and Administrative Costs
| 0 | [24 empty] | 177751-0-7 | Outreach and Engagement | Outreach and Engagement | Outreach and Engagement - Outreach and Engagement |  |  |  |  | 177716-0-5 | One year of staffing for both proposed projects - Housing Support Services
| 0 | [32 empty] | 177737-0-1 | Aspen Springs - Repurpose/Build New Facility
| 0 | [24 empty] | Clackamas | 177736 | [6 empty] | 177737-0-2 | 14-bedroom home in Pendleton - Repurpose/Build New Facility
| 0 | [25 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177737-0-3 | Hermiston Home (7 Bed) - Repurpose/Build New Facility
| 0 | [24 empty] | 177736-0-5 | Property Purchase | Repurpose/Build New Facility | Repurpose/Build New Facility - Property Purchase | 2022-10-01 | 2023-10-01 | 2024-03-01 | 10 | 177737-0-4 | Hermiston Home (5 Bed) - Repurpose/Build New Facility
| 0 | [24 empty] | 177736-0-6 | Operational and Administrative Costs | Operational and Administrative Costs | Operational and Administrative Costs - Operational and Administrative Costs |  |  |  |  | 177737-0-5 | Milton Freewater Home - Repurpose/Build New Facility
| 0 | [24 empty] | 177736-0-7 | Partner with HACC to Access SH Services | Housing Support Services | Housing Support Services - Partner with HACC to Access SH Services |  |  |  |  | 177737-0-6 | Home #1 for Supportive or Transitional Housing - Repurpose/Build New Facility
| 0 | [24 empty] | 177736-0-8 | Pursue Rent-to-Own or Purchase | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Pursue Rent-to-Own or Purchase |  |  |  |  | 177737-0-7 | Home #2 for Supportive or Transitional Housing - Repurpose/Build New Facility
| 0 | [24 empty] | 177736-0-9 | Outreach and Engagement Services | Outreach and Engagement | Outreach and Engagement - Outreach and Engagement Services |  |  |  |  | 177737-0-8 | Home #3 for Supportive or Transitional Housing - Repurpose/Build New Facility
| 0 | [32 empty] | 177737-0-9 | 2 unit house for Supportive Housing - Repurpose/Build New Facility
| 0 | [24 empty] | Clatsop | 177670 | [6 empty] | 177737-0-10 | Home #1 for Supportive or Transitional Housing - Repurpose/Build New Facility
| 0 | [25 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177737-0-11 | Home #2 for Supportive or Transitional Housing - Repurpose/Build New Facility
[26 empty] | 177670-0-1 | Build Permanent Supportive Housing and Clinic | Repurpose/Build New Facility | Repurpose/Build New Facility - Build Permanent Supportive Housing and Clinic | 2022-12-01 | 2025-08-31 | 2025-10-01 | 33 | 177737-0-12 | Home #3 for Supportive or Transitional Housing - Repurpose/Build New Facility
[26 empty] | 177670-0-2 | Vacant Land Purchase | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Vacant Land Purchase | 2022-12-01 | 2025-08-31 | 2025-10-01 | 32 | 177737-0-13 | 1-2 Homes for Supportive or Transitional Housing - Repurpose/Build New Facility
[26 empty] | 177670-0-3 | Staff for Transitional Housing | Operational and Administrative Costs | Operational and Administrative Costs - Staff for Transitional Housing | 2023-02-01 | 2024-02-01 | 2023-04-04 | 5 | 177737-0-14 | 1-2 Homes for Supportive or Transitional Housing - Repurpose/Build New Facility
[26 empty] | 177670-0-4 | Renovate Apartments in Clinic Building | Repurpose/Build New Facility | Repurpose/Build New Facility - Renovate Apartments in Clinic Building | 2023-02-01 | 2023-08-31 | 2023-06-01 | 3 | 177737-0-15 | Full-Time Housing Manager - Operational and Administrative Costs
[34 empty] | 177737-0-16 | Full-Time Support Service - Operational and Administrative Costs
[26 empty] | Columbia | 177716 | [6 empty] | 177737-0-17 | Provide funding to CTUIR - Operational and Administrative Costs
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177737-0-18 | CTUIR Wheelchair-Accessible Van - Housing Support Services
[26 empty] | 177716-0-1 | Transitional Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Transitional Supportive Housing |  | 2025-03-01 |  | 13 | 177737-0-19 | Architect, permit, planning fees work for remodel and construction projects - Planning, Coordinating, and Purchasing
[26 empty] | 177716-0-2 | Transitional Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Transitional Supportive Housing |  | 2025-03-01 |  | 10 | 177737-0-20 | Short-Term Funding for 400 Individuals - Short Term Bed Subsidy
[26 empty] | 177716-0-3 | Crisis Stabilization Center | Repurpose/Build New Facility | Repurpose/Build New Facility - Crisis Stabilization Center |  | 2023-08-01 |  |  | 177737-0-21 | Long-Term Funding for 60 Individuals - Long Term Rental Assistance
[26 empty] | 177716-0-4 | TBD | Operational and Administrative Costs | Operational and Administrative Costs - TBD |  |  |  |  | 177737-0-22 | Supplies and Support for Immediate Needs - Outreach and Engagement
[26 empty] | 177716-0-5 | One year of staffing for both proposed projects | Housing Support Services | Housing Support Services - One year of staffing for both proposed projects |  |  |  |  | 177671-0-1 | Supportive Housing Units - Repurpose/Build New Facility
[34 empty] | 177671-0-2 | Project-Based Vouchers for Supportive Housing Projects - Operational and Administrative Costs
[26 empty] | CCS | 177737 | [6 empty] | 177671-0-3 | Managing Additional Units - Housing Support Services
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177671-0-4 | Full Time Employee to Develop Projects - Planning, Coordinating, and Purchasing
[26 empty] | 177737-0-1 | Aspen Springs | Repurpose/Build New Facility | Repurpose/Build New Facility - Aspen Springs |  |  |  | 7 | 177671-0-5 | Expansion of Pallet Home Project - Short Term Bed Subsidy
[26 empty] | 177737-0-2 | 14-bedroom home in Pendleton | Repurpose/Build New Facility | Repurpose/Build New Facility - 14-bedroom home in Pendleton |  |  |  | 12 | 177671-0-6 | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177737-0-3 | Hermiston Home (7 Bed) | Repurpose/Build New Facility | Repurpose/Build New Facility - Hermiston Home (7 Bed) |  |  |  | 7 | 177671-0-7 | Provide Basic Needs to Homeless Population - Outreach and Engagement
[26 empty] | 177737-0-4 | Hermiston Home (5 Bed) | Repurpose/Build New Facility | Repurpose/Build New Facility - Hermiston Home (5 Bed) |  |  |  | 5 | 177672-0-1 | 16-Bed SRTF - Repurpose/Build New Facility
[26 empty] | 177737-0-5 | Milton Freewater Home | Repurpose/Build New Facility | Repurpose/Build New Facility - Milton Freewater Home |  |  |  | 3 | 177672-0-2 | Administrative Activities and Oversight - Operational and Administrative Costs
[26 empty] | 177737-0-6 | Home #1 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #1 for Supportive or Transitional Housing |  |  |  | 3 | 177672-0-3 | Inpatient Beds for Youth and Young Adults - Planning, Coordinating, and Purchasing
[26 empty] | 177737-0-7 | Home #2 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #2 for Supportive or Transitional Housing |  |  |  | 3 | 177726-0-1 | 30-Unit Permanent Supportive Housing - Repurpose/Build New Facility
[26 empty] | 177737-0-8 | Home #3 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #3 for Supportive or Transitional Housing |  |  |  | 3 | 177726-0-2 | Project Workgroup Planning - Planning, Coordinating, and Purchasing
[26 empty] | 177737-0-9 | 2 unit house for Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - 2 unit house for Supportive Housing |  |  |  | 2 | 177698-0-1 | RTF and CRC - Repurpose/Build New Facility
[26 empty] | 177737-0-10 | Home #1 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #1 for Supportive or Transitional Housing |  |  |  | 3 | 177698-0-2 | Administrative and Facility Expenses - Operational and Administrative Costs
[26 empty] | 177737-0-11 | Home #2 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #2 for Supportive or Transitional Housing |  |  |  | 3 | 177698-0-3 | Assume Ownership of Vacant Lots - Planning, Coordinating, and Purchasing
[26 empty] | 177737-0-12 | Home #3 for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Home #3 for Supportive or Transitional Housing |  |  |  | 3 | 177698-0-4 | Annual Contract with Travelodge - Short Term Bed Subsidy
[26 empty] | 177737-0-13 | 1-2 Homes for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - 1-2 Homes for Supportive or Transitional Housing |  |  |  | 4 | 177698-0-5 | Treatment Supports - Outreach and Engagement
[26 empty] | 177737-0-14 | 1-2 Homes for Supportive or Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - 1-2 Homes for Supportive or Transitional Housing |  |  |  | 4 | 177698-0-6 | Rental Subsidy Program - Long Term Rental Assistance
[26 empty] | 177737-0-15 | Full-Time Housing Manager | Operational and Administrative Costs | Operational and Administrative Costs - Full-Time Housing Manager |  |  |  |  | 177674-0-1 | Supportive Housing for SPMI and/or SUD - Repurpose/Build New Facility
[26 empty] | 177737-0-16 | Full-Time Support Service | Operational and Administrative Costs | Operational and Administrative Costs - Full-Time Support Service |  |  |  |  | 177674-0-2 | Job Skills Training, Childcare, and Screenings - Housing Support Services
[26 empty] | 177737-0-17 | Provide funding to CTUIR | Operational and Administrative Costs | Provide funding to CTUIR - Operational and Administrative Costs |  |  |  |  | 177674-0-3 | Planning and Coordination; Pre-Build Activities and Purchases - Planning, Coordinating, and Purchasing
[26 empty] | 177737-0-18 | CTUIR Wheelchair-Accessible Van | Housing Support Services | CTUIR Wheelchair-Accessible Van - Housing Support Services |  |  |  |  | 177674-0-4 | Immediate Client Needs - Outreach and Engagement
[26 empty] | 177737-0-19 | Architect, permit, planning fees work for remodel and construction projects | Planning, Coordinating, and Purchasing | Architect, permit, planning fees work for remodel and construction projects - Planning, Coordinating, and Purchasing |  |  |  |  | 177675-0-1 | Repurpose a 5-Bed RTH - Repurpose/Build New Facility
[26 empty] | 177737-0-20 | Short-Term Funding for 400 Individuals | Short Term Bed Subsidy | Short-Term Funding for 400 Individuals - Short Term Bed Subsidy |  |  |  |  | 177675-0-2 | 16-Bed RTF - Repurpose/Build New Facility
[26 empty] | 177737-0-21 | Long-Term Funding for 60 Individuals | Long Term Rental Assistance | Long-Term Funding for 60 Individuals - Long Term Rental Assistance |  |  |  |  | 177675-0-3 | 5-Bed RTH - Repurpose/Build New Facility
[26 empty] | 177737-0-22 | Supplies and Support for Immediate Needs | Outreach and Engagement | Outreach and Engagement - Supplies and Support for Immediate Needs |  |  |  |  | 177675-0-4 | 5-Bed AFH - Repurpose/Build New Facility
[34 empty] | 177675-0-5 | Purchase #1 of 2 housing units for Aid & Assist shelter/supportive services - Repurpose/Build New Facility
[26 empty] | Coos | 177671 | [6 empty] | 177675-0-6 | Purchase #2 of 2 housing units for Aid & Assist shelter/supportive services - Repurpose/Build New Facility
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177675-0-7 | Equipment, Training, and Administrative Costs - Operational and Administrative Costs
[26 empty] | 177671-0-1 | Supportive Housing Units | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing Units | 2023-05-01 | 2023-10-01 | 2023-12-01 | 20 | 177675-0-8 | Support Services for The Commons on MLK PSF - Housing Support Services
[26 empty] | 177671-0-2 | Project-Based Vouchers for Supportive Housing Projects | Operational and Administrative Costs | Operational and Administrative Costs - Project-Based Vouchers for Supportive Housing Projects |  |  |  |  | 177675-0-9 | Peer Navigator - Housing Support Services
[26 empty] | 177671-0-3 | Managing Additional Units | Housing Support Services | Housing Support Services - Managing Additional Units |  |  |  |  | 177675-0-10 | Project Coordinator - Planning, Coordinating, and Purchasing
[26 empty] | 177671-0-4 | Full Time Employee to Develop Projects | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Full Time Employee to Develop Projects |  |  |  |  | 177687-0-1 | Supportive Housing - Repurpose/Build New Facility
[26 empty] | 177671-0-5 | Expansion of Pallet Home Project | Short Term Bed Subsidy | Short Term Bed Subsidy - Expansion of Pallet Home Project |  |  |  |  | 177676-0-1 | Administrative costs to repurpose a group home as a 23 hour crisis resolution center. - Operational and Administrative Costs
[26 empty] | 177671-0-6 | Long Term Rental Assistance | Long Term Rental Assistance | Long Term Rental Assistance - Long Term Rental Assistance |  |  |  |  | 177676-0-2 | Development of a housing complex dedicated to housing individuals referred by LC HHS with SPMI - Planning, Coordinating, and Purchasing
[26 empty] | 177671-0-7 | Provide Basic Needs to Homeless Population | Outreach and Engagement | Outreach and Engagement - Provide Basic Needs to Homeless Population |  |  |  |  | 177676-0-3 | Emergency Items - Outreach and Engagement
[34 empty] | 177747-0-1 | Supportive Housing - Repurpose/Build New Facility
[26 empty] | Deschutes | 177672 | [6 empty] | 177747-0-2 | Community Center - Repurpose/Build New Facility
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177747-0-3 | APHCD Funding - Operational and Administrative Costs
[26 empty] | 177672-0-1 | 16-Bed SRTF | Repurpose/Build New Facility | Repurpose/Build New Facility - 16-Bed SRTF | 2023-08-01 | 2023-08-01 | 2023-08-01 | 16 | 177747-0-4 | LCHD Funding - Operational and Administrative Costs
[26 empty] | 177672-0-2 | Administrative Activities and Oversight | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Activities and Oversight |  |  |  |  | 177747-0-5 | APHCD and LCMH Funding - Housing Support Services
[26 empty] | 177672-0-3 | Inpatient Beds for Youth and Young Adults | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Inpatient Beds for Youth and Young Adults |  |  |  |  | 177747-0-6 | Oxford Housing for SUD/BH Population - Short Term Bed Subsidy
[34 empty] | 177688-0-1 | IDD/Behavioral Health RTH - Repurpose/Build New Facility
[26 empty] | Jackson | 177726 | [6 empty] | 177688-0-2 | Staffing, Training, and Support - Operational and Administrative Costs
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177688-0-3 | Start up costs for IDD/Behavioral Health RTH - Planning, Coordinating, and Purchasing
[26 empty] | 177726-0-1 | 30-Unit Permanent Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - 30-Unit Permanent Supportive Housing |  |  |  | 30 | 177688-0-4 | Develop an RTH for individuals diagnosed with Co-Occurring Disorders - Repurpose/Build New Facility
[26 empty] | 177726-0-2 | Project Workgroup Planning | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Project Workgroup Planning |  |  |  |  | 177688-0-5 | Staffing, Training, and Support - Operational and Administrative Costs
[34 empty] | 177688-0-6 | Nursing Service for Aging Population - Housing Support Services
[26 empty] | Klamath | 177698 | [6 empty] | 177688-0-7 | Acquire Building for Supportive Housing - Repurpose/Build New Facility
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177688-0-8 | Administrative costs - Operational and Administrative Costs
[26 empty] | 177698-0-1 | RTF and CRC | Repurpose/Build New Facility | Repurpose/Build New Facility - RTF and CRC |  | 2024-10-31 |  | 20 | 177688-0-9 | 0.5 FTE Care Coordinator - Operational and Administrative Costs
[26 empty] | 177698-0-2 | Administrative and Facility Expenses | Operational and Administrative Costs | Operational and Administrative Costs - Administrative and Facility Expenses |  | 2024-10-31 |  |  | 177688-0-10 | 0.5 FTE Peer Support Specialist - Operational and Administrative Costs
[26 empty] | 177698-0-3 | Assume Ownership of Vacant Lots | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Assume Ownership of Vacant Lots | 2022-09-09 | 2024-09-01 | 2025-01-01 |  | 177688-0-11 | 1.0 FTE Housing Navigator - Operational and Administrative Costs
[26 empty] | 177698-0-4 | Annual Contract with Travelodge | Short Term Bed Subsidy | Short Term Bed Subsidy - Annual Contract with Travelodge |  |  |  |  | 177688-0-12 | 1.0 FTE Program Coordinator 2 - Operational and Administrative Costs
[26 empty] | 177698-0-5 | Treatment Supports | Outreach and Engagement | Outreach and Engagement - Treatment Supports |  |  |  |  | 177688-0-13 | Five 2-Bed Subsidies - Long Term Rental Assistance
[26 empty] | 177698-0-6 | Rental Subsidy Program | Long Term Rental Assistance | Long Term Rental Assistance - Rental Subsidy Program |  |  |  |  | 177688-0-14 | Five 3-Bed Subsidies - Long Term Rental Assistance
[34 empty] | 177688-0-15 | 5 RAP Subsidies - Long Term Rental Assistance
[26 empty] | Lake | 177674 | [6 empty] | 177688-0-16 | Administrative Cost for Family RAP - Operational and Administrative Costs
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177688-0-17 | Barrier Removal - Housing Support Services
[26 empty] | 177674-0-1 | Supportive Housing for SPMI and/or SUD | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing for SPMI and/or SUD |  |  |  | 4 | 177688-0-18 | Hotel Vouchers & Tiny Homes - Short Term Bed Subsidy
[26 empty] | 177674-0-2 | Job Skills Training, Childcare, and Screenings | Housing Support Services | Housing Support Services - Job Skills Training, Childcare, and Screenings |  |  |  |  | 177688-0-19 | Barrier Removal - Outreach and Engagement
[26 empty] | 177674-0-3 | Planning and Coordination; Pre-Build Activities and Purchases | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Planning and Coordination; Pre-Build Activities and Purchases | 2023-01-12 | 2023-04-01 |  |  | 177689-0-1 | Supportive Housing - Repurpose/Build New Facility
[26 empty] | 177674-0-4 | Immediate Client Needs | Outreach and Engagement | Outreach and Engagement - Immediate Client Needs |  |  |  |  | 177689-0-2 | Operational and Administrative Costs - Operational and Administrative Costs
[34 empty] | 177689-0-3 | Peer Supports - Housing Support Services
[26 empty] | Lane | 177675 | [6 empty] | 177689-0-4 | Shelter Support - Short Term Bed Subsidy
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177689-0-5 | Street Outreach Program - Outreach and Engagement
[26 empty] | 177675-0-1 | Repurpose a 5-Bed RTH | Repurpose/Build New Facility | Repurpose/Build New Facility - Repurpose a 5-Bed RTH |  |  |  | 5 | 177677-0-1 | Holistic Healing Facility - Repurpose/Build New Facility
[26 empty] | 177675-0-2 | 16-Bed RTF | Repurpose/Build New Facility | Repurpose/Build New Facility - 16-Bed RTF |  |  |  | 16 | 177677-0-2 | Miracles Club Facility - Repurpose/Build New Facility
[26 empty] | 177675-0-3 | 5-Bed RTH | Repurpose/Build New Facility | Repurpose/Build New Facility - 5-Bed RTH |  |  |  | 5 | 177677-0-3 | VOA Recovery Homes - Repurpose/Build New Facility
[26 empty] | 177675-0-4 | 5-Bed AFH | Repurpose/Build New Facility | Repurpose/Build New Facility - 5-Bed AFH |  |  |  | 5 | 177677-0-4 | Quest Admin and Assistance Costs - Operational and Administrative Costs
[26 empty] | 177675-0-5 | Purchase #1 of 2 housing units for Aid & Assist shelter/supportive services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase #1 of 2 housing units for Aid & Assist shelter/supportive services |  |  |  | 1 | 177677-0-5 | Housing Program Specialist - Operational and Administrative Costs
[26 empty] | 177675-0-6 | Purchase #2 of 2 housing units for Aid & Assist shelter/supportive services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase #2 of 2 housing units for Aid & Assist shelter/supportive services |  |  |  | 1 | 177677-0-6 | Holistic Healing Admin and Assistance Costs - Operational and Administrative Costs
[26 empty] | 177675-0-7 | Equipment, Training, and Administrative Costs | Operational and Administrative Costs | Operational and Administrative Costs - Equipment, Training, and Administrative Costs |  |  |  |  | 177677-0-7 | Cascadia Enhanced Outreach Team - Housing Support Services
[26 empty] | 177675-0-8 | Support Services for The Commons on MLK PSF | Housing Support Services | Housing Support Services - Support Services for The Commons on MLK PSF |  |  |  |  | 177677-0-8 | MCHD BHD Internal Program Assistance - Housing Support Services
[26 empty] | 177675-0-9 | Peer Navigator | Housing Support Services | Housing Support Services - Peer Navigator |  |  |  |  | 177677-0-9 | MCHD BHD BHRC Program Specialist - Housing Support Services
[26 empty] | 177675-0-10 | Project Coordinator | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Project Coordinator |  |  |  |  | 177677-0-10 | MHAAO Headquarters - Planning, Coordinating, and Purchasing
[34 empty] | 177677-0-11 | Client Assistance Funds - Outreach and Engagement
[26 empty] | Lifeways | 177687 | [6 empty] | 177677-0-12 | TBD - Repurpose/Build New Facility
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177684-0-1 | Facility and Maintenance - Operational and Administrative Costs
[26 empty] | 177687-0-1 | Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing | 2023-08-31 | 2024-06-30 | 2024-07-01 | 12 | 177684-0-2 | Liability and Fire Insurance - Operational and Administrative Costs
[34 empty] | 177684-0-3 | Utility Costs - Operational and Administrative Costs
[26 empty] | Lincoln | 177676 | [6 empty] | 177684-0-4 | Administrative Costs - Operational and Administrative Costs
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177684-0-5 | Full Time Housing Case Manager - Housing Support Services
[26 empty] | 177676-0-1 | Administrative costs to repurpose a group home as a 23 hour crisis resolution center. | Operational and Administrative Costs | Operational and Administrative Costs - Administrative costs to repurpose a group home as a 23 hour crisis resolution center. |  |  |  |  | 177684-0-6 | Purchase Land and two structures for Men's TH - Planning, Coordinating, and Purchasing
[26 empty] | 177676-0-2 | Development of a housing complex dedicated to housing individuals referred by LC HHS with SPMI | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Development of a housing complex dedicated to housing individuals referred by LC HHS with SPMI |  | 2025-12-01 |  | 24 | 177684-0-7 | Purchase Manufactured/Modular Home for Men's TH - Planning, Coordinating, and Purchasing
[26 empty] | 177676-0-3 | Emergency Items | Outreach and Engagement | Outreach and Engagement - Emergency Items |  |  |  |  | 177684-0-8 | Purchase homes for women's transitional housing - Planning, Coordinating, and Purchasing
[34 empty] | 177684-0-9 | Purchase home for supportive housing - Planning, Coordinating, and Purchasing
[26 empty] | Linn | 177747 | [6 empty] | 177684-0-10 | Subcontract with Local Hotel - Short Term Bed Subsidy
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177684-0-11 | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177747-0-1 | Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing |  | 2025-07-01 |  | 20 | 177684-0-12 | Necessities for Homeless Population - Outreach and Engagement
[26 empty] | 177747-0-2 | Community Center | Repurpose/Build New Facility | Repurpose/Build New Facility - Community Center |  |  |  |  | 177684-0-13 | Sleep Supplies for Homeless Population - Outreach and Engagement
[26 empty] | 177747-0-3 | APHCD Funding | Operational and Administrative Costs | Operational and Administrative Costs - APHCD Funding |  |  |  |  | 177685-0-1 | Purchase house #1 of 3-4 houses to provide supportive/supported housing services - Repurpose/Build New Facility
[26 empty] | 177747-0-4 | LCHD Funding | Operational and Administrative Costs | Operational and Administrative Costs - LCHD Funding |  |  |  |  | 177685-0-2 | Purchase house #2 of 3-4 houses to provide supportive/supported housing services - Repurpose/Build New Facility
[26 empty] | 177747-0-5 | APHCD and LCMH Funding | Housing Support Services | Housing Support Services - APHCD and LCMH Funding |  |  |  |  | 177685-0-3 | Purchase house #3 of 3-4 houses to provide supportive/supported housing services - Repurpose/Build New Facility
[26 empty] | 177747-0-6 | Oxford Housing for SUD/BH Population | Short Term Bed Subsidy | Short Term Bed Subsidy - Oxford Housing for SUD/BH Population |  |  |  |  | 177685-0-4 | Purchase house #4 of 3-4 houses to provide supportive/supported housing services - Repurpose/Build New Facility
[34 empty] | 177685-0-5 | Housing Coordination Services - Operational and Administrative Costs
[26 empty] | Marion | 177688 | [6 empty] | 177685-0-6 | Housing Support Service Staff - Housing Support Services
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177685-0-7 | Transitional Step-Down Housing Program - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-1 | IDD/Behavioral Health RTH | Repurpose/Build New Facility | Repurpose/Build New Facility - IDD/Behavioral Health RTH | 2023-04-06 | 2024-04-21 | 2024-03-31 | 5 | 177685-0-8 | Short Term Shelter - Short Term Bed Subsidy
[26 empty] | 177688-0-2 | Staffing, Training, and Support | Operational and Administrative Costs | Operational and Administrative Costs - Staffing, Training, and Support | 2023-04-06 | 2023-04-21 | 2024-03-31 | 5 | 177685-0-9 | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177688-0-3 | Start up costs for IDD/Behavioral Health RTH | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Start up costs for IDD/Behavioral Health RTH | 2023-04-06 | 2024-04-21 | 2024-03-31 | 5 | 177685-0-10 | Necessities for Homeless Population - Outreach and Engagement
[26 empty] | 177688-0-4 | Develop an RTH for individuals diagnosed with Co-Occurring Disorders | Repurpose/Build New Facility | Repurpose/Build New Facility - Develop an RTH for individuals diagnosed with Co-Occurring Disorders | 2023-10-01 | 2024-04-21 | 2024-04-21 | 5 | 177690-0-1 | CSRC - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-5 | Staffing, Training, and Support | Operational and Administrative Costs | Operational and Administrative Costs - Staffing, Training, and Support | 2023-10-01 | 2024-04-21 | 2024-04-21 | 5 | 177690-0-2 | STTP - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-6 | Nursing Service for Aging Population | Housing Support Services | Housing Support Services - Nursing Service for Aging Population |  |  |  |  | 177690-0-3 | Salaries, Benefits, and Wages - Operational and Administrative Costs
[26 empty] | 177688-0-7 | Acquire Building for Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Acquire Building for Supportive Housing |  |  |  | 46 | 177713-0-1 | SH Apartments - Repurpose/Build New Facility
[26 empty] | 177688-0-8 | Administrative costs | Operational and Administrative Costs | Operational and Administrative Costs - Administrative costs |  |  |  |  | 177713-0-2 | Recovery Mentor - Operational and Administrative Costs
[26 empty] | 177688-0-9 | 0.5 FTE Care Coordinator | Operational and Administrative Costs | Operational and Administrative Costs - 0.5 FTE Care Coordinator | 2023-01-01 | 2025-06-30 |  |  | 177713-0-3 | Resident-Employed Coffee Shop - Housing Support Services
[26 empty] | 177688-0-10 | 0.5 FTE Peer Support Specialist | Operational and Administrative Costs | Operational and Administrative Costs - 0.5 FTE Peer Support Specialist |  | 2025-06-30 |  |  | 177713-0-4 | Building Purchase and Related Costs - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-11 | 1.0 FTE Housing Navigator | Operational and Administrative Costs | Operational and Administrative Costs - 1.0 FTE Housing Navigator | 2023-07-01 | 2027-06-30 |  |  | 177713-0-5 | Rental Assistance for 4-Plex Tenants - Long Term Rental Assistance
[26 empty] | 177688-0-12 | 1.0 FTE Program Coordinator 2 | Operational and Administrative Costs | Operational and Administrative Costs - 1.0 FTE Program Coordinator 2 | 2023-05-30 | 2027-06-30 |  |  | 177713-0-6 | Outreach and Resources - Outreach and Engagement
[26 empty] | 177688-0-13 | Five 2-Bed Subsidies | Long Term Rental Assistance | Long Term Rental Assistance - Five 2-Bed Subsidies | 2023-07-01 | 2025-06-30 | 2023-07-01 |  | 177679-0-1 | Supportive Housing - Repurpose/Build New Facility
[26 empty] | 177688-0-14 | Five 3-Bed Subsidies | Long Term Rental Assistance | Long Term Rental Assistance - Five 3-Bed Subsidies | 2023-07-01 | 2025-06-30 | 2023-07-01 |  | 177679-0-2 | Operations Manager - Operational and Administrative Costs
[26 empty] | 177688-0-15 | Five RAP Subsidies | Long Term Rental Assistance | Long Term Rental Assistance - Five RAP Subsidies | 2023-07-01 | 2025-06-30 | 2023-07-01 |  | 177679-0-3 | Purchase Microwaves - Housing Support Services
[26 empty] | 177688-0-16 | Administrative Cost for Family RAP | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Cost for Family RAP | 2023-07-01 | 2025-06-30 |  |  | 177679-0-4 | SH Flooring Replacement - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-17 | Barrier Removal | Housing Support Services | Housing Support Services - Barrier Removal | 2023-07-01 | 2025-06-30 |  |  | 177679-0-5 | Interior/Exterior Building Supplies, Equipment and Repairs - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-18 | Hotel Vouchers & Tiny Homes | Short Term Bed Subsidy | Short Term Bed Subsidy - Hotel Vouchers & Tiny Homes | 2023-07-01 | 2027-06-30 |  |  | 177679-0-6 | Striping for Parking - Planning, Coordinating, and Purchasing
[26 empty] | 177688-0-19 | Barrier Removal | Outreach and Engagement | Outreach and Engagement - Barrier Removal | 2023-07-01 | 2027-06-30 |  |  | 177692-0-1 | Supported Transitional Housing - Repurpose/Build New Facility
[34 empty] | 177692-0-2 | Add Two Units to Facility - Repurpose/Build New Facility
[26 empty] | MCCL | 177689 | [6 empty] | 177692-0-3 | Operational Costs - Operational and Administrative Costs
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 177692-0-4 | Offsite House Manager - Housing Support Services
[26 empty] | 177689-0-1 | Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing | 2023-03-23 | 2023-10-01 | 2023-09-01 | 22 | 177692-0-5 | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177689-0-2 | Operational and Administrative Costs | Operational and Administrative Costs | Operational and Administrative Costs - Operational and Administrative Costs |  |  |  |  | 178501-0-1 | Repurpose/Build New Housing Units - Outreach and Engagement
[26 empty] | 177689-0-3 | Peer Supports | Housing Support Services | Housing Support Services - Peer Supports |  |  |  |  | 178501-0-2 | TBD - Short Term Bed Subsidy
[26 empty] | 177689-0-4 | Shelter Support | Short Term Bed Subsidy | Short Term Bed Subsidy - Shelter Support |  |  |  |  | 178501-0-3 | TBD - Operational and Administrative Costs
[26 empty] | 177689-0-5 | Street Outreach Program | Outreach and Engagement | Outreach and Engagement - Street Outreach Program |  |  |  |  | 178501-0-4 | Purchase Items for Facility - Housing Support Services
[34 empty] | 178501-0-5 | Long Term Rental Assistance - Planning, Coordinating, and Purchasing
[26 empty] | Multnomah | 177677 | [6 empty] | 178501-0-6 | TBD - Long Term Rental Assistance
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable) | 178501-0-7 | TBD - Outreach and Engagement
[26 empty] | 177677-0-1 | Holistic Healing Facility | Repurpose/Build New Facility | Repurpose/Build New Facility - Holistic Healing Facility |  |  |  | 12 | 178501-0-8 | TBD - Short Term Bed Subsidy
[26 empty] | 177677-0-2 | Miracles Club Facility | Repurpose/Build New Facility | Repurpose/Build New Facility - Miracles Club Facility |  |  |  | 24 | 177694-0-1 | Permanent Supportive Housing - Repurpose/Build New Facility
[26 empty] | 177677-0-3 | VOA Recovery Homes | Operational and Administrative Costs | Operational and Administrative Costs - VOA Recovery Homes |  |  |  | 13 | 177694-0-2 | Center for Addictions Triage and Treatment - Repurpose/Build New Facility
[26 empty] | 177677-0-4 | Quest Admin and Assistance Costs | Operational and Administrative Costs | Operational and Administrative Costs - Quest Admin and Assistance Costs |  |  |  |  | 177694-0-3 | Supportive Housing for Aid and Assist Population - Repurpose/Build New Facility
[26 empty] | 177677-0-5 | Housing Program Specialist | Operational and Administrative Costs | Operational and Administrative Costs - Housing Program Specialist |  |  |  |  | 177708-0-1 | Transitional Treatment Recovery Services; Transitional Treatment with On-Site Support; On-Site Support and Services Expansion - Operational and Administrative Costs
[26 empty] | 177677-0-6 | Holistic Healing Admin and Assistance Costs | Operational and Administrative Costs | Operational and Administrative Costs - Holistic Healing Admin and Assistance Costs |  |  |  |  | 177708-0-2 | Barrier Removal Support - Housing Support Services
[26 empty] | 177677-0-7 | Cascadia Enhanced Outreach Team | Housing Support Services | Housing Support Services - Cascadia Enhanced Outreach Team |  |  |  |  | 177708-0-3 | Transitional Treatment Residential Services Expansion - Planning, Coordinating, and Purchasing
[26 empty] | 177677-0-8 | MCHD BHD Internal Program Assistance | Housing Support Services | Housing Support Services - MCHD BHD Internal Program Assistance |  |  |  |  | 177708-0-4 | Non-Congregate Transitional Housing with On-Site Support Expansion - Planning, Coordinating, and Purchasing
[26 empty] | 177677-0-9 | MCHD BHD BHRC Program Specialist | Housing Support Services | Housing Support Services - MCHD BHD BHRC Program Specialist |  |  |  |  | 177708-0-5 | Congregate Sheltering with On-Site Support and Services Expansion - Planning, Coordinating, and Purchasing
[26 empty] | 177677-0-10 | MHAAO Headquarters | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - MHAAO Headquarters |  |  |  |  | 177708-0-6 | Crisis House Renovation - Planning, Coordinating, and Purchasing
[26 empty] | 177677-0-11 | Client Assistance Funds | Outreach and Engagement | Outreach and Engagement - Client Assistance Funds |  |  |  |  | 177708-0-7 | Basic Necessities - Outreach and Engagement
[26 empty] | 177677-0-12 | Volunteers of America will purchase a facility to house their Latino Home Base Recovery Home (LHBR) | Repurpose/Build New Facility | Repurpose/Build New Facility - Volunteers of America will purchase a facility to house their Latino Home Base Recovery Home (LHBR)
[26 empty] | 177677-0-13 | MCHD BHD will work with partners to determine the best usage of remaining grant funds for one or more of the following activities: repurpose or build new secure residential treatment facilities, residential treatment homes, adult foster homes, supported housing units, and supportive housing units; operational and administrative costs to manage housing; supportive housing | Repurpose/Build New Facility | Repurpose/Build New Facility - MCHD BHD will work with partners to determine the best usage of remaining grant funds for one or more of the following activities: repurpose or build new secure residential treatment facilities, residential treatment homes, adult foster homes, supported housing units, and supportive housing units; operational and administrative costs to manage housing; supportive housing
[26 empty] | New | 177684
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177684-0-1 | Facility and Maintenance | Operational and Administrative Costs | Operational and Administrative Costs - Facility and Maintenance | 2023-03-02 | 2023-12-31 | 2023-08-15 | 16
[26 empty] | 177684-0-2 | Liability and Fire Insurance | Operational and Administrative Costs | Operational and Administrative Costs - Liability and Fire Insurance
[26 empty] | 177684-0-3 | Utility Costs | Operational and Administrative Costs | Operational and Administrative Costs - Utility Costs
[26 empty] | 177684-0-4 | Administrative Costs | Operational and Administrative Costs | Operational and Administrative Costs - Administrative Costs
[26 empty] | 177684-0-5 | Full Time Housing Case Manager | Housing Support Services | Housing Support Services - Full Time Housing Case Manager
[26 empty] | 177684-0-6 | Purchase Land and two structures for Men's TH | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Purchase Land and two structures for Men's TH |  |  |  | 6
[26 empty] | 177684-0-7 | Purchase Manufactured/Modular Home for Men's TH | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Purchase Manufactured/Modular Home for Men's TH |  |  |  | 8
[26 empty] | 177684-0-8 | Purchase homes for women's transitional housing | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Purchase homes for women's transitional housing |  |  |  | 4
[26 empty] | 177684-0-9 | Purchase home for supportive housing | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Purchase home for supportive housing |  |  |  | 2
[26 empty] | 177684-0-10 | Subcontract with Local Hotel | Short Term Bed Subsidy | Short Term Bed Subsidy - Subcontract with Local Hotel
[26 empty] | 177684-0-11 | Long Term Rental Assistance | Long Term Rental Assistance | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177684-0-12 | Necessities for Homeless Population | Outreach and Engagement | Outreach and Engagement - Necessities for Homeless Population
[26 empty] | 177684-0-13 | Sleep Supplies for Homeless Population | Outreach and Engagement | Outreach and Engagement - Sleep Supplies for Homeless Population
[26 empty] | Options | 177685
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177685-0-1 | Purchase house #1 of 3-4 houses to provide supportive/supported housing services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase house #1 of 3-4 houses to provide supportive/supported housing services |  |  |  | 3
[26 empty] | 177685-0-2 | Purchase house #2 of 3-4 houses to provide supportive/supported housing services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase house #2 of 3-4 houses to provide supportive/supported housing services |  |  |  | 3
[26 empty] | 177685-0-3 | Purchase house #3 of 3-4 houses to provide supportive/supported housing services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase house #3 of 3-4 houses to provide supportive/supported housing services |  |  |  | 3
[26 empty] | 177685-0-4 | Purchase house #4 of 3-4 houses to provide supportive/supported housing services | Repurpose/Build New Facility | Repurpose/Build New Facility - Purchase house #4 of 3-4 houses to provide supportive/supported housing services |  |  |  | 3
[26 empty] | 177685-0-5 | Housing Coordination Services | Operational and Administrative Costs | Operational and Administrative Costs - Housing Coordination Services
[26 empty] | 177685-0-6 | Housing Support Service Staff | Housing Support Services | Housing Support Services - Housing Support Service Staff
[26 empty] | 177685-0-7 | Transitional Step-Down Housing Program | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Transitional Step-Down Housing Program
[26 empty] | 177685-0-8 | Short Term Shelter | Short Term Bed Subsidy | Short Term Bed Subsidy - Short Term Shelter
[26 empty] | 177685-0-9 | Long Term Rental Assistance | Long Term Rental Assistance | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | 177685-0-10 | Necessities for Homeless Population | Outreach and Engagement | Outreach and Engagement - Necessities for Homeless Population
[26 empty] | Polk | 177690
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177690-0-1 | CSRC | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - CSRC |  | 2025-04-05 |  | 4
[26 empty] | 177690-0-2 | STTP | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - STTP |  | 2025-04-05 |  | 12
[26 empty] | 177690-0-3 | Salaries, Benefits, and Wages | Operational and Administrative Costs | Operational and Administrative Costs - Salaries, Benefits, and Wages |  | 2025-04-05
[26 empty] | Symmetry | 177713
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177713-0-1 | SH Apartments | Repurpose/Build New Facility | Repurpose/Build New Facility - SH Apartments |  | 2023-12-31
[26 empty] | 177713-0-2 | Recovery Mentor | Operational and Administrative Costs | Operational and Administrative Costs - Recovery Mentor
[26 empty] | 177713-0-3 | Resident-Employed Coffee Shop | Housing Support Services | Housing Support Services - Resident-Employed Coffee Shop
[26 empty] | 177713-0-4 | Building Purchase and Related Costs | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Building Purchase and Related Costs
[26 empty] | 177713-0-5 | Rental Assistance for 4-Plex Tenants | Long Term Rental Assistance | Long Term Rental Assistance - Rental Assistance for 4-Plex Tenants
[26 empty] | 177713-0-6 | Outreach and Resources | Outreach and Engagement | Outreach and Engagement - Outreach and Resources
[26 empty] | Tillamook | 177679
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177679-0-1 | Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing | 2023-04-01 | 2023-11-01 | 2024-01-01 | 30
[26 empty] | 177679-0-2 | Operations Manager | Operational and Administrative Costs | Operational and Administrative Costs - Operations Manager | 2023-04-01 | 2023-11-01 | 2024-01-01
[26 empty] | 177679-0-3 | Purchase Microwaves | Housing Support Services | Housing Support Services - Purchase Microwaves |  | 2023-09-01
[26 empty] | 177679-0-4 | SH Flooring Replacement | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - SH Flooring Replacement |  | 2023-09-01
[26 empty] | 177679-0-5 | Interior/Exterior Building Supplies, Equipment and Repairs | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Interior/Exterior Building Supplies, Equipment and Repairs |  | 2023-09-15
[26 empty] | 177679-0-6 | Striping for Parking | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Striping for Parking |  | 2023-10-01
[26 empty] | Wallowa | 177692
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177692-0-1 | Supported Transitional Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Supported Transitional Housing | 2022-08-17 | 2024-01-30 | 2022-08-17 | 11
[26 empty] | 177692-0-2 | Add Two Units to Facility | Repurpose/Build New Facility | Repurpose/Build New Facility - Add Two Units to Facility |  |  |  | 2
[26 empty] | 177692-0-3 | Operational Costs | Operational and Administrative Costs | Operational and Administrative Costs - Operational Costs
[26 empty] | 177692-0-4 | Offsite House Manager | Housing Support Services | Housing Support Services - Offsite House Manager
[26 empty] | 177692-0-5 | Long Term Rental Assistance | Long Term Rental Assistance | Long Term Rental Assistance - Long Term Rental Assistance
[26 empty] | Warm | 178501
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 178501-0-1 | Repurpose/Build New Housing Units | Repurpose/Build New Housing Units - 178501-0-1 | Repurpose/Build New Housing Units - 178501-0-1 - Repurpose/Build New Housing Units |  |  |  | 10
[26 empty] | 178501-0-2 | TBD | Short Term Bed Subsidy | Short Term Bed Subsidy - TBD
[26 empty] | 178501-0-3 | TBD | Operational and Administrative Costs | Operational and Administrative Costs - TBD
[26 empty] | 178501-0-4 | TBD | Housing Support Services | Housing Support Services - Purchase Items for Facility
[26 empty] | 178501-0-5 | Purchase Items for Facility | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Long Term Rental Assistance
[26 empty] | 178501-0-6 | Long Term Rental Assistance | Long Term Rental Assistance | #REF!
[26 empty] | 178501-0-7 | TBD | Outreach and Engagement | Outreach and Engagement - TBD
[26 empty] | 178501-0-8 | TBD | Repurpose/Build New Housing Units - 178501-0-1 | Repurpose/Build New Housing Units - 178501-0-1 - TBD
[26 empty] | 178501-0-9 | TBD | TBD
[26 empty] | Washington | 177694
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177694-0-1 | Permanent Supportive Housing | Repurpose/Build New Facility | Repurpose/Build New Facility - Permanent Supportive Housing | 2023-01-01 | 2024-12-01 | 2024-12-01 | 15
[26 empty] | 177694-0-2 | Center for Addictions Triage and Treatment | Repurpose/Build New Facility | Repurpose/Build New Facility - Center for Addictions Triage and Treatment | 2019-07-01 | 2025-04-01 | 2025-06-01 | 44
[26 empty] | 177694-0-3 | Supportive Housing for Aid and Assist Population | Repurpose/Build New Facility | Repurpose/Build New Facility - Supportive Housing for Aid and Assist Population | 2023-01-01 |  | 2023-03-01 | 20
[26 empty] | Yamhill | 177708
[27 empty] | Project Name | Category | Category - Project Name | Project Start Date | Est Project Completion Date | Initial Date of Occupancy | # Beds/Units (if applicable)
[26 empty] | 177708-0-1 | Transitional Treatment Recovery Services; Transitional Treatment with On-Site Support; On-Site Support and Services Expansion | Operational and Administrative Costs | Operational and Administrative Costs - Transitional Treatment Recovery Services; Transitional Treatment with On-Site Support; On-Site Support and Services Expansion
[26 empty] | 177708-0-2 | Barrier Removal Support | Housing Support Services | Housing Support Services - Barrier Removal Support
[26 empty] | 177708-0-3 | Transitional Treatment Residential Services Expansion | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Transitional Treatment Residential Services Expansion
[26 empty] | 177708-0-4 | Non-Congregate Transitional Housing with On-Site Support Expansion | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Non-Congregate Transitional Housing with On-Site Support Expansion |  |  |  | 30
[26 empty] | 177708-0-5 | Congregate Sheltering with On-Site Support and Services Expansion | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Congregate Sheltering with On-Site Support and Services Expansion
[26 empty] | 177708-0-6 | Crisis House Renovation | Planning, Coordinating, and Purchasing | Planning, Coordinating, and Purchasing - Crisis House Renovation
[26 empty] | 177708-0-7 | Basic Necessities | Outreach and Engagement | Outreach and Engagement - Basic Necessities
Formulas:
Due Date = EOMONTH([Third Month],0)+30