## Key
Status Colors
Task that is ongoing or in process
Task to be started in early 2025
Task completed
Objective | Part of the Strategic planning document
Strategy | Part of the Strategic planning document
Task | Ideas/concepts developed by the team to address the strategy
Leads | Person who is ultimately in charge of reporting and ensuring task occurs
Notes | Notes about what task may mean, maybe be for internal staff but might be more for external providers

## 1. Leadership and Culture
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
1.1 | Promote a culture that advances collaboration, inclusivity, equity, and caring
Lift community voice, building on foundations established through equity-focused engagements
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Continue to elevate the Multicultural and Marginalized Empowerment Consultant Program (MMECP) usage and expand number of consultants | Some work will be done by the PGS MAC and their efforts. For OHA PGS, promote during TA visits, semi-annual connection reviews, prevention connects, to ICD providers and adjunct team. Determine how to open and allow for ICD providers to use this service and how to promote to them. | In process | 2025-01-01 | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Add sections or questions related to equity within TA review process, connection reviews and prevention check ins for treatment and prevention |  |  | 2025-03-01 | PG TX Specialist Roxann Jones
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Continued communication about existing and new resources available | Development of communication plan that spaces frequency of communication related to PGS system and projects and that will notify lead of a project that it is time to communicate |  | 2025-01-01 | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Clarify BHD units and staff roles and resources | Review org chart and units webpages. Map out Subject Matter Experts and staff OHA PGS team should know and have informational interviews. |  | 6/1/2025 and ongoing | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Continue to support meeting and webinar opportunities for providers to network, to form partnerships, and to share successes | Continue development of yearly training calendar and look for other opportunities. Some regions are holding their own networking meetings. | In process | 2024-01-01 | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Lift community voice, building on foundations established through equity-focused engagements | Collect consumer voice to assist with system change | Treatment Follow Up Project- questions asked within the surveys and interviews. | In process | 2024-01-01 | Greta Coe
Work in partnership with providers to address disparities within the PGS system
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Work in partnership with providers to address disparities within the PGS system | Develop methods to gather feedback from consumers. | Treatment Follow Up Project- questions asked within the surveys and interviews, possible focus group method. | In process | 2024-01-01 | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Work in partnership with providers to address disparities within the PGS system | Continue to work with PGS MAC committee and efforts within their strategic planning. | Ensure PGS MAC's strategic goals align with OHA PGS system strategic goals. |  | 2025-01-01 | Greta Coe
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Work in partnership with providers to address disparities within the PGS system | Gather feedback from prevention field related to disparities | Implementation of CRAM 25-26, develop advisory groups as needed |  | 2025-04-01 | Roxann Jones
| Promote a culture that advances collaboration, inclusivity, equity, and caring | Work in partnership with providers to address disparities within the PGS system | Survey PG System Providers on priority areas and thoughts on disparities | To be completed every biennium- spring 2025, spring 2027, spring 2029 |  | 2025-01-01 | Greta Coe
1.2 | Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns
Utilize data to increase awareness of how gambling behaviors impact individuals, families, and communities
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Utilize data to increase awareness of how gambling behaviors impact individuals, families, and communities | Off quarter Research and Evaluation Outcomes Webinars (OREO) to share research and data |  | In process | 2024-01-01 | Greta Coe
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Utilize data to increase awareness of how gambling behaviors impact individuals, families, and communities | Continue quarterly reports sharing from PG Net | Through Connection reviews and PG Net dashboards | In process | 2024-01-01 | Greta Coe
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Utilize data to increase awareness of how gambling behaviors impact individuals, families, and communities | Continued promotion and additional sections within the PG and Impacts of Public Health booklet | Add to communication plan and continue to update and revise document. | In process | 2024-07-01 | Roxann Jones
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Utilize data to increase awareness of how gambling behaviors impact individuals, families, and communities | Include health related or other high risk behaviors to existing surveys and determine other means for collecting under reported data | Add to prevalence study and conduct focus groups to collect additional data currently missing, continue with BRFSS and SHS questions | In process | 2024-01-01 | Greta Coe Roxann Jones
Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts | Develop new partnerships with entities within OHA Behavioral Health Division | CLSS, CCOs, CFBH |  | 2025-06-01 | All
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts | Develop new partnerships with entities within OHA Public Health Division | PH- IVP, HPCD, adolescent school health |  | 2025-06-01 | Roxann Jones
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts | Develop partnerships with entities providing family services | CFBH |  | 2025-06-01 | Greta Coe
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts | Continue to cultivate existing partnerships through creation of champions for PG | Older Adult, Veterans, ODE | In process | 2024-01-01 | All
| Expand and increase awareness of the intersection of gambling related harms with other public health issues and concerns | Develop partnerships with state agencies and public health programs to infuse problem gambling awareness, screening, education, and referral into their efforts | Determine what GBIRT 2.0 is | Define what this entail as next step from efforts of the past 3 years. |  | 2025-06-01 | PG TX Specialist David Corse
1.3 | Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services
Promote the availability and utilization of data produced by OHA PGS systems and funded projects
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Promote the availability and utilization of data produced by OHA PGS systems and funded projects | Record data requests through centralized location that comes up in general conversations and often lost and filter to partnering organizations such as OCPG Research Center |  |  | 2025-01-01 | Greta Coe
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Promote the availability and utilization of data produced by OHA PGS systems and funded projects | Creation of annual data evaluation report | Review yearly data and publish report on outcomes- report to include PG Net data, SHS, BRFSS, Medicaid, and ICD programs. | In process | 2024-01-01 | Greta Coe
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Promote the availability and utilization of data produced by OHA PGS systems and funded projects | Quarterly Research and Evaluation Outcomes Webinar- OREO | Development of OREO Webinar Series | In process | 2024-01-01 | Greta Coe
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Promote the availability and utilization of data produced by OHA PGS systems and funded projects | Development of communication plan-what needs to be communicated and frequency and method |  |  | 2025-01-01 | Greta Coe
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Promote the availability and utilization of data produced by OHA PGS systems and funded projects | Creation of annual system report- report related to program and projects implemented and corresponding metrics. |  | In process | 2024-01-01 | Greta Coe
Continuously improve materials, processes, and tools to communicate with problem gambling service providers and partners and the public at-large
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Continuously improve materials, processes, and tools to communicate with problem gambling service providers and partners and the public at-large | Creation of specific topics - time limited workgroups, as needed to advise OHA PGS team.
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Continuously improve materials, processes, and tools to communicate with problem gambling service providers and partners and the public at-large | Development of communication plan- what needs to be communicated and frequency and method |  |  | 2025-01-01 | Greta Coe
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Continuously improve materials, processes, and tools to communicate with problem gambling service providers and partners and the public at-large | Continue to add at least one factsheet/brief to OHA PG and Public Health Impacts booklet each year |  | In process | 2024-07-01 | Roxann Jones
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Continuously improve materials, processes, and tools to communicate with problem gambling service providers and partners and the public at-large | Satisfaction survey of PG system Providers related to OHA PGS staff efforts, etc. | Conduct each biennium in spring 2025, spring 2025 and spring 2029 |  | 2025-01-01 | Greta Coe
Systematically engage in improvement processes to assess system needs and respond to emerging needs
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Systematically engage in improvement processes to assess system needs and respond to emerging needs | Use monthly Prevention connect calls as advisory committee and report on emerging needs and trends. |  | In process | 2024-01-01 | Roxann Jones
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Systematically engage in improvement processes to assess system needs and respond to emerging needs | Continue Semi Annual TX Connection Review and PX check in meetings |  | In process | 2024-01-01 | Greta Coe PG TX Specialist Roxann Jones
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Systematically engage in improvement processes to assess system needs and respond to emerging needs | Relaunch the Technical Assistance Reviews process for prevention and treatment (voluntary activity/offering) |  |  | 2025-03-01 | PG TX Specialist Roxann Jones
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Systematically engage in improvement processes to assess system needs and respond to emerging needs | Creation of topic specific time limited workgroups as needed. |  |  |  | All
| Continue to cultivate and advance relationships among state, provider networks and communities to inform on gambling related harms and gambling disorder, impacts and services | Systematically engage in improvement processes to assess system needs and respond to emerging needs | Conduct satisfaction survey of PG Provider System evaluating OHA PGS team and efforts. | Conduct each biennium in spring 2025, spring 2025 and spring 2029 |  | 2025-01-01 | Greta Coe

## 2.Health Promotion & Prevention
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
2.1 | Strengthening awareness of problem gambling through education, collaboration and community partnership development
Utilize community readiness assessments data to inform provider implementation plans and increase communities’ readiness to address problem gambling and knowledge of public health impacts of problem gambling
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Utilize community readiness assessments data to inform provider implementation plans and increase communities’ readiness to address problem gambling and knowledge of public health impacts of problem gambling | CRAM Implementation, Support and Communication | Will be conducted during the 25-26 FY | In process | 2024-07-01 | Roxann Jones
Seek out and implement various communication strategies to better inform and share materials
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Seek out and implement various communication strategies to better inform and share materials | Determine how stigma reduction and language and inclusivity project overlaps with prevention efforts |  |  | 2025-01-01 | Greta Coe Roxann Jones
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Seek out and implement various communication strategies to better inform and share materials | Survey providers on preferred communication method, etc. | Could be part of the provider satisfaction survey completed every odd year |  | 2025-01-01 | Greta Coe
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Seek out and implement various communication strategies to better inform and share materials | Creation of Prevention Hub- resource sharing site |  | Ongoing | 2024-01-01 | Roxann Jones
Empower local problem gambling prevention specialists to increase collaboration with local organizations, groups, and advocates that address social and health issues
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Empower local problem gambling prevention specialists to increase collaboration with local organizations, groups, and advocates that address social and health issues | Explore how to include this as part of implementation plan |  |  | 2025-03-01 | Roxann Jones
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Empower local problem gambling prevention specialists to increase collaboration with local organizations, groups, and advocates that address social and health issues | Explore with Tribal ATOD Px development of relationships at community level and how to support. |  | ongoing | 2024-01-01 | Roxann Jones
| Strengthening awareness of problem gambling through education, collaboration and community partnership development | Empower local problem gambling prevention specialists to increase collaboration with local organizations, groups, and advocates that address social and health issues | Community programs survey existing work groups, coalitions, partnerships as part of Implementation Plan for 2025-2027 |  |  | 2025-01-01 | Roxann Jones
2.2 | Build upon past efforts and current needs to continuously improve problem gambling prevention services
Continue to build from the Problem Gambling Prevention Core Competency Project to increase the capacity and readiness of prevention professionals to address issues related to gambling
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Continue to build from the Problem Gambling Prevention Core Competency Project to increase the capacity and readiness of prevention professionals to address issues related to gambling | Include link to Core Competency on "Getting Started Guide" for Px Providers to bring awareness and encourage review. |  | Completed |  | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Continue to build from the Problem Gambling Prevention Core Competency Project to increase the capacity and readiness of prevention professionals to address issues related to gambling | Webinar to PG Px Providers Core Competency | Provided webinar for prevention field to learn about the Core Competencies | Completed |  | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Continue to build from the Problem Gambling Prevention Core Competency Project to increase the capacity and readiness of prevention professionals to address issues related to gambling | Workgroup on Core Competency- areas to focus on as a system | Survey prevention providers on core competency skill set to determine areas in need of most focus |  |  | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Continue to build from the Problem Gambling Prevention Core Competency Project to increase the capacity and readiness of prevention professionals to address issues related to gambling | Explore training gaps to support development of core competencies for workforce development needs | Survey prevention providers on core competency skill set to determine areas in need of most focus |  |  | Roxann Jones
Create opportunities to weave the topic of gambling into other public health concerns and increase capacity to deliver services that have a focus on disproportionately affected individuals and communities
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Create opportunities to weave the topic of gambling into other public health concerns and increase capacity to deliver services that have a focus on disproportionately affected individuals and communities | Continue to revise and expand Prevention Tier Funding Concept | Cultural component to tier funding developed and added | ongoing | 2024-01-01 | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Create opportunities to weave the topic of gambling into other public health concerns and increase capacity to deliver services that have a focus on disproportionately affected individuals and communities | Determine how stigma reduction and language and inclusivity project overlaps with prevention efforts |  |  |  | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Create opportunities to weave the topic of gambling into other public health concerns and increase capacity to deliver services that have a focus on disproportionately affected individuals and communities | Creation of short educational videos and accompany guides |  | In process | 2024-07-01 | Roxann Jones
Raise awareness of the public health implications related to gambling and gaming, along with associated risks, and provide resources to educators, parents, and others to address these concerns
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Raise awareness of the public health implications related to gambling and gaming, along with associated risks, and provide resources to educators, parents, and others to address these concerns | Creation of short educational videos and accompany materials |  | In process | 2024-07-01 | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Raise awareness of the public health implications related to gambling and gaming, along with associated risks, and provide resources to educators, parents, and others to address these concerns | Promotion of PH Impacts Booklet and tutorials on how to utilize | Continue to add topical briefs and communication efforts |  | 2025-01-01 | Roxann Jones
Utilize data from Student Health Surveys and other surveillance measures to engage and inform
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Utilize data from Student Health Surveys and other surveillance measures to engage and inform | Continue to participate in SHS Advisory Content Committee to ensure PG questions are within survey |  | ongoing | 2024-01-01 | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Utilize data from Student Health Surveys and other surveillance measures to engage and inform | Continue to ensure analysis of SHS data and development of communication and utilization plan | Development of toolkits and materials highlighting the data |  | 2025-07-01 | Roxann Jones
| Build upon past efforts and current needs to continuously improve problem gambling prevention services | Utilize data from Student Health Surveys and other surveillance measures to engage and inform | Workgroup on Core Competency- areas to focus on as a system |  |  |  | Roxann Jones
2.3 | Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques
Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling | Determine if Oregon School Counselor Association has interest in partnership and is a valuable resource |  |  |  | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling | Determine what ODEs legislative mandate for financial literacy looks like and if gambling can be infused. |  | In process | 2024-10-15 | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling | Determine how to get problem gambling prevention and education materials into health standards |  |  |  | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling | Expand partnership with Tribal Prevention |  |  |  | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Work in partnership with colleagues across state and local agencies to reduce stigma associated with problem gambling | OYA, PH, ODHS - CW and Self Sufficiency |  |  |  | Roxann Jones
Explore opportunities for technological advances in the delivery of health promotion and prevention services
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Explore opportunities for technological advances in the delivery of health promotion and prevention services | Ensure that OPGR web page has prevention and educational information included to inform the general public and parents of risk associated with gambling and gaming |  | In process | 2024-07-01 | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Explore opportunities for technological advances in the delivery of health promotion and prevention services | Ensure that OPGR social media is messaging to parents through parent channels |  | on hold due to funding |  | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Explore opportunities for technological advances in the delivery of health promotion and prevention services | Development of brief video's for social media awareness campaign |  |  |  | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Explore opportunities for technological advances in the delivery of health promotion and prevention services | Determine location for prevention resources for those working in the field. | Creation of prevention hub | Completed | 2024-01-01 | Roxann Jones
| Increase public awareness of educational resources that will inform individuals of the risks associated with problematic gambling and health promotion and prevention techniques | Explore opportunities for technological advances in the delivery of health promotion and prevention services | Development of social media contractor and prevention messaging. |  | on hold due to funding |  | Greta Coe Roxann Jones

## 3. Treatment & Recovery
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
3.1 | Strengthen equitable, barrier-free access to treatment & recovery resources
Increase program capacity to deliver programs and services that have a focus on disproportionately affected individuals and communities
| Strengthen equitable, barrier-free access to treatment & recovery resources | Increase program capacity to deliver programs and services that have a focus on disproportionately affected individuals and communities | Promote and increase utilization of the MMECP with PGS provider system |  |  |  | PG Tx Specialist
| Strengthen equitable, barrier-free access to treatment & recovery resources | Increase program capacity to deliver programs and services that have a focus on disproportionately affected individuals and communities | Work with helpline for development of specialized directory of providers. |  |  |  | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Increase program capacity to deliver programs and services that have a focus on disproportionately affected individuals and communities | Continue to explore options for funding and expanding programs that specialize in disproportionately affected communities |  |  |  | PG Tx Specialist
Develop and implement plan to expand availability of treatment services
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Advance ICD PG Specialist to CGACs and ICD program to become PG OAR certified |  | In process | 2024-03-01 | David Corse
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Develop new funding mechanism based on grant based proposals and agencies determining level and type of services |  | In process | 2025-07-01 | Greta Coe PG TX Specialist
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Develop Center for Excellence Model for treatment agencies to strive for
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Development of Peer Center for Excellence Concept | Draft of RFP for this model completed | On hold due to funding |  | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Creation of Peer Warmline from Helpline Services |  | On hold due to funding
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Expand partnership with local tribes. |  |  |  | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Expand Affected others services |  | Need to develop large action plan around this.
| Strengthen equitable, barrier-free access to treatment & recovery resources | Develop and implement plan to expand availability of treatment services | Continue to support the Inclusivity, Language and Stigma movement ideas and impact on system |  | ongoing | 2024-06-01 | PG Tx Specialist
Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps)
| Strengthen equitable, barrier-free access to treatment & recovery resources | Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps) | Implementation of GamFin- financial counseling service available to Tx and peer providers |  | In process | 2024-02-01 | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps) | Offering of Evive app for motivation to change as resource to public not wanting to engage in traditional counseling services |  | In process | 2024-04-01 | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps) | Determine how to help clients and providers with payee services |  |  |  | PG Tx Specialist
| Strengthen equitable, barrier-free access to treatment & recovery resources | Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps) | Explore the Grief Recovery model curriculum being offered to clients statewide |  |  | 2025-01-01 | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Explore technological solutions and strategies to increase access to treatment and recovery supports (e.g., telehealth, recovery apps) | Explore the use of motivational texting through the helpline |  | on hold due to funding or may be met through other apps |  | Greta Coe
Build partnerships with behavioral health programs to expand their capacity to address gambling related problems
| Strengthen equitable, barrier-free access to treatment & recovery resources | Build partnerships with behavioral health programs to expand their capacity to address gambling related problems | Improve and expand OPGR social media sites reach and communication via a specialized contractor | Drafted RFP proposal for this and ready to go when funding is available. | on hold due to funding |  | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Build partnerships with behavioral health programs to expand their capacity to address gambling related problems | Continue to engage with Opioid treatment programs to form partnership of services | Started and put on hold due to BH WF crisis |  |  | Greta Coe
| Strengthen equitable, barrier-free access to treatment & recovery resources | Build partnerships with behavioral health programs to expand their capacity to address gambling related problems | Determine what GBIRT 2.0 entails |  |  | 2025-06-01 | PG Tx Specialist, David Corse
| Strengthen equitable, barrier-free access to treatment & recovery resources | Build partnerships with behavioral health programs to expand their capacity to address gambling related problems | Determine project for partnership among child and family programs to address problematic gaming and gambling. |  |  |  | PG Tx Specialist
| Strengthen equitable, barrier-free access to treatment & recovery resources | Build partnerships with behavioral health programs to expand their capacity to address gambling related problems | Continue to expand services within Oregon Department of Corrections BH unit | Expand to other prison system outside of CCCF and CRCI and OCI. 2025 expansion to SRCI and OSP | In process | 2024-01-01 | Greta Coe
3.2 | Encourage help-seeking behaviors for gambling related problems
Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers)
| Encourage help-seeking behaviors for gambling related problems | Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers) | Determine what the GBIRT 2.0 model entails
| Encourage help-seeking behaviors for gambling related problems | Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers) | Reengage with Commission on Criminal Justice related to drug court grantees and integration of problem gambling |  |  | 2025-01-01 | Greta Coe
| Encourage help-seeking behaviors for gambling related problems | Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers) | Require and implement PG screening of all intakes into ODOC system |  | In process | 2024-01-01 | Greta Coe
| Encourage help-seeking behaviors for gambling related problems | Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers) | Explore how PG can be integrated into CCBHCs |  |  |  | David Corse
| Encourage help-seeking behaviors for gambling related problems | Integrate problem gambling screenings across various physical, mental, and behavioral health sectors (e.g., specialty courts, community mental health centers) | Matching communication/marketing of services and level of need of services to the person in order to reduce stigma by modifying language and approaches. |  |  |  | Greta Coe
Empower providers to engage in client finding activities
| Encourage help-seeking behaviors for gambling related problems | Empower providers to engage in client finding activities | As funding allows, continue to offer SE 84 grants |  |  |  | Greta Coe
| Encourage help-seeking behaviors for gambling related problems | Empower providers to engage in client finding activities | Integrate Client finding outreach activities into Center of Excellence concept |  |  |  | PG TX Specialist
| Encourage help-seeking behaviors for gambling related problems | Empower providers to engage in client finding activities | Determine what the GBIRT 2.0 model entails |  |  | 2025-06-01 | Pg TX Specialist David Corse
3.3 | Continually improve service efficacy and efficiency
Commit to using data and evidence to inform program development
| Continually improve service efficacy and efficiency | Commit to using data and evidence to inform program development | Continue semi annual treatment connection reviews to review data reports and outcomes of individual provider and provide feedback loop to OHA |  | ongoing | 2024-01-01 | PG TX Specialist Greta Coe
| Continually improve service efficacy and efficiency | Commit to using data and evidence to inform program development | Reinstate a voluntary TA process for treatment providers |  |  | 2025-03-01 | PG TX Specialist
| Continually improve service efficacy and efficiency | Commit to using data and evidence to inform program development | Expand quarterly provider reports and promote usage and discussions |  | ongoing | 2024-01-01 | PG TX Specialist
Expand support services for programs (e.g., technical assistance, evaluation tools)
| Continually improve service efficacy and efficiency | Expand support services for programs (e.g., technical assistance, evaluation tools) | Reinstate a voluntary TA process for treatment providers |  |  | 2025-03-01 | PG TX Specialist
| Continually improve service efficacy and efficiency | Expand support services for programs (e.g., technical assistance, evaluation tools) | Determine how to use the PG Core competencies for clinicians or treatment professional development |  |  |  | PG TX Specialist
| Continually improve service efficacy and efficiency | Expand support services for programs (e.g., technical assistance, evaluation tools) | Implement GamFin- financial counselor service for Tx and peer providers |  | In process | 2024-02-01 | Greta Coe
| Continually improve service efficacy and efficiency | Expand support services for programs (e.g., technical assistance, evaluation tools) | Creation for system approved resource materials (library) and short term grab and go curriculum for those in need or new to system |  | In process | 2025-01-01 | Greta Coe
Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist)
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Creation of concept for Peer Center for Excellence | Drafted RFP proposal for this and ready to go when funding is available. | On hold due to funding |  | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Expand peer training offerings | Completed through contract with VPGR | in process | 2024-03-01 | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Creation of warm line for peers from helpline service |  | On hold due to funding |  | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Creation of Pg Peer supervisor or promotion or step up system for peer professionals |  |  |  | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Include peer services and CGRMs as part of Medicaid eligible covered service |  | Completed | 2024-01-01 | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Review and explore possibility of implementation of VPGR peer strategic plan | Completed through contract with VPGR | Completed | 2024-01-01 | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Creation of Peer network system to reduce isolation and increase connection and professional growth | Completed through contract with VPGR | Completed | 2024-01-01 | Greta Coe
| Continually improve service efficacy and efficiency | Increase the capacity, competency, and use of recovery-oriented approaches (e.g., peer support specialist) | Determine how to use the PG core competencies for peer professionals |  |  |  | PG Tx Specialist

## 4. Integration
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
4.1 | Integrate problem gambling awareness into broader public health prevention efforts
Locate champions within OHA to elevate awareness of gambling related impacts
| Integrate problem gambling awareness into broader public health prevention efforts | Locate champions within OHA to elevate awareness of gambling related impacts | Continue partnership with Older Adult BH system |  | Ongoing | 2024-01-01 | All
| Integrate problem gambling awareness into broader public health prevention efforts | Locate champions within OHA to elevate awareness of gambling related impacts | Continue to grow partnership with BH Veterans System |  | Ongoing | 2024-01-01 | All
| Integrate problem gambling awareness into broader public health prevention efforts | Locate champions within OHA to elevate awareness of gambling related impacts | Cultivate relationship with Oregon Public Health Division's numerous sections | Alcohol and drug, suicide prevention, violence prevention, school health |  |  | Roxann Jones
| Integrate problem gambling awareness into broader public health prevention efforts | Locate champions within OHA to elevate awareness of gambling related impacts | Continue partnerships with Oregon Department of Corrections (ODOC) and expand services |  | ongoing | 2024-01-01 | Greta Coe
| Integrate problem gambling awareness into broader public health prevention efforts | Locate champions within OHA to elevate awareness of gambling related impacts | Locate champions with the Opioid Treatment Program (OTP) system and expand services. |  | Currently on pause due to BH WF Crisis and capacity |  | Greta Coe
Encourage problem gambling community prevention programs to foster the integration of problem gambling prevention into community-based prevention programs
| Integrate problem gambling awareness into broader public health prevention efforts | Encourage problem gambling community prevention programs to foster the integration of problem gambling prevention into community-based prevention programs | Ensure within prevention program implementation plans, at least 1 focus population is being addressed |  | Ongoing | 2024-01-01 | Roxann Jones
| Integrate problem gambling awareness into broader public health prevention efforts | Encourage problem gambling community prevention programs to foster the integration of problem gambling prevention into community-based prevention programs | Develop resource sharing site |  | Completed | 2024-01-01 | Roxann Jones
4.2 | Expand efforts to integrate problem gambling into treatment agencies and systems
Problem gambling treatment providers shall implement the GBIRT model
| Expand efforts to integrate problem gambling into treatment agencies and systems | Problem gambling treatment providers shall implement the GBIRT model | Determine what GBIRT 2.0 entails |  |  | 2025-03-01 | PG TX Specialist David Corse
| Expand efforts to integrate problem gambling into treatment agencies and systems | Problem gambling treatment providers shall implement the GBIRT model | Implement GBIRT model within OTPs |  |  |  | PG TX Specialist David Corse
| Expand efforts to integrate problem gambling into treatment agencies and systems | Problem gambling treatment providers shall implement the GBIRT model | Determine how to implement GBIRT model within ICD programs |  |  |  | David Corse
| Expand efforts to integrate problem gambling into treatment agencies and systems | Problem gambling treatment providers shall implement the GBIRT model | Ensure Problem Gambling Treatment Providers are trained on the GBRIT model and using it. |  |  |  | Pg TX Specialist
Integrate gambling disorder treatment into the Oregon Medicaid system
| Expand efforts to integrate problem gambling into treatment agencies and systems | Integrate gambling disorder treatment into the Oregon Medicaid system | Review data on regular basis of system and creation of contact list for Medicaid pg. providers and communication plan |  |  | 2025-01-01 | Greta Coe PG Tx Specialist
| Expand efforts to integrate problem gambling into treatment agencies and systems | Integrate gambling disorder treatment into the Oregon Medicaid system | Expand the number of programs eligible for Medicaid PG services |  |  | 2025-01-01 | Greta Coe
| Expand efforts to integrate problem gambling into treatment agencies and systems | Integrate gambling disorder treatment into the Oregon Medicaid system | Offer TA and resources to programs that are PG Medicaid eligible |  |  |  | PG Tx Specialist
Encourage, empower, and enhance the ability for treatment and recovery programs to become informed and capable to address gambling related issues
| Expand efforts to integrate problem gambling into treatment agencies and systems | Encourage, empower, and enhance the ability for treatment and recovery programs to become informed and capable to address gambling related issues | Take the PG Tx System to the next level related to family therapy | Need to develop detailed plan related to this. |  |  | PG TX Specialist
| Expand efforts to integrate problem gambling into treatment agencies and systems | Encourage, empower, and enhance the ability for treatment and recovery programs to become informed and capable to address gambling related issues | Determine how to partner and inform Adolescent and family programs |  |  |  | Greta Coe
| Expand efforts to integrate problem gambling into treatment agencies and systems | Encourage, empower, and enhance the ability for treatment and recovery programs to become informed and capable to address gambling related issues | Look at the options of how to utilize Private Practitioners |  |  |  | Greta Coe
| Expand efforts to integrate problem gambling into treatment agencies and systems | Encourage, empower, and enhance the ability for treatment and recovery programs to become informed and capable to address gambling related issues | Define ICD 2.0 integration- where we go next? |  |  |  | David Corse
4.3 | Explore the integration of gambling related language inserted into policies and curriculums
Support the integration of problem gambling related topics into training programs and academic curriculums
| Explore the integration of gambling related language inserted into policies and curriculums | Support the integration of problem gambling related topics into training programs and academic curriculums | Determine how we better integrate our field/topic into the educational system (college or career training) |  |  |  | PG Tx Specialist
| Explore the integration of gambling related language inserted into policies and curriculums | Support the integration of problem gambling related topics into training programs and academic curriculums | Determine how to incorporate PG prevention into Public Health Courses like community health services etc. |  |  |  | Roxann Jones
| Explore the integration of gambling related language inserted into policies and curriculums | Support the integration of problem gambling related topics into training programs and academic curriculums | Determine how to incorporate PG education/content into Oregon Department of Education Standards or programs. |  |  |  | Roxann Jones
Seek out opportunities to add language that addresses gambling and/or problem gambling to policy documents such as legislative proposals, employer policies, request for proposals
| Explore the integration of gambling related language inserted into policies and curriculums | Seek out opportunities to add language that addresses gambling and/or problem gambling to policy documents such as legislative proposals, employer policies, request for proposals | Partner with the M110 OHA Team and how to integrate PG within services or programs that are BRNs grantees |  |  | 2025-01-01 | Greta Coe
| Explore the integration of gambling related language inserted into policies and curriculums | Seek out opportunities to add language that addresses gambling and/or problem gambling to policy documents such as legislative proposals, employer policies, request for proposals | OHA PGS staff to stay informed of upcoming BH funding opportunities |  | Ongoing |  | All
| Explore the integration of gambling related language inserted into policies and curriculums | Seek out opportunities to add language that addresses gambling and/or problem gambling to policy documents such as legislative proposals, employer policies, request for proposals | OHA PGS staff to review legislative bills to determine if PG needs to be incorporated or included |  | Ongoing |  | All

## 5. Workforce
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
5.1 | Identify and develop strategies to address current and future workforce challenges
Enact a multi-pronged effort to address workforce shortages
| Identify and develop strategies to address current and future workforce challenges | Enact a multi-pronged effort to address workforce shortages | Offer and promote training scholarships opportunities through WFD grant to PGS, PG Medicaid, and ICD providers |  | ongoing | 2024-01-01 | Greta Coe
| Identify and develop strategies to address current and future workforce challenges | Enact a multi-pronged effort to address workforce shortages | Implement PG Tx Refinement Vision | PG TX Refinement Vision is a 10 year project | In process | 2024-06-01 | Greta Coe PG TX Specialist
| Identify and develop strategies to address current and future workforce challenges | Enact a multi-pronged effort to address workforce shortages | Consult with Workforce Development Equity and Administrative Manager of BHD to determine system wide approaches in place or planned |  |  |  | Greta Coe
Continually develop skills and competencies of the current workforce
| Identify and develop strategies to address current and future workforce challenges | Continually develop skills and competencies of the current workforce | Review evaluations from ACORN to determine additional training needs |  | ongoing | 2024-01-01 | All
| Identify and develop strategies to address current and future workforce challenges | Continually develop skills and competencies of the current workforce | Revisit the previous WFD plan and develop provider survey for further needs and data | New WF questions could be included in the larger biennium provider survey. |  | 2025-03-01 | Greta Coe
| Identify and develop strategies to address current and future workforce challenges | Continually develop skills and competencies of the current workforce | Develop application, process and mentoring to become an ACORN trainer or training on how to present. |  |  |  | Greta Coe through WFD grant and PSR.
| Identify and develop strategies to address current and future workforce challenges | Continually develop skills and competencies of the current workforce | Utilize the core competencies guides for prevention, treatment and recovery professionals |  |  |  | All
5.2 | Increase the capabilities of the addiction and mental health prevention and treatment workforce to identify and address gambling-related impacts and root causes
Promote cross-training and workforce opportunities to increase behavioral health and public health providers’ knowledge of and capacity to address gambling related problems
| Increase the capabilities of the addiction and mental health prevention and treatment workforce to identify and address gambling-related impacts and root causes | Promote cross-training and workforce opportunities to increase behavioral health and public health providers’ knowledge of and capacity to address gambling related problems | Become aware of additional opportunities and communicate to system and offer financial resources | Use of subsidies/scholarships and communication plan | Ongoing | 2024-01-01 | All
| Increase the capabilities of the addiction and mental health prevention and treatment workforce to identify and address gambling-related impacts and root causes | Promote cross-training and workforce opportunities to increase behavioral health and public health providers’ knowledge of and capacity to address gambling related problems | Implement PG Tx Refinement Vision | PG TX Refinement Vision is a 10 year project | In process | 2024-06-01 | Greta Coe PG TX Specialist
5.3 | Build workforce capacity to provide problem gambling services
Create career pathways for persons representing underserved and marginalized communities
| Build workforce capacity to provide problem gambling services | Create career pathways for persons representing underserved and marginalized communities | Continue to review and revise current pg. trainings |  | Ongoing | 2024-01-01 | All
| Build workforce capacity to provide problem gambling services | Create career pathways for persons representing underserved and marginalized communities | Continue to offer free pg. trainings and scholarships opportunities for other BH/PH trainings | Needs to be included in communication plan. | Ongoing | 2024-01-01 | Greta Coe
| Build workforce capacity to provide problem gambling services | Create career pathways for persons representing underserved and marginalized communities | Continue to offer scholarships for pg. trainings and trainings that support the workforce. | Needs to be included in communication plan. | Ongoing | 2024-01-01 | Greta Coe
| Build workforce capacity to provide problem gambling services | Create career pathways for persons representing underserved and marginalized communities | Hold and offer a CADCA Prevention Bootcamp | This was a professional development training for PG Preventionists related to data collection and review, utilization and community planning, implementation and evaluation | Completed | 2024-01-01 | Roxann Jones
Develop programs that support persons from diverse backgrounds to join the problem gambling prevention and treatment workforce
| Build workforce capacity to provide problem gambling services | Develop programs that support persons from diverse backgrounds to join the problem gambling prevention and treatment workforce | Determine how to offer 30 hour PG certification training for Latino culturally specific providers, other languages or population specific |  |  |  | PG TX Specialist
| Build workforce capacity to provide problem gambling services | Develop programs that support persons from diverse backgrounds to join the problem gambling prevention and treatment workforce | Determine how to offer PG peer trainings for Latino culturally specific peer providers |  |  |  | PG TX Specialist
| Build workforce capacity to provide problem gambling services | Develop programs that support persons from diverse backgrounds to join the problem gambling prevention and treatment workforce | Earmark funding, as available, for contracts and training for culturally specific providers interested in pg. prevention, treatment and recovery services |  |  |  | Greta Coe

## 6. Evaluation & Research
Code | Objective | Strategy | Task | Notes | Status | Start Date | Lead
6.1 | Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services
Advance data collection systems and ensure analysis of data drives future programming
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Advance data collection systems and ensure analysis of data drives future programming | Continue to review and expand follow-up surveys for those enrolled in problem gambling treatment, determine how to share data and include in annual data evaluation reports. |  | Ongoing | 2024-01-01 | Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Advance data collection systems and ensure analysis of data drives future programming | Continue to expand and solidify data collection and sharing within PG Net for gambling treatment data. |  | Ongoing | 2024-01-01 | PG TX Specialist
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Advance data collection systems and ensure analysis of data drives future programming | Review and solidify prevention implementation plans and quarterly reporting tool |  |  | 2024-01-01 | Roxann Jones
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Advance data collection systems and ensure analysis of data drives future programming | Ensure all problem gambling data sources and outcomes are included in annual system data evaluation report or have individual data reports referencing each other. | PG Net, Medicaid, BRFSS, SHS, ICD, etc. | In process | 2024-04-01 | Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Advance data collection systems and ensure analysis of data drives future programming | Conduct CRAM assessment of all counties. | See Health Promotion and Prevention tab | In process | 2024-09-01 | Roxann
Continue to support the inclusion of gambling related questions on health surveillance surveys and seek opportunities to expand surveillance measures
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Continue to support the inclusion of gambling related questions on health surveillance surveys and seek opportunities to expand surveillance measures | Continue to represent and actively participant in the OHA SHS Advisory Committee and BFRSS workgroup and resource funding to meet needs |  | Ongoing | 2024-01-01 | Roxann Jones Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Continue to support the inclusion of gambling related questions on health surveillance surveys and seek opportunities to expand surveillance measures | Review and revise gambling questions within SHS and BRFSS, as needed. |  | Ongoing | 2024-01-01 | Roxann Jones Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Continue to support the inclusion of gambling related questions on health surveillance surveys and seek opportunities to expand surveillance measures | Determine video gaming questions and funding available to include in future SHS and BRFSS surveys |  |  |  | Roxann Jones Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Continue to support the inclusion of gambling related questions on health surveillance surveys and seek opportunities to expand surveillance measures | Determine how to obtain current gambling prevalence and behavior data |  | In progress |  | Greta Coe
Support the Oregon Gambling Research Center and contribute to developing the Center’s research agenda
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Support the Oregon Gambling Research Center and contribute to developing the Center’s research agenda | Continue OHAs representation on the Research Center Subcommittee of OCPG and be actively involved with their mission. |  | Ongoing | 2024-01-01 | Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Support the Oregon Gambling Research Center and contribute to developing the Center’s research agenda | Financially support Research Centers research and study efforts each biennium or as needed |  | Ongoing | 2024-01-01 | Greta Coe
Seek opportunities to partner with researchers and with agencies on projects investigating the impact of gambling on various populations and health outcomes
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Seek opportunities to partner with researchers and with agencies on projects investigating the impact of gambling on various populations and health outcomes | Conduct focus group with populations that are typically under represented within surveys to best understand and impact changes within system | Currently conducting focus groups with youth and parent/caregivers. | In Process | 2024-09-01 | All
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Seek opportunities to partner with researchers and with agencies on projects investigating the impact of gambling on various populations and health outcomes | Continue to represent and actively participant in the OHA SHS and BRFSS Advisory Committees |  | Ongoing | 2024-01-01 | Roxann Jones Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Seek opportunities to partner with researchers and with agencies on projects investigating the impact of gambling on various populations and health outcomes | Partner with ODOC on the PGSI and PGSI- WARNA Research Project |  | In Progress | 2024-03-01 | Greta Coe
| Strengthen and enhance capacity to conduct data collection, surveillance, and evaluation to analyze, and inform policy, programs, and impact of services | Seek opportunities to partner with researchers and with agencies on projects investigating the impact of gambling on various populations and health outcomes | Continue OHAs representation on the Research Center Subcommittee of OCPG |  | Ongoing | 2024-01-01 | Greta Coe
6.2 | Reduce health disparities and ensure effectiveness of programs by establishing an equity-informed approach to data, evaluation, and surveillance
Include measures of cultural responsivity within problem gambling data collection methods
| Reduce health disparities and ensure effectiveness of programs by establishing an equity-informed approach to data, evaluation, and surveillance | Include measures of cultural responsivity within problem gambling data collection methods | Include health equity inclusion/seeking questions and data collection within touch points and forms |  |  | 2025-03-01 | All
In the selection and design phases of evaluation, research projects and data systems include questions aimed to inform health equity
| Reduce health disparities and ensure effectiveness of programs by establishing an equity-informed approach to data, evaluation, and surveillance | In the selection and design phases of evaluation, research projects and data systems include questions aimed to inform health equity | SOGI integration in internal survey designs the best we can |  |  |  | Greta Coe
| Reduce health disparities and ensure effectiveness of programs by establishing an equity-informed approach to data, evaluation, and surveillance | In the selection and design phases of evaluation, research projects and data systems include questions aimed to inform health equity | Within the CRAM, determine how to include health equity type questions. |  |  | 2025-03-01 | Roxann Jones
| Reduce health disparities and ensure effectiveness of programs by establishing an equity-informed approach to data, evaluation, and surveillance | In the selection and design phases of evaluation, research projects and data systems include questions aimed to inform health equity | Improve the implementation of Real D within PG Net for better data collection |  |  |  | PG TX Specialist
6.3 | Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions
Utilize OHA PGS sponsored events to share and discuss data
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Utilize OHA PGS sponsored events to share and discuss data | Initiate and hold a Data and Research quarterly webinar where Oregon PG data and national trends can be shared and discussed. |  | Complete | 2024-01-01 | Greta Coe
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Utilize OHA PGS sponsored events to share and discuss data | Share research from the OCPG Research Center grants to the system at summits or via webinar sessions. |  | Ongoing | 2024-01-01 | Greta Coe
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Utilize OHA PGS sponsored events to share and discuss data | Ensure All Providers Webinar have one agenda topic at each quarterly session to share findings or data from our programs. |  | Ongoing | 2024-01-01 | Greta Coe
Develop and disseminate research and evaluation reports with purposeful intent
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Develop and disseminate research and evaluation reports with purposeful intent | Work with Data Consultant on different ways to analyze and communicate data |  |  |  | Greta Coe
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Develop and disseminate research and evaluation reports with purposeful intent | Initiate and hold a Data and Research quarterly webinar where Oregon PG data and national trends can be shared and discussed. |  | Complete | 2024-01-01 | Greta Coe
| Develop and employ communication strategies to disseminate evaluation and research findings to increase the influence of data on program and policy decisions | Develop and disseminate research and evaluation reports with purposeful intent | Ensure data and research is part of overall communication plan being developed |  |  | 2025-01-01 | Greta Coe