| LOGIC MODEL |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INPUTS |  | PROCESS |  |  |  | OUTCOMES |  |  |
| List of Needed Resources |  | Activities | Outcomes |  |  | Short-term | Intermediate | Long-term |
| Financial $250,000.00 Human Resources - 2.5 Staff - 12 Volunteers - 3 Peers Materials - Syringes and other IDU equipment - HIV and HCV Test - Educational materials - Site Poster - 2 computers Partnerships - Referral Orgs - Law Enforcement |  | Launch | - Convene Quarterly Advisory Board meetings - Hire new staff - Purchase 1 Mobile Van |  |  | Community input on SSP implementation Provision of SSP services | Ongoing Stakeholder engagement Ongoing services | SSP services are an established community resource |
|  |  | Communication | - Promotion Plan implemented by week 4 - Provide monthly updates to stakeholder groups - Quarterly information dissemination through community mass media |  |  | Increase and maintain stakeholder and community at large awareness of SSP services and impact | Established 2-way communication channel for informational inquiries and problem solving | Community support for SSP |
|  |  | Peer Outreach & Navigation Services | - 4 hours/day @ 3 days/week (48 weeks) - 300 referrals and navigation support to syringe and/or social services - 150 referrals and navigation support to screening and healthcare services |  |  | Increase awareness of SSP, social, healthcare, and social services among PWUD Increase successful referrals to social, healthcare, and drug use treatment services | Increase local PWUD resource utilization Increase utilization of social, healthcare, and drug use treatment services | Decrease unsafe injection drug use behaviors |
|  |  | Mobile Needle Exchange | - # Needles Exchanges - 4 hours/day @ 3 days/week (48 weeks) - Screen 300 PWUD for HIV and HCV - Link 200 participants to supportive social services - Link 200 participants to healthcare, mental health, behavioral health, medically assisted treatment, and/or drug treatment/recovery services |  |  | Increase access to safe injection drug use equipment Increase access to safe needle disposal sites Increased access to wound care Early Identification and treatment of communicable diseases | Decrease needle sharing and unsafe injection drug use practices Increase safe disposal of needles and syringes Improved monitoring and surveillance of communicable diseases | Decrease incidence of communicable disease rates Decreased negative health impacts (e.g. sepsis) Improved mental health |
|  |  | Stationary Needle Exchange Site |  |  |  |  |  |  |

SMART OBJECTIVES

- … - …. - …..

| ASSUMPTIONS | CONTEXTUAL FACTOR |
| --- | --- |
| - Funding will remain stable throughout the program period - Promotion of services is best accomplished via word-of-mouth and existing communications channels - Increased access to needles and disposal sites will impact needle use and disposal behaviors - Communicable diseases (HIV, HCV) in the county are primarily due to needle sharing practices - Law enforcement supports needle exchange services | - Existing city ordinances aimed to disrupt homelessness - Target populations socioeconomic status: 65% homeless |