OBJECTIVES

SMART OBJECTIVES (Specific, Measurable, Achievable, Realistic, and Time-framed)

- Purchase 1 mobile van to provide mobile SSP services by end of September 15, 2019

- Create program promotion/marketing plan by July 31, 2019

- Convene 1st stakeholder advisory board meeting for 12-member board during first quarter of funding period and once ever quarter there after

- Operate SSP services 4 hours/day @ 3 days/week for 48 weeks

- Enroll and conduct needs assessments for 300 PWUD as SSP participants by June 30, 2020

- Screen 300 participants for HIV and HCV by June 30, 2020

- Successfully link 95% of participants who test positive for HIV and/or HCV to healthcare by June 30, 2020