## READ - Instructions
Instructions
The Work Plan describes the projects that the partnership seeks to implement each biennium in relation to the Strategies and Conservation Actions outlined in the FIP Initiative Application. The Work Plan should directly relate to the Theory of Change and the Progress Monitoring Framework that is included in your Strategic Action Plan. The Work Plan can also be used to track progress of project implementation over time and support the required reporting for Project Tracking Reports to the OWEB Board.
FIP Applicants must submit a detailed Work Plan for their first biennium with the FIP Initiative Application. Awarded FIPs will submit an updated Work Plan to OWEB in advance of each new biennium to be shared with the board.
BIENNIUM 1: Entering Strategies, Conservation Actions, and project details
Strategies: | Include the name and a brief description of each proposed Strategy. Biennium 1 Work Plans should include all Strategies proposed in your FIP Initiative application.
Conservation Actions: | Under each Strategy, include the name of the Conservation Action(s) to be implemented, the indicator(s) that will be measured, the Conservation Output Objective (Target) for the Initiative, and the Limiting Factors that the Conservation Action is intended to address. There may be multiple Conservation Actions under a single Strategy. The Biennium 1 Work Plan should include all of the Conservation Actions proposed in your FIP Initiative application.
Projects: | Under each Conservation Action, enter the details for the projects to be implemented each biennium. The Project Lead Partner should be the anticipated grantee for the project. Project Type should be selected from the list of eligible project types to be funded under the FIP. The Brief Project Description should be no more than 2-3 sentences to describe the proposed project. Project Readiness/Status should be selected from the pull down options to indicate landowner engagement, design, and permitting status. Proposed Conservation Output/Deliverable should state what you anticipate accomplishing through the implementation of each project - it should be a portion of the Conservation Output Objective (Target) that was stated in the Conservation Action that each project is associated with. The Final Conservation Output/Deliverable should be left blank until the project is completed and the final numbers are known.
BIENNIA 2 and 3: Entering Project List
Projects: | Enter each project as a separate row. The Lead Partner should be the anticipated grantee for the project. Project Type should be selected from the list of eligible project types to be funded under the FIP. The Brief Project Description should be no more than 2-3 sentences to describe the proposed project. It is helpful to also provide an indicator of project readiness in the brief project description (e.g., landowner engagement status, anticipated start date, design status, permit status, etc.) Proposed Conservation Output/Deliverable should state what you anticipate accomplishing through the implementation of each project. Anticipated OWEB Requested Funding and Anticipated Match Funding should match the biennium 2 and biennium 3 budget request in your FIP Initiative application and budget form.
Work Plan Changes
OWEB recognizes that Initiative Work Plan are developed with the best available information and that unforeseen circumstances can delay or cancel a project or can create an opportunity for a project that wasn't originally anticipated. Projects that are delayed should be grayed out in the current work plan and added to the appropriate future biennium. Projects that are cancelled should be grated out in the current work plan. Do not delete projects from the work plan. You can include a note in the Project Readiness/Status to explain the reason for cancellation. New Projects added should simply be added to the Work Plan. Note that Work Plan changes must be discussed with the Partnership to address to shift funding allocations, when needed. All Work Plan changes should also be discussed with your OWEB Partnerships Coordinator.
Questions on developing the Work Plan or the FIP Initiative application can be directed to any of the following:
Eric Hartstein |  | eric.hartstein@oweb.oregon.gov
Denise Hoffert |  | denise.hoffert@oweb.oregon.gov
Jillian McCarthy |  | jillian.mccarthy@oweb.oregon.gov

## READ - Example Work Plan
Biennium 1 Work Plan
Partnership Name:
Initiative Name:
Start and End Dates:
Strategy 1: | Restore Instream Habitat Complexity and Diversity
Strategy 1 Description: | This Initiative will include feasibility, design, and implementation of approximately 14 instream habitat and floodplain connection projects.
Conservation Action 1.1: | Large Wood Placement
Indicator(s) to be measured: | Stream miles treated with large wood pieces and volume of wood per mile
Conservation Output Objective (Target): | By 2035, 33.6 miles of stream will be treated with large wood structures in priority reaches.
Limiting Factors Addressed: | Reduced instream habitat diversity and complexity from loss of large wood.
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output/Deliverable | Final Conservation Output/Deliverable | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 1.1 - 1 | Big Creek Large Wood Design | Big Creek Watershed Council | Technical Assistance | Develop final design/plan large wood installation on 9 miles of Big Creek | Landowner contacted and interested | Conceptual Design complete | NA | Final Restoration Design for 9 miles of large wood installation | To be completed at project completion. | 95000 | 5000
Project 1.1 - 2 | Big Creek Large Wood Installation | Big Creek Watershed Council | Restoration | Implement large wood installation on 9 miles of Big Creek | Landowner contacted and interested | Conceptual Design complete | Permitting not yet initiated | 9 miles | To be completed at project completion. | 325000 | 85000
Project 1.1 - 3 | Super Big Creek Large Wood Installation | Big Creek Watershed Council | Restoration | Implement large wood installation on 24.6 miles of Super Big Creek. | Secured Landowner Agreement in place | 60% Design Complete | Permitting underway | 24.6 miles | To be completed at project completion. | 695000 | 180000
[10 empty] | 1115000 | 270000

## ENTER - B1 Detailed Work Plan
Biennium 1 Detailed Work Plan
Partnership Name:
Initiative Name:
Start and End Dates:
Strategy 1: | Enter Strategy Name
Strategy 1 Description: | Enter brief description of Strategy
Conservation Action 1.1: | Enter Conservation Action Name
Indicator(s) to be measured: | Enter indicator that will be measured for this Conservation Action
Conservation Output Objective (Target): | Enter the Conservation Output Objective or the Target for the FIP initiative. This should be quantitative and timebound.
Limiting Factors Addressed: | Describe the limiting factor(s) that this Conservation Action Addresses
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output/Deliverable | Final Conservation Output/Deliverable | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 1.1 - 1 | Enter Project Name | Enter Lead Partner | Select Project Type | Enter brief project description | Select Landowner Status | Select Design Status | Select Permitting Status | Enter the anticipated Conservation Output/deliverable for this project. | AFTER PROJECT COMPLETION: enter final Conservation Output/deliverable for this project
Project 1.1 - 2
Project 1.1 - 3
[10 empty] | 0 | 0
Conservation Action 1.2: | Enter Conservation Action Name
Indicator(s) to be measured:
Conservation Output Objective (Target):
Limiting Factors Addressed:
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output | Final Conservation Output | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 1.2 - 1 | Enter Project Name | Enter Lead Partner | Select Project Type | Enter brief project description | Select Landowner Status | Select Design Status | Selecting Permitting Status
Project 1.2 - 2
Project 1.2 - 3
[10 empty] | 0 | 0
Strategy 2: | Enter Strategy Name
Strategy 2 Description: | Enter brief description of Strategy
Conservation Action 2.1: | Enter Conservation Action Name
Indicator(s) to be measured: | Enter indicator that will be measured for this Conservation Action
Conservation Output Objective (Target): | Enter the Conservation Output Objective or the Target for the FIP initiative. This should be quantitative and timebound.
Limiting Factors Addressed: | Describe the limiting factor(s) that this Conservation Action Addresses
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output/Deliverable | Final Conservation Output/Deliverable | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 2.1 - 1 | Enter Project Name | Enter Lead Partner | Select Project Type | Enter brief project description |  | Select Design Status | Selecting Permitting Status | Enter the anticipated Conservation Output/deliverable for this project. | AFTER PROJECT COMPLETION: enter final Conservation Output/deliverable for this project
Project 2.1 - 2 |  |  |  |  | Select Landowner Status
Project 2.1 - 3
[10 empty] | 0 | 0
Copy the rows above to add Strategies and Conservation Actions, as needed.

## Example Actions_Metrics Lists (hidden)
Instream and Wetland Habitat |  | Actions | Metric
| Total stream miles treated (instream habitat treatments) | Bank stabilization | Total miles treated (left and right streambanks)
| Total wetland acres treated | Fish Passage Improvement | Passage barriers remediated
Bank stabilization |  | Placement of materials in channel | Miles of habitat with improved access
| Total miles treated (left and right streambanks) | Channel reconfiguration and connectivity | # LWD structures
Fish passage improvement |  | Beaver Reintroduction | # BDA structures
| Passage barriers remediated | Other | # Boulder structures
| Miles of habitat with improved access |  | # Combination LWD/boulder structures
Placement of materials in channel |  |  | Constructed riffles
| # LWD structures |  | Ac off-channel or floodplain habitat connected
| # BDA structures |  | Pools created/added
| # Boulder structures |  | Mi. spawning gravels placed
| # Combination LWD/boulder structures |  | Channel created (Wetland habitat)
| Constructed riffles |  | Miles of wetland habitat treated
Channel reconfig and connectivity |  |  | Acres of wetland habitat connected
| Ac off-channel or floodplain habitat connected |  | Stream miles treated (beaver reintroduction)
Pools created/added
Mi. spawning gravels placed
Channel created (Wetland habitat)
Miles of wetland habitat treated
Acres of wetland habitat connected
Beaver reintroduction
Stream miles treated (beaver reintroduction)
Riparian Habitat |  | Actions | Metric
| Total linear stream miles treated | Fencing | Total linear stream miles treated
| L streambank miles treated | Vegetation Establishment/Management | L streambank miles treated
| R streambank miles treated | Non-native Plant Control | R streambank miles treated
| Total riparian acres treated | Debris and structure removal | Total riparian acres treated
Fencing |  | Other | Miles of fence
| Miles of fence |  | Stream miles
| Stream miles |  | Riparian acres protected from livestock grazing
| Riparian acres protected from livestock grazing |  | Acres planted
Vegetation est./mgmt |  |  | Stems planted
| Acres planted |  | Acres treated
| Stems planted |  | Acres treated
Non-native Plant Control
Acres treated
Debris and structure removal
Acres treated
Upland Habitat |  | Actions | Metric
| Total upland acres treated | Upland road activities | Total upland acres treated
Upload road activities |  | Vegetation Establishment/Management | Acres treated with fuels reduction treatments
Veg est/mgmt |  | Upland exlusion fencing | Miles of fence
| Acres treated with fuels reduction treatments | Other | Acres fenced
Upland exclusion fencing |  |  | Miles of stream protected (livestock exclusion)
Miles of fence
Acres fenced
Miles of stream protected (livestock exclusion)
Monitoring |  | Actions | Metric
| Total miles monitored | Monitoring | Total miles monitored
| Total acres monitored |  | Total acres monitored
| (Obj 7) Macroinvertebrate samples collected |  | Macroinvertebrate samples collected
| Miles of improved side channel habitat snorkeled |  | Miles of improved side channel habitat snorkeled
| Miles of improved side channel habitat surveyed |  | Miles of improved side channel habitat surveyed
Stakeholder Engagement |  | Actions | Metric
| Stakeholder engagement plan completed | Stakeholder Engagement | Stakeholder engagement plan completed
| Fish population status fact sheets distritubed to landowners and stakeholders |  | Fact sheets distritubed to landowners and stakeholders
| Meetings and tours hosted for agency staff and landowners |  | Meetings and tours hosted for agency staff and landowners

## ENTER - B2 Draft Work Plan
Biennium 2 Draft Work Plan
Partnership Name:
Initiative Name:
Start and End Dates:
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output/Deliverable | Final Conservation Output/Deliverable | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 1 | Enter Project Name | Enter Lead Partner | Select Project Type | Enter brief project description | Select Landowner Status | Select Design Status | Selecting Permitting Status | Enter the anticipated Conservation Output/deliverable for this project. | AFTER PROJECT COMPLETION: enter final Conservation Output/deliverable for this project
Project 2
Project 3
Project 4
Project 5
Project 6
Project 7
Project 8
Project 9
Project 10
Project 11
[10 empty] | 0 | 0
Copy the rows above to add Strategies and Conservation Actions, as needed.

## ENTER - B3 Draft Work Plan
Biennium 3 Draft Work Plan
Partnership Name:
Initiative Name:
Start and End Dates:
Work Plan Projects: | Project Name | Lead Partner | Project Type | Brief Project Description | Project Readiness/Status |  |  | Proposed Conservation Output/Deliverable | Final Conservation Output/Deliverable | Anticipated OWEB Requested Funding $ | Anticipated Match Funding $
Project 1 | Enter Project Name | Enter Lead Partner | Select Project Type | Enter brief project description | Select Landowner Status | Select Design Status | Selecting Permitting Status | Enter the anticipated Conservation Output/deliverable for this project. | AFTER PROJECT COMPLETION: enter final Conservation Output/deliverable for this project
Project 2
Project 3
Project 4
Project 5
Project 6
Project 7
Project 8
Project 9
Project 10
Project 11
[10 empty] | 0 | 0
Copy the rows above to add Strategies and Conservation Actions, as needed.

## Lists
Select Project Type
Acquisition - Land
Acquisition - Water
Engagement
Monitoring
Restoration
Technical Assistance
Partnership Technical Assistance
Select Landowner Status
Not yet contacted
Landowner contacted and interested
Secured Landowner Agreement in place
Select Design Status
NA
Conceptual Design complete
60% Design Complete
Final Design complete
Select Permitting Status
NA
Permitting not yet initiated
Permitting underway
Permitting complete